## Slide 1: Project Closeout:
Rules and Regulations Overview (2 CFR 200)

## Slide 2: Agenda
Understanding Closeout Requirements
Key Items:
  Disposition Plan
  Inventory List
  Closeout Letter
Planning for Closeout
  Developing Close-out Plan
  Creating a timeline

## Slide 3
Closeout Requirements
Notes: 2 CFR 200, subpart E

## Slide 4
Definition: the process by which the Federal awarding agency or pass- through entity determines that all applicable administrative actions and all required work of the Federal award have been completed:
  Closeout vendor, rental, consultancy, and employee contracts according to local laws
  Disposition plan for property and equipment over threshold, or useful life of +1yr (i.e. vehicle)
  Final programmatic and financial reporting as outlined in award
  Submit final inventory list
Review your AWARD or COUNTRY MANUAL for exact requirements and deadlines!
2 CFR 200.343-4
Closeout Requirements

## Slide 5
Final year budget projections
  Include budget for closeout activities
  Track accruals for final 9 months of project
Closeout contracts with vendors, contractors, and sub-recipients
  Recommended to start process 2-3 months before your award end date
  Review any require prior notices period required
Issue final payments
  Ensure all expenses have been reported
Pre-Award Ending
Financial Closeout
Notes: Real property may either be retained or sold and the federal agency must be compensated
(land, structures) does not include movable machinery and equipment
Equipment usually stays with the non-fed entity, unless otherwise stated, if current market value is less than $5,000 (otherwise need to consult agency for further disposition instructions)
Must be included in inventory, property records kept, safeguard (insurance)
Intangibles—vest with recipient : “whoever creates it, owns it” but USG has right to obtain, reproduce, publish or otherwise use data produced under award and authorize others to for fed purposes
Inventory of unused supplies exceeding $5,000 in total aggregate value upon termination or completion of the Federal program and not needed for any other Federal award, recipient must compensate the Federal government for its share.

## Slide 6
Categories for Project closeout:
  Financial
  Administrative
  Human Resources
  Programmatic
2 CFR 200.343-4
Closeout Requirements

## Slide 7
Complete and submit SF-425 form (only for prime recipient)
Submit final VAT (value added foreign tax) report
  Only include invoices relating to commodity purchases valued at USD 500 or more
    " Commodities" include any materials, article, supply, goods, or equipment
  Does not include services
  Only foreign taxes assessed by the foreign government in the country receiving U.S. assistance
  Period covered October 1 – September 30
Post-Award Ending
Financial Closeout

## Slide 8
Finalize total expenditures
  All expenses must be incurred by the end date of the award, expense beyond the award end date are not permitted
  Total award amount
  Total obligations
  Total Expenditures (including all final invoices and expenses from contractors, suppliers, and subrecipients)
Liquidate all obligations incurred as specified in the terms and conditions of the award
You must return any advanced funds that are unspent by the end of the award
Post-Award Ending
Financial Closeout

## Slide 9
Ensure compliance with USAID standards on the types of documents that need to be retained
Close project-specific bank account
Terminate leases on rented office space, supply contracts, utilities, other service providers (phone plans, insurance, security, etc.)
  Document vendor notice of termination(s)
  Charges for services provided beyond project end date are not allowed
Develop and submit disposition plan to donor
Pre-Award Ending
Administrative Closeout

## Slide 10
Record Retention
  Maintain all project documents and accounting records in accordance with award terms and local laws
  Minimum retention requirement of 3 years from the date of submission of the final expenditure report
  USAID reserves right to audit your project/organization at any point within these 3 years
  Subrecipients must also abide by same record retention requirements, including local country laws
Final Inventory List
Signed Closeout Letter
Post-Award Ending
Administrative Closeout

## Slide 11: Human Resource Closeout
Develop staff transition plan
Modify employee contracts to reflect the project closeout date
  Follow any prior notices required by law
Plan for proper termination of employee contracts/agreements:
  Identify and understand local payment requirements related to severance and other benefits as defined by law
  Understand organizational payment requirements
  Clear any staff outstanding advances
Pre-Award Ending

## Slide 12: Human Resource Closeout
Document staff terminations and final salary and benefits payments
Securely maintain HR files related to each staff member
Collect and document company or project property returned by staff members
  Clear any sensitive employee information from laptops, cellphones, etc.
Post-Award Ending

## Slide 13: Programmatic Closeout
Begin impact assessments
  Recommended at least 3-6 months prior to award ending
  Compare LOP actuals vs targets
  Document lessons learned
Develop and communicate closeout deliverables and requirements for subrecipients
Communicate project closeout with key stakeholders and partners
  Identify sustainability or continuity plans
Scale down project activities
Pre-Award Ending

## Slide 14: Programmatic Closeout
Final Project Reports
  Typically due between 30-90 days after award ends*
  Highlight project successes and lessons learned
Develop success stories and conduct outreach
Hold closeout meetings with key stakeholders
Securely archive project reports, key documents, and data
  Avoid later alterations of project documents
Submit final report to the USAID DEC
*Review award terms and conditions
Post-Award Ending

## Slide 15: Key Requirements

## Slide 16: Final Inventory Report
Complete list of all equipment and supplies purchased with project funds*
Items to include in inventory:
  All equipment with a market value of USD $5,000 or more and with a useful life of one year or more at the end of project,
  New/unused supplies with an aggregate current fair market value at the end of this award of $5,000 or more,​ and
  Real or intangible property, of any value
Report should cover:
  Original cost and USAID share of cost (i.e., cost shared with another project)
  Current fair market value
  Current location
  Condition of the equipment
*See award and/or organizational policies for exact thresholds and requirements
2 CFR 200.313​

## Slide 17: Disposition Plan
Detailed plan of what/how you propose to dispose of equipment or unused supplies after the award ends
For items below $5,000 USD:
  Items with a current per unit fair market value of $5,000 or less may be retained, sold or otherwise disposed of with no further responsibility to the donor
For items above $5,000 USD must request formal guidance, disposition may include:
  Retain title with no further obligation to the donor;
  Retain the items and the title but compensate donor for the current fair market value of items;
  Transfer the title of the items to donor or a third party
Submit Disposition Plan to donor for approval or further instructions
*See award and/or organizational policies for exact thresholds
2 CFR 226.34

## Slide 18: Closeout Letter
Once closeout requirements are complete, it is a best practice to obtain a signed letter by the donor or pass-through entity confirming all requirements were completed, including key items such as final invoice and, financial and narrative reports
Keep letter on file as documentation
Best Practice​

## Slide 19
Planning for Closeout

## Slide 20: Planning for Closeout
Identify and list all closeout requirements, and assign dates each task is due as defined by award
  Assign each task to an appropriate staff member
  Include requirements and deadlines for closeout of subrecipients
Create a plan to track progress towards closeout tasks
  A tracking sheet can help avoid confusion, delays, or disruptions throughout closeout process
  Especially important if there are staff transitions before tasks are completed
Closeout Plan

## Slide 21: Planning for Closeout
Closeout Plan

## Slide 22
Q&A