## Rapid Startup Plan
Rapid Startup Activities
Category | Responsible Parties | Post Award | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
By (date)
Monetization
Draft agreement for monetization agent | Completed
Sign agreement with monetization agent | Completed
First Monetization completed
Second Monetization completed
Staffing
Develop Scope of Work for start up consultant
Develop Job descriptions for local staff
Recruit and hire startup consultant(s)-- Field
Startup Specialist conducts assignment in COUNTRY
Recruit and hire startup consultant(s)-- HO
Program & Operations Manager conducts assignment in COUNTRY
COP Recruited and onboarded
COP Mobilizes to COUNTRY
DCOP Recruited and onboarded
F&A Director Recruited and onboarded
Component Leads recruited and onboarded
Post job descriptions for other open staff positions
Conduct interviews for open staff positions
Recruit and onboard operations staff
Operational Startup Tasks & Deliverables
Establish local registration
Engage local lawyers to assist with registration and HR matters
Develop COUNTRY Supplemental Manual
Obtain tax exemption
Establish local bank accounts
Project office in COUNTRY identified
Establish office and procure office furniture and equipment
Procure laptops, software, and initial IT equipment
Identify & Procure vehicles and transportation services
Develop project security plan and establish emergency action plan
Prepare and submit to HO emergency contact plan (updated regularly)
Train field staff on grants and subcontract compliance and management
Make arrangements and logistical preparations for work planning sessions; conduct initial work planning sessions
Prepare for and hold project launch event
Check on laws for legal representation and who can be on bank accts
Research how we can register in Mauritania in order to have tax exemption
Translate HO templates to XXXX language
Soft launch date
Accounting system - review local country laws and taxation
Contract payroll company
Creation of security assessment and briefings
Technical
Prepare Initial Activity Factsheet
Hold initial planning workshops with counterparts and staff
Draft and submit LOP and Annual work plan
Prepare, submit draft/final of Evaluation Plan and PMP
Procurement of baseline (TOR, publication, org selection)
Baseline study
COP meets with Analyst and other DONOR teams
Meet with key government officials, private sector stakeholders, and donors
Private Sector Engagement Framework under development
Semi-Annual Report
Communications plan in line with DONOR branding plan
Priority Stakeholder Meetings for the Startup Period

## Components & Activities
Components & Activities
| Activity | Actors | Beneficiaries | Cost Share | Budget | Year | Year | Year | Year | Year | Indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5
1 | Component 1: XXX
Component 2: XXX
Component 3: XXX
Component 4: XXX
Monetization
Special Studies