## 2025
USDA Food for Progress Tunisia - HO Master Contract Tracker | [10 empty] | In Process
Last Updated: 06/18/2025 | [10 empty] | Completed
No. | Contract ID | Vendor | Purpose | Budget Category | Contract Type | Amount | Period of Performance | Status | Stage | # of Deliverables | Total Paid to Date | Termination Notice
1 | N/A | JDM Monetization Services LLC | Monetization Agent | Admin | Other | 258850 | 10/01/2024-12/31/2025 | Signed | Under Implementation | N/A | 90000
2 | RKTCJ-CGONK-KNKW4-AOK45 | Donia Hedda Ellouze | Lawyer-HR Doc Review | Admin | FP-ICA | 2500 | 12/02/2024-08/31/2025 | Signed | Under Implementation | 2 | 1500 | Email Sent
3 | GTTD4-JUOPS-YQWD5-CAKEX | Donia Hedda Ellouze | Lawyer-Legal Entity | Admin | FP-ICA | 1313.45 | 12/02/2024-06/30/2025 | Signed | Under Implementation | 2 | 400 | Email Sent
4 | PTPTY-CDTBV-ORFJW-E3FMR | Abir Ben Nasr | HR Consultant (Start-Up) | Admin | Hourly-ICA | 1340 | 03/26/2025-04/30/2025 | Signed | Completed | N/A | 536
5 | FP-POS-FFPr Tunisia-2025-001 | Just Results LLC | Baseline | Admin | FP-POS | 149329 | 04/09/2025-07/31/2025 | Signed | Under Implementation | 7 | 44798.7 | Terminated
6 | FP-POS-FFPr Tunisia-2025-002 | J.E. Austin | Crop Cost-Benefit Analysis | Admin | FP-POS | 44999 | 05/09/2025-09/15/2025 | Signed | Under Implementation | 5 | 0 | Terminated
7 | 3MITU-ZV8MK-EROZY-JSUU3 | Mohamed Torgeman | M&E Consultant (Baseline) | Admin | FP-ICA | 3000 | 04/09/2025-05/30/2025 | Signed | Under Implementation | 1 | 0

## Sheet2
FP-ICA | Not Started | Not Started | Email Sent
Hourly-ICA | Pre-PRF | Under Implementation | Letter Sent
FP-POS | PRF Signed | Completed | Final Invoice Received
TD-POS | RFP Posted |  | Final Invoice in Process
BPA | Under Selection |  | Terminated
Sub-award | Under Negotiation
Other | Waiting for POA Signature
Waiting for Vendor Signature
Signed
Needs to be Modified