Subaward Manual

Update October 1st, 2025

# Table of Contents

1.	Table of Contents	2

2.	Acronyms	6

1.	Introduction and Overview	7

1.1 Purpose and Scope of Manual	7

1.2 Definitions	8

2.	Roles and Responsibilities	12

2.1 Standard Code of Conduct	14

2.1.1 Conflict of Interest	14

2.1.2 Unethical Conduct	15

2.1.3 Protection from Retaliation	16

3.	Subrecipient Process	16

3.1 Subrecipient vs. Contractor Determination	16

3.2	Notice of Funding Opportunity (NOFO)	17

3.2.1 RFA	17

3.2.1.1 RFA Process	18

3.2.2 Annual Program Statement	19

3.2.2.1 APS Process	19

3.2.3 Unsolicited Applications	21

3.2.4 Justification to Restrict Eligibility (JRE)	21

3.2.4.1 Restricted Eligibility Based on Pre-Approved Conditions	22

3.2.4.2 Restricted Eligibility Based on Programmatic Purposes	23

3.2.4.3 JRE Process	25

3.3 Evaluation and Selection of Applications	25

3.4 Eligibility of Subawards	26

3.4.1 Ineligible Organizations for Subawards	26

3.5 Subrecipient Risk Evaluation	26

3.5.1 Subrecipient Monitoring Plan	28

3.5.2 Reoccurring Subrecipient Risk Evaluation & Monitoring Plan	31

3.6 Pre-award and Negotiation	31

3.6.1 Requirements for Pass-Through Entities to Subaward	31

3.6.1.1 System for Award Management (SAM)	32

3.6.1.2 OFAC - Specially Designated Nationals and Blocked Persons, and the United Nations Security Council Consolidated List	32

3.6.2 Budget Analysis and Cost Negotiation	33

3.6.2.1 Allowable and Unallowable Costs	34

3.6.3 Program Description	35

3.6.4 Special Award Conditions	36

3.6.5 Negotiation Memorandum	37

3.6.6 Certifications, Assurances, and Other Statements	37

3.7 Prior Approval to Subaward	38

3.8 Subaward Mechanisms	38

3.8.1 Standard Grant Agreement (SGA) – Cost Reimbursable	41

3.8.1.1 Obligations	41

3.8.1.2 Eligibility for Advances	42

3.8.2 Fixed Amount Award (FAA)	43

3.8.3 In-Kind Grants	44

3.9 Standard Terms & Conditions	45

3.9.1 Mandatory Standard Provisions	45

3.9.2 Foreign Tax Reporting (as required)	45

3.9.3 Dispute Resolution	46

3.9.4 Termination and Suspension	46

3.9.5 Branding and Marking	47

3.9.6 Title to and Care of Property	47

3.9.7 Controlling Language	47

4.	Subaward Modifications	47

5.	Noncompliant Subrecipients/Subaward Conflict Resolution	49

6.	Subaward Management	49

6.1 Financial Management	50

6.1.1 Record Retention Requirements	51

6.1.2 Inventory Reporting Requirements	52

6.1.3 Audit Requirements	52

6.1.3.1 Audit Certification	53

6.1.4 Federal Funding Accountability and Transparency Act (FFATA)	53

6.1.5 Program Income	54

6.2 Programmatic Management	55

6.3 Subaward Closeout	55

6.3.1 Suspension	56

6.3.2 Disposition Plan	56

Annex A: Conflict of Interest Certification	58

Annex B: Subrecipient vs. Contractor Determination Checklist	60

Annex C: Subrecipient Risk Assessment Tool	64

Annex D: Pre-Award Assessment Questionnaire	68

Annex E: Pass-Through Entity Responsibilities Checklist	82

Annex F: Foreign Tax Report	88

Annex G: Inventory Listing Report	89

Annex H: Audit Certification	90

# Acronyms

AO		Agreements Officer*

AOR		Agreements Officer Representative**

APS		Annual Program Statement

CBO		Community-Based Organizations

CFO		Chief Financial Officer

COP		Chief of Party

EOI		Expressions of Interest

GAAP		Generally Accepted Accounting Principles

FAA		Fixed Amount Award

FFATA	Federal Funding Accountability and Transparency Act

JRE		Justification to Restrict Eligibility

NGO		Non-Governmental Organizations
NOFO		Notice of Funding Opportunity

OFAC 		Office of Foreign Assets Control

OMB 		Office of Management and Budget

PD		Program Description

PIO		Public International Organization

POA		Partners of the Americas

POA HQ	Partners of the Americas Headquarters

SAM 		System for Award Management

SDNBP	Specially Designated Nationals and Blocked Persons

SGA 		Standard Grant Agreement

UEI		Unique Entity Identifier

USG		United States Government

*Note Grants Officer (GO) may be the title under some USG awards.

**Note Grants Officer Representative (GOR) may be the title under some USG awards.

# Introduction and Overview

Partners of the Americas (POA) Subaward Manual provides a framework for managing grants under the U.S. Government (USG) Award. This manual is intended to provide a consolidated resource and tools for effective and compliant grants administration in accordance with POA’s and the Federal Awarding Agency’s requirements.

All Subrecipients of federal grant funds must comply with the Code of Federal Regulations (CFR), Title 2, Part 200, Subparts A through F, and appendices – Uniform Administrative Requirements, Cost Principles, and Audit Requirements for Federal Awards (2 CFR 200), published by the federal Office of Management and Budget (OMB). The full 2 CFR 200 is available electronically at www.ecfr.gov. All subaward protocols and processes will follow applicable Federal awarding agency regulations, and 2 CFR 200.

This manual is intended to supplement all the Federal Awarding Agency required financial and programmatic requirements that govern grant administration. It is not a substitute for familiarization with the actual requirements of the Federal Awarding Agency or the terms and conditions governing the prime award.

## 1.1 Purpose and Scope of Manual

This manual is applicable to all Program staff involved with grant administration. The manual provides an overview of the requirements to select, award, and manage subawards. This Manual describes the procedures, processes, criteria, and other requirements that the Program will require when soliciting applications, awarding, monitoring, and closing out subawards. POA expects that all the Program staff understand and implement all the policies and procedures found within this manual. It is the responsibility of each Program staff member to know the policies and procedures, or when necessary, request clarification. Any questions regarding the policies and procedures should be directed POA’s Contracts Department.

The policies and procedures contained in this Manual are subject to change based upon direction from the Federal Awarding Agency and/or POA Chief Financial Officer (CFO) and/or POA’s Contracts Director. This manual will be reviewed and updated semi-annually to reflect any changes to 2 CFR 200 or the applicable Federal awarding agency regulations or as new policies and procedures are approved by POA. the Program staff will be notified of updates by written communication.

## 1.2 Definitions

If any conflict occur between the definitions below and the definitions in 2 CFR 200.1 or the applicable Federal awarding agency regulations, the definitions in 2 CFR 200.1 or the applicable Federal awarding agency regulations take precedence.

- Advance payment – Advance payment means a payment that a Federal awarding agency or pass-through entity makes by any appropriate payment mechanism, including a predetermined payment schedule, before the non-Federal entity disburses the funds for program purposes.

- Annual Program Statement (APS) - An APS invites groups to apply for funds that support a variety of approaches to implement program objectives. It contains eligibility, total funds, and number of awards to be made, but the applicant has greater latitude in proposing the approach to meeting the objectives. They are good for a rolling acceptance of applications with no specific or multiple deadlines. The program can issue an APS for the year and accept applications on a first come, first served basis and/or until funds run out.

- Applicant - A the country of performance eligible entity as defined in Section 3.4 applying for a subaward.

- Application - A written document in form and substance conforming to the requirements of the solicitation and this manual, which outlines in detail the activity(s) being proposed by an applicant for funding.

- Award – Financial assistance that provides support or stimulation to accomplish a public purpose. Awards include grants, cooperative agreements, and other agreements in the form of money or property in lieu of money made by the USG to an eligible recipient.

- Closeout – Closeout means the process by which the Federal awarding agency or pass-through entity determines that all applicable administrative actions and all required work of the Federal award have been completed and takes actions as described in in § 200.344.

- Contract – Contract means a legal instrument by which a non-Federal entity purchases property or services needed to carry out the project or program under a Federal award. The term as used in this part does not include a legal instrument, even if the non-Federal entity considers it a contract when the substance of the transaction meets the definition of a Federal award or subaward.

- Contractor – An entity that receives a contract.

- Cost-reimbursement award – Cost-reimbursement awards contracts that provide for payment of allowable incurred costs, to the extent prescribed in the contract. These contracts establish an estimate of total cost for the purpose of obligating funds and establishing a ceiling that the contractor may not exceed (except at their own risk) without the approval of POA.

- Equipment - tangible personal property (including information technology systems) having a useful life of more than one year and a per-unit acquisition cost which equals or exceeds $10,000 USD.

- First Tier Subrecipient: –the entity provided a subaward directly from the Prime Recipient for the purposes of participating in the sponsored project.

- Fixed amount awards –a type of grant agreement under which the Federal awarding agency or pass-through entity provides a specific level of support without regard to actual costs incurred under the Federal award. This type of Federal award reduces some of the administrative burden and record-keeping requirements for both the non-Federal entity and Federal awarding agency or pass-through entity.. Since fixed amount awards focuses on outputs and results, limits risk for both parties, and requires only limited financial and management capacity. It is intended for use to support specific projects where there is a certainty about the cost, and in which the accomplishment of the purpose or milestone in the subaward is readily discernible, such as conferences and supplies, monitoring, oversight, and engagement of and with public and elected institutions.

- Grant agreement –a legal instrument of financial assistance between a Federal awarding agency or pass-through entity and a non-Federal entity that, consistent with 31 U.S.C. 6302, 6304:

  - Used to enter into a relationship. The principal purpose of which is to transfer anything of value from the Federal awarding agency or pass-through entity to the non-Federal entity to carry out a public purpose authorized by a law of the United States; and not to acquire property or services for the Federal awarding agency or pass-through entity's direct benefit or use;

  - Distinguished from a cooperative agreement in that it does not provide for substantial involvement between the Federal awarding agency or pass-through entity and the non-Federal entity in carrying out the activity contemplated by the Federal award.

  - Does not include an agreement that provides only: direct United States Government cash assistance to an individual; a subsidy; a loan; a loan guarantee; or insurance.

- Implementing Partner(s) –Any organizations contracted by the Prime Awardee to provide technical assistance and take part in the program implementation.

- Program Staff – Any staff member working directly under the Partners of the Americas Program. This includes the staff of POA and all implementing partners.

- Milestones – Key programmatic and financial targets that must be met to qualify for reimbursement of funds under fixed amount awards.

- Pass-through entity –A non-Federal entity that provides a subaward to a subrecipient to carry out part of a Federal program.

- Prime Recipient – An organization receiving direct financial assistance (a grant or Cooperative Agreement) to carry out an activity or program.

- Risk –a measure of future uncertainties in achieving program performance goals and objectives within defined cost, schedule, and performance constraints. Risk can be associated with all aspects of a program (e.g., technology efficiency, productive capability, financial stability, performance against plan).

- Risk Assessment - An assessment is completed for each new subaward or amendment. The risk assessment determines the level of risk associated with each subrecipient and subsequently to POA. A risk level is assigned to each subrecipient based on the criteria in the risk assessment.

- Risk Assessment Process - Continuous process that is accomplished throughout the length of a contractor/ subrecipient. It is an organized methodology for continuously identifying and measuring the risks; managing appropriate risk mitigations; and tracking the implementation to ensure successful risk reduction. Effective risk management depends on risk assessment planning; early identification and analyses of risks; early implementation of corrective actions; continuous monitoring and reassessment; and communication, documentation, and coordination.

- Second Tier Subrecipient: –The entity provided a subaward directly from the First Tier Subrecipient for the purposes of participating in the sponsored project. Although POA has a reduced oversight of these organizations, all applicable terms, and conditions under the subaward issued to the subrecipient will flow down to the 2nd tier subrecipients.

- Specific Award Conditions – Details the enforcement actions should a subrecipient be found noncompliant or require additional oversight regarding the laws, regulations, or specific award terms and conditions.

- Standard Subaward –Award which is not a simplified subaward or fixed amount award is considered a standard subaward.

- Subaward – An award provided by a pass-through entity to a subrecipient for the subrecipient to carry out part of a Federal award received by the pass-through entity. It does not include payments to a contractor or payments to an individual that is a beneficiary of a Federal program. A subaward may be provided through any form of legal agreement, including an agreement that the pass-through entity considers a contract.

- Subrecipient –A non-Federal entity that receives a subaward from a pass-through entity to carry out part of a Federal program; but  excludes individuals who are beneficiaries of such program. A subrecipient may also be a recipient of other Federal awards directly from a Federal awarding agency. Under the Program, an eligible Applicant that has been awarded a subaward is considered a subrecipient.

- Subrecipient Monitoring (SRM) Plan – Schedule of subrecipient monitoring activities, developed from the subrecipient Risk Evaluation, to be used by Program staff to adequately review and monitor the programmatic and financial performance of subrecipients to mitigate the risk of contracting with a subrecipient. Documentation of monitoring activities shall be retained within the subrecipient files.

- Subrecipient vs. Contractor Determination Checklist – Checklist provides a series of questions as well as expected responses to aid personnel in making the determination of a subrecipient vs. contractor.

- Subrecipient Risk Evaluation – Assessment of subrecipient capabilities, both programmatic and administrative.

# Roles and Responsibilities

POA: the US organization that is the Prime Recipient of the Federal Awarding Agency Cooperative agreement for implementing and managing the Partners of the Americas project.

The following personnel and teams play an important role in the management and monitoring of the subawards:

Chief of Party (COP): The COP is the technical project representative of POA in the country of performance. The COP has ultimate responsibility over the technical aspects of the Program, including the following:

- Oversee subrecipient’s technical activities as outlined in the approved work plan;

- Oversee implementation of the subaward manual for subrecipients based in the country of performance;

- Enforce remedies for noncompliance as appropriate; and

- Ensure Program staff receive adequate training on subaward administration and management.

Subaward Manager (SM): The SM is POA’s primary interface with subrecipients. The SM is the subrecipient’s main point of contact and responsible for ensuring:

- Subrecipient program descriptions are implemented in compliance with the policies and procedures as outlined in the subaward manual;

- Vetting potential subrecipients;

- Conducting pre-award assessments of potential subrecipients;

- Gathering supporting documents to support the review and evaluation of the criterion covered in the risk assessment;

- Monitoring performance and reporting upon the results of activity implementation;

- Providing as needed, organizational development training and technical assistance to subrecipients;

- Flagging any issues of noncompliance for the COP and POA HQ staff; and

- Ensuring that proper administrative and financial controls are in place to administer funds for compliance with applicable regulations and Federal Awarding Agency requirements.

Subrecipient Grants Team: They represent subrecipient’s staff person(s), who are responsible for:

- Implementation of subrecipient’s approved activities, within the approved budget and period of performance.

- Management of second tier subrecipients by ensuring following documents/reports:

  - Review of the following reports/documents:

    - due diligence report

    - financial and monitoring reports

    - audit reports

  - Conducting periodic review of financial and other project documents;

  - Monitor resolution of audit findings, if any.

POA’s Monitoring, Evaluation, and Learning (MEL) Team: It consists of the MEL Director, MEL Manager and MEL Officers. This unit is tasked with monitoring and reporting on all field activities. Any member of the MEL team may solicit specific information during project implementation on an ad-hoc basis.

Subrecipients’ MEL Teams: Subrecipients will have the responsibility to have a MEL team to conduct adequate monitoring and evaluation activities as per the subaward and AMELP guidelines. They are responsible to collect, analyze and provide data and information as solicited by POA.

POA Headquarter (HQ) Staff: US-based personnel providing operational support to the field office from the HQ office based in Washington DC. This team is composed of POA central services such as Compliance, Communications, Human Resources, Finance and Administration, who provide ad-hoc support as needed; and the Program backstop team, who provide day-to-day support to the project. These teams collaborate to ensure compliance with audit requirement and to ensure the manual is updated semi-annually and reflect most recent Federal Awarding Agency requirements in accordance with Applicable Federal awarding agency regulations and 2 CFR 200.

## 2.1 Standard Code of Conduct

Program staff shall maintain a high standard of ethical conduct in any activity implementation, including the selection of subrecipients, program management, and oversight of Program activities.

### 2.1.1 Conflict of Interest

All Program staff must sign a Conflict of Interest Certification, found in Annex A and adhere to USG and the Federal Awarding Agency’s rules and regulations, and POA’s policies and procedures. A conflict of interest is any interest, financial or otherwise, direct, or indirect; participation in any business, transaction, or professional activity; or incurring of any obligation of any nature, which is or appears to be in substantial conflict with the proper discharge of duties in relation to the Program.

All Program staff are expected to avoid any conflicts of interest, should any conflicts of interest arise. If any Program staff becomes aware of any conflicts of interest, they must immediately disclose to the COP in writing any real or potential conflict of interest. The COP may not approve the award or may determine the applicant to be ineligible for the award, if the COP determines that a conflict of interest cannot be adequately resolved..

A personal conflict of interest is a situation in which a Program staff member has a financial interest, personal activity or relationship that could impair the Program staff member’s ability to act impartially when performing activities on behalf of the Program. To avoid a conflict of interest, POA does not allow any Program staff, entity representative or any member of an Program staff’s immediate family to receive a subaward or have any financial or other interest in the entity selected for a subaward without disclosing the conflict. Additionally, all Program staff must neither solicit nor accept gratuities, favors, or anything of monetary value from subrecipients or prospective subrecipients. Any outside business dealings of Program staff members must be legal and not conflict in any manner with the Program operations. Outside business dealings include, but are not limited to, any investments, loans, employment, or business ownership by Program staff members.

### 2.1.2 Unethical Conduct

POA does not tolerate any unethical conduct. The following actions are considered unethical conduct:

- Making facilitation payments – Program staff must not make small payments to “grease” or speed-up approvals or actions on the part of government or other officials.

- Providing “gratuity” payment – Program staff must never pay or provide a gift, favor, or hospitality to a government official after receiving a favorable action or decision.

- Accepting bribes – Program staff must not directly, or indirectly, solicit, accept, offer, promise, or give a bribe or other improper payment, gift, favor, or hospitality to obtain or retain business, approvals, or other improper business advantage.

- Receiving Kickback – Program staff can never ask for or accept anything of value by vendors, suppliers, contractors who do business with under the Program. Program staff may accept gifts and hospitality of nominal value (meal offered during a business meeting or a pen/notepad).

If a Program staff member suspects or becomes aware of any allegations or violation of applicable laws, rules or regulations or this Standard Code of Conduct, they must immediately report the information POA HQ and/or the COP. POA will take prompt action to investigate and if found true, determine appropriate action in response to violations of this Code.

### 2.1.3 Protection from Retaliation

POA prohibits any retaliation against anyone who makes a good faith report of a suspected violation of the Standard Code of Conduct or who participates in an investigation. There is to be no interference, coercion, discrimination, reprisal, or retaliation against any person for making a valid and truthful complaint or good faith report of a violation. Nothing in this policy is meant to, nor should it be interpreted to, in any way limit Program staff rights under any applicable federal, state, or local laws.

# Subrecipient Process

POA is considered the prime recipient for the Program, and receives its funds directly from the Federal Awarding Agency. Once POA issues a subaward to another entity, the entity is considered a subrecipient and POA is considered the pass-through entity. If the subrecipient subsequently issues a subaward to a second entity, the second entity is considered a second tier subrecipient.

## 3.1 Subrecipient vs. Contractor Determination

Before entering into a contractual relationship with another entity, the pass-through entity has the responsibility to determine the proper classification of the entity, as either a subrecipient or contractor. This step is critical to ensure proper accounting for costs and compliance with requirements. Pass-through entities are held accountable for flowing down the appropriate requirements from the prime award to subrecipients or contractors. Generally, most of the provisions from the prime award flow down to any subrecipient, meanwhile more limited provisions flow down to contractor. Failure to correctly distinguish could subject the pass-through entity to increase audit risk and noncompliance.

An entity, may be either a contractor or a subrecipient depending on the nature of the work and relationship with the pass-through entity.

Characteristics of a subrecipient include if it:

- Determines who is eligible to receive what Federal assistance;

- Has its performance measured in relation to whether objectives of a Federal program were met, meaning the entity has substantive programmatic work or an important or signification portion of project;

- Has responsibility for programmatic decision making;

- Has responsibility for adherence to applicable Federal program requirements specified in the Federal award; and

- Uses the Federal funds to carry out a program for a public purpose specified in authorizing statute, as opposed to providing goods or services for the benefit of the pass-through entity.

Characteristics of a contractor include if it:

- Provides the goods and services within normal business operations;

- Provides similar goods or services to many different purchasers;

- Operates in a competitive environment normally;

- Provides goods or services that are ancillary to the operation of the program; and

- Is not subject to the compliance requirements of the program, though similar other procurement requirements may apply.

To ensure the appropriate classification, prior to the initiation of an agreement with an entity, Program staff must complete the Subrecipient vs. Contractor Determination Checklist found in Annex B. The results of the checklist will guide Program staff to making the appropriate classification of the entity as either a subrecipient or contractor. The completed checklist will be maintained with the subrecipient or purchasing file, depending on the determination, to serve as support for the designation.

## Notice of Funding Opportunity (NOFO)

The Program will utilize the following options as methods to issue notice of funding opportunities for potential subrecipients.

### 3.2.1 RFA

The Program may competitively award subawards through a public notice/RFA process. The pass-through entity will ensure maximum competition by publishing an announcement to seek applications from all eligible and qualified entities. The competition requirement will be met when an announcement is published. Next, the Program will convene a selection committee to conduct an impartial review and evaluation of all applications, where applicants will be selected if they meet the minimum technically acceptable requirements. Once a potential subrecipient is identified, POA HQ will request prior approval to subaward from the Federal Awarding Agency.

#### 3.2.1.1 RFA Process

The first step in the competitive process is the issuance of a public notice in the form of a Request for Applications (RFA).

The POA’s Program policy is for RFAs to be published 30-60 days prior to review of applications. The exact time period will depend on the nature of the RFA, the program description, and determination by the Program team for what is sufficient amount of time for interested organizations to submit an application that responds to the RFA. RFAs are appropriate if the grant program is intended to support a specific type of activity and when the application and review process is done in cycles. The Program may opt to utilize a tiered competition process depending on the anticipated number of applications to be received, capacity of the applicants to submit full applications, and time period allocated for implementation of the grants program. The tiered competition process will be conducted in accordance with the applicable federal awarding agency and will use a concept paper for tier one and then a full application for tier two. When competition will not be tiered, applicants will be required to submit a complete application. The Program may hold pre-RFA workshops to increase interest from potential applicants and clarify certain requirements, so applications better respond to the RFA.

All RFA’s issued under the Program must include:

- A statement that the program is authorized under the Federal Awarding Agency;

- Point of contact for questions and information;

- Eligibility requirements;

- Deadline for submission;

- Expected duration of award;

- General description of the objectives of the proposed grant activities;

- Evaluation criteria and detail on their importance;

- Estimated funds available and number and type of awards if available;

- Necessary leverage or cost share (as applicable);

- Required certifications;

- Sample application and budget template; and

- Statement indicating that the Program reserves the right to fund any or none of the application submitted.

### 3.2.2 Annual Program Statement

The Program may issue an APS to find prospective applicants/grantees with a fair opportunity to develop and submit competitive applications regarding the Program’s strategic objectives for potential funding.

When used, the pass-through entity will publish an APS at least once a year, either with an open-ended response time or a closing date of at least six months after issuance. The APS will be drafted by the pass-through entity. A final draft version of the APS will be sent to POA HQ for review and approval. Once POA HQ approves, if necessary, POA HQ will request concurrence/approval of the Awarding Officer’s Representative (AOR).

#### 3.2.2.1 APS Process

The application process under and APS will include at least the following two phases:

Phase 1 – Expressions of Interest (EOIs):

- Short description of the applying organization, their capacity, and the proposed activity that the applicant would like to implement along with a budget estimate.

- Phase 1 - POA selection committee will be review and evaluated all EOIs based on the categories and criteria that were previously defined by the Program’s technical team.

- EOIs from eligible organizations that are determined to be responsive to the APS will be accepted, and applicants will be contacted by the pass-through entity and invited to participate in Phase 2.

Format and Content of Applications

The following documents constitute Phase 1 EOI package. All documents must be submitted with the application to be considered:

- Completed Authorized Representatives (On template provided by the Program);

- Expression of Interest Template (On template provided by the Program);

- Organization’s legal registration certificate;

- Organization’s by-laws or charter, which stipulates the goals, objectives, and major activities of organization; and

- Resumes of key personnel and technical personnel.

Phase 2 – Applications:

During this second phase all applicants will receive guidance and capacity building necessary to finalize a detailed project technical application, including a program description and timeline, and to develop an itemized project budget.

Once Phase 2 applications are completed, they will be submitted to the pass-through entity and reviewed by an evaluation committee for a final decision on whether to fund the proposed activity. Participating in Phase 2 does not guarantee that the applicant will receive funding from the Program.

Summary of Contents

Complete APS document must include the following content:

- Project background

- Eligibility Requirements

- Submission Requirements

- Application Reviews

- Instructions on Content and Format Application

- Other Terms and Conditions

- Annexes

### 3.2.3 Unsolicited Applications

The Program may make an award based on an unsolicited application (note if the APS is open this category doesn´t apply), without the benefit of competition, when the application:

- Clearly demonstrates a unique, innovative, or proprietary program;

- Demonstrates a unique capacity by the applicant to carry out proposed activities where there is clear support for such activities and there is compliance with Program objectives, deliverables, and plans; and

- Is supportive of the Federal Awarding Agency’s development objectives.

Unsolicited applications are those submitted by an applicant to the Program or the Federal Awarding Agency solely on the applicant’s initiative, without prior formal or informal solicitation from POA, the Program, or the Federal Awarding Agency. In this case the pass-through entity, must certify that:

- The Program did not solicit the application.

- Based on a review by the appropriate technical committee, the application is considered unique, innovative, or proprietary.

- It fits within an Assistance Objective and the prime award’s Statement of Work and the Work Plan.

When the terms of an unsolicited application fits within the scope of a published and open APS, the application may be considered under the APS. The unsolicited application is considered to have competed under the APS and no justification for an exception to competition is required. A grantee request to extend an on-going relationship must not be considered an unsolicited application. In that case, the Program must prepare a justification using the guidance for amendments and follow-on assistance awards.

### 3.2.4 Justification to Restrict Eligibility (JRE)

Eligibility may be restricted for awards when justified in accordance with Federal awarding agency regulations. Restricted eligibility refers to any funding opportunity that is limited to a specific type of entity or otherwise narrows the pool of applicants that may compete for a grant. This limitation is most typically used for sole source awards (including follow-on awards). These awards may be used to restrict an award to one or a limited number of recipients, to extend an award other than those authorized by 2 CFR 200.308(e)(2), to increase the total estimated amount of the award, or to change the fundamental scope of the award objectives. Restricted eligibility awards can take the form of any subaward mechanism as defined in 3.8 Subaward Mechanisms, as program needs dictate. As unrestricted eligibility awards limit competition, the Program must document the need to limit competition in a Justification to Restrict Eligibility (JRE). All non-competitive application, together with complete justifications, shall be submitted to POA HQ for review and approval, after review by the COP and Grants Manager.

Eligibility must not be restricted for:

- Personal preference, for example, personal relationships with key personnel, the perceived burden of a competitive process, or other non-programmatic rationales;

- Avoidance of mobilization or demobilization costs;

- Lack of adequate planning; or

Concerns about the availability of funds, such as expiring funds.

Eligibility can be restricted based on either pre-approved conditions or for programmatic purposes.

#### 3.2.4.1 Restricted Eligibility Based on Pre-Approved Conditions

Only the AOR has the authority to make a determination to restrict eligibility based on one of the following pre-approved conditions that are applicable to the Program. The Program must provide a written description to the AOR and request a determination.

- Simplified Acquisition: Eligibility will be limited when the award is at or below the simplified acquisition threshold set by the Federal Acquisition Regulation. This restriction should generally not be used to restrict eligibility to a single organization; however, if there are unique circumstances that support an award to a single organization then the Program must document these circumstances and submit it in writing to the AOR.

- Congressionally Mandated Programs: The Federal Awarding Agency may ask the Program’s pass-through entity to make an award for which legislation includes a binding Congressional directive that specifies that the Federal Awarding Agency make an award to the particular organization. The determination must include a copy of the statute that identifies the awardee, as well as any information that supports the planned activity. the Awarding Officer’s Representative (AOR)’s communication on this account to the Program will be needed for the JRE memo.

#### 3.2.4.2 Restricted Eligibility Based on Programmatic Purposes

The Program must submit a programmatic rationale for restricting eligibility consistent with this section, and support how the rationale outweighs the Federal Awarding Agency’s preference for, and the benefits of, an unrestricted competitive process. Only the AOR has the authority to make a determination to restrict eligibility based on programmatic purposes.

The following are some examples of programmatic rationales for restricting eligibility based on a written determination:

- New Entrants:  Increasing the Agency’s partner base by restricting eligibility to organizations that have not previously received direct award from the Federal Awarding Agency;

- Local entities: Developing the capability of a local entity or locally established entity by making a direct award to such entity that has previously only received subawards or grants under contract (for example, a transition award). If eligibility for award is restricted to local entity or locally established entity, U.S. organizations may not submit an application for the award unless the program is re-advertised to provide unrestricted eligibility, allowing all U.S. organizations an opportunity to submit an application;

- Exclusive or Predominant Capability: The Program may restrict eligibility when trying to access specialized skills or experience through an award to a grantee with exclusive or predominant capability based on proprietary resources, specialized facilities, or unique relationship with the national government or other institutions in the cooperating country or intended beneficiaries

    - The pass-through entity must describe in sufficient detail the uniqueness of the proposed grantee and how it applies to the supported activity. The justification must also describe what, if any, other options the Program explored. This exception may not be used to continue an ongoing relationship when the applicant developed the exclusive or predominant capability during performance of an award. In that case, the pass-through entity should prepare a justification following the guidance for amendments and follow-on agreement awards. It also may not be used to continue an ongoing relationship with a grantee that received a non-competitive award.

- Disasters: Responding to a disaster, violent conflict, political crisis, or other emergency situation that requires an award to be made more rapidly than unrestricted competition can accommodate; or

- Science and Technology: Eligibility may also be restricted for developing promising science and technology concept; or a unique, innovative, or proprietary solution addressing a pressing development challenge. For purposes of this exception, innovation means significant, not incremental, improvements in development impact and the process that translates knowledge into economic growth and social wellbeing;

- Science means the process of generating knowledge based on evidence, including the systematic study of the nature and behavior of the material and physical universe, based on observation, experiment, and measurement, and the formulation of laws to describe these facts in general terms; and

- Technology means the application of scientific knowledge to practical problems, including the tools, processes, and techniques, created by such application of knowledge.

- Follow-on Award or Amendments: The AOR must also approve the written determination for an award or amendment to a single organization as a follow-on with substantially the same program description as an existing award to that organization.

To use this exception to restrict eligibility, the Program must provide a written rationale that the proposed award or extension is for science and technology purposes.

#### 3.2.4.3 JRE Process

The JRE sets forth the facts and rationale justifying the restricted eligibility and includes a description of the activity, its estimated value, the exception being used and why it needs to be used. Each justification must contain sufficient facts and rationale to justify the use of the specific exception cited. For contracts awarded under restricted eligibility, the pass-through entity will also ensure that proposed costs are fair and reasonable.

The pass-through entity is responsible for preparing the JRE for POA HQ review and approval. The JRE must first be reviewed by the COP and Grants Manager. Once POA HQ approves, if necessary, POA HQ will request concurrence/approval of the Awarding Officer’s Representative (AOR).

## 3.3 Evaluation and Selection of Applications

All eligible applications will be reviewed by a selection committee composed of at least three (3) Program staff members. Committee members must possess the requisite technical knowledge or expertise to review the programmatic merits of the applications. This committee will be led by a selection committee chairperson, who will be a non-voting member of this group. His/her main role will be to collect all applications, ensure these meet the requirements of the announcement, follow up with applicants to clarify any information submitted in the application. Next, the chairperson will coordinate with senior managers to appoint the Program staff members, who will serve on each selection committee, ensuring there is no conflict of interest with the organizations whose applications are being reviewed. Finally, the chairperson will provide the selection committee the evaluation/scoring criteria stated in the APS or RFA, location of eligible applications, evaluation tools, establish deadlines, coordinate any evaluation meetings as needed, and document the selection process to ensure all the eligible applications are reviewed and evaluated with rigor and compliance to the selection criteria outlined in the solicitation. All participating members of the Selection Committee must keep selection information and applicant proprietary data confidential.

## 3.4 Eligibility of Subawards

Eligibility for subawards refers to the criteria and requirements that organizations must meet to receive funding passed through a primary award recipient.

### 3.4.1 Ineligible Organizations for Subawards

the Program organizations that will be ineligible for subawards include the following:

- Those who had prior awards terminated by POA or the Federal Awarding Agency for performance issues.

- Entities that appear on the System for Award Management (SAM) with an active exclusion as suspended or debarred.

- Entities that refused to sign all the required the Federal Awarding Agency certification and assurances.

- Entities that appear on the Specially Designated Nationals and Blocked Persons (SDNBP), or entities that appear on the Office of Foreign Assets Control (OFAC) list, or the United Nations Security Council Consolidated List.

## 3.5 Subrecipient Risk Evaluation

Prior to the issuance of a subaward agreement with a potential subrecipient under this Program, the pass-through entity must evaluate the risks posed by subrecipient that may affect the success of the Program.

The goal is to determine if the applicant possesses or has the ability to obtain the necessary management competence to plan and carry out the program description to be funded, and the applicant will practice mutually agreed upon methods of accountability for funds and other assets provided by POA. The assessment will inform Program staff of the potential risk for non-compliance to guide the appropriate level of monitoring. The Program staff must assess the administrative, financial, and programmatic capabilities of the subrecipient. Critical criteria include, but are not limited to:

- Access the ability of the subrecipient to perform the services required by the Program, including assessment history of performance;

- Confirm that subrecipient has not been debarred or suspended from receiving federal funds;

- Confirm the subrecipient is able to properly account for Federal Awards and has a cost control system that complies with Generally Accepted Accounting Principles (GAAP);

- Review Internal controls, financial stability, and quality of management systems to ensure they are adequate to manage and administer the program description to be performed. Including review of the subrecipient’s system of internal controls on segregation of duties, handling of cash, contracting procedures, and personnel and travel policies

- Access the subrecipient’s ability to comply with the requirements included in the Subpart D of the Uniform Guidance, Post Award Requirements, 2 CFR 200, and mandatory provisions under the prime award;

- Determine if the subrecipient meets the requirements in 2 CFR 200.331-333 for the administration and monitoring of subawards (if there will be subawards issued)

- Determine if the subrecipient meets the standards set forth in 2 CFR 200.317-327 regarding procurements (if procurement is a large portion of the award); and

- Review Uniform Guidance Audit or other audit results, if available, for factors that could affect the release of a subaward.

To complete the pre-award risk assessment, Program staff will need to complete the Subrecipient Risk Assessment Tool found in Annex C and collect the required supporting documentation. Required documentation includes but is not limited to:

- Registration documents including Charter or Constitution and Articles of Incorporation.

- Audited Financial statements for the past 2-3 years (if available).

- Copies of the last 2-3 years external audits (if available).

- Profile and experience of the organization.

- Organizational Chart.

- CVs of the proposed team for the implementation of the project.

- Copies of internal controls, policies and procedures for human resources, operations, finance, etc.

- Copies of sample expenditures and documentation.

- To support the data collection process, potential subrecipients will be asked to complete the Pre-Award Assessment Questionnaire found in Annex D. The questionnaire is designed to help determine a subrecipient’s financial and management strengths and weakness, which helps assess risk and dictates the monitoring plan for subrecipients.

Once the Subrecipient Risk Assessment Tool is completed, the Program staff member leading the subrecipient evaluation process will need to convene a risk assessment review panel. The panel at a minimum should be comprised of the Program staff leading the evaluation, the grants/compliance officer, and the other member of the finance and administration department. The panel will be responsible for jointly reviewing the supporting documentation submitted by the subrecipient and finalizing the Subrecipient Risk Assessment Tool. Based on the panel’s results, risk assessment tool will identify the subrecipient as “Low,” “Medium,” or “High” risk. The varying risk levels will dictate the specific monitoring activities to be performed by Program staff. The Program staff leading the evaluation process will be responsible for summarizing the results and notes from the panel in a memo.

### 3.5.1 Subrecipient Monitoring Plan

Based on the results of the pre-award risk assessment, the Program staff will need to create an effective subrecipient monitoring (SRM) plan to ensure proper stewardship of Federal funds. Subrecipient monitoring is essential at all stages of the subaward process from application to award closeout. The plan should implement monitoring and oversight where necessary to ensure that subaward is used only for authorized purposes; in compliance with established requirements; and that subaward performance goals are being met.

The below are some of the suggested subrecipient monitoring strategies to implemented as special award conditions based on a subrecipient’s perceived riskiness.

- Review audit reports from the subrecipient as available.

Low

Risk

Review invoices and expenditures for:

  - Reasonable, allocable, and allowable expenses for performance of both the subaward and the Federal award.

  - Timeliness, completeness and accuracy of expense report and invoice.

  - Expenses made in accordance with GAAP and represent actual costs and not budget and/or projected amounts.

  - Expenses ordinary and necessary for operation or performance.

  - Work completed is in accordance with the period of performance.

  - Proper procurement methods were followed.

  - Travel costs are reasonable and consistent with established travel policy.

  - Identify any conflicts of interest that exist.

  - Correct calculation of indirect or de minimis rates.

  - Compliance with all requirements including 2 CFR 200 and mandatory provisions under the prime award and special terms (as applicable)

- Complete all monitoring steps listed for low risk, plus the following:

Medium

Risk

If findings exist on audit reports, determine risk to the program and implement a mitigation strategy.

- Perform frequent review of audits and one on-site audit annually.

- Request support documents for all financial reports and expenses.

- Request and monitor invoices and financial report on a more frequent basis (i.e. monthly).

- Establish additional prior approvals.

- Request samples of suspension and debarment search results.

- Require payments as reimbursements rather than advances.

- Withholding authority to proceed to the next phase until receipt of evidence of acceptable performance within a given performance period.

- Provide training and technical assistance throughout the period of performance including:

  - Educate subrecipients on subaward guidelines and 2 CFR 200 requirements.

  - Host workshops prior to or throughout the period of performance to educate subrecipients.

  - Invite subrecipients to trainings or webinars relating to the subaward.

High

Risk

Complete all monitoring steps listed for low and medium risk, plus the following:

- Test internal controls of subrecipient to determine compliance with 2 CFR 200:

  - Sample procurement document.

  - Sample travel policy documents.

  - Sample inventory tracking and documentation.

- Perform frequent on-site audits and review audits.

- Withhold payment, if necessary, for supporting documentation that is not complete or sufficient.

If the risk assessment reveals a high potential for financial risk, a proposed risk mitigation strategy will be developed where the frequency and monitoring strategies are based upon the specific organization and the nature of the program description to be completed by the subrecipient.

Complete documentation of monitoring activities performed must be retained which includes reports received, supporting documentation collected, trainings provided, site visit results, and all contact/ communications.

The results of the pre-award risk assessment and the propose subrecipient monitoring plan must be submitted to POA HQ and POA’s COP for prior approval from POA and then the Federal Awarding Agency before the pass-through entity can issue a subaward.

### 3.5.2 Reoccurring Subrecipient Risk Evaluation & Monitoring Plan

The subrecipient risk evaluation and monitoring plan is a continuous process that is accomplished throughout the length of the subrecipient. It is an organized methodology for continuously identifying and measuring the risks; managing appropriate risk mitigations; and tracking the implementation to ensure successful risk control and reduction. Effective risk management depends on risk assessment planning; early identification and analyses of risks; early implementation of corrective actions; continuous monitoring and reassessment; communication, documentation, and coordination. As part of the continued monitoring process, the Program will require the pass-through entity to complete a reoccurring risk evaluation annually upon the contract renewal date. The pass-through entity should complete the “reoccurring risk assessment tab” in the Subrecipient Risk Assessment Tool found in Annex C. Based on the results of the reoccurring risk evaluation, the pass-through entity must update the subrecipient monitoring plan.

## 3.6 Pre-award and Negotiation

The selection of a potential subrecipient does not guarantee an award. The final determination must be made by the pass-through entity after it is satisfied that the potential subrecipient has the capacity to adequately perform the award in accordance with the terms and conditions of the prime award from the Federal Awarding Agency.

Potential subrecipients must demonstrate that they possess, or have the ability to obtain, the necessary financial and management competencies to account for federal funds. To make the determination, the pass-through entity will enter into a pre-award and negotiation phase.

### 3.6.1 Requirements for Pass-Through Entities to Subaward

Every pass-through entity issuing awards under the Program has certain responsibilities to ensure potential subrecipients are vetted and eligible to receive subawards in accordance with 2 CFR 200.332. To comply with the requirements, POA requires that pass-through entities complete the Pass-Through Entity Responsibilities Checklist found in Annex E. A copy of the checklist must be submitted to POA HQ and the COP as part of the package to obtain prior approval from POA and the Federal Awarding Agency.

#### 3.6.1.1 System for Award Management (SAM)

To be eligible for a subaward a subrecipient must have an active unique entity identifier (UEI) number prior to signing a subaward agreement with the pass-through entity. Any recipient (including prime recipients and subrecipients) of federal funds must not transact or conduct business with any individual or entity that has an active exclusion on the System of Award Management (SAM) (www.sam.gov). The list contains those individuals and entities that the USG has suspended or debarred based on misconduct or a determination by the USG that the person or entity cannot be trusted to safeguard USG funds. Suspended or debarred entities or individuals are excluded from receiving any new work or any additional USG funding for the duration of the exclusion period.

Prior to signing subaward agreements with subrecipients, the pass-through entity must conduct a suspension and debarment check on SAM and retain a PDF or screenshot copy of the search results and retain in the subrecipient file. SAM checks must also be run on any subaward key personnel to ensure they are not prohibited from receiving federal funds.

If the pass-through entity fails to complete the SAM check, POA and/or the Federal Awarding Agency may disallow costs, annul, or terminate the contract, debar, or suspend the recipient, or take other remedies as appropriate, if any recipient violates this provision.

#### 3.6.1.2 OFAC - Specially Designated Nationals and Blocked Persons, and the United Nations Security Council Consolidated List

To prevent against providing support to entities determined to have committed or pose a significant risk of committing acts of terrorism that threaten U.S. interests, pass-through entities are required to check potential subrecipients against the OFAC list, the SDNBP, and the UN Security Council Consolidated List. Proof the showing that these searches have been completed must be retained by the pass-through entity and stored in the subrecipient file. POA must be immediately notified, and the pass-through entity must cease support, transactions, or dealings with any individual or organization that is designated by the USG as a Foreign Terrorist Organization or as a Specially Designated Terrorist.

### 3.6.2 Budget Analysis and Cost Negotiation

As part of the award process, the pass-through entity must perform a budget analysis and enter into cost negotiations with the subrecipient. All proposed costs and budgets must reflect reasonable, allocable, and allowable costs; and be in accordance with the applicable cost principles and OMB Circulars for U.S. Federal government grants.

When reviewing costs, the pass-through entity must review the cost breakdown; and evaluate and analyze specific elements of costs for reasonableness and allowability of costs in the budget, and the allowability of the costs under the applicable cost principles. Specifically, the budget and cost analysis will help determine:

- The extent of the subrecipient’s understanding of the financial aspects of the program;

- If the budget is clear and reflects best use of resources;

- The subrecipient’s ability to perform activities within budget;

- The extent to which the subrecipient’s plans will accomplish the program objectives with reasonable, economy and efficiency; and

- Any special conditions relating to the costs that are in the award.

The pass-through entity must determine the level of the cost review based on the nature of the program, the amount and type of costs involved, and past experience with the potential subrecipient.

The budget and cost analysis will be documented, along with other pre-award evaluations in a Negotiation Memorandum. The memo will include information on any points or costs negotiated.

In the case of Fixed Amount Awards (FAA), the pass-through entity determines and negotiates the fixed price of an FAA and payment structure. In the memo, the pass-through entity should also provide justification for selecting an FAA mechanism.

#### 3.6.2.1 Allowable and Unallowable Costs

Principals for allowable cost are based on the premise that subrecipients are managing the funds in a manner that is consistent with the program objects and employing sounds management practices and internal controls to ensure proper, efficient, and compliance expenditures.

For cost to be considered allowable under a subaward, the cost must be:

- Reasonable - A cost is reasonable if, in its nature or amount, it does not exceed that which would be incurred by a prudent person under the circumstances prevailing at the time the decision was made to incur the costs. To be reasonable, a cost must be:

  - Of a type generally recognized as ordinary and necessary for the performance of the award;

  - Be incurred using generally accepted business practices; and

  - Be incurred with prudence concerning the circumstances.

- Allocable - A cost is allocable to a particular grant in accordance with the relative benefits received. A cost is allocable to a grant if is treated consistently with other costs incurred for the same purpose in like circumstances and if it is incurred specifically for the award or benefits both the award and other work and can be distributed in reasonable proportion to the benefits received.

- Necessary – A cost is necessary to accomplish the project objectives and applicable industry or program standards.

Additionally, allowable costs conform to any limitations or exclusions set forth in cost principles established by 2 CFR 200-Subpart E, are determined in accordance with GAAP, not included as cost share in another USG funded award, be adequately documented, and be treated in a consistent manner. Any commodities purchased by the Program must not be on the Federal Awarding Agency’s list of “ineligible commodities.

Unallowable costs are those that cannot be reimbursed under the subaward. If there are any questions on allowability of costs, the subrecipient should consult the pass-through entity. Certain costs are explicitly unallowable under the Program. These include but are not limited to:

  - Equipment purchases are prohibited by subrecipients. Any equipment purchased with USG funds must vest in accordance with the prime award; either with the Federal Awarding Agency or POA. Equipment cannot vest with the subrecipient; However, the subrecipient may use equipment, assuming proper protocols are in place for tracking the condition and location of said equipment.

  - Any commodity which does not comply with, or which is not procured in a manner that compiles with, the USG commodity procurement procedures.

  - Lobbying and political activity;

  - Bad debts of the subrecipient;

  - Entertainment costs;

  - Fines and penalties;

  - Fundraising costs;

  - Alcoholic beverages;

  - Goods or services for personal use;

  - Purchase of goods from suppliers as may be identified by the Federal Awarding Agency's as debarred, suspended, or ineligible;

  - Costs related to cost share claimed under the Program or other USG funded awards; and

  - All other costs deemed unallowable under 2 CFR 200.

### 3.6.3 Program Description

As part of the pre-award negotiation, pass-through entities must evaluate and review the subrecipients program description (PD). The PD should provide the following:

- A brief background (including context and current situation);

- Purpose of the award including statement on the specific problem or opportunity the activity the award is designed to address;

- State the development method and describe the theory of changes that is the basis for the program design (including results and logical framework);

- List of deliverables and timelines for completion;

- Proposed team composition and management capabilities; and

- Budget/cost application.

During the pre-award negotiation phase, the pass-through entity should strengthen the PD, as necessary. The final PD for subrecipients will require written approval from the COP, and the Federal Awarding Agency (as applicable).

### 3.6.4 Special Award Conditions

If a potential subrecipient has a strong application, but after the risk evaluation the subrecipient is found to have a history of poor performance, is not financially stable, has insufficient management systems, has not conformed to the terms and conditions of a previous award, or presents another deficiency, the pass-through entity may impose additional requirements as needed in the form of special award conditions. The potential subrecipient must be notified in writing of the following:

- The nature of the additional requirements;

- The reason(s) the additional requirements are being imposed;

- The nature of the corrective action needed to remove the additional requirements, if applicable;

- The time allowed for completing the corrective actions if applicable; and

- The method for requesting reconsideration of the additional requirements imposed.

Special conditions to an award may include:

- Requiring payments as reimbursements rather than advance payments;

- Withholding authority to proceed to the next phase until receipt of evidence of acceptable performance within a given performance period;

- Requiring additional, more detailed financial reports;

- Requiring additional project monitoring, which can include site visits;

- Establishing additional prior approvals; or

- Requiring the recipient to obtain technical or management assistance, which includes:

  - Requiring the subrecipient to contract for technical assistance or

  - Having POA staff provide technical assistance and training.

Special award conditions may be removed once the subrecipient has demonstrated that issues of concern no longer exists. All special award conditions must be included in the negotiation memorandum, along with the weakness identified.

### 3.6.5 Negotiation Memorandum

Prior to issuing the award the pass-through entity will enter into negotiations on the cost for the total award and technical implementation. The pass-through entity is responsible for determining that the cost application meets the objective(s) of the proposed program by the applicant and the costs are reasonable, allowable, and allocable. A memo of negotiation will be prepared for each award and may include the following: cost analysis, summary of selection process, selection committee review, competition process, explanation of award, etc. For FAAs, the pass-through entity must have adequate cost information (historical and/or unit pricing) available to allow the pass-through entity to determine and negotiate the fixed price of an FAA and payment structure. In the memo, the pass-through entity should also provide justification for selecting an FAA mechanism. Negotiation Memorandums will also be prepared for any proposed grant modifications.

### 3.6.6 Certifications, Assurances, and Other Statements

Prior to signing grant agreements, the pass-through entity must obtain signed copies of the following:

- Certification on Lobbying (22 CRF 227);

- Prohibition on Assistance to Drug Traffickers for Covered Countries and Individuals;

- Certification Regarding Support to Terrorists;

- Certification Regarding Trafficking in Persons; and

- Certification of Recipient;

- Self-Certification; and

- Other statements (as applicable):

## 3.7 Prior Approval to Subaward

For all subawards (assistance instruments) including modifications thereafter, POA will need to obtain prior approval from the Federal Awarding Agency. The Awarding Officer’s Representative (AOR) has approval authority up to the stated threshold as outlined in the AOR Designation Letter. The Agreements Officer (AO) approval is required for anything above this threshold, if applicable. Federal Awarding Agency approval is needed either during the negotiation/award process or through separate approval during the implementation phase.

## 3.8 Subaward Mechanisms

During discussions with potential subrecipients, anticipated subaward payment mechanism should be raised. Depending on the dollar value of the expected award, capacity of the subrecipient, activity design/nature of activity, duration, and anticipated payment method, subawards are issued as cost‐reimbursable, fixed amount or as in-kind grants. Cost reimbursement subawards should be used when the work is general and few, if any, deliverables are anticipated other than progress reports. Fixed amount subawards may be used when specific, well‐defined deliverables are listed in the statement of work. In-kind grants are particularly useful when the subrecipients experience capacity and/or experience is limited, as it provides a tool for the pass-through entity to procure goods and services on behalf of the subrecipient and allow the subrecipient to utilize the goods and services for implementation of the program. Below is a chart summarizing key difference of the potential contract mechanisms.

| Category | Cost Reimbursable Awards | Fixed Amount Awards | In-Kind Grants |
| --- | --- | --- | --- |
| Payment mechanism | Provides for payment of allowable incurred costs to the extent permitted in the prime award | Provides for a price that is not subject to any cost adjustment on the basis of the subrecipient’s experience in performing the subaward | Pass-through entity will make all payments, no actual cash is received by the subrecipient. |
| Certainty of Costs | Establishes an estimate of total costs for the purpose of obligating funds and establishes a ceiling that the subrecipient may not exceed | Provides for the maximum incentive for the subrecipient to control costs and perform the milestones in the most effective manner | Pass-through entity has complete control over costs and procurement. |
| Type of work | Appropriate if work cannot be precisely defined or cost precisely estimated | Appropriate if there can be a clear program description, solid cost estimate and well‐articulated deliverables | Appropriate for procurement of goods and services when the subrecipient has limited capacity and/or no experience. |
| Administrative Management and Flexibility | Higher administrative burden but allows greatest flexibility (add $ or time and perform work within scope until funds/time are exhausted) | Lower administrative burden for Program staff but less flexible as milestones would need to be updated and costs reviewed to negotiate updated fixed price | Higher administrative burden for Program staff as all goods and services must be procured by the pass-through entity, but more flexibility in determine price and quantity of goods and service |
| Maximum Amounts | No maximum amount | Simplified Acquisition Threshold set by the Federal Acquisition Regulation in accordance with § 200.333 | No maximum amount, rather based on expected amount of goods and services |
| Advances | Advances are allowed as long as subrecipient meets the conditions of § 200.3 for advances. | No advances allowed | No advances as subrecipient does not receive any cash |
| Duration | In accordance with prime award start and end dates | Maximum three years | In accordance with prime award start and end dates |
| Subawards | Allowed with prior approval | Not allowed | Not allowed |

Cost Reimbursable Awards:

Why might Program staff issue one?

- Program description cannot be sufficiently detailed at start to create specific milestones.

- Cost analysis at application stage is easier.

- More control over spending – can monitor by budget line item.

- Effective way to provide initial funds to cash‐strapped organizations, can provide advances.

Why might Program staff issue not one?

- More time consuming to program team to ensure continued performance and award compliance.

- Increased reconciliation and financial reporting required.

- If Subrecipient runs out of money, they are not required to continue working, however, could have other implications.

Fixed Amount Awards:

Why might Program staff issue one?

- Subrecipient has freedom to re-budget within funding ceiling.

- Limited financial reporting ‐ less administrative burden, no reconciliations.

- Risk is on Subrecipient to provide all work within established price.

- Payments tied to deliverables provide incentive to complete work.

Why might Program staff not issue one?

- Comprehensive price analysis needs to be done upfront, before subaward is issued.

- Program description and deliverables/milestone schedule needs to be specific and detailed; the more milestones, the better.

- Modifications on price cannot occur unless there is a corresponding increase in program description’s tasks/deliverables.

- Subrecipient must perform work for a fixed price – if they run out of money, they may lose incentive to complete performance.

- In situations where subrecipient entities lack sufficient capital and requires an advance. It must be cost reimbursable if advances are used.

In-Kind Grants:

Why might Program staff issue one?

- Subrecipient has limited capacity and/or no experience to properly procure goods or services.

- Safer option for high risk subrecipients as the pass-through entity will ensure compliance with the Federal Awarding Agency’s procurement regulations and pass-through entities policies and procedures.

- More control over spending as procurement is done by the pass-through entity.

Why might Program staff issue not one?

- Higher administrative burden as all procurement is done by the pass-through entity.

- Subrecipient has sufficient capacity and experience to properly procure goods and services.

### 3.8.1 Standard Grant Agreement (SGA) – Cost Reimbursable

A standard grant agreement (SGA) is a contract mechanism that requires greater financial responsibility and accountability, is often used to fund larger and/or complex activities funding larger, and based on the subrecipients needs for advances which require special conditions. SGA are based on a cost reimbursement basis, which implies that the subrecipient spends the money on subaward activities using their own resources and subsequently requests reimbursement for reasonable, allocable, and allowable costs. Cost reimbursement subawards involve much more monitoring of performance and cost during the life of the project, and each invoice must be analyzed for reasonableness and for determining whether adequate work is being completed. If the reimbursement method is used, the pass-through entity will make the payment within 30 days after receipt of the financial reports, unless the reporting is incorrect, incomplete, or improper.

#### 3.8.1.1 Obligations

When issuing SGAs, the pass-through entity must utilize obligations. Obligations are the total amount of funding the pass-through entity has committed to spend on the grant to date, which may be only a portion of the total award, meaning it is the maximum amount currently available to the subrecipient for implementation of the Program. Meanwhile, the total award amount is the anticipated amount to be spend on the grant by the pass-through entity. Incremental funding will be allocated if and when additional funding becomes available, and the obligation amount increased. If the subrecipient’s expenditures exceed the obligated amount, the pass-through entity may not excess amount.

#### 3.8.1.2 Eligibility for Advances

Under the SGA if the financial needs of the subrecipient require, they may be eligible for program advances. An advance mechanism means that payments will be made before the services are received and the advance will be adjusted against the financial and technical reports provided by the subrecipient after for reasonable, allocable, and allowable expenses. Subsequent advances are then provided based on the funding needs of next period and obligated amount of subaward. Subrecipients will be required to submit a monthly detailed cash flow request with projected expenditures to the pass-through entity’s review. Once reviewed if the pass-through entity may issue the advance. Often the cash flow advances will not clear entirely each month, and therefore any leftover funds should be taken into consideration as cash on hand when determining the next month’s cash flow request. Advances should be in accordance with actual working capital needs for the month to avoid excess cash on hand and to minimize the time elapsed between the receipt of the advance and subsequent expenditure disbursement. The timing and amount of cash advances must be as close as is administratively feasible to the actual disbursements by the subrecipients. Advances should be deposited into and maintained in insured account when possible.

In order for a subrecipient to be eligible for program advances:

- They must meet the requirements of § 200.3 for advances.

- The subrecipient must maintain financial managements systems that meet the standards for both fund accountability and control.

- The subrecipient must maintain written procedures that minimize the time elapsing between the transfer of funds and their disbursement by the subrecipient.

- Subrecipients will be authorized to submit requests for advances and reimbursements monthly.

- The advances will be limited to the minimum amounts needed and be timed to be in accordance with the actual, immediate cash requirements of the subrecipient in carrying out the purpose of the approved program or project.

- The timing and amount of cash advances shall be as close as is administratively feasible to the actual disbursements by the subrecipient.

### 3.8.2 Fixed Amount Award (FAA)

A FAA is typically used when programmatic accomplishments and results are easily quantifiable into benchmarks or deliverables and when the work that will be performed can be priced with a reasonable degree of certainty. With FAAs, due diligence is done at the application stage through a price analysis and review of past experience with similar types of work for which outcomes and their costs can be reliably predicted, or for which the pass-through entity can easily obtain price estimates such as bids and quotes. FAA invoices are paid only when deliverables are received and approved. Under 2 CFR § 200.333, FAAs cannot exceed the Simplified Acquisition Threshold, provided that the subawards meet the requirements for fixed amount awards. Additionally, FAA subaward durations cannot exceed three years. FAAs must be approved by the POA HQ and the Federal Awarding Agency.

Under FAAs payments are fixed, tied to deliverables and milestones, and governed by the following conditions:

- Award complies with the conditions for fixed amount awards found at 2CFR 200.201;

- Pass-through entity complies with the requirements of applicable federal awarding agency.

- All allocable costs must be identified in the grant agreement and sufficient cost information (historical or unit pricing) available to determine and negotiate the FAA.

- Negotiations ensure to the extent possible that the funds budgeted will be the actual cost of the effort and that no funds will remain upon completion of the project;

- Pass-through entity must be able to quantify programmatic results and develop milestones in accordance with applicable federal awarding agency requirements.

- Equipment costing more than $10,000 or having a useful life of more than one year and the purchase of real property (such as land and improvements) are not allowable costs.

- Subrecipient receives payment on a reimbursement basis (no advances).

The milestones will typically include the following:

- Description of the product, task, deliverable, or measurable goal to be accomplished;

- Description of how the subrecipient will document the completion of the product, task, deliverable, or goal;

- Amount the subrecipient will receive for the deliverable and milestone.

- Some milestones may also have dates indicating when the milestone is expected or required to be completed.

FAAs can be a tool utilized to with subrecipients that have little to no experience implementing with USG/Federal award funds that allows the pass-through entity to build their capacity. During the FAA period, the subrecipient can work with the pass-through entity to strengthen and improve their internal procedures, systems, and policies. By doing so, they can then improve their ability to access and manage resources from the Federal Awarding Agency or other donors. If a FAA is awarded to a subrecipient with little to no experience, the pass-through entity will need to provide assistance during all stages of the subaward including pre-award, implementation, and post-award for compliance with all USG and applicable Federal rules and regulations and to achieve expected outcomes of the subaward.

### 3.8.3 In-Kind Grants

In-kind grants for goods, supplies, or services, the pass-through entity will directly procure goods and services in close coordination with the subrecipient. A property disposition request will be submitted to the AO to seek prior approval before the in-kind grants are passed to the subrecipient. Once the request is approved and the goods or services are purchased, they are delivered immediately to the subrecipient. The subrecipient is required to use the goods and services directly for the purposes specified in the program description awarded with the grant.

For in-kind grants, the pass-through entity undertakes the entire procurement process and ensure its compliance with the Federal Awarding Agency’s procurement policies and regulations. Additionally, all in-kind grants will follow the pass-through entity’s procurement policy and procedures. The pass-through entity in coordination with the subrecipient must ensure that all program property is properly used once the grant is completed. In-kind grants may be for, but is not limited to the procurement of supplies, workshop venues, transportation costs, airfare, and other items that the grantee is not able to procure directly. In-kind grants may be useful in situations where the subrecipients have limited capacity and/or experience. As the pass-through entity will handle all the procurement, a review of the subrecipients financial and programmatic policies and procedures are not considered necessary, instead the focus will be to determine the most effective and efficient way to achieve the intended objectives and outcomes.

Under in-kind grants no disbursements are made directly to the subrecipient, however, the subrecipient is an active partner in determining procurement needs and how the goods and services will be utilized. The pass-through entity will procure all the necessary goods and services on behalf of the subrecipient and issue payment directly to the vendors. The subrecipient can participate in the procurement process including obtaining quotes and participating the evaluation panel, however, ultimate responsibility for compliance resides with the pass-through entity.

## 3.9 Standard Terms & Conditions

The standard terms and conditions that will control the subaward will be set forth in the subaward agreement signed by the pass-through entity and subrecipient. The standard terms and conditions ensure that the required flow down provisions are incorporated as an integral part of the agreement and are in full compliance with the Federal Awarding Agency policies, rules, and regulations. Pass-through entities should use a subaward template. Upon request, the template will be provided. All subaward agreements will contain at a minimum the following items, clauses, and provisions.

### 3.9.1 Mandatory Standard Provisions

All subaward protocols and processes will follow Applicable Federal awarding agency regulations, applicable Federal awarding agency regulations, and 2 CFR 200.

### 3.9.2 Foreign Tax Reporting (as required)

As required by the prime award, entities will be required to report the amounts of foreign taxes assessed by the foreign government on commodities financed with U.S. Foreign Assistance funds. Any organization (including prime recipients, pass-through entities, and subrecipients) that purchased $500 USD or more worth of commodities with USG funds or paid any customs duties in the country where it is operating during the prior fiscal year is required to submit an annual report on foreign taxes. All subrecipients are required to submit a Foreign Tax Report to the pass-through entity by March 1st of each year. A copy of the required format for the report is found in Annex F: Foreign Tax Report. The following transaction must be reported regarding taxes paid to the government in the country of performance:

- Transactions valued at $500 USD or more (not including the VAT).

- Transactions related to a commodity as defined as supplies, materials, goods, or equipment.

- Purchase related to your USG-funded project.

### 3.9.3 Dispute Resolution

All subaward agreements must include language that delineates dispute resolution mechanisms which need to be followed for any contractual disputes. A dispute is any disagreement which cannot be resolved by the pass-through entity and the subrecipient and any controversy, claim, or dispute otherwise arising out of or in connection with the subaward.

Additionally, all subrecipients should be given a copy of POA’s Whistleblower Policy, for complaints and issues which are required escalation to the COP or POA HQ. Subrecipients must be given orientation about these mechanisms of dispute resolution.

### 3.9.4 Termination and Suspension

Language must be included in the agreement giving the pass-through entity and the Federal Awarding Agency the right terminate a grant, in whole or part, or suspend payments, should the subrecipient become insolvent during the performance of the award or should the subrecipient fail to fulfill their responsibilities as set forth in the subaward agreement. The pass-through entity and/or the Federal Awarding Agency must also have the right to terminate the grant activity (activities) whole or in part on an immediate basis unilaterally in extraordinary circumstances or if such assistance is deemed not in the U.S. national interest, in violations of an applicable law or other extreme circumstance. Termination may also occur upon request of the subrecipient and/or with consent of the subrecipient.

### 3.9.5 Branding and Marking

As a condition of any subaward issued, subrecipients must adhere to the Federal awarding agency’s Branding and Marking Plan. This includes marking with the Federal Awarding Agency Identity of a size and prominence equivalent to or greater than the recipient’s, subrecipient’s, another donor’s, or third party’s is required. In the event the recipient chooses not to require marking with its own identity or logo by the subrecipient, the Federal Awarding Agency may, at its discretion, require marking by the subrecipient with the Federal Awarding Agency Identity.

### 3.9.6 Title to and Care of Property

All property purchased and provided to subrecipients shall be subject to the provisions “Title to and Use of Property.” The title to all property financed under the grant is vested in POA upon acquisition unless otherwise specified in the agreement, however POA and the Federal Awarding Agency reserves the right to make changes to the title of the property during the subaward.

In addition, the provision on title to and use of property, the subrecipient must maintain an accurate description and inventory of the Federal Awarding Agency funded property in accordance with the template provided in Annex G. The subrecipient must also have a system in place to maintain the property and ensure adequate safeguards to prevent loss, damage, or theft. Should loss, damage, or theft of property financed under the subaward occur, the subrecipient must inform the COP immediately, in writing.

### 3.9.7 Controlling Language

It is the Federal Awarding Agency policy that English shall be the official language of all award documents. If an award or any supporting documents are also provided in a foreign language it must be stated in each version that the English language version is the controlling version.

# Subaward Modifications

Subrecipients may request subaward modifications to extend the period of performance, realign the budget, change key personnel, etc. Any modification of a subaward agreement required a written endorsement of the changes by both parties.

Types of modifications:

Unfunded Modifications – are issued when there is a need for material alteration of a programmatic aspect of an agreement and when there is no impact on cost. This can include no cost extensions to the program’s period of performance. If a subrecipient requests an extension on the period of performance, the pass-through entity may approve an extension for a period of performance within their own period of performance under the prime award. Modifications can be used for budget realignment between major line items to cover deficits of line items in excess of the 10% clause on budget flexibility, as long as the budget realignment but does not increase the total budget. The budget re-alignment will require written approval from the COP. Unfunded modifications can also include changes in the scope or objectives of the subaward, change in beneficiaries or targets, changes in key personnel, or changes in the program approach or workplan. The the COP will discuss and receive AOR concurrence on any unfunded modifications to subawards.

Funded Modifications – are all modifications that increase the total funding value of the grant. Before a modification is issued, the COP approval is required and subsequently Federal Awarding Agency approval. While funded modifications may be authorized, the following criteria needs to be considered:

- Must have a clear justification for the need to increase funding and explain the risk of jeopardizing program achievements and/or activities if additional funding is not received.

  - Poor planning or project management by the subrecipient is not an acceptable rationale for requesting a cost modification.

- Cost modifications must be supported by a revised budget and budget narrative, including revised lines and expenditures to date.

  - Revised budgets will be analyzed for accuracy and allowability of expenditure to date.

- Revised program narrative indicating the changes in the program description.

# Noncompliant Subrecipients/Subaward Conflict Resolution

In the event that a subrecipient has been identified to be noncompliant with federal statutes, regulations or the terms and conditions of the subaward, the pass-through entity may impose additional conditions. The determination of the specific condition is at the discretion of Program staff. Potential specific conditions may include, but are not limited to one or more of the following:

- Dictate how subrecipients receive payment.

- Require additional reporting requirements or prior approvals.

- Require subrecipient obtain technical or management assistance.

Program staff will explicitly inform subrecipients of imposed specific conditions and properly removed them once corrected. If noncompliance cannot be remedied through specific conditions, Program staff may enforce one or more severe actions in accordance with 2 CFR 200.339 including:

- Temporarily withhold cash payments pending correction of the deficiency by the subrecipient or more severe enforcement action by the pass-through entity.

- Disallow all or part of the cost of the activity or action not in compliance.

- Wholly or partly suspend or terminate the subaward.

- Recommend that the Federal Awarding Agency initiate suspension or debarment proceedings.

- Withhold further subawards for the project or program.

- Pursue other legal remedies that may be available.

# Subaward Management

The Program will administer the grants in accordance with the prime contract between the Federal Awarding Agency and POA. Grants will be managed in accordance with the appliable Federal awarding agency regulations, 22 CFR 226, and 2 CFR 200.

## 6.1 Financial Management

All subrecipient are required to have financial management and accounting system that will provide for effective financial controls and enable the subrecipient to track, classify, and report financial data to the pass-through entity as required. Financial and accounting records must:

- Provide clear, accurate, current, and complete financial information.

- Be integrated with an adequate system of internal controls to safeguard federal funds and assets.

- Correctly identify purchases made with federal funds and track any cost share (as applicable).

- Maintain financial records, books, documents, and other evidence to performance of, and charges to, the Program that have proper and complete supporting documentation and justify the expenditures as reasonable, allocable, and allowable.

- Ensure records comply with the generally accepted accounting principles (GAAP) in the U.S. and the country of performance to sufficiently substantiate charges to the grant.

- Provide receipt and use of goods and services acquired under the Program.

- Demonstrate overall progress of the program.

Under the Program subrecipients will be expected to provide the following financial reporting:

- Monthly financial reports

  - The report must be in accordance with the approved budget, submitted in the same detailed level as approved within 7 days after the end of each month.

  - Supporting documentation for expenditures over $25 USD will be required.

- Final financial report

  - A complete and final report must be submitted within forty-five (45) following the end date of the subaward. The final report shall include.

    - Cumulative amount disbursed.

    - Resolution of audit findings/questioned costs.

    - Amount of program income earned, if any, and

    - Total amount of unspent funds.

  - Unspent funds at the end of the subaward shall be returned to the pass-through entity together with the final report.

- Inventory Listing

  - Annually, each subrecipient must send the pass-through entity a listing of all inventory items purchased under the Program. A sample of the reporting form can be found in Annex G: Inventory Listing Report.

  - Equipment purchases are prohibited by subrecipients. Any equipment purchased with USG funds must vest in accordance with the prime award; either with the Federal Awarding Agency or POA. Equipment cannot vest with the subrecipient; However, the subrecipient may use equipment, assuming proper protocols are in place for tracking the condition and location of said equipment.

- Foreign tax report

  - By March 15th of each year, subrecipients must submit a foreign taxes report to the pass-through entity. Foreign taxes mean value-added taxes and customs duties assessed by a foreign government on a commodity. A sample of the reporting form can be found in Annex F: Foreign Tax Report.

    - Under the Program the Federal Awarding Agency Agreements Officer has provided an exemption letter, therefore, the prime recipient, and all subrecipients must take reasonable steps to secure an exemption or tax refund.

    - If the prime recipient and/or subrecipients take all necessary steps to obtain exemption and/or a refund, and they are not able to obtain it, the host government taxes will be treated as an allowable cost.

### 6.1.1 Record Retention Requirements

All financial records must be maintained in good order and must be available to the Federal Awarding Agency, POA, and/or the pass-through entity for audit purposes. Unless otherwise notified by POA HQ, the pass-through entity records and subrecipient records that pertain to the Program must be retained for a period of three years from the date of submission of the final expenditure report. Additionally, records must be adequately protected against fire, loss, theft, or damage.

### 6.1.2 Inventory Reporting Requirements

Annually all subrecipients will be required to submit an inventory report to the pass-through entity. As part of the reporting process, the subrecipient must take a physical inventory and reconcile the results with the records and submit a copy of the physical inventory and report to the pass-through entity.

The report must include all large inventory that was purchased with the Program funds. The template for required reporting can be found in Annex G: Inventory Listing Report.

### 6.1.3 Audit Requirements

Any pass-through entity or subrecipient that expends $1,000,000 USD or more during the entity's fiscal year in Federal awards (includes all USG funding prime and subawards) must have a single or program-specific audit conducted for that year. The audit must be done by an independent firm. U.S. nonprofit subrecipients must be audited in accordance with 2 CFR Part 200, Subpart F. The costs associated with this audit are an allowable cost to the subaward. If the pass-through entity or subrecipient has multiple the Federal Awarding Agency and/or USG awards to be audited, the cost of the audit should be split proportionally.

For-profit entities are exempt from the audit requirement, as are any subrecipients spending less than $1,000,000 a year in federal funds. However, the Program may require a subrecipient to conduct an audit according to federal government auditing standards if warranted by the subrecipient’s risk level or past noncompliance. With for-profit entities, the Program will build in compliance requirements into the award documents. Methods to ensure compliance may include pre-award audits, monitoring during the agreement, and post-award audits with for-profit entities.

Once a pass-through entity or subrecipient completes their audit, they will be required to submit a copy to POA HQ within 30 days. If the report reflects any deficiencies, the pass-through entity or subrecipient must also submit a plan for correction.

If the pass-through entity or subrecipient show continued inability or unwillingness to have an audit performed, the Federal Awarding Agency and/or POA HQ will consider appropriate sanctions which may include suspension of all, or a percentage of, disbursements until the audit is satisfactorily completed.

In addition to the audit requirements above, the Federal Awarding Agency may make a request and has the right to conduct an audit any time during the life of the Program. POA also retains the right to conduct a financial review, require an audit, or otherwise ensure adequate accountability of organizations expending federal funds, regardless of the audit requirements above.

#### 6.1.3.1 Audit Certification

Annually by March 31st, each subrecipient must complete an Audit Certification in Annex H. The audit certification will be used to verify if subrecipients must comply with audit requirements contained in 2 CFR Part 200, Subpart F for USG expenditures over $1,000,000 USD. If the subrecipient is required to complete an audit, the subrecipient must confirm the month and year the pass-through entity will receive a copy of the audit. Note, this audit certification requirement does not apply to FAA.

### 6.1.4 Federal Funding Accountability and Transparency Act (FFATA)

The Federal Funding Accountability and Transparency Act (FFATA) requires all prime recipients of federal awards to report purchases of $30,000 USD and greater under federal contracts. The act requires the reported data be made available to the pubic via www.USASpending.gov. The FFATA reporting requirements apply to both U.S. and foreign based entities. The FFATA Subaward Reporting System (FSRS) is the reporting tool Federal prime recipients use to capture and report subaward and executive compensation data regarding their first tier subawards to meet the FFATA reporting requirements.

The reporting thresholds for whether contracts or grants are susceptible to FFATA are found below.

- Subrecipient Reporting

All subawards from March 1, 2011 forward, if the contract value is greater than or equal to $30,000. Modifications or increases in obligation amounts should be reported incrementally in accordance with the obligation date.

- Total Compensation and Names of Top Five Executives

A prime awardee is required to report the names and total compensation of the five most highly compensated officers of the prime or a subaward if:

  - More than 80% of annual gross revenues from the Federal government, and those revenues are greater than $25M annually; and

  - Compensation information is not already available through reporting to the Securities Exchange Act of 1934 or section 6104 of the Internal Revenue Code of 1986.

Award Modifications:

If the initial award is below $30,000 USD but subsequent grant modifications result in a total award equal to or over $30,000 USD, the award will be subject to the reporting requirements, as of the date the award exceeds $30,000 USD.

If the initial award equals or exceeds $30,000 USD but funding is subsequently de-obligated such that the total award amount falls below $30,000 USD, the award continues to be subject to the reporting requirements of FFATA.

### 6.1.5 Program Income

Program income is any gross income earned by the subrecipient that is directly generated by a program activity or earned because of the subaward. Program income can include but not limited to event registration fees, income from other fees or services performed, etc. Any interest earned from program advances is not considered program income. Any program income under the Program will be added to the funds committed by the pass-through entity and may be used in accordance with 22 CFR 226.24 and 2 CFR 200.307.

## 6.2 Programmatic Management

All program reports must be submitted in accordance with the schedule specified in the subaward agreement.

Under the Program subrecipients will be expected to provide the following programmatic reporting:

- Initial workplan

  - A detailed initial workplan covering the first year of program implementation.

- Quarterly progress report

  - Including all updates or accomplishments against the planned activities, updates on targets, milestones, and intermediate results, as well as problems encountered, and interventions implemented to address said problems. The report shall also include cumulative accomplishments.

- Final report

  - The final report will cover final accomplishments against the planned activities.

- Others as required by POA and in agreement with the subrecipient organization

## 6.3 Subaward Closeout

As part of the closeout process of a subaward, the pass-through entity must:

- Closeout the subaward when all applicable administrative actions and all grant related work have been completed.

  - For FAA, this will be done through the approval and acceptance of the final milestones, approval of final payment.

  - For in-kind grants, this will be done through Federal Awarding Agency approval on the formal disposition plan for inventory, and the subrecipients acceptance in writing.

  - For SGA (cost reimbursable), this will be done through review, approval and acceptance of the final financial and programmatic reporting requirements as indicated in the subaward agreement. It includes issuing a final payment if necessary. Similarly, it requires a return of any unused funds.

  - For all grants, subrecipients will need to sign a formal closeout letter.

- Confirm the subaward files contain the essential documents to demonstrate that the subaward was successfully completed and that funds were spent prudently, and costs justified.

- Ensure closeout is completed in time to meet the federal agency’s closeout timeline.

- Make prompt payments to subrecipients for allowable and authorized reimbursable costs charged to the Program.

- Collecting any excess cash and obtain a refund from the subrecipient, which includes the following situations:

  - When any funds are disbursed to but not expended by the subrecipient at the time of expiration or termination of the subaward.

  - If, as a result of audit conducted by POA or the Federal Awarding Agency, it is determined that funds have been expended for purposes not in accordance with the terms of the subaward and the applicable cost principles.

- Establish procedures for accounting for any real or personal property acquired under the Program.

### 6.3.1 Suspension

If a subrecipient fails to comply with certain terms and conditions of the subaward, the pass-through entity may suspend the award. All suspension notices must be provided in writing to the subrecipient and indicate the corrective action to be taken. When an award is suspended, the pass-through entity removes all authority from the subrecipient and no funds may be incurred or expended against the subaward, until corrective action completed by the subrecipient.

### 6.3.2 Disposition Plan

At its discretion, the Federal Awarding Agency determines the disposition of all USG-funded goods and commodities. As part of the closeout process, subrecipients will be required to send an inventory listing of items paid by the Program funds, template found in Annex G. The listing must be accompanied by a disposition plan, which is a detailed description of what the subrecipient proposes to do with unused supplies when the award ends. Final dispositions may:

- Dispose of the items to the subrecipient with no further obligation to POA, the Program or the Federal Awarding Agency;

- Retain the items and the title but pay compensation to the Federal Awarding Agency for the current fair market value of items;

- Transfer the title of the items to the Federal Awarding Agency, POA or another third party.

The disposition plan must be submitted to the pass-through entity and POA’s COP. POA’s COP with obtain approval from the Federal Awarding Agency as necessary on the subrecipients disposition plan.

## Annex A: Conflict of Interest Certification

Conflict of Interest Certification

I, [insert name of individual], hereby certify that, to the best of my knowledge and belief, there are no present or currently planned interests (financial, contractual, organizational, or otherwise), relevant facts or circumstances relating to the work to be performed under the Partners of the Americas award that could give rise to an organizational or personal conflict of interest or would create any actual or potential conflict of interest (or apparent conflicts of interest). This includes conflicts of interest for immediate family members: spouses, parents, children, that would impinge on my ability to render impartial, technically sound, and objective assistance or advice or result in it being given an unfair competitive advantage. In this clause, the term “potential conflict” means reasonably foreseeable conflict of interest.

If applicable, I have disclosed all such relevant information if such a conflict of interest appears to exist to a reasonable person with knowledge of the relevant facts (or if such a person would question the impartiality). Conflicts may arise in the following situations:

- Unequal access to information. A potential contractor, subrecipient, employee, or consultant has access to non-public information through its performance on a contract.

- Biased ground rules. A potential contractor, subrecipient, employee, or consultant has worked, in one contract, or program, on the basic structure or ground rules of another contract.

- Impaired objectivity. A potential contractor, subrecipient, employee, or consultant, or member of their immediate family (spouse, parent, or child) has financial or other interests that would impair, or give the appearance of impairing, impartial judgment in the evaluation of programs, in offering advice or recommendations, or in providing technical assistance or other services as part of its contractual responsibility.

I further certify that I have and will continue to exercise due diligence in identifying and removing or mitigating any such conflict of interest (or apparent conflict of interest).

Name (Please Print)					Signature				Date

## Annex B: Subrecipient vs. Contractor Determination Checklist

| Subrecipient vs. Contractor Determination Checklist |  |  |  |
| --- | --- | --- | --- |
|  |  |  | Comments |
| Subrecipient: |  | Award Start Date: |  |
| Award No. |  | Award End Date: |  |

| Subrecipient / Contractor Determination |  |  |
| --- | --- | --- |
| Listed below are common characteristics of subrecipients and contractors. In determining whether an entity is a subrecipient or contractor, you should consider the substance of the agreement over its form. This list does not include all possible attributes nor does an entity have to meet every attribute. |  |  |
| Questions | Subrecipient | Contractor |
| Solicitation and Competition Is the transaction with the lower tier party subject to free and open competition (or justification as to why sole source)? If “yes”, this is an indicator of a contractor relationship. Instead of procuring the goods or services as described above, did your entity announce the “availability of funding” or announce that you were “seeking applications” for funding? If “yes”, this is an indicator of a sub recipient relationship. |  |  |
| Purchasing Relationship Does the lower tier party provide similar goods or services to many different purchasers? If “yes”, this is an indicator of a contractor relationship. If “no” then indication of a subrecipient. If the entity was chosen because they have the best good/services for the price, it typically has a contractor relationship. Usually, a procurement method is followed, such as a competitive bid or RFP process. In this type of agreement, the entity usually makes a profit by delivering this good or service to the State agency. |  |  |
| Criteria for Selection Which criteria was the most important in selecting the lower tier party: - Ability to demonstrate a financial or public need for funding in order to carry out a project or provide a service; or - Capability to deliver the goods or services to meet your entity’s needs? Answer 1 is an indicator of a subrecipient and answer 2 is an indicator of a contractor. |  |  |
| Statement of Work / Scope of Services Which statement is the most appropriate for the scope of your agreement: - The lower tier party identified the details (scope) of the project/service for which it is seeking financial support; or - You define the scope of work for which you will pay the lower tier party (i.e., you identify what you are buying). Answer 1 is an indicator of a subrecipient and answer 2 is an indicator of a contractor. A contractor normally provides goods and services to the public in a competitive environment and those goods and services are normally available to others for purchase. A subrecipient normally operates in a less competitive environment and the goods or services provided are normally "unique" in nature and available on a limited basis. |  |  |
| Nature of the Award Which statement is most appropriate for the intended use of the funds: - The lower tier party will use the funds to carry out its own public program/project and/or provide a public service; or - The lower tier party is providing goods or services to assist you in meeting your program objectives and these goods/services are ancillary to the overall program scope. Answer 1 is an indicator of a subrecipient and answer 2 is an indicator of a contractor. |  |  |
| Decision-making Authority Does the lower tier party have a substantial amount of authority for making decisions about program delivery and/or does it determine who is eligible to receive assistance or participate in program? If “yes”, this is an indicator of a subrecipient relationship. If “no” then indication of a contractor. |  |  |
| Pricing of the Agreement Which statement best fits the terms of payment: - The lower tier party is reimbursed only for its actual costs incurred for allowable activities as outlined in the contract and the lower tier party should not earn a profit from the terms of payment; or - The lower tier party is paid a set fee-for-service or fixed price at increments above its costs (profit) usually in exchange for the risk it assumes in competing with others to offer the needed goods or services. Answer 1 is an indicator of a subrecipient and answer 2 is an indicator of a contractor. Although a subrecipient is not prohibited from making a profit, typically, a subrecipient does not make a profit and may provide its own non-Federal funding as match or cost sharing. A subrecipient is normally chosen through an application process or an announcement of funding, as opposed to the procurement process described below. Payment to a subrecipient is generally based on actual expenses unless awarded on a fixed amount sub award (2CFR 200.332). It is typical of subrecipients to submit budgets, financial reports, or copies of invoices to the State agency to document activity. |  |  |
| Cost Sharing / Matching As a condition of receiving funds, is the lower tier party required to contribute its own resources (or seek third party in-kind contributions) to help pay for the project/service? If “yes”, this is an indicator of a subrecipient relationship. If “no” then indication of a contractor. |  |  |
| Award Risk Which statement is most appropriate concerning award risk: - The funding is contingent on the lower tier party making its "best effort" to meet the objectives of the award. Although its performance is measured against whether the objectives of the program are met, the grantee assumes little financial risk if performance does not meet goals. This recognizes that assistance is often awarded to try to solve intractable problems that may not respond. - The lower tier party accepts the risk of financial consequences for not achieving the award objectives or failing to provide the agreed-upon goods or services. Answer 1 is an indicator of a subrecipient and answer 2 is an indicator of a contractor. |  |  |
| Applicable Rules Is the lower tier party required to follow the provisions of 2CFR 200 (uniform guidance)? If “yes”, this is an indicator of a subrecipient relationship. If “no” then indication of a contractor. |  |  |
| Treatment of Property Purchased with Award Monies Under the terms of the award, can the lower tier party use the funding to purchase real property, equipment and/or supplies? And, if disposed of or sold, is the lower tier party required to obtain disposition guidance from you and/or return your percentage of the proceeds if the per-unit fair market value exceeds $10,000? If “yes”, this is an indicator of a subrecipient relationship. If “no” then indication of a contractor. |  |  |
| Other factors not listed above: |  |  |
| Final Determination Note: One check in a subrecipient box does not necessarily mean the entity is a subrecipient nor does one check in a contractor box make it a contractor. A judgement should be based on a review of all indicator criteria above. Many agreements or contracts will contain both contractor and subrecipient indicators. Please justify and document your final determination below: Justification: |  |  |

Reviewer Name:________________________________		Date:______________

Signature:_______________________________

## Annex C: Subrecipient Risk Assessment Tool

## Annex D: Pre-Award Assessment Questionnaire

Subrecipient Compliance and Financial Compatibility Questionnaire for USG funded awards

Through accepting a subrecipient, Name of Pass-Through Entity creates a legal duty on the part of the grantee to use the funds in accordance with the provisions of the subaward agreement and applicable U.S. regulations. The purpose of this questionnaire is to provide Name of Pass-Through Entity with current information to assess the financial, accounting, and other operational systems of a prospective grantee. It will also identify any need for technical assistance to help prepare for receiving a Name of Pass-Through Entity grant and to ensure proper accountability in the event a grant is awarded. All information requested in the questionnaire should be answered as completely as possible, using supplemental sheets if necessary, and will be kept in strict confidence. If a grant is awarded, Name of Pass-Through Entity may commission an audit of the program's financial records.

This questionnaire should be returned to Name of Pass-Through Entity as soon as possible. Please contact us to obtain assistance in completing this questionnaire if you have any questions. The completed questionnaire must be received prior to the issuance of a grant by Name of Pass-Through Entity.

Points of Contact:

- XXXXX

Email: XXXXX

- XXXXX

Email: XXXXX

SECTION A: General Information

Legal Name of Organization:

Mailing Address:

Street Address (if different):

Telephone:

Fax Number:

Other (Email):

Telex:

1. What type of organization are you (profit, non-profit, private volunteer organization, university, etc.)?

2. Is your organization incorporated or registered?	Yes:		No:

When and where was your organization incorporated or registered?

3. Please provide a copy of the following:

a) Your organization's incorporation or registration certificate;

b) SAM registration (if available).

4. What is your organization's tax status?

5. Financial Information. Please complete the requested information and provide a copy of your most recent financial statement.

Current Year Information (indicate period):

Revenues:	U.S.D. $			 	Local currency:

Expenses:	U.S.D. $			 	Local currency:

Assets:	U.S.D. $			 	Local currency:

Liabilities:	U.S.D. $			 	Local currency:

Exchange Rate:			per $1

Prior Year Information (indicate period):

Revenues:	U.S.D.	$			 	Local currency:

Expenses:	U.S.D.	$			 	Local currency:

Exchange Rate:			per $1

Of the current year funding, how much comes from the following (in U.S. dollars):

Membership dues/Contributions: $			Seminars/conferences: $

Publications:		 $			Services: $

U.S. Government:	 $			Other {specify: $

Local Government:	 $			Funding from non-U.S. sources

(International): $

Private Foundations (please list):

6. Enter the beginning and ending dates of your organization's fiscal year:

From: (Month, Day) _________________ To: (Month, Day) ________________

7. Please list the names of the following individuals (as applicable):

Chairman of the Board:

President:

Director:

Secretary (of the Board):

Treasurer:

Chief Financial Officer:

Bookkeeper/Accountant:

Other Senior Management:

8. Please include the full list of board of directors or trustees.

Enclosed:		Not Enclosed (Explain):

9. Is your organization affiliated with any other organization? (Local or International)

Yes:		No:

If yes, please provide details:

10. Please complete and attach the Conflict-of-Interest Certification.

Enclosed:

SECTION B: Organizational Capacity

1. List the number of employees your organization has:

Full-Time Employees: ______ Part-Time Employees: _______ Consultants: ______

2. Please attach a full organizational chart that clearly defines the lines of management authority and responsibility in the organization.

Enclosed:

3. How many offices does your organization have operating locally?

4. Complete the following information concerning the person or accounting firm who will maintain your accounting records for this subaward:

a. How many years of experience does this person have?

b. How many years has this person been with your organization?

c. Does this person know how to use Excel?					Yes: 		No:

d. Does this person know how to use a computerized accounting system?	Yes:		No:

e. Does this person have a degree in accounting or finance?			Yes:		No:

f. Can this person communicate in English?					Yes:		No:

If no, please list their preferred languages:

SECTION C: Financial Systems

1. Describe your organization's accounting system. At a minimum, describe a) any manual ledgers used to record transactions (general ledger, cash disbursements ledger, accounts payable ledger, etc.); b) any computerized accounting system used (please indicate the type); c) how recorded transactions are summarized for financial reporting purposes, and d) the frequency of financial reports.

2. Can the accounting records identify and distinguish the receipts and payments of a Name of Pass-Through Entity grant from the receipts and payments of other activities?

Yes:		No:

3. Can the accounting records summarize payments by budget category?	Yes:		No:

4. Do you have a negotiated overhead rate? (This is a flat rate for administrative expenses that is charged for each project.)	Yes:		(Please enclose approved rates)	No:

SECTION D: General Internal Controls

1. Do you have written accounting policies and procedures? 		Yes: 		No:

If yes, please include a copy.

Enclosed:

2. Are your financial reports prepared on a: 	Cash basis:		Accrual basis:

3. Does your organization have a schedule of authorization to approve purchases and expenses?

Yes:		No: 		(Please attach or describe)

4. Briefly describe how duties and responsibilities are segregated in your organization.

5. How often does management review:

- Monthly financial statements:

- Subsidiary ledgers:

- Payroll:

- Capital asset purchases:

SECTION E: Documentation

1. Do you maintain invoices, receipts, vouchers, and timesheets for all payments?

Yes: 		No:

2. Briefly describe your organization's system for filing and maintaining supporting documentation.

3. Are there any circumstances in which invoices, receipts, vouchers, and timesheets cannot or will not be obtained?	Yes:		(if yes, explain)		No:

4. If you need to convert funds from one currency to another, how will the conversion occur and how will it be documented?

5. Is there a match for this grant? 	Yes:			No:

If yes, please explain how the match will be recorded in financial records and how it will be documented and reported:

6. Will you be able to maintain accounting records including invoices, receipts, vouchers, and timesheets for at least three years after the final financial report is submitted?

Yes:		No:

(Please explain)

SECTION F: Banking and Cash Management

1. Does your organization have a bank account?	Yes:		No:

If yes, please list the country where the bank account is located and bank name:

2. Can a separate bank account be established just for Name of Pass-Through Entity grant funds?

Yes:		No:

3. Are all bank accounts and check signers authorized by the Board of Directors, Trustees, Executive Committee or Financial Management Committee of the Board?	Yes:		No:

Please list authorized check signers:

4. Will any cash from Name of Pass-Through Entity funds be maintained outside the bank (in petty cash funds, etc.)?

Yes:		No:

If yes, please explain the amount of funds to be maintained, the purpose and person responsible for safeguarding these funds.

5. Please answer the following:

- Are bank deposits insured by the government?	Yes:		No:

- Do you intend to convert U.S. currency to local currency? 		Yes:		No:

- Are there any taxes or other charges when converting U.S. dollars to local currency?

Yes:		No:		(Please explain.)

- Are there any government or bank restrictions on the use of checks for making payments or withdrawals? (Please explain.)	Yes:		No:

- Are checks usually accepted by vendors?		Yes:		No:

- Will it be possible for you to establish a bank account in U.S. dollars?

Yes:		No:

- Are there any government or bank restrictions, taxes, or other charges that will be placed on U.S. dollar bank accounts? (Please explain).		Yes:		No:

SECTION G: Personnel/Payroll

1. Does your organization have written standardized personnel policies? Yes:	 No:

If yes, please enclose. 	Enclosed:

2. Are timesheets maintained for each employee to document payroll expenses?

Yes:		No:	 (Explain why not)

3. Does the organization have a salary scale with salary ranges for different positions?

Yes:		No:	 (Explain why not)

4. Is each employee's salary documented in an employment letter or contract?

Yes:		No:		 (Explain why not)

5. Is there an organizational policy or country requirement on fringe benefits?

Yes:		No:

If yes, please list the percentage:

SECTION H: Procurement

1. Does your organization have a standard procurement manual? 	Yes:		No:

If yes, please enclose. 	Enclosed:

Briefly describe how your organization solicits, obtains, documents, and selects competitive bids, including the threshold for obtaining multiple bids or price quotes.

3. Who has the authority to select suppliers?

4. Do you use reports and inventory records to substantiate the receipt of commodities and suppliers?	 Yes:		No:		(if no, explain why not)

SECTION H: Asset Management

1. Do you maintain inventory records of capital equipment (e.g. computers, copier, fax, etc.)?

Yes:		No:		(if no, explain why not)

2. How often do you compare inventory records to the actual inventory? Please list when the last inventory check was performed.

SECTION I: Travel

1. Does your organization have a written policy for travel expenses, such as accommodations and meals? 		Yes:			No:

If yes, please enclose. 	Enclosed:

SECTION J: Grant Management

1. Have you implemented funding from this funder in the past?

Yes:			No:

If yes, please list project, dates, donor, and total budget:

SECTION K: Knowledge of Prime Donor Rules & Regulations

1. Have you or any of the personnel who will be working on this subgrant attended regulations training for this donor? 	Yes:		No:

2. Are you familiar with OMB 2 CFR 200 Subpart E cost principles? Yes: 		No:

SECTION L: Audit

Name of Pass-Through Entity grant provisions may require an audit to be performed of your accounting records. Please provide the following information on prior audits of your organization.

1. Have external accountants ever performed an audit of your organization's financial statements?

Yes: 		No:

2. If an audit was performed, please provide this office with a copy of your most recent report.

Enclosed:

3. Does your organization have regular audits? 	Yes:		No:

- If yes, who performs the audit and how frequently is it performed?

- If you receive a Name of Pass-Through Entity grant, will Name of Pass-Through Entity grant funds be included in such an audit?

Yes:		No:		N/A(not applicable):

- If yes, would it appear as a separate project?	Yes: 		No:		N/A:

- Would the report be prepared in, or translated into, English? Yes:		No:		N/A:

4. If you do not have a current audit of your financial statements, please provide this office with a copy of the following financial statements, if available:

- A "Balance Sheet" for the most current and previous year; and

- An "Income Statement" for the most current and previous year.

5. Are there any reasons (local conditions, laws, or institutional circumstances) that would prevent an independent accountant from performing an audit of your organization?

Yes: 		No:

If yes, please provide details:

SECTION M: Form Certification

Completed by:

PRINTED NAME			SIGNATURE

TITLE					DATE

APPROVED BY:

PRINTED NAME			SIGNATURE

TITLE					DATE

## Annex E: Pass-Through Entity Responsibilities Checklist

Pass-Through Responsibilities Checklist

| Subrecipient Name: |  | Date: |  |
| --- | --- | --- | --- |
| Section | Uniform Guidance Requirement | Completed Y/N | Response and/or Support |
| Subrecipient and Contractor Determinations |  |  |  |
| 200.300 | A determination has been made as to whether the non-federal entity receiving the funds is a subrecipient or contractor based on the definitions outlined in in the 2 CFR 200 Uniform Guidance. Complete “Subrecipient vs Contractor Determination Checklist” and link to completed document under support. |  |  |
| 200.331 (a) | The subaward has been clearly identified to the subrecipient as a subaward and the subrecipient has been made aware they are to comply with the provisions outlined in the 2 CFR 200 Uniform Guidance. |  |  |
| Required Award Identification Information |  |  |  |
| 200.331 (a)(1) | Subrecipient name (must match registered name in SAMS) |  |  |
|  | Subrecipient’s UEI number |  |  |
|  | Award Assistance Listing number |  |  |
|  | Federal Award Date |  |  |
|  | Subaward period of performance start and end date |  |  |
|  | Subaward budget period start and end date |  |  |
|  | Amount of federal funds obligated by this action |  |  |
|  | Total amount of federal funds obligated to the subrecipient (including the current financial obligation) |  |  |
|  | Total amount of the federal award committed to the subrecipient by the pass-through entity |  |  |
|  | Federal award project description, as required to be responded to the Federal Funded Accountability and Transparency Act (FFATA) |  |  |
|  | Name of federal awarding agency, pass through entity, and contact information for awarding official |  |  |
|  | CFDA number and name |  |  |
|  | Identification of whether the award is R&D |  |  |
|  | Indirect cost rate for the federal award (including if the de minimis rate is charged) per § 200.414 |  |  |
| Requirements for Pass-Through Entities |  |  |  |
| 200.331 (a)(2) | The subaward includes all requirements imposed bypass-through entity so that the Federal award is used in accordance with Federal statutes, regulations and terms and conditions of the Federal award. |  |  |
| 200.331 (a)(3) | Any additional requirements imposed by the pass-through entity in order to meet its responsibilities with the Federal awarding agency to include identification of any required financial and performance reports. |  |  |
| 200.331 (a)(4) | A negotiated indirect cost rate between the subrecipient and the federal government. If no such rate exits, a rate negotiated between the pass-through entity and the subrecipient or the De minimis rate of 15%. |  |  |
| 200.331 (a)(5) | The subaward includes a requirement that the subrecipient provide access to its records and financial statements to the pass-through entity and its auditors. |  |  |
| 200.331 (a)(6) | The subaward includes appropriate terms and conditions regarding the closeout of the subaward. |  |  |
| 200.331 (b) | The subrecipient’s risk of non-compliance with federal statutes, regulations, and terms and conditions of the subaward has been evaluated and the following risk factors have been considered: - The subrecipient’s prior experience with the same or similar awards; - The results of previous audits including whether or not the subrecipient receives a Single Audit in accordance with Subpart F of the 2 CFR 200 Uniform Guidance, and the extent to which the same or similar subaward has been audited as a major program; - If the subrecipient has had a change in personnel or major change in systems; and - The extent and results of Federal awarding agency monitoring. (e.g., if the subrecipient also receives Federal awards directly from a Federal awarding agency). Complete “Subrecipient Risk Assessment Tool” and link to completed document. |  |  |
| 200.331 (c) | Consider imposing specific subaward conditions on a subrecipient if appropriate as described in section in § 200.207 (Specific Conditions). Indicate additional specific subaward conditions on a subrecipient in response/support box. |  |  |
| Subrecipient Monitoring Requirements |  |  |  |
| 200.331 (d) | Activities of the subrecipient are monitored to ensure the subaward is used for authorized purposes, is in compliance with Federal statutes, regulations, and the terms and conditions of the subaward and performance goals are met. |  |  |
| 200.331 (d)(1) | Review financial and programmatic reports required by the pass-through entity. |  |  |
| 200.331 (d)(2) | Follow-up process to ensure that the subrecipient takes timely and appropriate action on all deficiencies pertaining to the Federal award provided to the subrecipient from the pass-through entity detected through audits, on-site reviews, and written confirmation from the subrecipient, highlighting the status of actions planned or taken to address Single Audit findings related to the particular subaward. |  |  |
| 200.331 (d)(3) | Issue management decisions for all applicable audit findings pertaining to the Federal award provided to the subrecipient from the pass-through entity. |  |  |
| 200.331 (d)(4) | Issue subawards that conform to agency and award-specific requirements, to manage risk through ongoing subaward monitoring, and to monitor the status of the findings that are specifically related to the subaward. Note: the pass-through entity is not responsible for resolving cross-cutting findings. If a subrecipient has a current Single Audit report posted in the Federal Audit Clearinghouse and has not otherwise been excluded from receipt of Federal funding, the pass-through entity may rely on the subrecipient's cognizant audit agency to perform audit follow-up and make management decisions. |  |  |
| Subrecipient Monitoring Tools |  |  |  |
| 200.331 (e) | Based on the risk assessment performed, consider additional monitoring tools to ensure proper accountability and compliance with program requirements and achievement of performance goals. |  |  |
| 200.331 (e)(1) | Provide subrecipients with training and technical assistance on program related matters. |  |  |
| 200.331 (e)(2) | Perform on-site reviews of the subrecipient’s program operations. |  |  |
| 200.331 (e)(3) | Arrange for agreed upon procedures engagement as described in § 200.425 (Audit Services). |  |  |
| Additional Monitoring Requirements |  |  |  |
| 200.331 (f) | Verify every subrecipient is audited as required by Subpart F when it is expected that Federal awards expended during the fiscal year either equaled or exceeded the $1,000,000 threshold as set forth in section § 200.501 (Audit Requirements). |  |  |
| 200.331 (g) | Make necessary adjustments to the pass-through entity’s records based on the results of a subrecipient’s audit, on-site review, or other monitoring efforts. |  |  |
| 200.331 (h) | Consider taking enforcement action against non-compliant subrecipients as described in § 200.338 (Remedies for Non-compliance). |  |  |

Completed By:

Name:___________________________________

Signature:________________________________

Date: ________________________________________________

## Annex F: Foreign Tax Report

## Annex G: Inventory Listing Report

## Annex H: Audit Certification

Audit Certification

Name of Subrecipient:_________________

Address of Subrecipient:_______________

Subrecipient Point of Contact (Name and Title):___________________________

Subrecipient Point of Contact (email):___________________________

Subaward number:_________________________________

Subaward period of performance:_____________________

Fiscal year covered in this certification:__________________

As a non-US organization, please confirm which of the following situations applies to your organization in the fiscal year noted above:

_____ I confirm that my organization did expend $1,000,000 or more during the fiscal year in Federal awards from a cost-reimbursement contract and we will conduct an audit in accordance with the provisions of this part, which we expect to submit for your review and approval by __(month-day-year)_____.

_____ I confirm that my organization did NOT expend $1,000,000 or more during the fiscal year in Federal awards from a cost-reimbursement contract and it will not be necessary to conduct an audit in accordance with the provisions of this part.

Name of Authorized Representative _________________

Title of Authorized Representative _________________

Signature and Date _________________