## 3YR Strategy
Partners Strategy Roadmap |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022
| Goal |  | Strategies | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
4 | Operational and Financial Excellence
|  | A. | Strategy to develop the Board | bar: 2020 Q1 to 2021 Q4
1. Platform | bar: 2020 Q1 to 2021 Q4
‐-Consider the pros and cons of several platforms (Slack, WhatsApp, etc.) to decide which one to be the central communication platform for the Board of Directors. | bar: 2019 Q2 to 2019 Q3; 2020 Q1 to 2021 Q4
--Schedule a demo/training on how to use the chosen platform for the board members. Include here chapter leaders, and Barbara and Susie. | bar: 2019 Q2 to 2019 Q3; 2020 Q1 to 2021 Q4
2. Training | bar: 2020 Q1 to 2021 Q4
--Create a questionnaire to find out the topics that board members would like to be trained on. (fundraising/reimbursement procedures) | bar: 2019 Q3 to 2021 Q4
--Consider bringing staff and volunteers who have specialty on particular field to do training for the board. | bar: 2019 Q3 to 2021 Q4
|  | B. | HR & Resources management | bar: 2020 Q1 to 2021 Q4
1. Staffing matrix update | bar: 2020 Q1 to 2021 Q4
--Procurement/selection of the HR firm (include interviews with the firms). | bar: 2019 Q2; 2020 Q1 to 2021 Q4
--Receive deliverables from the firm (update on position descriptions & recommendation on salaries). | bar: 2019 Q3; 2020 Q1 to 2021 Q4
--Meet with president council to decide if any changes to the organization's structure are needed, and update the salary matrix for next year. | bar: 2019 Q3; 2020 Q1 to 2021 Q4
--Develop and finalize 2020 budget based on all the adjustments. | bar: 2019 Q4 to 2021 Q4
2. Employee training/Webinar | bar: 2020 Q1 to 2021 Q4
--Streamline training on the Package of Benefits & general Policies for the new employees (including timesheets via Paycom) | bar: 2019 Q3; 2020 Q1 to 2021 Q4
--Provide recurring annual updates to employees on the Benefits package (in the last quarter.) | bar: 2019 Q4 to 2021 Q4
--Provide training on various topics that are important for staff: the new FMLA taxation, work-time-flex policy, corporate credit cards, etc. | bar: 2019 Q3 to 2021 Q4
3. Consultancy management | bar: 2020 Q1 to 2021 Q4
--Define our organization type: employee based or consultant based company, and make decisions on how many consultants may become employees and how many consultants are needed each year in each unit. | bar: 2019 Q2; 2020 Q1 to 2021 Q4
--Develop procurement policy for purchasing consultant services | bar: 2019 Q3; 2020 Q1 to 2021 Q4
--Develop standardized salary categories based on experience and skillset. | bar: 2019 Q3; 2020 Q1 to 2021 Q4
--Develop policies that applied to consultants. | bar: 2019 Q3; 2020 Q1 to 2021 Q4
|  | C. | Create Project Management Manual | bar: 2020 Q1 to 2021 Q4
1. Creating table of content | bar: 2020 Q1 to 2021 Q4
--Collect available resources (PM manual of other NGO, resources of project management platform, etc) to use as references. | bar: 2019 Q3; 2020 Q1 to 2021 Q4
--First-level headings of the content will be based on the life cycle of a project: Set-up; Implementation; Monitoring and Evaluation; Close out. There will be subsections under each main sections. | bar: 2019 Q3; 2020 Q1 to 2021 Q4
--Finalize table of content. | bar: 2019 Q3 to 2021 Q4
2. Creating a Draft Manual | bar: 2020 Q1 to 2021 Q4
--Assign sections to different people based on their strengths and interest, check-in meetings will be arranged in this phase. | bar: 2019 Q4 to 2021 Q4
--Other policies (Travel Policy, etc.) and instructions which have been developed will be linked to this manual instead of copying and pasting all materials into this manual, so that users of this manual will have the knowledge of what resources are available and where to find them. | bar: 2019 Q4 to 2021 Q4
3. Revising and finalizing the Final Draft Manual | bar: 2020 Q1 to 2021 Q4
--Send out the draft manual to other staff to collect feedback, and revise the manual if necessary. | bar: 2020 Q1 to 2021 Q4
--Get the final approval. | bar: 2020 Q1 to 2021 Q4
4. Popularizing the Final Draft Manual | bar: 2020 Q1 to 2021 Q4
--Arrange staff meeting/brown bag meeting(s) to introduce the manual and answer any questions people may have. | bar: 2020 Q1 to 2022 Q1