## 3YR Strategy
Partners Strategy Roadmap |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
| Goal |  | Strategies | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
4 | Operational and Financial Excellence
|  | A. | Strategy to develop the Board
1. Platform
‐-Consider the pros and cons of several platforms (Slack, WhatsApp, etc.) to decide which one to be the central communication platform for the Board of Directors. | bar: 2019 Q2 to 2019 Q3
--Schedule a demo/training on how to use the chosen platform for the board members. Include here chapter leaders, and Barbara and Susie. | bar: 2019 Q2 to 2019 Q3
2. Training
--Create a questionnaire to find out the topics that board members would like to be trained on. (fundraising/reimbursement procedures) | bar: 2019 Q3 to 2019 Q4
--Consider bringing staff and volunteers who have specialty on particular field to do training for the board. | bar: 2019 Q3 to 2019 Q4
|  | B. | HR & Resources management
1. Staffing matrix update
--Procurement/selection of the HR firm (include interviews with the firms). | bar: 2019 Q2
--Receive deliverables from the firm (update on position descriptions & recommendation on salaries). | bar: 2019 Q3
--Meet with president council to decide if any changes to the organization's structure are needed, and update the salary matrix for next year. | bar: 2019 Q3
--Develop and finalize 2020 budget based on all the adjustments. | bar: 2019 Q4
2. Employee training/Webinar
--Streamline training on the Package of Benefits & general Policies for the new employees (including timesheets via Paycom) | bar: 2019 Q3
--Provide recurring annual updates to employees on the Benefits package (in the last quarter.) | bar: 2019 Q4; 2020 Q4; 2021 Q4
--Provide training on various topics that are important for staff: the new FMLA taxation, work-time-flex policy, corporate credit cards, etc. | bar: 2019 Q3 to 2021 Q4
3. Consultancy management
--Define our organization type: employee based or consultant based company, and make decisions on how many consultants may become employees and how many consultants are needed each year in each unit. | bar: 2019 Q2
--Develop procurement policy for purchasing consultant services | bar: 2019 Q3
--Develop standardized salary categories based on experience and skillset. | bar: 2019 Q3
--Develop policies that applied to consultants. | bar: 2019 Q3
|  | C. | Create Project Management Manual
1. Creating table of content
--Collect available resources (PM manual of other NGO (Danielle), resources of project management platform which Janira has access to, etc) to use as references. | bar: 2019 Q2
--First-level headings will be based on the life cycle of a project: Set-up; Implementation; Monitoring and Evaluation; Close out. | bar: 2019 Q2
--Finalize table of content. | bar: 2019 Q2 to 2019 Q3
2. Creating a Draft Manual
--Assign sections to different people based on their strengths and interest, check-in meetings will be arranged in this phase. | bar: 2019 Q3 to 2019 Q4
--Other policies and instructions which have been developed will be linked to this manual, so that users of this manual will have the knowledge of what resources are available and where to find them. | bar: 2019 Q3 to 2019 Q4
3. Revising and finalizing the Final Draft Manual
--Send out the draft manual to other staff to collect feedback, and revise the manual if necessary. | bar: 2020 Q1
--Get the final approval. | bar: 2020 Q2
4. Popularizing the Final Draft Manual
--Arrange staff meeting/brown bag meeting(s) to introduce the manual and answer any questions people may have. | bar: 2020 Q3 to 2021 Q4