## 3YR Strategy
Partners Strategy Roadmap |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
| Goal |  | Strategies | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
4 | Operational and Financial Excellence
|  | A. | Strategy to develop the Board
1. Platform
‐-Consider the pros and cons of several platforms (Slack, WhatsApp, etc.) to decide which one to be the central communication platform for the Board of Directors. | bar: 2019 Q2 to 2019 Q3
--Schedule a demo/training on how to use the chosen platform for the board members. Include here chapter leaders, and Barbara and Susie. | bar: 2019 Q2 to 2019 Q3
2. Training
--Create a questionnaire to find out the topics that board members would like to be trained on. (fundraising/reimbursement procedures) | bar: 2019 Q3 to 2019 Q4
--Consider bringing staff and volunteers who have specialty on particular field to do training for the board. | bar: 2019 Q3 to 2019 Q4
|  | B | HR & Resources management
1. Staffing matrix update
--Procurement/selection of the HR firm (include interviews with the firms). | bar: 2019 Q2
--Receive deliverables from the firm (update on position descriptions & recommendation on salaries). | bar: 2019 Q3
--Meet with president council to decide if any changes to the organization's structure are needed, and update the salary matrix for next year. | bar: 2019 Q3
--Develop and finalize 2020 budget based on all the adjustments. | bar: 2019 Q4
2. Employee training/Webinar
--Streamline training on the Package of Benefits & general Policies for the new employees (including timesheets via Paycom) | bar: 2019 Q3
--Provide recurring annual updates to employees on the Benefits package (in the last quarter.) | bar: 2019 Q4; 2020 Q4; 2021 Q4
--Provide training on various topics that are important for staff: the new FMLA taxation, work-time-flex policy, corporate credit cards, etc. | bar: 2019 Q3 to 2021 Q4
3. Consultancy management
--Define our organization type: employee based or consultant based company, and make decisions on how many consultants may become employees and how many consultants are needed each year in each unit. | bar: 2019 Q2
--Develop procurement policy for purchasing consultant services | bar: 2019 Q3
--Develop standardized salary categories based on experience and skillset. | bar: 2019 Q3
--Develop policies that applied to consultants. | bar: 2019 Q3
|  | C | Create Project Management Manual
This Part will be mainly focused in the next meeting.
PM Manual will include: project set up, compliance rules, FM role, communications (including stakeholder outreach, social media, etc.), procurement and subaward management, admin protocols. Risk management, contingency planning and project closure.