## Slide 1: NEW 2015 Organizational Structure & Midyear Goals Review Process
Date | Activity | Leads
June 3 | Finalize 2015 NEW Organizational Structure | Steve & Horacio
June 4 | Announce 2015 NEW Organizational Structure to DC Staff (begin feedback and adoption process) | Steve
June 9 - 19 | Send feedback to Program/Units on 2015 Goals & schedule meetings with Program/Unit Directors to review organizational priorities and provide in-person feedback on goals. | Sherrita
June 22 | Hold President’s Council Meeting to Share and Review Revised Mid-year Goals (team by team) | President’s Council
June 30 | Each Team Submits Final 2015 Goals. Begin Lifting Core 2015 Goals and Organizational Priorities into a Draft 2016-2018 Strategic Plan | Each Program/Unit Senior Management
July 9 | Send Corporate Goals and Draft Strategic Plan to Boards | Sherrita
July 23 | Tentative: Joint International & Foundation Board Meeting | Sherrita to confirm date