## Summary
| Summary | 2014 Corporate Performance Evaluation Ratings
Rating Definitions
Exemplary: Consistently achieves at a high level. Exceeds expectations. |  | 5
Solid: Consistently achieves above the satisfactory level. Meets all expectations |  | 4
Satisfactory: Accomplishes tasks in a satisfactory manner. Meets most expectations. |  | 3
Needs Improvement: Improvement is necesssary to more consistently meet expectations. |  | 2
Seriously Deficient: Problems with approach or execution. Expectations are generally not met. |  | 1
Major Corrective Actions
Corrective Actions in 2014: 1) Budget & NICRA - Internal restructuring to allow VP of Operations to directly oversee the Program Managers for our largest grants to ensure timely execution of operations and spending. As a result, the Corporation should successfully avoid significant program underspending and lower NICRA to the competitive rate of 25% 2) PartnersConnect & Rechartering - Established Engagement Strategy Working Group to strengthen Chapter Network and improve the overall affiliations strategy. 3) A Ganar now fully staffed and procedures in place to fulfill donor requirements and hit program spending targets 4) Inter-American Development Bank (IDB) reimbursement and audit will recieve additional technical support Corrective Actions Outlined for 2015:

## Section A- PD Goals Review
Program Development 2014 Goals Performance Evaluation
Pre-filled based on information provided during Mid-Year Performance Evaluation.
A. Goals Review - 75%
| Communications | Actual Performance to Date:
| Goal 1 - Build a Financially Stable Organization Win Proposals that will bring in $750,000 in revenue to spend in 2014. Fundraise $1.5M in revenue for 2015 and $2.5M for 2016. | Watchlist: - USAID/ Barbados and Eastern Caribbean Youth at Risk – Subcontractors to DAI - DOL/Project to Reduce Child Labor and Improve Working Conditions in Haiti Under Development (Total $966,484): - USAID/ Guatemala Community Strengthening Program – Subcontractors to DAI- $966,484 Won (Total $ 685,455): - DOS/Emerging Leaders in Action Program (ELAP) - $400,000 - DOS/Youth Ambassadors (YA) – Colombia, Venezuela and US - $285,455 Submitted and Pending (Total $22,860,140): - DOL/Project to Reduce Child Labor and Improve Working Conditions - $7,000,000 - DOS/English Language Fellow and Specialist Program (ELFS) - $12,000,000 - DOS/Community Solutions Program - $1,500,000 - DOS/ Panama CARSI Program - $$497,615 - DOS/Professional Exchange Congresses - $600,000 - DOS/ Professional Exchanges – Legislative Process and Governance – $695,000 - USAID/ Barbados and Eastern Caribbean Climate Change Preparedness Program (BECPP) - $567,525 Lost (Total $500,000): - DOS/DRL Nicaragua - $300,000 - DOS/ American Youth Leadership Program (AYLP) - $200,000 | 4
| Goal 2 - Strengthen Network of Volunteers, Programs & Projects Renew Core Program Grants (i.e. American Youth Leadership Program (AYLP), Energy & Climate Partnership of the Americas Senior Fellows Program (ECPA), International Sports Programming Initiative: Sports for Social Change (ISPI), Legislative Fellows Program (LF), and the Youth Ambassadors Program) Explore new funding opportunities for programs, Work with A Ganar expansion team to secure $1.5M in revenue 2015 | The Program Development Unit (PD) continues to work very closely with all program staff to renew Partners' core program grants. In the January - June 2014 proposal season, PD led and supported 12 proposal processes: YA, AYLP, ELAP, Professional Exchanges, Professional Exchanges Congresses, among others. PD is also providing support to the Matching Fellows team by exploring potential opportunities with the Government of Chile and Government of Uruguay. PD is working closely with the A Ganar team to explore potential funding opportunities in Mexico. PD supported this team with the development of a concept paper and budget to the Government of Mexico and the Clinton Foundation. PD hired a new Program Officer I that will lead the development of non-traditional opportunities, especially those that support the expansion of PnP programs. PD hired Catalina Lillo, our former intern, to take on this new role. With an additional staff in our team, PD will be able to provide consistent support to Expansion Teams and follow up with program staff as we seek to expand our current programs and diversify our funding. | 4
| Goal 3 - Well-Governed, Accountable & Transparent Organization Seek out Professional Growth Opportunities for PD Team, Prepare Annual Review/Preview Reports + Performance Evaluations of Staff, Prepare Monthly Reports to All Staff and Quarterly Reports for the Board. Maintain Strong Communication w/ Donors (current and potential). | The Program Development Unit is taking advantage of a unique opportunity for professional growth. We are young group of talented individuals that works very well independently and as a team, we communicate very well with each other and divide and conquer tasks as needed. In early 2014, Elizabeth Holst travelled for the first time with Partners to conduct intelligence gathering and incubator meetings in Guatemala with the DAI Team that we are subcontractors to under the Guatemala Community Strengthening solicitation. Leonard Noel also travelled for the first time to conduct a similar trip with DAI to Barbados and Eastern Carribbean. Elizabeth and Leonard positioned Partners very well, and met with Chapter members in country to understand even better our network and volunteer work. Carmen Pena travelled to Haiti to explore a potential opportunity for a DOL/Project to Reduce Child Labor in Haiti (the solicitation has not dropped). Carmen Pena and Elizabeth Holst travelled to Honduras in June 2014, to conduct needs assesment, key personnel recruitment, project design and proposal work for the DOL/Project to Reduce Child Labor and Improve Working Conditions in Honduras. Travel opportunities support professional growth opportunities by allowing the PD team to learn in depth about these countries, understand needs and funding trends in the region. In addition, it provides an opportunity to connect with chapter members and meet local program staff. The PD team is also taking advantage of event opportunities to network with donors. We attend external events organized by USAID, DOL and DOS in a regular basis. Recent events we have attended include: World Day Against Child Labor (DOL) on June 12th and BBL Violent Crime, Youth Gangs, and Local Prevention Practices, among others. | 4
| Goal 4 - Evaluate and Communicate Our Impact and Value In collaboration with M&E specialist and other units, update program impact and capacity statements for proposals and external communications materials. | The PD unit met with A Ganar's M&E Consultant for an initial orientation about the work she is currently performing for the A Ganar Team. We have also participated in the A Ganar Team's report out of the Impact evaluation perfromed by Social Impact in Central America. These meetings allow us to understand better the current ysstems and mechanims in place to monitor and evaluate our programs. As part of all proposal development processes, PD continues to update program impact and capacity statements that are current and updated for each and every proposal we submit. PD keeps thesee 'bona fides' records updated in order to state and demonstrate Partners capacity in the field of work. Moreover, PD led the hiring of the Youth Lead Curriculum Consultant, in an effort to develop a structured and packaged methodology of our signature Youth Lead Program. This new curriculum was adapated and an excerpt was included in the youth exchanges proposals we applied for this year. In addition, we will utilize this new methodology to sell the Youth Lead program to other donors. | 4
| Corrective Action(s): | Comments:
|  | Department Total | 4
4
1
1
5
1
2
3
4
5

## Section A- DOL Goals Review
Combating Child Labor 2014 Goals Performance Evaluation
Pre-filled based on information provided during Mid-Year Performance Evaluation.
A. Goals Review - 75%
| Communications | Actual Performance to Date:
| Goal 1 - Build a Financially Stable Organization Meet the projected spending goal. Monitor spending to ensure correct projected expenses and NICRA recovery. Manage budget without overspending amounts available for each component. Secure outstanding match for A Ganar component implementation. | EducaFuturo started the provision of direct services to children in March 2014. In Ecuador, the Project targets 1,350 from which 1,324 have been enrolled. In Panama, the Project targets 800 children, from which 634 have been enrolled. By the next reporting period (September 2014), the Project will have enrolled the pending number of children in both countries (26 in Ecuador and 166 in Panama). To date the EducaFuturo Project is on track with the spending goal (approximately $50,000 less that should be met by end of this month when we send out wire transfers. The next six months of this year will be monitored closely, as we continue to provide direct services to children, youth and families. As the number of beneficiaries increase, spending will continue to increase as well. M&E Field Verification Visits are been intensified in the last few weeks, to ensure that there is proper enrollment and attendance of beneficiaries. In addition, EducaFuturo program staff is monitoring the NGOs in Panama to ensure that they are spending the resources properly. We have not received proper documentation for 100% of the funds being spent and are working with them to ensure we do have all the documentation that is needed and instruct them on how to keep track of their expenses. We have come across challenges with NGO's in Ecuador and Panama, and therefore the need to increase their capacity to empower them to do their job correctly. Working in close collaboration with the A Ganar team, we are exploring potential donations from: One World Futbol and TOM'S Shoes. In addition, we received a call from the International Book Bank letting us know there are Spanish books available. The EducaFuturo program is considering this potential offer as part of our counterpart as well. | 4.5
| Goal 2 - Strengthen Network of Volunteers, Programs & Projects Program staff must attend DOL trainings and workshops in order to be better informed of current requirements and regulations, and inform the team about these guidelines. Monitor and track progress of the baseline survey and ensure it takes place within a reasonable time. | DOL has informed us that there will not be trainings this year. Rather, DOL will use these resources to bring two program staff up after the mid term evaluation takes place in order to discuss corrective actions as needed. We are coordinating an orientation meeting for EducaFuturo's new Education Specialist, Mr. Javier Cueva, to introduce him to Partners and the EducaFuturo Project. Mr. Cueva will join Carmen Pena and Martha Villada along with the EducaFuturo Panama program staff the week of July 7th and go over USG/DOL rules and regulations, expectations and his new role of Education Specialist and leadership position at the Ecuador office. The revised Baseline Survey (BLS) has been concluded and the data is currently being processes (data input) to the system. We expect to have the new revised statistics, and corrections to the Baseline Survey Report by mid July. By July 26th, the BLS Report will be submitted to DOL for final approval. | 4
| Goal 3 - Well-Governed, Accountable & Transparent Organization Engage Partners Chapters and Partners Campus in Program activities. EducaFuturo Staff participation at Partners Chapters and Partners Campus events. | EducaFuturo's Project Director has been in touch with the Partners Campus President. There are potential opportunities in the future in which the Program and the volunteers would like to collaborate. Once the Program is up and running smoothly, we hope for more active engagement of the volunteers with the program itself (i.e.: sponsoring a community, mentorship to A Ganar participants, among others). | 4
| Goal 4 - Evaluate and Communicate Our Impact and Value Communicate number of children withdrawn/prevented. Share success stories with DOL, other potential donors, and our Network. Participate in Roundtables/Events about Child Labor issues. Engage Communications Units in Program activities and events. | EducaFuturo created its web page under Partners’ website. We have a direct access to the web page that displays a summary of what the Project is about and the communities we will be working in both countries. We hope to revise the information and include pictures, success stories, and blog posts through out the rest of the year. This week, we have a new intern starting, that will help us create the Project's Facebook page to share photos and success stories as a way to raise awareness about issues related to child labor and how the program contributes to the fight against child labor. During the World Day Against Child Labor, which is commemorated on June 12th, Project staff participated at the Caminata Contra el Trabajo Infantil along with other local events that raised awareness on child labor and issues around social protection. Three different stories about the events were shared with DOL and will be posted on ILAB's website. EducaFuturo is also in the process of revising the one pager and updated the information with number of beneficiaries and testimonies directly from the beneficiaries. | 4
| Corrective Action(s): | Comments:
|  | Department Total | 4.0714
4
1
1
5
1
2
3
4
5

## Section B-Perf. Expectations
Rating Definitions (This portion will not print). 5.0 Exemplary Consistently achieves at a high level. Exceeds expectations. 4.0 – 4.5 Solid Performance Consistently achieves above the satisfactory level. Meets all expectations. 3.0 – 3.5 Satisfactory Accomplishes the task in a satisfactory manner. Meets most expectations. 1.5 – 2.5 Needs Improvement Improvement is necessary to more consistently meet expectations. 0.0 – 1.0 Seriously Deficient Problems with approach or execution. Expectations are generally not met.
B. Performance Expectations - 25%
Financial Management | Comments
• Manages funds and resources responsibly and judiciously within area of responsibility. • Works proactively to improve program/unit financial oversight and sustainability.
Rating:
0
Time Management | Comments
• Prioritizes effectively according to program/unit goals, based on outside feedback and own judgment. • Consistently meets deadlines and program/unit goals with quality and accuracy.
Rating:
0
Internal & External Communication | Comments
• Responds promptly and accurately to requests. • Communicates program/unit activities and accomplishments appropriately.
Rating:
0
Problem Solving | Comments
• Responds to unexpected demands and problems with resilience and resourcefulness. • Works proactively to improve program/unit functions and efficiency.
Rating:
0
Accountability | Comments
• Follows policies and procedures. • Complies with program/unit requirements when submitting reports and maintaining records.
Rating:
0
Personal & Professional Development | Comments
• Exhibits strong communication and listening skills. • Brings an attitude of positivity and cooperation to the workplace. • Exercises leadership within area of responsibility.
Rating:
0
Supervisory Functions | Comments
• Provides leadership to staff and organization. Manages conflict successfully. • Sets clear expectations, gives effective feedback and provides strong oversight. • Follows and enforces policies and procedures.
Rating:
0
Section B- Supervisor Comments (optional): | Section B- Employee Comments (optional):
SECTION B
0
C. OVERALL PERFORMANCE |  |  | OVERALL SCORE
3.0536
Supervisor Signature Date |  | President Signature Date
Employee Signature Date |  | Vice President Signature ( if applicable) Date