## Sheet1
2015 Program / Unit Goals
Program/ Unit
GOAL #1 |  | CRITERIA / METRIC FOR SUCCESS |  |  |  | TIMELINE
Build a Financially Stable Organization PLE/YE 1.1) Build PLE program portfolio 1.2) Build new program models that can be marketed to new donors while being financially sustainable 1.3) Market the Youth Lead Curriculum |  | 1.1.1) Renew/replace $1.5 million in new funding for 2015 and beyond. 1.1.2) Secure $500,000 in non-USG funding 1.1.3) Contribute to refining the non-traditinal proposal development and funding process. 1.2.1) Build skills in business models and business planning 1.2.2) Develop 3-4 new budget models and present them to potential donors 1.3.1) Finalize YouthLead Curriculum. 1.3.2) Secure funding for two new YL programs |  |  |  | 1.1)December 31, 2015 1.2) December 31, 2015 1.3) July 31, 2015
GOAL #1 |  | CRITERIA / METRIC FOR SUCCESS |  |  |  | TIMELINE
100K STRONG 1. Raise operational funding to sustain and grow the program: land DOS funding 2. Implement targeted fundraising now initiated, using the Summit and Boston workshop to close deals 3. Run CAF-SENA-community college training and competition; renew Coke and execute Colombia strategy 4. Leverage USG senior management assistance with the donor list, follow-through! 5. Manage expenditures prudently to avoid unexpected challenges 6. Implement fully F&A policies and use all tools provided to improve management |  | $500,000 CAF-SENA-community college initiative 2 new $1 million commitments 4 new $250,000 commitments $600,000 mininum DOS recommitment of public funds for operations |  |  |  | April Summit of the Americas May Boston workshop June operational funding deadline
GOAL #1 |  | CRITERIA / METRIC FOR SUCCESS |  |  |  | TIMELINE
NETWORK STRENGTHENING/MSHIP 1) Retain significant portion of paid HEIs and organizations recruited in 2014 2) Increase recruitment of HEI Members 3) Increase recruitment of Organizational Members 4) Increase dues collected from the Chapter network 5) Expand Chapters' capacity to develop and implement programs in collaboration with the International Office |  | 1) Retain 50% of the paid HEIs and orgnaizations recruited in 2014 2) Recruit 15 new paid HEIs 3) Recruit 10 new paid Org Members 4a) Add 10 new Chapters, in some combination of PartnersCampus, Affiliate and Community Chapters 4b) Build support among the Board and network for an increase in Chapter dues to take place in 2016 5a) Chapter training on building language programs developed and piloted 5b) 3 Chapters receive training on building language programs 5c) Chapter training on hosting YL delegations developed and piloted 5d) 3 Chapters receive training on hosting YL delegations (NOTE: Goal 5 will depend heavily on support from the PLE team) |  |  |  | 1) June 30 2) December 30 3) December 30 4a) December 30 4b) December 30 5a) December 30 5b) December 30 5c) December 30 5d) December 30
GOAL #1 |  | CRITERIA / METRIC FOR SUCCESS |  |  |  | TIMELINE
STRATEGIC PARTNERS 1) SENA (Along with the local liaison) Renew, extend and manage the strategic partnership with SENA. 2) Private Sector: (Along with Private sector consultant) Open new initiatives with the private sector in Colombia, specially via 100,000 Strong in the Americas 3) Other Organizations Create new and strengthen the current partnerships with organizations 4) Convention 2016 Oversee the planning process and commercial/financial strategy for the Convention. |  | • New 3 years International Cooperation MOU with SENA • Efficiently manage the budget of YL-FTF project generating $20,000 in unrestricted funds. • Develop together with SENA a sustainable model for YL-FTF that allows during at least 3 years more, the renewal and expansion of YL-FTF • Facilitate the implementation of A Ganar together with SENA and Partners team • Identify and propose new potential projects for 2015 and 2016 • Develop a strategy to approach the private sector in Colombia via 100,000 Strong in the Americas • Develop a strategy to approach the private sector in Mexico via Convention 2016 sponsorships • Confirm investment from at least 2 private companies in any of our programs • Develop and strengthen the relationships with Colombian Government Agencies MinEd, MinTic, DNP. • Develop at least 1 more project funded by other Colombian Government agency (keeping in mind that this most likely will required counterpart in cash from US – Work with PD) • Develop and strengthen the relationships with Mexican Agencies related with the convention such as “Oficina de Convenciones y Visitantes”, “Secretaria de Turismo de Guadalajara”, ‘Consorcio de Universidades” among others. • Make visible and develop new partnerships for the 100,000 Strong initiative and the Innovation Fund in Colombia • Ensure at least 2 rounds Colombia-US in 2015-2016 • Work together with Jalisco Chapter; confirm at least 50% of the sponsorship goal. • Manage the convention 2016 budget avoiding deficit and generating profit. |  |  |  | December 30
GOAL #1 |  | CRITERIA / METRIC FOR SUCCESS |  |  |  | TIMELINE
CAMPUS ENGAGEMENT [Draft - Pending New Hire] PartnersCampus Student Chapters: 1) Apply and enforce a new Charter process to ensure that 80% of the student groups receiving support and recognition as PartnersCampus Student Chapters pay annual dues. 2) Provide information about fundraising strategies and resources to Student Chapters so they may develop financially sustainable projects locally and have the opportunity to participate in network-wide events with minimal intervention from the International Office. 3) Support member HEIs in establishing PartnersCampus Student Chapters to encourage new and renewed institutional membership. Non-traditional proposals: 1) Finalize and promote among CCID member colleges: YouthLead Service-Learning as a credit-bearing international service and leadership program for college students. 2) Continue to support the proposal development and, if awarded, early implementation of non-traditional proposals related to student leadership and network development like WK Kellogg, for example. |  | PartnersCampus Student Chapters:) 80% of the student groups marked as "active" in internal databases (those who are known to be in existence and coordinating programs with the name PartnersCampus XXX) have been granted a Charter (meaning they have paid annual dues for the year of the Charter). 2) Resources shared can be accessed on the PartnersCampus Student Chapter webpage (for members only) and on the PartnersCampus Facebook group page. Student Chapters report fundraising strategies applied in annual reports. Participants in network-wide events apply and report fundraising strategies in blog and social media posts or through Partners' FundMyTravel page. 3) Messages sent to 100% of HEI members with information about PartnersCampus Student Chapters. "Case Study and Testimonial" of successful HEI member highlights PartnersCampus Student Chapter (draft for blog post or for supplemental recruitment material). Non-traditional proposals: 1) Proposal sent to Ida Flippo (Clackamas CC) and Dan Creed (Normandale CC). Participation in CCID Conference with follow up to list of interested institutions. 2) Participation on PD teams or Red Teams for all relevant proposals. |  |  |  | PartnersCampus Student Chapters: 1) By August for 2015 Charter year and renewals/new memberships by January for 2016 Charter year. 2) Web resources available on website launch timeline (anticipate end of March); Resources post to Facebook as they become available or relevant throughout year. Student Chapter use of resources will be assessed upon collection of Annual Reports (October 2015-January 2016) and/or after network-wide events (October 2015). 3) As HEI members join or renew membership. Testimonial/Case Study to be completed alongside development of HEI recruitment strategy (by December 2015). Non-traditional proposals: 1) Proposal sent by Feb 1. CCID Conference: Feb 20-23. Follow up by March 1. 2) Throughout year.
GOAL #2 |  | CRITERIA / METRIC FOR SUCCESS |  |  |  | TIMELINE
Strengthen Partners' Network
GOAL #3 |  | CRITERIA / METRIC FOR SUCCESS |  |  |  | TIMELINE
Maintain a Well-Governed, Accountable & Transparent Organization
GOAL #4 |  | CRITERIA / METRIC FOR SUCCESS |  |  |  | TIMELINE
Evaluate and Communicate Our Impact and Value
Program/Unit Manager Signature |  |  | Date |  | Vice President Signature (If Applicable) |  | Date
CFO/VP of Operations Signature |  |  | Date |  | President Signature |  | Date