## Hoja1
Milestone Timeline of Recruitment Process
Activity | Responsibility | Projected Cycle
|  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25
Attend Recruitment Strategy Meeting | HM/HRO | bar: Projected Cycle Day 1
Position Description & Job Requisition | Hiring Manager | bar: Projected Cycle Day 1 to Projected Cycle Day 2
Announcement of vacancy and External Job posts | HR Officer
Collect Resume/CVs and sort into Recruitment Folders | HR Officer | bar: Projected Cycle Day 3 to Projected Cycle Day 9
Attend weekly check-ins | HM/HRO | bar: Projected Cycle Day 9
Determine candidates for initial screen | Hiring Manager | bar: Projected Cycle Day 9
Collaborate and finalize pre-screen questions | HM/HRO | bar: Projected Cycle Day 9
Pre-screen interviews | HR Officer | bar: Projected Cycle Day 10 to Projected Cycle Day 12
Hiring Team Panel/Interview structuring & scheduling | HM/HRO | bar: Projected Cycle Day 13
Competency Questions finalization | HM/HRO
Interviewing of candidates | Hiring Manager/Panel | bar: Projected Cycle Day 14 to Projected Cycle Day 18
Selecting Finalists | Hiring Manager/Panel | bar: Projected Cycle Day 19
President/CEO Interview | HRO/President's Office | bar: Projected Cycle Day 22
Verbal and Official Offer | HR Officer | bar: Projected Cycle Day 23
Remission of Policy documents and onboarding procedures | HR Officer | bar: Projected Cycle Day 24 to Projected Cycle Day 25

## Hoja2
Cargo | Cartagena | Medellín | Valledupar
Coordinador de Proyecto | 4200000 | 4200000 | 4240000
Asistente de proyecto | 1750000 | Técnico de proyecto $2.200.000 | No hay
Oficial de Proyecto | 2500000 | 2700000 | 2400000
Técnico de Enlace | 2200000 | 2100000 | 2100000
Servicios Generales y mensajería | 1000000 | 877803 | 877803
Técnico Administrativo | 2200000 | 2100000 | 2226000
Asistente de Rendición de Cuentas - CARM | 1750000 | 1755607 | 1755607
Asistente M&E | 1750000 | No hay | No hay
Oficial de M&E | 2600000 | 2400000 | Técnico de M&E $2.332.000