## Summary
Summary Risk Register & Treatment Plan
Description of Risk | Likelihood of Risk | Potential Impact of Risk | Risk Rating - Pre-Mitigation | Risk Rating - Post-Mitigation | Risk Mitigation Plan/Actions
Hostile Acts
Proximity to violence (guns/explosives) | 2 | 5 | 10 | 8 | Monitoring of risk environment to determine any escalated threat (recognizing that, in the project's intended area of operations, this is assessed to be low). Where the risk environment deteriorates substantially (manifest as a significant increase in the number and severity of attacks in proximity to staff and operations), escalates through measures from the suspension of non-essential project travel through to hibernation, relocation and, ultimately, evacuation of any international staff. Subject-specific Pre-planned responses to form the basis of staff safety and security awareness training on this subject.
Carjacking and highway robbery | 2 | 4 | 8 | 4 | Travel Risk Management and Journey Management Plan. Subject-specific Pre-planned responses to form the basis of staff safety and security awareness training on this subject. .In-traffic protocols to be rigorously applied: seatbelts worn at all times, items of value hidden from view (including smartphones/laptops/tablets), doors and windows closed and locked, and the driver must maintain space in front of the vehicle (particularly at junctions and traffic lights) to enable them to maneuver evasively if required.
Violent [street] crime | 2 | 3 | 6 | 4 | Limitations on travel to/through areas where violent crime is prevalent. Rigorously maintained high standards of personal risk management (avoiding situations where isolated, particularly at night), always aiming to ‘lower personal profile’ through dressing modestly, not displaying wealth/items of high value, through being alert (walking purposefully, with head up and avoid being ‘plugged in’ to headphones or cellphones). Staff safety and security awareness training to include focus on actions people can practically take to minimize targeting risk.
Death threats, extortion and intimidation | 2 | 3 | 6 | 3 | Maintenance of low organizational profile in-country. Advisory guidance to all staff on escalating any intimidatory/threatening acts to the Local Incident Management Team.
In-stride crimes | 3 | 2 | 6 | 2 | Rigorously maintained high standards of personal risk management (avoiding situations where isolated, particularly at night and areas targeted by petty criminals), always aiming to ‘lower personal profile’ through dressing modestly, not displaying wealth/items of high value, through being alert (walking purposefully, with head up and avoid being ‘plugged in’ to headphones or cellphones). Staff safety and security awareness training to include focus on actions people can practically take to minimize targeting risk.
Arrest and detention | 2 | 3 | 6 | 4 | Identification of local legal counsel, able to act swiftly on Partners’ behalf. Maintain up-to-date details for the US Embassy and other consular staff relevant to the nationalities of staff working on the project (including STTA international travelers). Staff safety and security awareness training to include focus on actions people can practically take in the event they are detained by the police.
Civil disorder | 3 | 4 | 12 | 9 | Development of a specific triggered response plan, providing detailed guidance on the approach taken to monitoring the risk context associated with the upcoming elections in particular (but with more general application to other potential drivers of civil unrest), and tying a series of actions to observed indicators that the security context many be deteriorating . Staff safety and security awareness training to include focus on actions people can practically take when security conditions are deteriorating and / or they find themselves in proximity to an episode of civil disorder.
Safety Hazards (Human Factors)
Road Traffic Accident | 3 | 4 | 12 | 8 | Rigorously applied Journey Management Planning (trip requesting and risk-based authorizing process, en route risk assessments to identify safe havens and point of elevated risk, including a through-route communications viability assessment and emergency communications plan, check-in protocols, development of medical emergency plan with one component specifically focused on actions in the event of a Road Traffic Accident. Driver to check for vehicle roadworthiness as a standard pre-trip step and to validate the route and any protocols directed through the trip approving process (e.g., check in timings, etc.). Drivers to receive training on defensive driving and all project staff to received training on their role as a vehicle passenger in controlling unsafe driving behavior and remaining alert to potential risks en route.
Building fire | 2 | 3 | 6 | 2 | Hotel / Residence / Office to be security and safety assessed, and any significant remediations prioritized (e.g., sufficient and fully functioning smoke detectors and primary firefighting equipment (extinguishers, fire blankets, etc.). All staff to receive basic fire response training.
Natural Hazards
Seasonal Heavy Rains (far south only) | 2 | 2 | 4 | 2 | Monitor local weather. Where travel outside of principal urban areas coincides with severe forecast rains, a risk-based decision as to whether to proceed should be made.
Sickness/illness associated with food, water or vector-borne disease, or other infection route | 3 | 3 | 9 | 4 | Development of a Medical Emergency Plan for the project, that identifies [insurer-approved] medical facilities in proximity to the project offices / expatriate staff residences and identifies medical facilities (likely poorly equipped / supplied community clinics) outside of Nouakchott on the project's principal field travel routes. Ensure all travelers have emergency medical insurance in place. All staff must know any insurance and learn how to contact them. Ensure HR have up to date Next of Kin details. Provide all traveling staff with a concise aide memoire covering: Ensuring all are medically and dentally fit to travel; immunizations are current and have consulted their physician; and ensuring all relevant medical information is within the pre-travel advice document.
Notes:
[1] This summary risk register and treatment plan (RRTP) provides an initial scoping of project-related risk to the safety and security of project personnel. This will be extended and deepened, and then validated by on-the-ground observation and assessment during the field consulting component of the task.
[2] Risks are assessed in relation to the understood project operations area, broadly defined as being confined to Trarza, Brakna and Gorgol provinces (bounded by the overland routes conecting Nouakchott to towns along the Senegal river valley (south to Rosso, east as far as Aleg) and speccifically excluding any operations that place personnel in proximity to the Malian and Algerian borders, where insecurity is very significvantly heightened.
[3] Likelihood and Impact Ratings are calculated based on the metrics show on the Assessment Tab.;

## Assessment - Impact
Impact Descriptors
The following provides a guide for evaluating the impact score system:
Impact Focus | Negligible – Score = 1 | Low – Score = 2 | Medium – Score = 3 | High – Score = 4 | Extreme – Score = 5
People - Physical Harm | Low-level injuries or symptoms. First aid treatment. | Reversible injuries require treatment but do not lead to restricted duties. | Reversible injury or moderate irreversible damage or impairment to one or more persons. Short-term unavailability of people or skills. | Single fatality, severe irreversible damage, or severe impairment to one or more persons. | Multiple fatalities or permanent damage to various people.
People - Emotional Harm | Low-level short-term impact on the victim’s emotional well-being and integrity. | Reversible impact on the victim’s emotional integrity. Low impact on skills or people availability. | Moderate irreversible damage to emotional integrity. | Severe irreversible damage to emotional integrity. | Severe irreversible damage to the emotional integrity of multiple people. Professional counseling is required, potentially over a protracted timeframe and to several individuals directly witnessing the incident or associated with it in some other way—protracted unavailability of skills or people.
|  |  | Victims potentially require stress trauma or other counseling. | Severe psychological trauma to the victim(s) requiring professional counseling.
|  |  | Short-term unavailability of skills or people. | Protracted unavailability of skills.
Physical Asset Damage | Damage to part of one building or site infrastructure that does not result in any substantive operational disruption. | Damage to part of one building or site infrastructure that has a temporary and fully recoverable impact on the continuity of site operations. | Damage to the whole building or site infrastructure that results in marked but recoverable continuity of site operations, including partial site evacuation or complete site evacuation where personnel can return to work within 24 hours. | Damage to whole building buildings or site infrastructure, resulting in complete site evacuation, where personnel cannot return to work for at least 24 hours, significantly disrupting business continuity. | Damage to the whole compound or all site infrastructure. The extent of the damage requires complete site evacuation with no return to work possible for at least 72 hours and, even then, potentially for only a fraction of the workforce. The extent of damage is of an order of magnitude that the business case for reconstruction/refurbishment may conclude costs outweigh benefits, resulting in fundamental and irrecoverable disruption of business continuity.
Digital Asset Security and Information | Impact on information otherwise available in the public domain or whose loss or compromise has limited risks if compromised. | Impact on information intended for organizational personnel only may create modest and recoverable operational, reputational, or business disadvantages. | Impact on information that could be detrimental to the organization and, potentially, more generally from a business or reputational standpoint, albeit of a recoverable nature. | Impact on information that seriously harms the organization weakens its competitive advantage or whose loss could cause severe financial, reputational, or litigation risks. | Significant impacts on the organization or other stakeholders’ confidential information, intellectual property, and Personally Identifiable Information, with seriously substantial and irreparable damage from a legal, reputational, business, or financial perspective.
Business | Minor harm for the ability to win or retain work at the activity or local level, with small fines or penalties. | Noticeable harm for the ability to win or retain work at the activity or local level, with medium-level fines or penalties. | It damages the ability to win or retain work at the activity or local level, with sizeable fines or penalties. | It seriously damages the ability to win or retain work at the functional or geographic level, with significant fines or penalties. | It catastrophically damaged the ability to win or retain work at the organizational level, with crippling fines and penalties.
Operations | Marginal impact – possibly no more than a hindrance – on specific, non-critical aspects of operations. The effect is transient and fully recoverable within 24 hours. | Limited impact on specific aspects of operations, leading to a meaningful disruption in activity, but one fully recoverable within 48 hours and requiring little or no additional or specialist resourcing. | The moderate impact does disrupt mission-critical aspects of operations. | Significant impact on mission-critical aspects of operations. | Catastrophic impact on the full range of operations. Continuity of operations is disrupted to the extent that complete recovery may be impossible or require significant additional or specialist resources to achieve and only over a protracted timeframe (>3 months)
|  |  | The impact is recoverable within 72 hours but may require additional or specialist resources to recover fully. | Continuity of operations is disrupted for up to a week, and full recovery is possible, but over a protracted period (1-3 months) and requires additional or specialist resources.
Reputation and Liability | Impact on reputation from an activity or limited geographic perspective. Public exposure in local media or by word of mouth. | Transient impact on the reputation of activity or location. Substantial (adverse) local media reporting. | Recoverable, but the severe short-term impact on the reputation of the activity or location. Some adverse national media reporting. | Long-term impact on the activity's reputation or geographic operating area, as well as a hit at the organizational level. Adverse international and national media reporting. | Severe and lasting impact on reputation at the organizational level and, potentially, terminally damaging for the activity or geographic operating area. Continuous, continual, and negative coverage in international media.

## Assessment - Probability
Probability Descriptors
The following provides the terms used by the leadership team to discuss risks in terms of probability and impact, understanding that the nature of the threat will influence the frequency.
Probability | Score | Description | Frequency
Almost certain (Extreme) | 5 | Repetitive event | Likely to occur once within a week
Likely (High) | 4 | Events that may occur frequently | Likely to occur once within a month
Possible (Medium) | 3 | Possibly during the activity lifespan | Likely to occur 2-3 times within a year
Unlikely (Low) | 2 | Unlikely during the activity lifespan | Likely to occur within five years
Rare (Negligible) | 1 | Very unlikely that during the activity lifespan | More significant than a 5-year event

## Assessment - Combined Scoring
The function of this stage in the process is to turn what might be a theoretical or conceptual understanding of risk into something that will inform the organizational response. The probability and impact assessments generate an overall Risk Rating concerning each Threat and Associated Risks. The assessments for probability and impact are combined, generating an overall Risk Rating. Risk Ratings range from 1 (negligible and requiring no active management) to 25 (requiring urgent and immediate mitigation and continuous monitoring). The Risk Rating is calculated by plotting the likelihood and consequence ratings in a 5x5 matrix:
5 x 5 Risk Matrix
Probability | Impact
| Negligible (1) | Low (2) | Medium (3) | High (4) | Extreme (5)
Almost certain (Extreme ) (5) | 5 | 10 | 15 | 20 | 25
Likely (High Risk) (4) | 4 | 8 | 12 | 16 | 20
Possible (Medium Risk) (3) | 3 | 6 | 9 | 12 | 15
Unlikely (Low Risk) (2) | 2 | 4 | 6 | 8 | 10
Rare (Negligible Risk) (1) | 1 | 2 | 3 | 4 | 5
Any risk rated as 12 or higher requires active management and continuous monitoring by the LIMT:
Risk Rating | Response
1-4 | Risks that are below the risk acceptance threshold, requiring monitoring but no active management
5-11 | Risks that lie on the risk acceptance threshold and require active monitoring and proportionate control measures to ensure the risk is managed adequately
12-20 | Risks that exceed the risk acceptance threshold and require urgent attention, proactive management, and continuous, dedicated monitoring
21-25 | Risks that require immediate senior-level leadership involvement and all activities stop.