# Introduction

This Risk Register and Treatment Plan for Partners of the Americas in Guatemala is part of the Safety, Security and Emergency Management ‘system’ and is designed to map, assess, and manage all forms of risk for a specific country. Risk is a large and complex subject, however by having a basic understanding of the principles by which to effectively manage risks then the management team will be better placed to ensure the risk ‘posture’ is proportionate to the risks faced and the resourcing available. This is not a ‘one-shot’ exercise; risk analysis and management must be undertaken continuously and must be integrated into the overall organizational management structure, business strategies and operational processes.

The management risk considerations include:

- Conducting a scheduled risk review annually of locational and activity-based risks; or where new influences warrant, conducting event driven risk reviews.

- Considering risk in terms of the nature and operating practices of the organization, as well as in relation to our operating areas and the risks these present.

- Assessing who we interact with, or who we are dependent on, and how their risks may impact or influence our risks.

- Determining how regulatory or legal requirements may influence our risks, and how we manage them.

- Understanding when risk reviews are triggered, notably where information indicates an escalation in the threat and associated risks, and where the current risk management approach and ‘posture’ may require to be adjusted.

When the management team is subject to an incident or ‘near-miss’ then a review will also be conducted as part of the standard ‘After Action Review’ within the Transition and Recovery phases of incident management. This may be conducted in partnership with the Headquarters team.

This Plan is broken into 2 sections:

- The Risk Register and Treatment Plan section which multiples the probability and impacts of potential risks for a pre-treatment risk rating, before then offering potential strategies to control identified risk. The multiplied probability and impact end risk ratings are then reassessed to reach a final risk rating score.

- The Risk Calendar which seeks to identify predictable periods of risk [holidays, elections, commemorative dates, seasonal risk factors etc].

Risk Register and Treatment Plan

The following Risk Register and Treatment Plan will be developed and maintained to assist the management team in determining the most likely and impactful risks to people, business, property, information, operations, and reputation. Instructions on how to complete this Plan are provided at the end of the document. Five levels have been offered to account for flexibility and nuances in evaluating risks – while still aligning the process to the defined gradings of RED, YELLOW, GREEN and BLACK:

N - 1 Negligible  	       L - 2 Low	 	M - 3 Medium	        H - 4 High	            E - 5 Extreme

P: Is the probability of occurrence                I: Is the impact if the threat occurs           R: Is the final risk RANKING where P x I   = R

JiT: Means Just in Time (as an event occurs / is identified as imminent or highly probable)

Owner: The Risk Owner is responsible for managing this risk response (with others supporting as needed).

Common and cross-cutting solutions for managing most or all forms of risk include:

| Risk Control Area | Control Measure |
| --- | --- |
| - Management Structures and Leadership | - A formal Safety Security and Emergency Management Team aka Local Incident Management Team structure - A defined lead on safety and security [qualified and supported] with a Security Focal Point - The ability to access and work with a defined headquarters team [crisis management leadership] - Available expert assistance to support with performance monitoring and unique needs |
| - Communications and stakeholder engagement | - The ability to communicate to the headquarters team - The ability to communicate within the country – especially to travelling teams - A Crisis Communications / Warden System / Phone Tree system - Pre-identified critical stakeholders and resources - The ability to share emergent safety and security information quickly and effectively |
| - Infrastructure [offices, residences, and warehouses] | - Facilities selected with safety and security as a consideration - Fire and medical equipment in place for offices and residences - Appropriate security [structural and technology] for offices - Security guards being provided – where conditions warrant |
| - Training, exercising and testing | - Access to relevant and credible training resources - Establishing a formal Security Focal Point training program - Training for international staff travelling into the country - All staff training on common safety and security topics - Safe Driver programs for fleet personnel - Formal security personnel training programs - Access and use of Just-in-Time training resources - Leadership training and certifications on key risk and emergency areas |
| - Insurance | - Medical and medical evacuation insurance programs - Local medical insurance programs - Political risk evacuation insurance programs |
| - Equipment | - Appropriate vehicles [profile, safety, and security] - Effective and redundant communications systems - Medical, fire and security equipment and technologies - Sat Phones and BGANSs - Encrypted laptops and flash drives |

Specific to risk type probability and impact evaluations and control measures include:

| Risk Nature | Baseline Ratings |  |  | Risk Management Solutions – Controls Applied | Ratings post-Mitigation |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | P | I | R |  | P | I | R |
| Abductions (kidnapping) | 3 | 5 | 15 | - K&R awareness training for vulnerable staff - Pre-Planned Response measures [PPRs] for K&R incidents - Effective travel security protocols and security trained drivers - Avoiding higher risk areas - Facility security measures – including guards where needed - Effective intelligence gathering and reporting protocols | 2 | 4 | 8 |
| Armed Aggressors | 3 | 5 | 15 | - Reporting suspect people and vehicles training for vulnerable staff - Pre-Planned Response measures [PPRs] for Armed Aggressor incidents - Effective travel security protocols and security trained drivers - Avoiding higher risk areas [government infrastructure, public gatherings, and social venues] - Facility security measures – including guards where needed - Pre-defined safe rooms and evacuation routes - Effective intelligence gathering and reporting protocols | 2 | 4 | 8 |
| Arrests and Detentions | 2 | 2 | 4 | - Legal awareness training for international staff - Pre-Planned Response measures [PPRs] for arrest and detention incidents - Pre-identified legal aid | 1 | 2 | 2 |
| Blackouts / Power Failures | 2 | 2 | 4 | - Pre-Planned Response measures [PPRs] for blackout incidents - Emergency food and water supplies - Emergency lighting - Generators and fuels | 2 | 1 | 2 |
| Bomb Threats | 1 | 4 | 4 | - Staff training on identifying and responding to bomb threats - Mail room and administration staff training on managing suspect letters and parcels - Pre-Planned Response measures [PPRs] for bomb threat incidents - Avoiding selecting facilities near high-risk targets - Staff avoiding higher risk areas [government infrastructure, public gatherings, and social venues] | 1 | 3 | 3 |
| CBRN Threats | 1 | 3 | 3 | - Just-in-Time training for staff on CBRN threats [esp. if located near chemical or industrial facilities] - Pre-Planned Response measures [PPRs] for CBRN incidents - Avoiding selecting facilities near high-risk infrastructures | 1 | 2 | 2 |
| Civil Disorder [and labor disputes] | 3 | 4 | 12 | - Staff training [Just-in-Time] when civil disorder threats are identified - Pre-Planned Response measures [PPRs] for civil disorder incidents - Effective travel security protocols and security trained drivers - Avoiding higher risk areas [government infrastructure, public gatherings, and social venues] - Facility security measures – including guards where needed - Effective intelligence gathering and reporting protocols | 2 | 2 | 8 |
| Community Incidents | 2 | 3 | 6 | - Cultural and social awareness training for staff and leaders - Effective intelligence gathering and reporting protocols - Stakeholder engagement strategies - Understanding profile and activity implications and effects within the local community | 2 | 2 | 4 |
| Criminal Incidents | 3 | 3 | 9 | - Training for leaders on managing criminal incidents - Pre-Planned Response measures [PPRs] for criminal [including fraud] incidents - Facility security measures – including guards where needed - Effective intelligence gathering and reporting protocols | 2 | 2 | 4 |
| Cyber Threats | 2 | 4 | 8 | - Acceptable Use Policy and Information and Operational Security Awareness Training for staff - Information sharing controls to protect sensitive or restricted information within the team - Pre-Planned Response measures [PPRs] for information loss incidents - Management instructions on operational and information security - Staff instructions on operational and information security | 2 | 2 | 4 |
| Earthquakes | 3 | 3 | 9 | - Staff training on natural disaster preparedness and response - Pre-Planned Response measures [PPRs] for earthquake incidents - Work from home policies instigated as needed - Emergency cash supplies available - Rapid procurement of emergency stores - Emergency supplies and stores [food, water, power, bedding etc] | 3 | 2 | 4 |
| Espionage and Information Security Breaches | 3 | 3 | 9 | - Reporting suspect people and vehicles training for vulnerable staff - Information and cyber security control instructions and measures - Facility security measures – including guards where needed - Effective reporting protocols | 2 | 2 | 4 |
| Fatalities / Casualties (serious) | 2 | 4 | 8 | - Basic medical training for staff - Support staff [drivers/guards] training on basic medical skills - Pre-Planned Response measures [PPRs] for medical incidents - Effective travel security protocols and trained drivers - Medical emergency plan with pre-identified doctors and hospitals - Appropriate medical equipment in facilities and vehicles | 2 | 2 | 4 |
| Facility Fires and Explosions | 3 | 3 | 9 | - Fire awareness and response training for staff - Fire awareness and emergency evacuation protocols for support staff [guards] - Pre-Planned Response measures [PPRs] for fire incidents - Facility safety [detection, alarm and fire-fighting equipment] - Evacuation and mustering protocols | 1 | 2 | 2 |
| Fires (forest) | 2 | 2 | 4 | - Just-in-Time training for staff - Pre-Planned Response measures [PPRs] for forest and bus fire incidents - Effective travel security protocols and trained drivers - Facility selection avoiding high risk areas - Work from home policies instigated as needed - Facility fire safety measures - Effective intelligence gathering and reporting protocols | 2 | 1 | 2 |
| Flooding [for infrastructure and travel] | 3 | 3 | 9 | - Just-in-Time training for staff - Pre-Planned Response measures [PPRs] for flooding incidents - Work from home policies instigated as needed - Effective travel security protocols and trained drivers - Facility selection avoiding high risk areas - Work from home policies instigated as needed - Effective intelligence gathering and reporting protocols | 3 | 2 | 6 |
| Fraud and Corruption | 4 | 4 | 16 | - Ethics and compliance training staff - Pre-Planned Response measures [PPRs] for fraud incidents - Management controls to identify / prevent fraud - Security factored into the termination of employment or contracts - Facility security measures – including guards where needed - Effective intelligence gathering and reporting protocols | 2 | 3 | 6 |
| Gender Risks | 3 | 4 | 12 | - Vulnerable staff training - Pre-Planned Response measures [PPRs] for intimidation or assault incidents - Effective travel security protocols and security trained drivers - Avoiding higher risk areas - Facility security measures – including guards where needed | 2 | 3 | 6 |
| Labor Disputes | 2 | 2 | 4 | - Understanding the local labor laws and culture on labor disputes - Pre-Planned Response measures [PPRs] for labor dispute incidents - Legal aid pre-identified - Work from home policy instigated as needed - Effective intelligence gathering and reporting protocols | 1 | 1 | 1 |
| LGBTQIA Risks | 4 | 5 | 20 | - Staff awareness building on legal and cultural considerations - Pre-Planned Response measures [PPRs] for arrest or assault incidents - Effective travel security protocols and security trained drivers - Facility security measures – including guards where needed - Effective intelligence gathering and reporting protocols | 3 | 3 | 9 |
| Media Attention | 2 | 3 | 9 | - Briefing staff on media engagement strategies – as required - Pre-Planned Response measures [PPRs] for negative or intrusive media incidents - Effective intelligence gathering and reporting protocols | 2 | 3 | 6 |
| Missing Persons [more than 24hrs] | 3 | 4 | 12 | - Safety and security training for staff - Pre-Planned Response measures [PPRs] for missing person incidents - Effective travel security protocols and security trained drivers - Avoiding higher risk areas [government infrastructure, public gatherings and social venues] - Effective intelligence gathering and reporting protocols | 2 | 3 | 6 |
| Pandemics / outbreaks of serious infectious disease | 3 | 3 | 6 | - Just-in-Time training for staff - Pre-Planned Response measures [PPRs] for pandemic incidents - Effective travel security protocols - Avoiding higher risk areas during an outbreak - Work from home policies instigated as needed - Emergency stores [medical, food and water] procured as required - Effective intelligence gathering and reporting protocols | 3 | 1 | 3 |
| Political Instability (Coups / War) | 3 | 3 | 9 | - Just-in-Time training for staff - Pre-Planned Response measures [PPRs] - Effective travel security protocols - Triggered Critical Event Planning - Work from home policies instigated as needed - Emergency stores [medical, food and water] procured as required - Effective intelligence gathering and reporting protocols | 3 | 2 | 6 |
| Political Risks (hostile government targeting) | 2 | 4 | 8 | - Focused training for staff - Pre-Planned Response measures [PPRs] - Effective engagement with key actors and diplomatic and government decision-makers - Work from home policies instigated as needed - Emergency stores [medical, food and water] procured as required - Effective intelligence gathering and reporting protocols | 2 | 3 | 6 |
| Proximity Risks [local area of facility or events] | 2 | 5 | 10 | - Security and safety selection criteria for facilities - Avoiding higher risk areas [government infrastructure, religious and public areas and social venues] - Facility security measures – including guards where needed - Effective intelligence gathering and reporting protocols | 1 | 2 | 2 |
| Road Traffic Accident [RTA] | 4 | 4 | 16 | - Fleet management and safe driving training programs - Pre-Planned Response measures [PPRs] for RTA and medical incidents - Effective travel security protocols - Medical emergency plan with pre-identified doctors and hospitals - Effective communications and reporting protocols | 2 | 2 | 4 |
| Severe Weather Fronts | 3 | 3 | 9 | - Just-in-Time training for staff - Pre-Planned Response measures [PPRs] for severe weather incidents - Effective travel security protocols and trained drivers - Avoiding higher risk areas [especially for flooding and landslides] - Facility safety measures and emergency stores - Work from home policy instigated - Effective intelligence gathering and reporting protocols | 3 | 2 | 4 |
| Threats and Intimidation | 3 | 3 | 9 | - Safety and security awareness training for staff - Pre-Planned Response measures [PPRs] for threats and intimidation incidents - Effective travel security protocols and security trained drivers - Facility security measures – including guards where needed - Effective intelligence gathering and reporting protocols | 2 | 2 | 4 |
| Tsunamis | 3 | 3 | 9 | - Just-in-Time training for staff - Pre-Planned Response Measures [PPRs] for tsunamis incidents – and associated risks - Emergency stores and communications equipment - Hibernation, relocation, and evacuation plans | 3 | 2 | 6 |
| Utility Failure | 4 | 2 | 8 | - Pre-Planned Response measures [PPRs] for critical utility failure incidents - Emergency supplies [food, water, power, fuels] and generator | 4 | 1 | 4 |
| Volcanic Eruptions | 3 | 3 | 9 | - Just-in-Time training for staff - Pre-Planned Response measures [PPRs] for volcanic eruption incidents - Effective travel security protocols and trained drivers - Avoiding higher risk areas [down-wind and lava stream hazards] - Facility safety measures - Work-from-home policies - Evacuation plans - Effective intelligence gathering and reporting protocols | 3 | 2 | 6 |
| Winter Storms | 1 | 1 | 1 | - Just-in-Time training for staff - Pre-Planned Response measures [PPRs] for winter storms incidents - Effective travel security protocols and security trained drivers - Work-from-home policies - Avoiding higher risk areas [avalanches and rock falls] - Effective intelligence gathering and reporting protocols | 1 | 1 | 1 |
| Workplace Violence | 2 | 3 | 6 | - Zero tolerance policy is articulated to all staff - Training and support to vulnerable staff - Pre-termination of employment security considerations - Pre-Planned Response measures [PPRs] for workplace violence incidents - Effective travel security protocols and security trained drivers - Security provisions offered – as needed - Facility security measures – including guards where needed - Effective intelligence gathering and reporting protocols | 1 | 2 | 2 |

# Risk Calendar

The following predicable points of risk are provided as part of the Risk Register and Treatment Plan.

| Date or Period of Risk | Name or Description of Risk | Risk Concerns | Risk Control Measures |
| --- | --- | --- | --- |
| 27 March 2023 | Start of electoral campaigns | Demonstrations, political violence | Monitor news and alerts & avoid areas with demonstrators |
| 23 June 2023 | Campaigns close | Suppression of election related media | Avoid areas of demonstrations in response to enforced limits |
| 25-30 June 2023 | Elections and challenges to results | Fomentation of civil disturbance | Avoid areas of demonstrations and riot control units |
| 20 August 2023 | Run-off elections | Civil disturbance between supporters | Monitor and avoid any civil disturbance or rallies |
| June to November | Hurricane season | Related disaster & infrastructure risks | Prepare emergency kits & evacuation plans |

# Risk Context

Health

- Zika virus and malaria are widespread in Guatemala, and there is risk of other insect borne illnesses such as dengue, chagas. Use repellent and insect nets.

- There is a significant risk of HIV/AIDS. Those participating in high-risk activities should take precautions

- Foodborne and waterborne illnesses are a risk; food should be thoroughly cooked, and bottled or boiled water consumed

Natural Disasters

- Guatemala is an active volcanic region and most natural disasters center around this fact

- There is a significant risk of earthquakes, ash, tsunamis, landslides, and forest fires

- There is also some risk of tropical storms and hurricanes which raise flood and infrastructure risks, especially the middle to Caribbean side of the country

Security & Safety

- Violent crime is common and increases at night. There is a significant risk of carjackings and express kidnappings, and murder rates are high.

- Borders are transit and transshipment points for transnational criminal organizations and related gang activity. Drugs and human trafficking are endemic

- Scams targeting tourists and foreign travelers are common; be aware of how to identify official service providers

- Corruption is endemic in the country and travelers should be wary of interactions with law enforcement who may attempt to extort individuals

- Civil disturbances are likely to increase during this election cycle in response to corruption, illegal campaign finance, and institutional deterioration

- Gang violence is a constant in Guatemala, with networks across several Central American countries

# Management Guidelines

The following section offers guidance into how the Risk Register and Treatment Plan section can be most effectively completed.

## The Language of Risk

Having a shared understanding of the language of risk will enable good communication and more effective decision-making. The basic definitions employed are as follows:

- Asset: An asset is anything deemed to have value, including people, information, physical assets such as buildings and equipment, and those less tangible, but often as important, such as our reputation. Assets are what our risk management strategy is designed to protect.

- Threat: A threat is anything that might happen that could cause harm to an asset, damage, or its loss. The level of threat would be determined by the probability that it would materialize, and the motivation or cause of this event to occur, whether human-made or natural.

- Vulnerability: A vulnerability is a weakness or gap in our approach to protecting assets that could be exploited or compounded by threats. Mitigation strategies are designed to protect assets from threats.

- Risk: A risk is the intersection of threats, assets, and vulnerabilities; it is the effect that a threat has upon assets where vulnerabilities occur.

## The Risk Management Process

Risk management must be a structured, coherent process that works through a logical sequence. It must also be iterative – operating continuously as a live feedback loop. The threat identification process should be a team effort, bringing together both internal (and where appropriate, external stakeholders) to determine where threats are specifically focused on a function or activity, to where threats are cross-cutting in nature. Care must be taken not to confuse threats and the associated risks risk with either the things that create a risk (the cause) or what happens if the risk materializes (the consequences). It is useful to delineate threats thematically, as this can form a useful starting point for those undertaking this step in the process when confronted with what can seem a mass of information, intelligence, and opinion.

Two broad groupings of risk exist within these thematic areas:

- Humanmade Threats: Incorporating those related to hostile acts such as terrorism, criminality and civil disorder, and safety issues resulting from human factors such as road traffic accidents caused by aggressive, risky local driving behavior, and building fires resulting from inadequate fire safety regulation and practices.

- Natural Hazards: Incorporating those associated with severe weather, natural disasters and risks resulting from disease.

It is important for management teams to also understand that threats may create both direct and indirect (or cascading) risks.

## Risk Assessment

The risk assessment stage involves defining an estimate of the probability of a risk actually happening, and the severity of impact if it does occur. Risks are categorized according to whether they affect: [1] People, [2] Physical Assets, [3] Digital Assets or Information, [4] Business, [5] Operations, and [6] Reputation and Liability. The estimates of Probability and Impact are given ‘ratings’, ranging from Negligible to Extreme, culminating in a final Risk Ranking score.

### Impact Descriptors

The following provides a guide for evaluating the impact score system:

| Impact Focus | Negligible – Score = 1 | Low – Score = 2 | Medium – Score = 3 | High – Score = 4 | Extreme – Score = 5 |
| --- | --- | --- | --- | --- | --- |
| People - Physical Harm | Low-level injuries or symptoms. First aid treatment. | Reversible injuries requiring treatment but does not lead to restricted duties. | Reversible injury or moderate irreversible damage or impairment to one or more persons. Short term unavailability of people or skills. | Single fatality and/or severe irreversible damage or severe impairment to one or more persons. | Multiple fatalities or permanent damage to multiple people. |
| People - Emotional Harm | Low-level and short-term impact on the victim’s emotional well-being and integrity. | Reversible impact on the victim’s emotional integrity. Low impact on skills or people availability. | Moderate irreversible damage to emotional integrity. Victims potentially require stress trauma or other counselling. Short-term unavailability of skills or people. | Severe irreversible damage to emotional integrity. Severe psychological trauma to victim(s) requiring professional counselling. Protracted unavailability of skills. | Severe irreversible damage to emotional integrity of multiple people. Professional counselling is required, potentially over protracted timeframe and to a number of individuals directly witnessing the incident or associated with it in some other way. Protracted unavailability of skills or people. |
| Physical Asset Damage | Damage to part of one building and/or site infrastructure that does not result in any substantive operational disruption. | Damage to part of one building and/or site infrastructure that has a temporary, and fully recoverable, impact on continuity of site operations. | Damage to whole building and/or site infrastructure that results in marked, but recoverable, continuity of site operations, including partial site evacuation or whole site evacuation where personnel can return to work within 24 hours. | Damage to whole building buildings and/or site infrastructure, resulting in full site evacuation, where personnel are unable to return to work for at least 24 hours, resulting in significant disruption to business continuity. | Damage to whole compound and / or all site infrastructure. Extent of damage requires full site evacuation with no return to work possible for at least 72 hours and, even then, potentially for only a fraction of the workforce. Extent of damage is of an order of magnitude that the business case for reconstruction / refurbishment may conclude costs outweigh benefits, resulting in fundamental and irrecoverable disruption of business continuity. |
| Digital Asset Security and Information | Impact on information otherwise available in the public domain, or whose loss or compromise has limited risks if compromised. | Impact on information intended for organizational personnel only, which may create modest and recoverable operational, reputational, or business disadvantage. | Impact on information which could be detrimental to the organization and, potentially more generally from a business or reputational standpoint, albeit of a recoverable nature. | Impact on information which seriously harms the organization or weakens its competitive advantage, or whose loss could cause serious financial, reputational or litigation risks. | Significant impacts on the organization or other stakeholder’s confidential information, intellectual property, and Personally Identifiable Information, with seriously significant and irreparable damage from a legal, reputational, business, or financial perspective. |
| Business | Minor harm for the ability to win or retain work at the activity or local level, with small fines or penalties. | Noticeable harm for the ability to win or retain work at the activity or local level, with medium level fines or penalties. | Damaging the ability to win or retain work at the activity or local level, with sizeable fines or penalties. | Seriously damaging the ability to win or retain work at the functional or geographic level, with significant fines or penalties. | Catastrophically damaging the ability to win or retain work at the organizational level, with crippling fines and penalties. |
| Operations | Marginal impact – possibly no more than a hindrance – on specific, non-critical aspects of operations. Impact is transient and fully recoverable within 24 hours. | Limited impact on specific aspects of operations, leading to a meaningful disruption in activity, but one that is fully recoverable within 48 hours, and requiring little or no additional or specialist resourcing. | Moderate impact that does disrupt mission-critical aspects of operations. Impact is recoverable within 72 hours but may require additional or specialist resourcing to achieve full recovery. | Significant impact to mission-critical aspects of operations. Continuity of operations is disrupted for up to a week, and full recovery is possible, but over a protracted period (1-3 months) and requiring additional or specialist resources. | Catastrophic impact on the full range of operations. Continuity of operations is disrupted to the extent that full recovery may be impossible or require significant additional or specialist resourcing to achieve and only over a protracted timeframe (>3 months). |
| Reputation and Liability | Impact on reputation from an activity or limited geographic perspective. Public exposure in local media or by word of mouth. | Transient impact on reputation of an activity or location. Substantial (negative) local media reporting. | Recoverable, but short-term serious impact on reputation of the activity or location. Some negative national media reporting. | Long term impact on the reputation of the activity or geographic operating area, as well as an impact at the organizational level. Negative international and national media reporting. | Severe and lasting impact on reputation at the organizational level and, potentially, terminally damaging for the activity or geographic operating area. Persistent, continual, and negative coverage in international media. |

### Probability Descriptors

The following provides the terms used by the management team to discuss risks in terms of probability and impact, understanding that the frequency will be influenced by the nature of the threat.

| Probability | Score | Description | Frequency |
| --- | --- | --- | --- |
| Almost certain (Extreme) | 5 | Repetitive event | Likely to occur once within a week |
| Likely (High) | 4 | Event that may occur frequently | Likely to occur once within a month |
| Possible (Medium) | 3 | Possibly during the activity lifespan | Likely to occur 2-3 times within a year |
| Unlikely (Low) | 2 | Unlikely during the activity life-span | Likely to occur within a 5-year time span |
| Rare (Negligible) | 1 | Very unlikely during the activity life-span | Greater than a 5-year event |

In relation to security risks, it useful to think of the probability of a threat being manifest as a function of the following three factors:

- The Intent: A measure of a hostile party’s determination to carry out an aggressive act.

- The Capability: The degree to which a hostile party has the skills, knowledge, and resources to be successful in an attempted hostile act.

- The Opportunity: A combination of the access that a hostile party might have and the vulnerability of the environment within which the target of such an act is present.

The function of this stage in the process is to turn what might be a theoretical or conceptual understanding of risk into something that will inform the organizational response. As such, the assessments of probability and impact are used to generate an overall Risk Rating in relation to each Threat and associated Risks. The assessments for probability and impact are combined, generating an overall Risk Rating.

Risk Ratings range from 1 (negligible and requiring no active management) to 25 (requiring urgent and immediate mitigation and continuous monitoring). The Risk Rating is calculated by plotting the likelihood and consequence ratings in a 5x5 matrix.

| Probability | Impact |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Negligible (1) | Low (2) | Medium (3) | High (4) | Extreme (5) |
| Almost certain (Extreme Risk) (5) | 5 | 10 | 15 | 20 | 25 |
| Likely (High Risk) (4) | 4 | 8 | 12 | 16 | 20 |
| Possible (Medium Risk) (3) | 3 | 6 | 9 | 12 | 15 |
| Unlikely (Low Risk) (2) | 2 | 4 | 6 | 8 | 10 |
| Rare (Negligible Risk) (1) | 1 | 2 | 3 | 4 | 5 |

Any risk rated as 12 or higher automatically require active management and continuous monitoring by the leadership team:

| Risk Rating | Response |
| --- | --- |
| 1-4 | Risks that are below the risk acceptance threshold, requiring monitoring but no active management |
| 5-11 | Risks that lie on the risk acceptance threshold and require active monitoring, and proportionate control measures to ensure the risk is managed adequately |
| 12-20 | Risks that exceed the risk acceptance threshold and require urgent attention, proactive management, and continuous, dedicated monitoring |
| 21-25 | Risks which require immediate senior level leadership involvement, and all activities stop |

## Risk Management

Risks assessed as requiring mitigation are allocated to a ‘Risk Owner’. Actions to mitigate the risks are specified in the Risk Treatment Plan, and the Risk Owner is responsible for ensuring these actions are carried out – against agreed milestones and standards. Ownership of risk is critical, as failure to allocate responsibility (and accountability) can mean that risk is not actively managed. A Risk Committee (at the activity, location or organizational levels) then reviews all risks to determine how all threats and vulnerabilities are managed. Risks are typically managed in one, or a combination, of the following ways:

- Transfer: Shifting the burden of risk onto a third party. Commonly this is done through acquiring insurances or service contracts that pass responsibility for the management of risk or the treatment of its consequences to external parties.

- Avoid: Risks can be avoided, including through deciding not to conduct an activity or operate in an area, where the risks, even though transferred or reduced, remain intolerable.

- Reduce: Through the active management of a risk exposure and impacts can be reduced through the application of training, contracted services, resources, operating practices, or assets.

- Accept: In some cases, risks would be regarded as tolerable, either because the probability that they would ever materialize is so low, or the impact so minimal, that the costs of managing that risk are deemed disproportionate.

## Risk Monitoring

Risk Analysis and Management is a dynamic process – new risks emerge, background risks escalate, and present risks can diminish or disappear. Risk Owners should provide updates on their achievement in managing risks, and the Risk Committee should constantly review the changing risk landscape, communicating implications up and down the management chain, and proactively managing potential consequences and probabilities.

## Hierarchy of Controls

The Hierarchy of Controls system ascribes a rating (1-5) to the level of risk control the measures create, where 1 is limited or no control measures in place, and 5 is full control, typified by well-communicated, integrated plans, procedures and processes that have been rationally constructed to directly manage assessed risks, and where these documented approaches are operationalized through a systematic awareness and competency program that looks to develop and exercise knowledge and skills at individual and collective levels. Controls rated as 5 would also typically evince the resourcing of assets, technology, equipment, and services that have been procured or engaged proactively and [demonstrably] proportionately to the level of assessed risk, with resourcing planned as a component of wider budgetary cycles (i.e., not reactive).

To arrive at a final Risk Rating (i.e., the Risk Rating once the risk has been treated by the control measures, the Risk Rating (/25) is ÷ the ascribed Control Rating yielding the following outcomes:

The hierarchy of controls may provide risk management solutions against the following thematic categories:

- People: The provision of qualified and experienced managers and experts.

- Documents: The extent to which documented plans, procedures and processes capture and articulate best practice and expertise and are then effectively shared and communicated.

- Training and testing [or Awareness and Competency]: The ability of individuals and teams to understand and implement the policies, plans and protocols, procedures, and processes.

The following may fall under the broad category of ‘Operational Risk Management’:

- Service support: The engagement of external services to support risk management, including risk and resiliency expertise, logistics, guard force, medical, legal, intelligence and training providers.

- Assets and resources: The use of equipment and materials by which to manage risks, such as vehicles, technologies, software, physical structures, medical assets, to food and water supplies.

- Movement controls: The control of movement (land/sea/air), including vehicle types and configurations, trip planning, security resourcing, equipment, technologies and training.

- Facility measures: The provision of perimeter security measures, access control points, restricted areas, CCTV, Intruder Detection Systems, lighting, generators, the use of ‘defensive’ structures, and safe rooms.

- Activity Risk Management: The application of ‘risk management in practice’ relating operational risk management measures, whether as cross cutting controls, or as applied to a specific activity