# Instructions: 10 pages, maximum, addressing all 12 numbered sections.  Delete template instructions in each section after completing.

# Submit via email as attachment to: GTM-PASGrants@state.gov 

1. Coversheet

| Name of Project | Expanding Central America-U.S. Higher Education Climate Cooperation and Inclusive Education Exchanges through 100K Strong Americas |
| --- | --- |
| Name of organization or individual applying | Partners of the Americas |
| For organizations: provide DUNS # | DD5WNYRUYFE5 |
| Amount of funds requested (USD) | $200,000 |
| Location of project | Central America |
| Timeframe (start/end of project) | October 1, 2023 – September 30, 2025 |
| Name of primary point of contact | Penelope Kim |
| Telephone number | (770) 713-4899 |
| Email address | pkim@partners.net |
| Name of Legal Representative to sign documents | John McPhail President & CEO |
| Funds previously received from U.S. government, if any | Purpose: Expand strategic engagement to leverage partnerships from the Guatemalan/Central American private/public sector and government partners to support the 100K Innovation Fund grants and programming. Amount: $165,000 Date: Sep 30, 2020 – Feb 28, 2023 |
| Are any State Department program alumni involved in this project? | No |
| Date of Submission | September 18, 2023 |

## 2. Proposal Summary

Program Description, Background, Track-Record

100,000 Strong in the Americas (100K Strong) is the U.S. Department of State, Bureau of Western Hemisphere Affairs (WHA/DOS) signature hemisphere-wide initiative to champion the power of education to transform societies, provide opportunity, and stimulate economic prosperity. The 100K Strong Innovation Fund is the public-private sector collaboration between the Bureau of Western Hemisphere Affairs (WHA/PDA) and Partners of the Americas (POA), working with regional private and public sectors to stimulate and support higher education institution (HEI) partnerships between the United States and regional HEIs.

The 100K Strong Initiative strengthens collaboration and transparency among governments, business, and academic networks – critical to economies in the Americas. In ten years (2013-2023), the 100K Strong Innovation Fund has become the trusted mechanism for the U.S. and regional public/private sectors to invest in innovative, inclusive higher education partnerships and student exchange and workforce training programs.  Teams of U.S. colleges and universities compete for 100K grants from matched U.S. government, private-sector, and HEI-funds; with those 100K grants, HEIs in the U.S. and Latin America create sustainable institutional partnerships and strengthen regional education cooperation and competitiveness.

For the purpose of this award, Partners of the Americas (POA) requests a one-time allotment of $200,000 to support WHA policy priorities and to ensure that the U.S. is the leading partner of choice for regional exchange and training programs via a new Central America-focused 100K Strong competition in 2024-2025. These USG (via WHA/DOS) funds will be used to identify, cultivate, and leverage potential, additional non-USG resources to launch a new 100K Strong Climate competition in Summer/Fall 2024 to expand higher education partnerships between a diversity of Central American and U.S. HEIs and increase access to innovative, inclusive student exchange and training program opportunities for students in diverse academic disciplines.

## 3. Introduction to the Organization or Individual applying

Partners of the Americas (POA), under a cooperative agreement with WHA/PDA, is the lead 100K Strong implementing partner entity (NGO) that manages 100K Strong programming in coordination with WHA/PDA, along with U.S. embassies. POA’s scope of work includes developing potential regional private/public sector entities to secure potential non-USG funds that support regional 100K Strong and leverages USG resources to expand 100K grant opportunities for HEIs in WHA region.  For ten years (2013-2022), POA has been working with WHA/PDA and U.S. embassies to develop and expand 100K Strong partnerships and student exchanges with regional public, private, academic sectors. POA has 60 years of robust experience in Latin America and the Caribbean managing networks of civil society and implementing other USG-sponsored programs.

Since 2019, POA has worked closely with PAS-Guatemala and WHA/PDA to cultivate and leverage collaboration with and funding from private sector entities to regional higher education cooperation with a diversity of HEIs in the U.S. to increase new models of innovative exchanges so that more students can work in teams in Central America and gain technical, linguistic, and intercultural skills imperative for workforce development.

NOTE: Previous USG funds from WHA/DOS as well as other Posts (i.e., Panama and Honduras) were used to cultivate and secure non-USG contributions upwards of $500,000 from regional private sector entities (based in Guatemala), that made it possible to launch three sets of regional 100K Central America competitions between 2017 and 2021. As a result of the three (3) sets of 100K Strong Central America competitions, a total of 22 grants ($25,000 each) were awarded – on a competitive basis in the 100K evaluation/selection process managed by POA with WHA/PDA and Posts --to teams of 45 HEIs that engaged and benefitted over 650 students and faculty (and growing) in the U.S. and Central America. POA received 76 proposals for three (3) sets of 100K competitions, while 22 available grants (close to $440,000) were awarded competitively to regional HEIs in Central American and U.S. colleges and universities (including HBCUs). To date, Costa Rica, Guatemala, El Salvador are leading countries in terms of 100K partnerships and exchanges with HEIs in the U.S.

## 4. Problem Statement

Opportunities for sustained, innovative student/faculty exchanges between HEIs in the U.S. and regional HEIs in Latin America and the Caribbean (LAC) lag behind other world regions, despite factors such as proximity, cost, cultural, and social similarities. 100K Strong partnerships and exchanges help to address challenges and barriers so that more students in the Western Hemisphere can gain access to inclusive, regional exchange and workforce training programs.

WHA/DOS and POA coordinated the design and implementation of the 100K program based on the premise that if we build the capacity of HEIs to develop and sustain inclusive educational exchanges, and if student mobility within the U.S. and the rest of the Western Hemisphere grows accordingly, students will gain skills needed to strengthen the regional workforce and contribute to stronger, greener, and more equitable economies. The 100K program also reflects the public diplomacy premise that participation in inclusive exchange programs enhances cross-cultural competence and global perspectives, which may induce favorability toward the United States.

Through experience managing three sets of 100K-Central America-focused grant competitions (2018-2022), POA, along with WHA/DOS and Posts, know demand for 100K grants continues to exceed the availability. A fourth Central America-focused competition in 2024-2025 will support WHA/DOS, PAS-Guatemala, and other regional Posts’ goals for a greener, more inclusive, prosperous Hemisphere via 100K Strong program that fosters through collaboration with public, private, and academic sectors to support regional workforce development.

## 5. Program Goals and Objectives

POA, in coordination with WHA/PDA, will work with PAS-Guatemala (and other Posts in Central America) to secure non-USG funds as well as carry-out the following 100K Innovation Fund programming activities, including, but not limited to:

- Identify and lead efforts to engage with prospective non-USG donors for potential resource cultivation to support a new 100K Central America-focused grant competition.

- Secure non-USG commitments from regional private/public sectors to leverage the USG-funds to support 100K Central America-USA competition and HEI partnerships (2024-2025).

- Launch a new 100K Strong “CLIMATE” competition in 2024 and implement 100K Strong grant activities in collaboration with WHA/PDA and Post-Guatemala, including promotion, 100K grant evaluation/selection process, and providing/monitoring 100K Strong sub-awards to teams of Central American-U.S. grant winning HEIs.

- Build 100K Strong brand sustainability in Central America and conduct robust 100K targeted, regional communication plans (e.g., 100K website, 100K webinars, social media, press releases).

## 6. Program Activities

Participants:

- WHO will participate?  Participants will include students, faculty, administrators from HEIs in Central America and the U.S.

- WHO will benefit?  Students and faculty in Central America and the U.S.

- HOW will participants be selected? 100K grant-winning HEIs will be selected via the 100K Strong review/evaluation program. POA will work with 100K-HEIs to ensure that there is diversity of participants (eg students and faculty)

- WHERE will the activities take place? HEIs in Central America and the U.S.

Project Plan:  See below.

POA will collaborate with WHA/PDA, PAS-Guatemala, and regional Posts, along with (TBC) private sector entities) to implement the 100K Strong CLMATE competition to expand bidirectional student exchange and training programs between HEIs in the U.S. and Central America.

100K Strong Climate (“100K CLIMA) Competition (in support of SOA 2022 Deliverables and WHA Policy Priorities.

- Geographic Focus: Central America and the United States

- Number of Grants: 5-8

- Strategic Focus/Themes: The 100K Strong CLIMATE themes will be determined by collaboration between POA, WHA/DOS, and Posts, in coordination with (TBC) private sector entities that contribute non-USG funds to support the 100K Strong CLIMATE competition. Thematic examples include following: Climate Action, Green Technology, Clean Energy, Social Inclusion, STEM, WASH, sustainable agriculture, among others. POA will coordinate with WHA/PDA and Posts to ensure best practices from previous 100K Strong regional competitions focused on workforce development, innovation, and DEIA.

Development and Promotion of the Request for Proposals (RFP)

In coordination with WHA/PDA, PAS-Guatemala, Posts, and (TBC) private sector entities, POA will develop and promote the RFP for the 100K-Central America grant competition. POA will announce the 100K Strong competition in future virtual and/or in-person events to be determined with WHA/DOS and Posts. Examples include 100K events with Posts and leadership from private/public/academic sectors in Central America and at regional workshops or conferences engaging a diversity of HEIs, including community colleges, HBCUs, and other minority-serving institutions (MSIs). POA will develop all related 100K Strong Central America competition communications plans—in coordination with WHA/PDA and Posts — to ensure that target audiences are reached, both for program promotion as well as overall visibility.

100K Strong Central America Launch Announcement

POA will work with WHA/PDA, PAS-Guatemala, and Posts to announce the launch or the opening of the 100K Strong competition. Additionally, POA will work with WHA/PDA and Posts to plan the forum for the 100K Strong partners and future 100K Strong grant-winning teams of HEIs. These announcements have been held both in the U.S. and in Latin America involving high-level government officials, private sector supports, and representative institutions.

Promotion of 100K-Central America Grant Competition

POA will disseminate information about the 100K Strong RFP to HEIs through marketing, the 100K website, communications (e.g., social media, press releases), as well as conduct at least two (2) sets of informational webinars, in English & Spanish. Other 100K Strong outreach includes POA, WHA/PDA, and Posts engagement with regional higher education conferences and other events to promote 100K grants opportunities and future partnerships between HEIs in the U.S. and Central America to encourage HEI teams to submit 100K grant proposals.

Capacity-Building Webinars/Workshop

POA will host informational webinars/workshop for interested institutions to learn about the grant competition, RFP requirements, how to apply, and how to develop a winning proposal.  Resources from the webinars, including recordings, email list of participants, presentations, and a Question-and-Answer report will be shared on 100K Strong website. POA invites support from PAS-Guatemala to hold webinars in Spanish.

Proposal Review and Evaluation, and Selection of Grant Winning Projects

POA manages a rigorous, comprehensive review, evaluation, and selection process of 100K grant proposals with volunteer expert reviewers from international education, academic exchanges, WHA/DOS, Posts, and 100K Strong alumni. Following the closing date of the competition, POA will implement the process to review/evaluate 100K proposals from teams of HEIS, including the organization of panels, notetaking of virtual, live review sessions, and compilation of proposals’ score sheets and other required documents. The estimated timelines to complete to complete the 100K proposals’ review/selection process takes 6-8 weeks, with the 100K winners’ announcement event to follow this process.

Winners Announcement

POA will work with the WHA/PDA, PAS-Guatemala, and other Posts to plan the official-public facing event to announce the 100K-grant winning institutions and highlight the 100K Strong cross-sector collaboration. The in-person 100K Strong “winners” announcements can be conducted in the U.S. and/or in Latin America, and typically bring together leadership from WHA/DOS, Posts, regional government,  private sector, academic institutions.

Digital/Social Media Promotion

To ensure 100K Strong program outreach, POA will promote the 100K-Central America competition in coordination with WHA/DOS and Posts, and provide comprehensive 100K Strong branded communications, including Press Releases, Social Media Kits, visibility on 100K Strong website, including the Grants webpage, a series of e-blasts to the 100,000 Strong in the Americas Innovation Network (4,000+ HEI contacts representing 2,300 HEIs). Additionally, POA will coordinate outreach with EducationUSA, regional education conferences/event (e.gg NAFSA, AIEA, FAUBAI) and social media tagging WHA/DOS, Posts, and HEIs across Facebook,  Twitter, and Instagram.

Distribution of Funds and Project Monitoring and Evaluation

POA will distribute sub-grant funds to the winning institutions and will monitor the implementation of their projects through completion.

## 7. Program Methods and Design

To expand 100K Strong-branded education exchanges between HEIs in Central America and the U.S in 2024-2025, POA will coordinate with WHA/PDA, PAS-Guatemala, and other Posts in Central America, to identify, cultivate, and leverage potential non-USG funds from regional private sector entities that would support a new 100K Central America-U.S.-focused grant competition. Target date for this 100K Strong Central-America regional competition would be Summer/Fall 2024.

Through targeted outreach and coordination between POA, WHA/PDA, and Posts in Central America, the target goal would be to secure additional non-USG funds (upwards of $200,000) from regional public/private sector entities to launch the new 100K Strong “CLIMATE” competition in Summer/Fall 2024 to expand HEI partnerships focused on climate action, green technology, clean energy, sustainable agriculture, and social inclusion for students and faculty to work virtually and in-person in Central America and in the U.S.s via expanded 100K Strong higher education collaboration.

## 8. Proposed Program Schedule

The estimated launch of new 100K Strong CLIMATE competition for Central America in Summer/Fall 2024, pending funding. The 100K-RFP application process takes 16-20 weeks; the process to review/evaluate/select 100K grant-winning teams takes 6-8 weeks; and the 100K Strong announcement of winners would take place in late 2024. ESTIMATED timeline below (subject to change).

| ACTIVITY | DESCRIPTION | DATES | LOCATION |
| --- | --- | --- | --- |
| Public/Private Sector Cultivation | Implement targeted outreach campaigns to identify and cultivate new prospective donor-partners, raising their awareness of the strategic need for regional education cooperation to contribute to workforce development in the Americas. Campaigns will be tailored to focus on sectors and countries that align with U.S. foreign policy goals and regional workforce development needs. | October 2023 – Spring 2024 | Virtual/In-person (U.S. and Central America) |
| RFP Design & Development | Prepare, review, and publish the request for proposal (RFP) for 100K U.S.-Central-America Grant Competition, taking into account the eligibility criteria and thematic areas established by PAS-Guatemala and private sector partners. | Spring/Summer 2024 | Virtual |
| Launch of Grant Competition | Plan a public event to announce the new grant competition and 100K partnership with private sector partners. | Summer/Fall 2024 | Virtual or In-person |
| Promotion of Grant Competition | Disseminate information about the RFP to HEIs through marketing/communications strategies; conducting at least two (2) sets of informational webinars, in English & Spanish; and attendance of regional higher education conferences and other events, in which POA, PAS-Guatemala, and WHA/PDA participate to promote partnerships between HEIs in the U.S. and Central America, and thus encourage their participation and submission of 100K grant proposals. | Summer/Fall 2024 | Virtual (e-marketing and webinars) In-person (HEI conferences) |
| Review & Selection of Grant-Winning Proposals | Organize committees to evaluate proposals; conduct multi-stage evaluation process to verify that proposals meet all the requirements in accordance with the terms of the RFP; and select grant winners. | September – October 2024 | Virtual |
| Announcement of Grant Winners | Plan and carry out an event to announce the grant-winning partnerships with the participation of PAS-Guatemala, WHA/PDA, public and private sector partners, and HEIs. | November 2024 | Virtual or In-person (Guatemala City) |
| Disbursement of Sub-grants | Award sub-grants to selected grant-winning HEIs. | November-December 2024 |  |
| Implementation of HEI Projects | Selected grant-winning institutions implement their proposed projects in the U.S. and Central America. | January - September 2025 | Virtual and in-person student mobility |
| Monitoring & Evaluation of Sub-grant Projects | Monitor progress of HEI projects, collect sub-grant reports, and provide support as necessary in implementation. | January - September 2025 | Virtual |

## 9. Key Personnel

Penelope Kim, Program Director, will oversee all aspects of program implementation and ensure grant compliance with PAS-Guatemala and that activities align with and meet program goals, as well as strengthen the 100K program’s relationship with HEIs. Her time will be covered by POA’s grant with WHA/PDA. Ms. Kim will be supported by members of the 100K program team at POA, including the Director of Public-Private Partnerships and the following individuals, who will charge a portion of their time to the grant to ensure 100K visibility and the collection and sharing of program impact on students, faculty, and administrators at recipient institutions.

Melisa Arrázola, Communications Officer, will dedicate 5% of her time to support outreach, communications, and marketing for partnership development, grant competition promotion, material design, and event planning.  She will lead digital communications/marketing efforts, including update and maintenance of the 100K website, promotion of the 100K Alumni Network and student/alumni engagement efforts, and online and social media presence.

Mariana Cabrera, Program Officer, will dedicate 5% of her time to implement Monitoring, Evaluation, and Learning (MEL) activities and ensure collection and sharing of 100K Strong grant impact on HEIs and students. Responsibilities include determining designing/administering survey tools, tracking, collecting, and analyzing data/reports, and reporting on HEI project achievements and impact.

## 10. Program Partners

During Fall 2023 and Winter/Spring 2024, POA will work with WHA/PDA and PAS-Guatemala, along with other Posts in Central America, to identify, cultivate, and leverage potential additional non-USG funds from regional private sector entities that would support a new 100K Central America-U.S.-focused grant competition.

## 11. Monitoring and Evaluation Plan

POA will monitor the implementation of their projects through completion to ensure that they meet benchmarks and achieve project objectives and goals. POA will employ a range of tools to assess performance indicators and collect both quantitative and qualitative data. These tools, along with a combination of monitoring and observation, will help POA assess the degree to which program goals are being met, project plans and activities are progressing, and virtual activities are working as intended.

Document Reviews. POA will track program progress through review and analysis of documents submitted.

- 100K-HEI programs: Monitoring of 100K projects starts with the 100K proposal/application process in which HEIs provide student mobility data in their proposal, institutional barriers/ challenges to student mobility, and level of collaboration with their proposed HEI partners. Proposals typically include additional baseline data on the profile of participating institutions or diversity of students. This contributes to the baseline data if the applicant is selected as a grant recipient and is then compared with information collected throughout and after the implementation of the 100K project.

- HEI Project Reports: One of the conditions of the 100K sub-grant agreement is that HEI grantees provide a progress report every four months and a final, cumulative report. The progress report contains quantitative as well as qualitative information. Quantitative data includes the number of students and faculty going abroad, additional students and faculty that participate in the program, and other project indicators presented in their proposals. Qualitative data includes project accomplishments, implementation challenges, student & faculty anecdotes, and other relevant information. The final report provides an evaluation of project accomplishments and challenges and summarizes the short-term outcomes (e.g., capacity increase, network expansion, funding, plans to continue the program).

Surveys

- HEI (faculty and administrators) surveys will be administered to HEI grantees after key program activities, such as the grant application process, capacity building webinars/workshops, and implementation of 100K projects.

- 100K Student surveys will be administered before and after the 100K Strong exchanges to assess their technical; linguistic, and intercultural learning; views of host/home country, and factors that influence their decision-making regarding their academic / career development. Demographic information will be captured during the pre-program survey.

Secondary Data/Activity Analysis. POA will monitor student and HEI conduct throughout the program, using the virtual engagement activities as opportunities for more personal observation and interaction with participants.

- Ongoing & Direct Support to HEIs & Students: Monitoring of 100K projects take place during the grant period through regular email communications, virtual meetings, etc. POA also offers grantees one-on-one support appointments to discuss concerns of a project individually. Through these meetings, POA answers grantees questions, clarifies doubts, and work closely with grantees to resolve project-related issues. Notes from these meetings are saved in an issues/notes log in the program’s grants management system and can be used to track project progress and identify trends and issues as they relate to international education programming that may affect other 100K projects.

- Program Activities: All program activities will be monitored and reviewed to gather information for the performance indicators.

## 12. Sustainability and Follow-Up Plan

Grant-Winning HEIs: Supporting Post-Program Partnerships and Activities

POA’s plan for program sustainability and long-term engagement includes ensuring that 100K grant-winning HEIs continue to have opportunities to form and sustain partnerships, invest in student mobility, and share lessons learned, while 100K student/faculty alumni remain engaged with WHA/PDA and 100K, access to job/internship opportunities, and expand networks. POA will maintain participant contact information so they can contribute to long-term outcome evaluation.

100K grant-winning HEIs have achieved incredible levels of sustainability. In fact, NAFSA researchers found that 60% of grant-funded 100K projects continued for two years after the grant period ended and 50% continued for a full four years. In a separate study, 88% of respondents indicated that the number of students participating in the study abroad program either increased or stayed the same after project completion.  POA has achieved this sustained mobility by requiring that HEIs invest their own resources and present a Sustainability Plan in their proposals. POA will additionally provide the following resources, platforms, and engagement opportunities to sustain HEI activity after the grant period:

- 100K Strong Innovation Network: POA has built a massive network of HEIs in the Americas that support 100K program goals and WHA/DOS policy priorities. The 100K Network includes over 2,300 unique HEIs and over 4,000 individual faculty, staff, and administrators.  POA manages this 100K network, or virtual platform, that also serves as  one-stop shop for domestic and regional HEIs to connect, collaborate, and create partnerships.

- Workshops, Webinars, and Other Events: POA will engage HEI grantees through in-person and virtual training workshops, webinars, conference sessions, and other events. For example, POA invites 100K-HEI project leaders to join 100K panel sessions in higher education conferences and 100K webinars from around the region, creating opportunities for them to share lessons learned with future 100K applicants.

By providing a robust 100K Strong Network, frequent opportunities to attend or present in regional education events and webinars, and ongoing guidance from experienced staff, POA supports 100K grant-winning HEI teams in sustaining partnerships and exchanges after the initial grant period.

The 100K Alumni Network

POA will strengthen engagement among participants, alumni, beneficiaries, and HEIs through the implementation of a dynamic 100K Alumni Network. Program participants will enroll during pre-departure webinars and then be able to work with an alumni mentor, connect with peers, browse job/internship postings, participate in career fairs, and receive updates about 100K and other relevant USG programs and opportunities. WHA/PDA, PAS-Guatemala, and other donor-partners will have opportunities to interact with alumni and share open mentorship, employment, or internship opportunities. In addition, the platform will allow POA to maintain alumni contact information for long-term outcome evaluation.

https://www.nafsa.org/sites/default/files/ektron/files/underscore/long_term_impact.pdf pg. 1

https://www.nafsa.org/sites/default/files/ektron/files/underscore/moving_the_needle.pdf pg. 19