Expanding Colombia-U.S. Higher Education Climate Cooperation and Inclusive Education Exchanges through 100K Strong Americas

Program Description & Background

100,000 Strong in the Americas (100K Strong) is the U.S. Department of State, Bureau of Western Hemisphere Affairs (WHA/DOS) signature hemisphere-wide initiative to champion the power of education to transform societies, provide opportunity, and stimulate economic prosperity. The 100K Strong Innovation Fund is the public-private sector collaboration between the Bureau of Western Hemisphere Affairs (WHA/PDA) and Partners of the Americas (POA), working with regional private and public sectors to stimulate and support higher education institution (HEI) partnerships between the United States and regional HEIs.

The 100K Strong Initiative strengthens collaboration and transparency among governments, business, and academic networks – critical to economies in the Americas. In over ten years (2013-2024), the 100K Strong Innovation Fund has become the trusted mechanism for the U.S. and regional public/private sectors to invest in innovative, inclusive higher education partnerships and student exchange and workforce training programs. Teams of U.S. colleges and universities compete for 100K grants from matched U.S. government, private sector, and HEI funds. With the 100K grants, HEIs in the U.S. and Latin America create sustainable institutional partnerships and strengthen regional education cooperation and competitiveness.

For the purpose of this award, Partners of the Americas requests a one-time allotment of $80,000 to support WHA policy priorities and to ensure that the U.S. is the leading partner of choice for regional exchange and training programs via a new Colombia-focused 100K Strong competition in 2024-2025. These USG funds will be used to leverage potential, additional non-USG resources from Colombia’s Ministry of Education (MinEd) to launch a new 100K Strong grant competition in Summer/Fall 2024 to expand higher education partnerships between a diversity of Colombian and U.S. HEIs and increase access to innovative, inclusive student exchange and training program opportunities for students in diverse academic disciplines.

Rationale for Grant Recipient

Partners of the Americas (POA), under a cooperative agreement with WHA/PDA, is the lead 100K Strong implementing partner entity (NGO) that manages 100K Strong programming in coordination with WHA/PDA, along with U.S. embassies. POA’s scope of work includes developing potential regional private/public sector entities to secure potential non-USG funds that support regional 100K Strong and leverages USG resources to expand 100K grant opportunities for HEIs in WHA region. For more than ten years (2013-2024), POA has been working with WHA/PDA and U.S. embassies to develop and expand 100K Strong partnerships and student exchanges with regional public, private, academic sectors. POA has 60 years of robust experience in Latin America and the Caribbean managing networks of civil society and implementing other USG-sponsored programs.

Since 2017, POA has worked closely with the Public Affairs Section at the U.S. Embassy in Colombia (PDS-Bogotá) and WHA/PDA to cultivate and leverage collaboration with and funding from public and private sector entities to regional higher education cooperation with a diversity of HEIs in the U.S. to increase new models of innovative exchanges so that more students can work in teams in Colombia and gain technical, linguistic, and intercultural skills imperative for workforce development.

Today, Colombia is the leading country in the 100K Strong initiative in terms of partnerships with a diversity of HEIs in the United States. This has been made possible by the commitment of Colombian Government Agencies, such as the Ministry of Science, Technology and Innovation (MinCiencias), ICETEX and SENA, as well as the visionary support of corporate and foundation partners and 100K Strong donors, to join forces with the U.S. Department of State and POA to expand innovative and cooperative educational programs between Colombia and the United States.

These visionary investments in the 100K Strong initiative have increased student mobility and strengthened institutional capacity through partner institutions in Colombia and the United States. To date, 112 100K Strong grants have been awarded to U.S.-Colombian HEI teams, impacting nearly 1,500 students and over 300 faculty members who have participated in the program, gaining language and technical skills in science, technology, engineering, and mathematics (STEM), public health, sustainable agriculture, creative industries, and other areas.

Program Goals and Objectives

POA, in coordination with WHA/PDA, will work with PDS-Bogotá to plan, design, and implement the following 100K Strong-branded programming activities in 2024-2025 including, but not limited to:

- Secure non-USG commitments from regional private/public sectors to leverage the USG-funds to support 100K Colombia-U.S. competition and HEI partnerships (2024-2025).

- Launch a new 100K Strong competition in 2024 and implement 100K Strong grant activities in collaboration with WHA/PDA and Post-Bogotá, including promotion, 100K grant evaluation/selection process, and providing/monitoring 100K Strong sub-awards to teams of Colombian-U.S. grant winning HEIs.

- Build 100K Strong brand sustainability in Colombia and conduct robust 100K targeted, regional communication plans (e.g., 100K website, 100K webinars, social media, press releases).

Program Activities

The contribution from PDS-Bogotá will co-fund a new 100K Strong grant competition in collaboration with Colombia’s Ministry of Education (MinEd) to design and launch a new 100K Strong grant competition, strengthening educational cooperation and academic exchange programs between the United States and Colombia, and increasing the diversity of HEIs in both countries to design and implement virtual and face-to-face exchange and training programs for teams of students and faculty from both countries. This call will be part of the 100K Climate Alliance (100K CLIMA) and 100K Inclusive Education Alliance (100K Inclusive Education) initiatives announced by the White House and the State Department at the Summit of the Americas in 2022.

As in previous 100K Strong programming, POA will work in partnership with WHA/DOS, PDS-Bogotá, and MinEd to ensure the involvement of a diversity of Colombian HEIs and Historically Black Colleges and Universities in the United States, promoting the participation of Afro-descendant, and indigenous students and faculty.

100K Strong Climate (“100K CLIMA) Competition (in support of SOA 2022 Deliverables and WHA Policy Priorities

The new 100K Strong U.S.-Colombia grant competition will:

- Expand access to innovative exchange programs focused on inclusion, diversity, equity and social justice, workforce development programs and for students and faculty from underrepresented populations in international educational exchange experiences and social justice fields to be defined in the request for proposal (RFP) document.

- Stimulate collaborative cross-border partnerships to develop environmental solutions that reduce inequality of opportunity.

The 100K Strong grant competition will encourage the participation of a diversity of universities, colleges and technical/vocational and technological institutions from the United States and Colombia. This competition will prioritize projects that present partnerships between HEIs in Colombia with Historically Black Colleges and Universities (HBCUs) and Hispanic-Serving Institutions (HSIs) in the United States.

Development of the Request for Proposals (RFP)

The general areas of study and sub-themes will be defined during the development of the RFP, in collaboration with MinEd, PDS-Bogotá, and WHA/DOS. The general themes of the RFP will be Inclusive Education, Diversity, Equity and Social Justice with an emphasis on racial justice.

The partnership and collaboration with the Government of Colombia and MinEd will be a driving force to boost the impact of the 100K Strong program, contributing not only with financial resources, but also with leadership, relationships and strategies to create synergies and leverage alliances with new partners in the public and private sectors. In addition, it will leverage the visibility and momentum of international events, such as NAFSA and the HBCU Summit, to motivate HEIs to propose collaborative projects between the United States and Colombia, strengthen their institutional capacities and expand international exchange opportunities for their students, faculty and researchers. This will have a long-term positive impact on improving workforce readiness of cohorts of students, improving their employability and income.

100K Strong Colombia Launch Announcement

POA will announce the 100K Strong competition in future virtual and/or in-person events to be determined with WHA/DOS and PDS-Bogotá. Examples include 100K events with Post and leadership from private/public/academic sectors in Colombia and at regional workshops or conferences engaging a diversity of HEIs, including community colleges, HBCUs, and other minority-serving institutions (MSIs).

To maximize participation and access to 100K Strong grants, it is critical to broadly promote the opportunity to the international higher education audience. For all 100K Strong competitions, POA works closely with WHA/DOS, Embassies, and all donor-partners to coordinate promotion, outreach, digital marketing, event planning and communications. POA will develop all related 100K Strong Colombia competition communications plans—in coordination with WHA/PDA and PDS-Bogotá—to ensure that target audiences are reached, both for program promotion as well as overall visibility.

Capacity Building and Partnership Support

POA, in coordination with WHA/DOS and PDS-Bogota, strive to promote inclusiveness and ensure that all eligible types of HEIs, faculty and students from diverse academic fields can benefit from 100K Strong grants. This is especially important for smaller and less experienced institutions, such as community colleges and technical and vocational institutions. To ensure broad participation and accessibility, POA and WHA/DOS organize a series of capacity building workshops and webinars for each competition, providing detailed guidance on how to prepare and develop strong, competitive proposals that result in impactful training and exchange experiences. HEIs also receive support in identifying potential partners based on academic fields of interest and institutional and geographic profiles. Resources from the webinars, including recordings, email list of participants, presentations, and a Question-and-Answer report will be shared on 100K Strong website.

Proposal Review and Evaluation, and Selection of Grant Winning Projects

POA manages a rigorous, comprehensive review, evaluation, and selection process of 100K Strong grant proposals with volunteer expert reviewers from international education, academic exchanges, WHA/DOS, Posts, and 100K Strong alumni. Following the closing date of the competition, POA will implement the process to review/evaluate 100K Strong proposals from teams of HEIs, including the organization of panels, notetaking of virtual, live review sessions, and compilation of proposals’ score sheets and other required documents. The estimated timelines to complete to complete the 100K Strong proposals’ review/selection process takes 6-8 weeks, with the 100K winners announcement event to follow this process.

Winners Announcement

POA will work with the WHA/PDA, PDS-Bogotá, and MinEd to plan the official-public facing event to announce the 100K Strong grant winning institutions and highlight the 100K Strong collaboration. The 100K Strong winners announcements can be conducted in the U.S. or Colombia, and typically bring together leadership from WHA/DOS, Posts, regional government, private sector, and academic institutions.

Distribution of Funds and Project Monitoring and Evaluation

POA will distribute sub-grant funds to the winning institutions and will monitor the implementation of their projects through completion.

Proposed Program Schedule

The estimated launch of new 100K Strong competition for Colombia is Summer/Fall 2024, pending confirmation of funding. The 100K Strong RFP application process takes approximately 12-16 weeks; the process to review/evaluate/select 100K Strong grant-winning teams takes 6-8 weeks; list of grant winners; and the 100K Strong announcement of winners would follow. Estimated timeline below.

| Date* | Activity |
| --- | --- |
| August 2024 | 100K Strong Competition Launch Announcement Event during the HBCU Summit in Cali, Colombia - Plan a public event to save the date/announce the new grant competition and 100K partnership with donor-partners - Publish the request for proposal (RFP) for 100K U.S.-Colombia Grant Competition, taking into account the eligibility criteria and thematic areas established by WHA/DOS, PDS-Bogotá, and MinEd |
| August-October 2024 | Open Application Period/Promotion of Grant Competition - Disseminate information about the RFP to HEIs through marketing/communications strategies - Conduct at least two (2) sets of informational webinars, in English & Spanish - Attendance of regional higher education conferences and other events, in which POA, PDS-Bogotá, and WHA/PDA participate to promote partnerships between HEIs in the U.S. and Colombia, and thus encourage their participation and submission of 100K grant proposals. |
| November-December 2024 | Review & Selection of Grant-Winning Proposals - Organize committees to evaluate proposals - Conduct multi-stage evaluation process to verify that proposals meet all the requirements in accordance with the terms of the RFP - Select grant winners |
| 2025 | Project Implementation Period - Selected grant-winning institutions implement their proposed projects in the U.S. and Colombia - POA monitors progress of HEI projects, collects sub-grant reports, and provides support as necessary in implementation. |

*The schedule is subject to adjustment.

Budget

POA has prepared a budget to cover program and administrative costs of implementing the proposed 100K Strong Colombia-U.S. grant competition.

A. Personnel

A.1.1 Program Officer – Mariana Cabrera Figueroa, with an annual salary of $60,064 equal $5,005/month, will dedicate approximately 15% of her time to manage the 100K Strong grant competition cycle, with a focus on technical HEI support and capacity-building, including conducting bilingual webinars & workshops and organizing the proposal review & selection process. She will also provide technical support to selected grant-winning HEI teams. The total for this position is $18,019 for 24 months.

A.1.2 Communications Officer – Melisa Arrázola, with an annual salary of $45,630 equal to $3,802/month, will dedicate 10% of her time to implement the grant competition’s communications and marketing strategy. She will support outreach, communications, and marketing for the grant competition, material design, and event planning. She will lead digital communications/marketing efforts, including promoting the grant competition and grant projects on the 100K website, managing the competition’s online and social media presence. The total for this position is $9,126 for 24 months.

A.1.3 Monitoring, Evaluation, and Learning (MEL) Officer – Ben Rauch, with an annual salary of $59,076 equal to is $4,923/month, will dedicate 10% of his time to support MEL activities related to the 100K Strong Colombia-U.S. grant competition. This includes determining data collection timeline; designing/administering survey tools; tracking, collecting, and analyzing data/reports; supporting the implementation of learning and feedback activities. The total for this position is $11,815 for 24 months.

B. Fringe Benefits

B.1 U.S. Based Personnel Fringe Benefits – In accordance with POA’s personnel policy, we have charged a 23.47% fringe rate for POA Headquarters staff. Fringe benefits include insurance, mandatory taxes, pension, and other employee benefits. The total cost for fringe benefits for staff is $9,144 for 24 months.

C. Travel

Travel will be made by staff for the purpose of donor management, launch of the grant competition, announcement of grant winners, program promotion, and stakeholder engagement. Specific cities for travel cannot be specified in advance because it will not be known where events will occur until the locations have been confirmed by WHA, PDS-Bogotá, and 100K donor-partners. The budgeted costs for flights and lodging, are based on a sample of various cities throughout the region, past experiences attending events for stakeholder engagement for similar programs. M&IE are based on a percentage of GSA approved rates included in POA’s travel policy. The following is a detailed breakdown of the expected international travel.

    - International Round Trip Airfare: POA is budgeting 2 international roundtrip trip tickets at an estimated average rate of $800 per trip for events and stakeholder engagement between the U.S. and Colombia. Flights will comply with the Fly America Act and be in economy class. The total estimated amount is $1,600.

    - International M&IE: POA is budgeting an M&IE rate of $156/day for 10 days total to cover the 2 trips. This is a reduced M&IE rate based on previous trips and a portion of the USG government per diem rates. The total estimated amount is $1,560.

    - International Lodging: POA is budgeting a lodging rate of $200/night based on an average across a sample of different WHA countries. POA estimates 8 nights to cover the 2 trips. The total estimated amount is $1,600.

    - International Local Transportation: POA is budgeting an average of $50/day for 10 days during international travel to cover taxis, subways, buses, metro, and trains over the 2 trips. The total estimated amount is $500.

F. Contractual

F.1 Sub-grants – Sub-grants to higher education institution (HEI) teams for new U.S.-Colombia exchange programs. These funds will also facilitate fundraising by reducing the amount required from public-private donors and showing DOS/POA investment.

F.1.1	HEI Sub-grants: 100K Strong sub-grants are typically $25,000 at 8-10 grants per grant competition. POA is budgeting approximately $9,000 to assist with fundraising efforts to attract new donors to launch a new 100K U.S.-Colombia grant competition during 2024-2025. The actual number of sub-grants in this proposed budget are approximate. Final amounts of sub-grants will vary according to potential non-USG funds and agreements with private-public sector partners as well as the results of the proposal evaluation/selection process. The anticipated total amount for line F.1.1, however, will not vary.

Indirect Costs

In accordance with POA’ NICRA, indirect costs are calculated at 28.28% of total project funding for a total of $17,636. Please see copy of NICRA agreement attached.

POA’ NICRA indirect costs include the cost of an audit that complies with the requirements of the Office of Management and Budget’s Guidance 2 CFR (Code of Federal Regulations) Parts 200 Subpart F Single Audit Requirements and 600, entitled the Uniform Administrative Requirements, Cost Principles, and Audit Requirements for Federal Awards. These funds cover the cost of the audit of the basic financial statements, and supplemental reports and schedules required by OMB (Office of Management and Budget) (Office of Management and Budget) Guidance 2 CFR Parts 200 Subpart F Single Audit Requirements.

The total program costs are $80,000.