## Mexico United Activity Timeline
Mexico United 2026
Partners of the Americas
Expected Start Date: | 2020-10-01
Project End Date: | 2023-03-31
Proposed End Date (No-Cost Extension): | 2023-09-30
Key:
Original Approved Timeline
New Proposed Timeline with No Cost Extension
Activity | Responsible | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
|  | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2021-01-20 | 2021-02-01 | 2021-03-01 | 2021-04-21 | 2021-05-21 | 2021-06-21 | 2021-07-01 | 2021-08-01 | 2021-09-21 | 2021-10-21 | 2021-11-21 | 2021-12-21 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01
Objective 1: Increase workers’ knowledge of labor law, and ability to understand the applicability of labor regulations and international labor standards relevant to the United 2026 games.
Activity 1: Expand educational programs led by labor rights organizations in Mexico with experience in popular education methods, to train workers on protections under Mexican labor law, international labor standards, business and human rights frameworks relevant to the United 2026 games, and the risks of the games for Mexican workers. | POA, CDM, RMS, CEREAL | bar: 2020-12-20 to 2022-11-01
Objective 2: Increase engagement and coordination between labor rights organizations, the private sector, and democratic, independent unions on the UHRS and around pre-games planning of United 2026 events, including the implementation of the human rights strategy in each host city, and ways that the Government of Mexico, FIFA and the MFA will address and mitigate labor rights risks associated with the games.
Activity 2: Establish and facilitate a civil society labor advisory network in Mexico. Contact and hold outreach meetings with different key stakeholders involved in the human rights strategy for the 2026 FIFA World Cup; identify opportunities for collaboration and coordination. | POA, CDM, RMS, CEREAL
Objective 3: Strengthen the capacity of civil society actors, independent unions, and workers to monitor and report labor and human right abuses, to prepare to effectively document violations, and make strategic use of reporting and enforcement mechanisms related to the operation of the games.
Activity 3: Develop trainings programs for human rights and labor rights defenders on monitoring, case development, and filing processes for existing grievance and conciliation procedures, and assist with the planning and implementation of alternative grievance procedures. | POA, CDM, RMS, CEREAL | bar: 2021-04-21 to 2022-07-01
Activity 4: Strengthen collaboration between civil society and journalists to monitor and report on labor rights impacts during the lifecycle of the games, including tracking violations and complaints submitted to grievance channels. | POA, CDM, RMS, CEREAL | bar: 2021-01-20 to 2022-11-01
Objective 4: Increase awareness among the general public of Mexico’s commitments to human rights in regards to the United 2026 games.
Activity 5: Provide technical assistance to civil society to develop a media campaign to socialize information of labor rights risks, in preparation for the United 2026 games. Development and publication of awareness-raising materials on labor rights and the 2026 FIFA World Cup, in collaboration with the CNDH and with the IMJUVE. Host two virtual events on human rights in the workplace, in collaboration with the CNDH, and to commemorate the International Day of Sport for Development and Peace (April 6). | POA - Consultant, CDM. RMS, CEREAL, CNDH, IMJUVE | bar: 2021-02-01 to 2023-09-01
Monitoring and Evaluation (General)
Conduct M&E Training with project staff and CDM, CEREAL and RMS staff | POA - Program Coordinator, Program Specialist, Program Assistant | bar: 2020-12-20 to 2023-01-01
Hold coordination meetings with CDM, CEREAL and RMS to monitor project progress and make adjustments | POA - Program Coordinator, Program Specialist, Program Assistant | bar: 2020-12-20 to 2023-01-01
Conduct an open competition for external mid-term project evaluation | POA - Program Coordinator, Program Specialist, Program Assistant | bar: 2021-11-21 to 2021-12-21
Carry out an external mid-term evaluation | POA - Program Coordinator, Program Specialist, Program Assistant, Program Manager, External Evaluator | bar: 2022-01-01 to 2022-02-01