July 6, 2023

Pat Davis

Director

Office of Global Programs

Bureau of Democracy, Human Rights, and Labor

U.S. Department of State

Re: Partners of the Americas (Partners) response to questions regarding the proposal entitled “Mexico United 2026”.

Dear Ms. Davis:

Partners is pleased to submit responses to conditions and recommendations from the Review Panel regarding the proposal entitled “Mexico United 2026”.

Partners certifies that our organization will comply with the Terms and Conditions of the Award, to include the Standard Terms and Conditions, Award Provisions, and USG Federal Regulations outlined in 2 CFR200 and 2CFR 600.

Partners is pleased to provide the following information for the Organization’s Signatory and Program Manager:

Organization’s Signatory:

John McPhail

Partners of the Americas

President and CEO

jmcphail@partners.net

(703) 678- 9277

1424 K Street NW, Suite 700

Washington, DC 20005

Program Manager:

Macarena Jiménez Granda

Partners of the Americas

Senior Director, Labor Unit

mjimenez@partners.net

(202) 628-3300

1424 K Street NW, Suite 700

Washington, DC 20005

Please see below response to the conditions:

Conditions

1. Provide critical analysis of the problems to be addressed, including specific labor rights concerns identified.

Mega-sporting events (MSEs) organized across the world, including World Cups led by the International Federation of Association Football (FIFA), have been prone to high incidences of labor rights violations, with abusive labor practices and poor working conditions that impacted negatively migrant populations and host communities. During the most recent FIFA World Cup held in Qatar from November through December of 2022 severe labor rights violations resulted in the death of approximately 6,500 migrant workers. To prevent these issues from happening during the 2026 World Cup, host countries Mexico, United States, and Canada developed a strategy (United 2026 Human Rights Strategy-UHRS), addressing risks for human rights violations and compliance with international labor standards throughout the organization, preparation, and celebration of the games.

Partners’ risk analysis, which includes external sources such as UHRS, Human Rights Watch’s Open Letter to FIFA President Gianni Infantino as well as data collected during the project implementation, has identified non-payment of minimum wages and overtime, excessive  working hours, restrictions to freedom of association and collective bargaining, workplace discrimination and harassment, and non-compliance with occupational safety and health regulations as the most common violations in the sectors commonly engaged with MSEs, such as construction, hospitality, and transportation.

Possibly as important as the risks already identified, are the risks that will become more prominent in Mexico as the World Cup date approaches and during the game. The need for additional workers and services can likely trigger instances of forced labor, especially for local migrant workers searching for jobs in the hosts cities of Mexico City, Guadalajara and Monterrey. For the most vulnerable workers, especially for the indigenous population, the payment of recruitment fees, debt bondage, job deception, and even sexual exploitation and trafficking are real potential dangers.

The three host Mexican cities developed their plans to protect human rights in their own municipalities, but even FIFA’s independent analyses identified some critical weaknesses in the implementation of those strategies such as unclear timeframes, no stakeholder engagement, and minimal risk mitigation. The lack of clarity for how to effectively protect the workers’ rights, calls for the need raised public awareness, engage directly with the social actors and support a strong net of CSOs. All those aspects are central in the strategy of the Mexico United 2026 Program, as it facilitates CSOs engagement with public and private entities to identify, prevent and mitigate labor rights violations.

2. Include a discussion of results to date that goes beyond number of trainings and materials developed to describe the impact of activities.

The Mexico United 2026 Program raises awareness around the issues of labor rights in connection to the World Cup. The dissemination of information through training and materials will get Mexico ready to face a major event that could trigger severe labor and human rights violations. The coordination of actors and the visibility of the topics are critical and constitute the most important achievement of the program. Besides the work through organizations, the program also engaged the media, building journalists’ understanding of the topics, which led to a proliferation of articles and columns published in different national and local media.

The program facilitated a dynamic multi-stakeholder cooperation between CSOs, human and labor rights defenders, journalists, government entities, business sector, and trade unions on the topics of human and labor rights. During its initial period of performance, the project established the Mexico United 2026 Network at the national level to increase commitment and coordination among LROs and key actors in the implementation of the UHRS. The Network includes Partners, CDM, RMS and CEREAL, and various organizations and governmental entities such as the Comision Nacional de Derechos Humanos (CNDH) and the Instituto Mexicano de la Juventud (IMJUVE).

Members of the Network raised awareness among human rights defenders, workers, and the public on risks to labor rights and mitigation strategies, positioning itself as a key coalition for the promotion and defense of labor rights around the World Cup. The project has carried out awareness-raising activities with CNDH, IMJUVE, the Comisión Nacional de Cultura Física y Deporte (CONADE), and the Consejo Nacional para Prevenir la Disciminación (CONAPRED), of human rights risks and commitments of the GOM.

With the support of implementing partners and key actors, the project has successfully positioned its activities and objectives on the public agenda of the Government of México (GOM), CNDH, and the Comisión Estatal de Derechos de Nuevo León (CEDHNL). The signing of Memoranda of Understanding (MOUs) with CNDH in November 2022, and the Instituto Mexicano de la Juventud (IMJUVE) in December 2022, formalized communication and coordination mechanisms for the protection and promotion of labor rights.

3. Provide concrete lessons learned from previous work and a clear strategy building from those lessons. Explain how the proposed work builds on and learns from results to date.

Since the beginning of the implementation in October 2020, the Mexico United 2026 Program has adapted to address challenges to kick-off activities, form alliances, and maximize the outreach.

- There was an initial lack of interest from stakeholders to engage in a process for something that was more than five years into the future. The program used social media, its website, and Partners’ network to capitalize on the interest generated by labor issues related to the 2022 FIFA World Cup in Qatar and presented the topics in a broader international context. The same strategy was used to overcome the difficulties to engage the Mexican Football Federation (FMF), when the program focused on forming an alliance with FIFA. FIFA’s recognition of the program’s network as primary contact regarding labor rights, opened the door to access national actors such as FMF and focus on Mexico specific issues. The open cooperation with FIFA was also instrumental as the program identified they were developing a weak and somehow non-transparent human and labor rights strategy. Partners was able to bring on CSOs, LROs, and the Mexico United 2026 Network to support planning a stronger and clearer approach.

- At the federal and state-level public, the program built productive relationships with CNDH, IMJUVE, state-level human rights commissions, STPS and other public agencies with an interest in and ability to protect human labor rights.   However, the project recognized the risks posed by changes in government administrations and leadership as the upcoming general elections in 2024 could shift their priorities. To mitigate potential disruptions to the implementation, the program employs a cross-sector approach, engaging CSO and private entities that are less likely to experience shifts in priorities or commitments over the course of program implementation.

- Host cities have been tasked with the development of human rights protection strategies in the World Cup context.  Those city-level plans have significant gaps and blind spots, as cities have not significantly engaged with CSOs and LROs for their development and execution. Realizing this need, the program reached out to local human rights entities, promoting their engagement with Partners, implementing organizations, and the Mexico United 2026 Network. CEREAL has formed and leads an additional network specific to Guadalajara, engaging other CSOs to address the gaps in the city’s human rights strategies. Partners has been working with the State of Nuevo Leon’s Human Rights Commission, who has expressed interest in forming its own state-level network with key actors to promote labor rights.

4. Clearly articulate how the proposed strategy addresses identified problems and further target activities to address specific labor rights concerns.

As mentioned in the response to condition 1 of this letter, Partners’ risk analysis has identified non-payment of minimum wages and overtime, excessive working hours, restrictions to freedom of association and collective bargaining, workplace discrimination and harassment, and non-compliance with occupational safety and health regulations as the most common violations in the sectors commonly engaged with MSEs, such as construction, hospitality, and transportation. In addition, the need for additional workers and services can likely trigger instances of forced labor, especially for local migrant workers searching for jobs in the hosts cities of Mexico City, Guadalajara and Monterrey. For the most vulnerable workers, especially for the indigenous population, the payment of recruitment fees, debt bondage, job deception, and even sexual exploitation and trafficking are real potential dangers.

In this regard, the program will design and implement different strategies aimed at promoting, disseminating and increasing the knowledge and understanding of the labor rights of workers who will participate directly and indirectly in the 2026 FIFA World Cup. The program will also promote coordination, collaboration and participation of key actors from business, government, CSOs, labor unions, human rights defenders, and academia to learn about Mexico's labor rights commitments in relation to this MSE, and to identify, prevent and mitigate labor rights violations.

In addition, the program will strengthen the capacity of civil society actors, journalists, and workers organizations to monitor and report labor abuses during the lifecycle of the World Cup, make strategic use of existing complaint mechanisms and socialize information among the general population.

5. Provide more detailed explanations of each activity and how activities will be achieved. Activities should be clearly developed and detailed, and the narrative should clearly articulate how the proposed activities contribute to objectives and overall program goal.

The table below contains a summary of the program's activities and how they relate to the objectives. Please refer to the Proposal Narrative where we added more detailed information on each activity.

| Objectives | Activities | Description |  |
| --- | --- | --- | --- |
| Objective 1: Increase workers’ knowledge of labor law, and ability to understand the applicability of labor regulations and international labor standards relevant to the United 2026 games. | Activity 1: Expand educational programs led by LROs in Mexico with experience in popular education methods, to train workers on protections under Mexican labor law, international labor standards, business and human rights frameworks relevant to the United 2026 games, and the risks of the games for Mexican workers. | These in person workshops and seminars for workers and human rights defenders on labor rights, national labor regulations, international labor standards, employers’ responsibilities, will target specific sectors and refer to the risks in each sector, including contracting forms such as outsourcing and subcontracting. The technical assistance provided to LROs will be delivered using training-of-trainers methodology (ToT) to promote sustainability, duplicability and extend its reach. |
| Objective 2: Increase engagement and coordination between LROs, the private sector, and democratic, independent unions on the UHRS and around pre-games planning of United 2026 events, including the implementation of the human rights strategy in each host city, and the ways in which the GOM, FIFA and the Mexican Football Association (MFA) will address and mitigate labor rights risks associated with the games. | Activity 2: Establish and facilitate a civil society labor advisory network in Mexico. | Partners will coordinate the Mexico United 2026 Network, establishing a Work Plan and bimonthly follow-up meetings. CEREAL will coordinate the Guadalajara Network. In collaboration with CEDHNL, the program will seek to create and coordinate a business and human rights network in Nuevo León. |
| Objective 3: Strengthen the capacity of civil society actors, independent unions, and workers to monitor and report labor rights abuses, to prepare to effectively document violations, and make strategic use of reporting and enforcement mechanisms related to the operation of the games. | Activity 3: Develop training programs for labor rights defenders on monitoring, case development, and filing processes for existing grievance and conciliation procedures, and assist with the planning and implementation of alternative grievance procedures. | Partners and implementing partners will design, organize and conduct in person workshops for labor rights defenders on existing grievance mechanisms. A ToT model will be used to expand the reach of the program’s promotion of available mechanisms to remedy violations of labor rights. Partners and implementing partners will disseminate knowledge assessment forms, informative booklets, and practical exercises. The organizations will be trained in the effective use of mechanisms for themselves and to train others in their use. |
|  | Activity 4: Strengthen collaboration between civil society and journalists to monitor and report on labor rights impacts during the lifecycle of the games, including tracking violations and complaints submitted to grievance channels. | The program will facilitate collaboration between civil society and journalists to monitor and report on the impact on labor rights through virtual and in-person trainings to build their capacity to identify labor rights issues, and effective ways to report them in the media to avoid fear of retaliation and promote positive changes. |
| Objective 4: Increase public awareness of Mexico’s commitments to labor rights regarding the United 2026 games. | Activity 5: Provide technical assistance to civil society to develop a media campaign to socialize information on labor rights risks, in preparation for the United 2026 games. | Partners will develop, implement, monitor, and evaluate a communication plan including a dissemination campaign on social media channels and publications in national and state media, to increase the awareness of the population. Partners will continue to update content on the program's website, including relevant news, learning resources, awareness-raising materials, links to content of potential interest, reference documents, international and national regulations, available complaint mechanisms, and information on the Mexico United 2026 Network. Other digital awareness-raising strategies will include the generation of videos, infographics, and tools, as well as the organization of events and/or dialogue tables. |

6. Remove activity six or justify the need for this work. Provide more detail on the audience and specific objectives of this activity and how it will be achieved. Ensure the proposed activity adds to and does not duplicate existing work such as the guide and tools developed by the Centre for Sport and Human Rights.

Activity 6 has been removed from the proposal.

7. Submit an updated M&E narrative for the program. The mid-term is currently positioned in the timeline at the end of the award. Since the award has been ongoing since 2020, move the mid-term toward the beginning of the extension period to assess work to date and inform work going forward. Share the scope of work for the evaluation with DRL and allow two weeks for input.

Please see the M&E Narrative attachment. This narrative includes Partners’ plan to undergo a midterm evaluation within the first three months of the extension period, and the corresponding Scope of Work for the evaluation in the Midterm Evaluation Scope of Work attachment.

8. Work with DRL to finalize an M&E plan within 90 days of award. Focus on measuring impact.

POA commits to working with the DRL M&E team to strengthen and finalize the M&E plans within 90 days of award, including clarifying and being more specific about the program’s goals, objectives, outcomes, and anticipated impact.

9. Describe the target population and sector (s) for each activity in the various cities or how they will be identified. The current description of the target population is very broad. Provide information about workers reached to date in each target city, including the sectors in which they work.

Within the first 90 days of the extension of the program, the program will hold a workshop with RMS, CDM and CEREAL to narrow the focus from six to three or four sectors and decide the sector focus in each of the three host cities. The sectors will be selected from the six identified in the Ergon risk analysis (hospitality, concessions and catering, security, vending, construction, and transport, and including temporary and subcontracted workers). It is crucial to select sectors in conjunction with our local implementing partners, not only because the sector selection criteria rely on their insight and capabilities, but also because Partners is committed to fomenting close collaboration on decision-making processes.

Until now, the program has trained 525 workers and human rights defenders (290 from Mexico City, 181 from Guadalajara, 42 from Monterrey and 12 from other cities) on labor rights, national labor regulations, international labor standards, human rights risks and labor rights associated with mega sporting events, equality and non-discrimination in employment, and the UN Guiding Principles on Business and Human Rights. These activities have focused on the sectors of transportation, restaurants, hotels, construction, cleaning services, clothing, security, food and beverages. For this new phase of the program, the Ergon risk analysis confirmed most of these original sectors and added the contracting forms of temporary contracts and subcontracting, which cut across all sectors and generate high risk for labor abuses.

Please see activities and target populations in the chart below

| Activity | Target Population |
| --- | --- |
| Activity 1: Expand educational programs led by LROs in Mexico with experience in popular education methods to train workers on protections under Mexican labor law, international labor standards, business and human rights frameworks relevant to the United 2026 games, and the risks of the games for Mexican workers. | Workers from priority sectors identified with the implementing organizations and human rights defenders within the first 90 days of the program extension. |
| Activity 2: Establish and facilitate a civil society labor advisory network in Mexico. | Key actors from business, government, CSOs, labor unions, human rights defenders, and academia. |
| Activity 3: Develop training programs for human rights and labor rights defenders on monitoring, case development, and filing processes for existing grievance and conciliation procedures, and assist with the planning and implementation of alternative grievance procedures. | Human rights and labor rights advocates and LROs. |
| Activity 4: Strengthen collaboration between civil society and journalists to monitor and report on labor rights impacts during the lifecycle of the games, including tracking violations and complaints submitted to grievance channels. | Journalists and human and labor rights advocates. |
| Activity 5: Provide technical assistance to civil society to develop a media campaign to socialize information of labor rights risks, in preparation for the United 2026 games. | Workers, general public, and individuals and entities invested in the defense of human rights and MSEs. |

10. Further describe the network and its activities.

During the first part of the program, the United Mexico 2026 Network was formed at the national level to increase commitment and coordination between LROs and key actors in the implementation of the UHRS, and to generate a space for dialogue. The Network includes Partners, CDM, RMS, CEREAL, and various organizations and governmental entities seeking collaboration, and it became a key coalition for the promotion and defense of labor rights in preparation for the World Cup. CEREAL formed a sister local network in Guadalajara, including academics and various CSOs interested in promoting actions to prevent violations of workers' rights.

In the first months of the program's extension, Partners will present to the Network a draft Work Plan to discuss and agree. The Work Plan will be based on the following objectives:

- Improve Mexico's knowledge on the promotion, protection and defense of labor rights related to mega sporting events, through the implementation of a dissemination and awareness strategy.

- Promote actions to disseminate complaint mechanisms to strengthen the capacity of Mexican workers' organizations to identify, prevent and mitigate the impacts of the 2026 FIFA World Cup on labor rights and working conditions.

- Generate spaces for dialogue - such as working groups, events, seminars, forums or meetings - for the exchange of valuable information and successful experiences that contribute to the design, implementation and monitoring of the actions contemplated in the program.

- Promote strategic alliances with public, private or social, national or international organizations to achieve the program's objectives.

To achieve the objectives, the Work Plan will present the following activities:

- Disseminate, on the websites and social networks of the member organizations, the information developed or generated by the member organizations and their allies.

- Promote awareness-raising events and a dissemination campaign in social networks on the protection of labor rights related to mega sporting events.

- Conduct a mapping exercise of local actors relevant to the municipal monitoring committees and stakeholders, considering the sectors (to be) identified.

- Encourage local and federal government entities to promote the Network's activities.

- Disseminate and raise awareness of available complaint mechanisms and legal advice on labor issues, targeting workers.

- Conduct bimonthly virtual meetings with the member organizations of the Network to present updates, seek solutions for challenges in the implementation of activities, and promote unified messages.

- Attend meetings and fora organized by government, FIFA and business associations to draw attention to labor rights issues.

- Submit status reports and a final report of the actions implemented during the program extension period.

Prior to the conclusion of the implementation of the program extension, Partners will transfer the leadership of the Network to local stakeholders with established interests in the UHRS, to ensure its sustainability beyond the conclusion of the program and its continuity until the United 2026 World Cup.

11. Include M&E expertise for General M&E activities or provide the M&E qualifications of the positions proposed to carry out this work.

The program will include requirements for substantive M&E experience in the scope of work of the Program Coordinator, which will include the following:

- Experience in strategic planning and performance measurement, including indicator selection, target setting, reporting, database management, and developing M&E and performance monitoring plans.

- Proven success in designing, implementing, and operating program M&E systems from program initiation to closeout stages.

12. Hire a labor expert to work on the program.

The program will identify a labor expert to be incorporated as a consultant into the development and implementation of activities. Specifically, this expert will evaluate strategies and materials developed by the program to ensure adherence to best practices and international standards for the protection of labor rights.

Please refer to the attached program Budget, which reflects spending allocated for a labor expert in the “contractor” line item.

13. Hire a communications officer in the program and the development of a communications plan to maximize the reach and impact of program campaigns and materials.

Upon award, the program will identify an individual or firm to develop a comprehensive communications plan to expand the reach of awareness-raising materials and campaigns. Additionally, the program will hire a communications officer to design virtual and physical communications materials, such as infographics, flyers and animated videos. This person will keep the program’s website updated, including materials and relevant news regarding the 2026 World Cup and human labor rights.

Please refer to the attached Budget, which reflects spending allocated for communications in the “contractor” line item.

14. Submit an updated key personnel document. Please refer to Partners’ internal policies for key personnel and the current key personnel document approved for the award.

Please see the Key Personnel attachment for the updated Key Personnel document approved for the original award.

15. Provide additional detail as to how Partners promotes equality, diversity, and inclusion in all proposed activities how activities will prioritize the needs of, and challenges faced, by marginalized groups affected by the 2026 World Cup, as noted in the proposal.

Information on Partners’ commitment to equality, diversity, and inclusion can be found in the Proposal Narrative, “Target Populations” section, as well as references in the design of each activity of the same document.

Please see below responses to the recommendations:

Recommendations

1. Consider a training of trainer model for activities 1 and 3 to expand reach, build capacity, and increase the multiplier effect of the program.

We have incorporated a training of trainer (ToT) methodology into both activities 1 and 3. Please refer to the Proposal Narrative for more information on the application of the model under each activity.

2. Develop a strategy for targeted expansion of the network beyond the three subcontracted organizations to maximize reach and potential for sustainability.

Please refer to the Objective 2 section of the proposal narrative and Condition number 10 above for more information on how the program will work to expand the reach of the Mexico United 2026 Network.

3. Engage independent labor unions in the program, potentially leveraging other labor programs Partners is implementing in Mexico.

Mexico United 2026 will leverage existing connections with independent labor unions already established by Partners’ U.S. Department of Labor-funded programs in Mexico: The Mexico Awareness-Raising Program (MAP) and the Improving Substantive Gender Equality in the Mexican Workplace program (GEM). Mexico United 2026 will participate in events held by these other programs with unions and use them as an opportunity to share the program’s objectives and activities to generate interest. Upon definition of target sectors, the program will be better able to identify specific workers’ organizations with whom to collaborate.

We are available to provide additional information and clarifications, as needed and appropriate to any of the responses provided above. We look forward to working closely with DRL on any further clarifications and refinements.

Many thanks in advance for your guidance and consideration.

Sincerely,

John McPhail

President and CEO

Partners of the Americas

1424 K Street NW, Suite 700

Washington, DC 20005

jmcphail@partners.net

https://digitalhub.fifa.com/m/35837f1073bdad15/original/s2xnrvfjg9kp0zelhxnt-pdf.pdf

https://www.hrw.org/news/2022/08/26/qatar-joint-open-letter-gianni-infantino-regarding-remedy-labor-abuses-behind-2022

https://digitalhub.fifa.com/m/6fb6b77c01fd470c/original/Evaluation-of-Monterrey-s-Human-Rights-Stakeholder-Engagement-Submission-to-FIFA.pdf

Some of the articles and news can be found in the following link: https://mexicounido2026.rmsindicalistas.mx/category/actividades/

Information about the Network can be found in the following link: http://mexicounido2026.partners.net/red.html

The awareness-raising activities can be found at the following link: http://mexicounido2026.partners.net/

http://mexicounido2026.partners.net/