# LOGIC MODEL

Introduction/Context

Mega-sporting events (MSEs) organized across the world have seen high incidences of labor rights violations, including abusive labor practices and poor working conditions, with negative impacts on host communities. To remedy these issues, the United 2026 bid incorporated a strategy to address all aspects of human rights risks in the lifecycle of the 2026 World Cup, seeking to ensure compliance with internationally recognized labor standards. As part of the bid, Mexico committed to promoting human rights throughout the organization, planning, and implementation of the games. The United 2026 Human Rights Strategy (UHRS) incorporates civil society stakeholders in the dissemination, planning, monitoring and implementation of measures to prevent and mitigate the labor rights risks associated with hosting the games.

Hosting the World Cup games may compound the challenges Mexico faces. Nonetheless, the games provide an unprecedented opportunity to promote labor rights compliance and best practices in Mexico, with positive effects that will last long after the games have ended. Our proposed activities expand worker education and promote coordination between Mexican Civil Society Organizations (CSOs), labor unions, the business sector, and government to ensure their active participation in planning and implementing mitigation strategies. The project will improve documentation and reporting of labor rights violations and disseminate information on Mexico’s human rights commitments throughout the course of the games, setting a new precedent for future MSEs worldwide.

The main goal of the Mexico United 2026 project is to strengthen Mexico's capacity to identify, prevent, and mitigate the impacts of the United 2026 games on the realization of labor and human rights guarantees. It is important to highlight that the first step to achieve this goal is to train and raise awareness among workers, as a process of empowerment that begins individually, and then is extended to the community, to promote a culture of respect for labor human rights, challenging discriminatory practices in employment.

Furthermore, once workers are aware of their rights, they can critically analyze their own human rights challenges, and thereby seek solutions compatible with human rights standards, thus becoming agents of change for the defense of their interests.

There are major challenges when it comes to generating a culture of defense of labor rights; therefore, training not only involves learning about labor regulations and their protection mechanisms, but also acquiring and consolidating the ability of workers to apply them in a practical way in their daily lives and in actions for the defense and promotion of their human rights.

Problem Statement

The high probability of human rights violations associated with hosting the 2026 International Federation of Association Football (FIFA) World Cup, may exacerbate Mexico’s existing human rights crisis, which includes shortcomings in the adjudication and protection of internationally recognized labor rights.

Identified community need

Strengthen local capacity and collective action to leverage Mexico’s current labor rights context to promote best practices, setting in motion new models for the respect and enforcement of labor rights both during and beyond the games.

Inputs

- Human resources

- Financial resources

- Material resources

- Technological resources

- Implementing partners

- Time

Assumptions

The project assumes that: 1) Government entities agree to participate in project activities and promote compliance with human and labor rights in the country; 2) The Mexican cities hosting the World Cup form local committees, develop and implement their human rights plan; 3) Workers, human rights defenders, journalists, and human and labor rights organizations are interested in participating in the project training activities; and 4) Members of the Mexico United 2026 Network continue to be interested in participating in Networks activities.

External Factors

The main external factors identified are: 1) Potential challenges in engaging with private sector, in coordination with unions, due to sensitivities around labor issues and differing perspectives; 2) Potential economic downfall lead to social, economic, and political crisis, policy shifts, etc.; 3) Change in political cycle in Mexico and the US at a state level, elections to come in Mexico, and the states of Jalisco and Nuevo Leon on June 2, 2024; 4) Changes in Mexican government labor and human rights policies; 5) Precarious security situation due to mafias associated with real estate, drug trafficking cartels and organized crime threats, particularly in Monterrey and Mexico City; 6) Human rights defenders, human rights organizations, journalists and stakeholders refuse to participate in the training and awareness activities; 7) Obstacles in the ability of Mexican host cities to ensure effective implementation of their human rights plans (limited financial and human resources); 8) Lack of experience of the organizations in the implementation of activities; and 9) General security risks, such as earthquake, medical emergencies and/or accidents, harassment/bullying, contact with armed groups, armed attack, harassment or shootings, illegal checkpoints, theft, and threatening phone calls.

Objectives, Activities, Pathways, Expected Outputs and Expected Outcomes

| PROJECT GOAL: To strengthen Mexico’s capacity to identify, prevent and mitigate the impacts of the United 2026 games on the realization of labor rights and human rights guarantees. |  |  |  |
| --- | --- | --- | --- |
| Objective 1: Increase workers’ knowledge and ability to understand the applicability of labor law and international labor standards relevant to the United 2026 games. and international labor standards relevant to the United 2026 games. |  |  |  |
| Activity 1: Expand educational programs led by LROs in Mexico with experience in popular education methods, to train workers on protections under Mexican labor law, international labor standards, business and human rights frameworks relevant to the United 2026 games, and the risks of the games for Mexican workers. |  |  |  |
| Output 1.1: Labor rights stakeholders and workers are educated and trained about labor rights, including cross-cutting issues (subcontracting, minimum wage, freedom of association and collective bargaining and non-discrimination) and protections under Mexican labor law, international labor standards, business and human rights frameworks and risks of the games for Mexican workers. | Output Indicators 1.1: 1.1.1 DRL.1 (DR. 6.1-2) # of human rights defenders trained and supported (Target: 350) Cost amendment target:300 Life of Project (LOP) target: 650 1.1.2 DRL.2 (DR. 4.2-1) # of human rights organizations trained and supported Cost amendment target: 15 LOP target: 30 1.1.3 # of awareness raising events to share the information received during project training and informational events conducted in target areas (Target: 6) Cost amendment target: 16 LOP target: 22 1.1.4 DRL.3 # of human rights materials supported by DRL (Target: 66) Cost amendment target: 85 LOP target: 151 | Outcome 1.1: Labor rights organizations understand and raise awareness on labor rights and protections under Mexican labor law, international labor standards, business and human rights frameworks, and risks of the games for Mexican workers. | Outcome Indicator 1.1: 1.1.1 # of labor rights organizations promoting the materials developed by the project, through digital or print media (Cost amendment target: 5) |
| Objective 2: Increase engagement and coordination between labor rights organizations, the private sector, and democratic, independent unions on the UHRS and around pre-games planning of United 2026 events, including the implementation of the human rights strategy in each host city, and ways that the Government of Mexico, FIFA and the MFA will address and mitigate labor rights risks associated with the games. |  |  |  |
| Activity 2: Establish and facilitate a civil society labor advisory network in Mexico. |  |  |  |
| Output 2.1: Labor rights stakeholders (CSOs, unions, labor lawyers, academics) engaged in the civil society labor advisory network establish thematical Working Groups and organize labor representation for business and government forums. | Output Indicator 2.1: 2.1.1 # of stakeholders that participate in strategies led by the civil society labor advisory network (Target: 9) Cost amendment target: 20 LOP target: 29 | Outcome 2.1: Labor rights stakeholders participate in the civil society labor advisory network and Working Groups. | Outcome Indicator 2.1: 2.1.1 DRL.4.3-1 # of newly formed labor networks implementing strategic plans (Target 1) Cost amendment target: 0 LOP target: 1 |
| Objective 3: Strengthen the capacity of civil society actors, independent unions, and workers to monitor and report labor and human right abuses, to prepare to effectively document violations, and make strategic use of reporting and enforcement mechanisms related to the operation of the games. |  |  |  |
| Activity 3: Develop training programs for human rights and labor rights defenders on monitoring, case development, and filing processes for existing grievance and conciliation procedures, and assist with the planning and implementation of alternative grievance procedures. |  |  |  |
| Output 3.1: Human rights and labor rights organizations are trained in monitoring, case development and filing processes for both- existing and alternative- grievance procedures. | Output Indicator 3.1: 3.1.1 # of human rights and labor rights organizations that receive training or orientation from the project (Target: 15) Cost amendment target: 15 LOP target: 30 | Outcome 3.1: Human rights and labor rights organizations understand and raise awareness on monitoring, case development and filing processes for existing and alternative grievance procedures. | Outcome Indicator 3.1: 3.1.1 # of human rights and labor rights organizations promoting information related to grievance mechanisms, through digital or print media (Cost amendment target: 5) |
| Activity 4: Strengthen collaboration between civil society and journalists to monitor and report on labor rights impacts during the lifecycle of the games, including tracking violations and complaints submitted to grievance channels. |  |  |  |
| Output 4.1: Collaboration with journalists to monitor and report labor rights impact during lifecycle of the United 2026 games strengthened. | Output Indicator 4.1: 4.1.1 DRL.10 (DR.5.2-2) # of journalists trained and supported (Target: 60) Cost amendment target: 20 LOP target: 80 | Outcome 4.1: Journalists understand and raise awareness of potential risks and/or violations. | Outcome Indicator 4.1: 4.1.1 # of journalists who report on labor rights issues relevant to United 2026 games. Can be articles, blogs, radio or video reports or other new reports that are presented to the public (Target: 15) Cost amendment target: 8 LOP target: 23 |
| Objective 4: Increase public awareness of Mexico’s commitments to labor rights regarding the United 2026 games. |  |  |  |
| Activity 5: Provide technical assistance to civil society to develop a media campaign to socialize information of labor rights risks, in preparation for the United 2026 games. |  |  |  |
| Output 5.1: Information sessions for civil society stakeholders, the private sector and democratic unions established to disseminate and promote United 2026 strategy and UN Guiding Principles on Business and Human Rights, particularly as related to internationally recognized workers’ rights | Output Indicator 5.1: 5.1.1 DRL.4 (DR.4.2-2) # of civil society organizations (CSOs) receiving USG assistance engaged in advocacy interventions (Target:15) Cost amendment target: 15 LOP target: 30 5.1.2 # of informational events organized by the project (Target: 12) Cost amendment target: 15 LOP target: 27 | Outcome 5.1: Stakeholders linked and using the media campaign | Outcome Indicator 5.1: 5.1.1 # of stakeholders promoting the media campaign, through digital or print media (Target: 15) Cost amendment target: 15 LOP target: 30 |
| Data Sources/Comments: - Attendance logs from trainings and meetings. These logs will include sufficient detail to produce the disaggregation required for the DRL common indicators. - Analytics of data generated by media software can be used to measure the reach of media campaigns. - More information on the details of the indicators can be found in the M&E Plan. |  |  |  |

Flowchart