Monitoring and Evaluation (M&E) Narrative

Overview. Partners of the Americas (Partners) is committed to developing and implementing a rigorous Monitoring & Evaluation (M&E) system. Partners has extensive experience developing M&E plans, and therefore comfortable to lead the process in close coordination and collaboration with USDOS-DRL.

Partners has demonstrated capacity to successfully comply with USG-funded M&E requirements under multiple contractual mechanisms with USDOS, USDOL, and USAID, spanning over 40 years and multiple countries, including Brazil, Guyana, Ecuador, Panama, Paraguay, Colombia, and Costa Rica (where we work as a sub-grantee and our major role is the provision of M&E technical assistance). Partners has vast experience designing and implementing databases, collaborating with external contractors and donors to carry out Midterm and Final Evaluations, and reporting on project performance. Mexico United 2026’s field-based staff and implementing partners will be accompanied by Partners’ home office M&E team of specialists, who will provide guidance and oversight throughout the life of the project.

M&E activities are designed to comprehensively track project results, ensuring sound project implementation and management. Project monitoring, evaluation, data collection and data analysis strategies are integrated into the framework of a Mexico United 2026 M&E Plan.

The M&E Plan will not only allow the project to monitor results, but also to address the issues of “how” and “why” the changes occurred. The project will use the M&E Plan as a management tool to monitor products and key outcomes, manage the project based on results, and evaluate the project effectiveness based on results and measurable impact. The uniformity and consistency of data collection procedures is critical for the success of the intervention and the M&E Plan will help to ensure that standard procedures, terms and definitions are used correctly, in all locations, at all times.

The M&E Plan systematically integrates monitoring and evaluation (described below) throughout the life of the project and provides an important resource for decision making and adjustments to implementation, based on both quantitative information obtained from verification sources used in project activities, and qualitative information (lessons learned, best practices, Pause and Reflect M&E workshops and success stories). This data analysis includes the following strategies:

- Quantitative data collection: numerical data is essential to ensure the accuracy of the information provided by each indicator included in the M&E Plan. Verification sources collected from the project activities will provide information the program will use to analyze progress towards indicators and report on the progress and/or adjustments the goals contemplated in the M&E Plan. The program, after verifying the consistency and reliability of the information, will enter the data into a  database of the Mexico United 2026 project, the Performance Indicator Tracking Table  (PITT). Partners will conduct feedback workshops with the staff of the implementing organizations to ensure the correct use of verification sources, care in handling the information and validating data reliability.

- Lessons Learned and Good Practices: the project, supported by its implementing partners, will report on lessons learned and good practices identified from the execution of project activities, to be analyzed in the project's Pause and Reflect workshops. Qualitative information will be collected that will help the project to: i) guide implementation, ii) addressed the issues identified in these FG, iii) develop a manual of lessons learned and good practices that may be useful to other similar projects in the future, and above all, iv) improve the implementation of project activities to ensure advancement towards the project's results and objectives.

- Pause and Reflect: Partners will conduct three Pause and Reflect activities (in the final months of 2023 and 2024 and before project closure in 2025) with project staff and implementing partners to continually assess the activities and impact of Mexico United 2026. The Pause and Reflect methodology aims to facilitate constructive dialogue on topics such as the project's Theory of Change, the implementation of activities and the context in which they take place, challenges and how to deal with them, and to identify success stories, best practices and lessons learned. The outcome of Pause and Reflect sessions in 2023 and 2024 will be applied to improve implementation of project activities, and the last workshop in 2025 will focus on project results and lessons learned, to be disseminated in the final Mexico United 2026 report.

- Success stories: during the implementation of project activities, there may be individuals (whether they are participants in the activities, stakeholders, or members of the implementing organizations) who, as a result of their participation in the project, have had a positive change in any area of their lives, particularly related to labor rights. These cases will be reported by the implementing organizations in the reports submitted by the project and compiled in the Pause and Reflect sessions. The program will conduct an initial workshop with the implementing organizations to train them on how to identify and report on success stories throughout implementation.

The PMP is based in the main goal of the project is to strengthen Mexico’s capacity to identify, prevent and mitigate the impacts of the United 2026 games on the realization of labor rights and human rights guarantees. To achieve this, the project has four objectives:

O1: Increase workers’ knowledge and ability to understand the applicability of labor law and international labor standards relevant to the United 2026 games.

Activity 1: Expand educational programs led by LROs in Mexico with experience in popular education methods, to train workers on protections under Mexican labor law, international labor standards, business, and human rights frameworks relevant to the United 2026 games, and the risks of the games for Mexican workers.

The project will develop new training and awareness materials that will be based on the topics covered in the training module developed by the project in the first implementation phase, which will be designed, created and followed up with the support of the project, for which the following information will be available: the number of materials, the type of materials (digital or print media), the subject, the media type and the stakeholder type (Output 1.1.4 and Outcome 1.1.1).

The program will monitor this activity to ensure the correct collection of data for the five indicators that report on the number of individuals, organizations, awareness-raising events, and tools or materials developed. For this purpose, the definitions included in the M&E Plan for each of them will be taken into account, thus avoiding duplicity of information in the number of individuals and organizations, unreliable data, and delays in M&E reporting.

The implementing organizations will provide the data collected from the activities, making use of the tools designed by the project, which are: training attendance lists to track the number of workers and labor rights stakeholders receiving training (Output 1.1.1 and Output 1.1.2). Attendance lists will be a simple and efficient way of informing the project about its training targets, while also allowing the project to verify that the participants have complied with the percentage of assistance required for them to count towards the achievement of the indicator. Additionally, event agendas and summaries, as well as participant attendance lists will inform the project of the awareness raising events under this objective (Output 1.1.3). The event agendas and summaries will inform on the specific topics included in each event and the participant attendance lists will document the reach of this activity for the intended target group.

O2: Increase engagement and coordination between labor rights organizations (LROs), the private sector, and democratic, independent unions on the United 2026 Human Rights Strategy (UHRS) and around pre-games planning of United 2026 events, including the implementation of the human rights strategy in each host city, and the ways in which the Government of Mexico (GOM), International Federation of Association Football (FIFA) and the Mexican Football Association (MFA) will address and mitigate labor rights risks associated with the games

Activity 2: Establish and facilitate a civil society labor advisory network in Mexico.

The project will continue to implement this activity in order to reach a greater number of stakeholders that participate in strategies led by the civil society labor advisory network. Project M&E tools and strategy will be used to verify compliance in data collection and continue measuring the number of newly formed labor networks (formal or informal) that establish a strategic plan and take actions towards it. As such, the project will not only report on the progress of this activity but will also have a robust database of stakeholders and networks formed, which can be available for other activities to amplify results and make them sustainable.

The project will use civil society advisory network and working group attendance lists to monitor the output and outcome under this activity (Output 2.1.1 and Outcome 2.1.1). The attendance lists will be an efficient way of informing the project about the number of labor rights stakeholders engaged in the civil society labor advisory network. The attendance lists will be an efficient way to verify that the participants have complied with the indicator requirements such as the number and percentage of meetings they must attend to be counted.

O3: Strengthen the capacity of civil society actors, independent unions, and workers to monitor and report labor and human right abuses, to prepare to effectively document violations, and make strategic use of reporting and enforcement mechanisms related to the operation of the games.

Activity 3: Develop training programs for human rights and labor rights defenders on monitoring, case development, and filing processes for existing grievance and conciliation procedures, and assist with the planning and implementation of alternative grievance procedures.

The project goes a step further in this activity, not only by training human rights and labor rights organizations, but also by working to ensure that these organizations, based on the training received, can promote information related to grievance mechanisms.  The project will verify compliance with both indicators that measure Activity 2, especially in digital media promotion, considering that the project will have to obtain external sources, such as administrative reports from the digital networks where the materials are promoted.

It will also rely on the sources produced by the project, such as attendance lists to track the number of human and labor rights defenders receiving orientation (Output 3.1.1). Attendance lists will be a simple and efficient way of informing the project about its targets, while also allowing the project to verify that the participants have complied with the percentage of assistance required for them to count towards the achievement of the indicator.   In addition, based on the information collected in the previous indicator, and taking into consideration what is mentioned in various articles, stories, news, posts, communications or documents, the number of labor rights and human rights organizations that promote information related to the content and the channel of access of grievance mechanisms will be obtained, for which the following information will be available: the type of materials (digital or print media), the media type and the stakeholder type (Outcome 3.1.1).

Activity 4: Strengthen collaboration between civil society and journalists to monitor and report on labor rights impacts during the lifecycle of the games, including tracking violations and complaints submitted to grievance channels.

The project has broadened the scope of targets for the two indicators under Activity 4, not only to reach a larger number of journalists trained but also to increase the number reports published on labor rights issues relevant to United 2026 games. The program will analyze and categorize related information to ensure non-duplicity from the attendance lists of the trainings. Additionally, the program will design a tracking lists to monitor these journalists and their reports published after the training received.

The attendance lists will assist the project in monitoring the number of journalists that receive information (Output 4.1.1), as well as the number of journalists that use this training to report on labor rights issues relevant to United 2026 (Outcome 4.1.1). The attendance lists will include a space where each journalist can indicate which media platform they work for, helping to understand the reach of the project across different types of media formats. Additionally, journalists that attended the press events and subsequently developed a news piece on the subject, will also serve to measure the effectiveness of the trainings.

O4: Increase awareness among the general public of Mexico’s commitments to human rights regarding the United 2026 games

Activity 5: Provide technical assistance to civil society to develop a media campaign to socialize information of labor rights risks, in preparation for the United 2026 games.

The project will use meeting attendance lists to track the number of Civil Society Organizations (CSOs) included in the development of the media campaign (Output 5.1.1). Attendance lists will be a simple and efficient way of informing the project about its interventions.

The project will use event agendas and summaries, as well as participant attendance lists, to inform the project regarding the informational events organized by the project under this objective (Output 5.1.2). The event agendas and summaries will provide information on the specific topics included in each training and the corresponding region. The attendance lists collected for these outputs will be supplemented by the agendas of or strategies, plans, or materials developed from these events and meetings in order to provide the program with specific information on the topics addressed.

In addition, based on the information collected in the previous indicator, and taking into consideration what is mentioned in various articles, stories, news, posts, communications or documents, the number of stakeholders promoting the media campaign will be obtained, for which the following information will be available: the type of materials (digital or print media), the media type and the stakeholder type (Outcome 5.1.1).

Roles and Responsibilities. In compliance with the conditions of the award of a project extension, Partners will work closely with DRL within the first 90 days to expand upon Mexico United 2026’s existing M&E plan to ensure thorough and effective oversight and management of project implementation. The Program Coordinator, with support from the program implementing partners, will direct the development and implementation of the M&E Plan, collection, storage, retrieval, and analysis of all data used to measure common and special performance indicators reported to DRL. The Program Coordinator will closely integrate all project areas to reinforce overall program interventions while providing needed evidence-based information for program improvements as well as for future planning. Additionally, the Program Coordinator will coordinate with sub-grantees, sharing the data collection strategies and tools to be used in tracking project indicators, as well as monitoring and collecting the data gathered.

Data Security. Partners recognizes that confidentiality of Personally Identifiable Information (PII) and other sensitive data is of vital importance. Partners will safeguard all data, including all data exchanges conducted over the life of the project and PII, in a manner consistent with Federal law. Partners will provide training for all staff and project partners before activities begin. Trainings will be led by the Project Coordinator. Employees will also be asked to sign agreement to follow Partners confidentiality and security standards for handling sensitive data. Employees will be trained to understand the particularities to protect PII, and procedures to ensure that information is kept confidential. Partners will incorporate security controls to protect PII, such as information of respondents to project surveys. The data will be encrypted, and passwords will be used for employees authorized to access the data for legitimate purposes only. The devices used to store the data will have security software installed, and with secure wi-fi access. Devices that contain sensitive data are configured so that users cannot download any software or change the security settings without approval from Partners IT Specialists. An 'auto-destroy function' will be added to devices that contain sensitive data in case it is reported stolen or missing. Based on best practices implementing other USG funded projects, Partners will perform data quality control on a monthly basis.

Internal / External Evaluation. This M&E plan includes not only internal strategies to be led by Partners for performance monitoring, but also external evaluations conducted by external entities. Specifically, Partners plans to develop terms of reference for and collaborate with DRL in the identification of an independent consultant or firm to conduct a midterm evaluation of the successes and shortcomings of project implementation. This evaluation will be scheduled for the last quarter (September through December) of 2023. As such, the information learned from the evaluation will be used to improve implementation and M&E strategies as project activities continue during preparations for the 2026 FIFA World Cup. The midterm evaluation will identify if the activities and their respective targets are being met as of the implementation of the study and if the remaining period of implementation will provide the project with sufficient time to achieve its established objectives.

Likewise, with the results of the midterm evaluation will be:

- Learning: the study will show the challenges and successes of that the project has experienced so far in implementation. It will allow the project to make adjustments to strategy and activity as necessary to guarantee the achievement of the proposed results.

- Accountability: the. The study will assess if project processes and strategy objectively contributed to any results observed. It will also respond to questions about the project’s operations, progresses, or context that cannot be answered exclusively through the available M&E data.

Please see the Midterm Evaluation Scope of Work attachment for the proposed scope of work developed by Partners for the midterm evaluation.

Addressing Barriers to Equal Participation. When collecting sensitive data, such as information about religious minorities, women, LGBTQ+ persons, persons with disabilities, racial and ethnic minorities, and indigenous communities, Partners is committed to respecting the sensitivities that this data collection requires. Project staff and sub-grantees will make sure to inform the participants that provision of such information is optional and that if it is indeed shared, the data will be used confidentially for project M&E purposes. Additionally, Partners will seek to disaggregate data by demographic identity as possible and appropriate, to better understand the impact of activities on vulnerable groups and adjust implementation as necessary to better support vulnerable communities.