Risk Analysis

The purpose of this Risk Analysis is to identify the internal and external risks associated with the extension of the project, rate the likelihood of the risks and their potential impact on the project, and establish actions that could help mitigate the risks to personnel, implementing organizations, participants, or communities, in alignment with Do No Harm principles.

Partners of the Americas (Partners) has Sexual Exploitation and Abuse Prevention Code of Conduct that promotes a safe and supportive working environment, free from sexual abuse, exploitation, and harassment for all employees and program beneficiaries who attend or participate in programs, activities, and/or events sponsored by Partners. Additionally, Partners has a Child Safeguarding Policy to ensure that Partners’ programs and operations are safe for children and to promote awareness and prevention to mitigate the risk of any harm that may come to children involved in Partner’s programs and operations. These policies are known to all its employees and are accompanied by training activities to increase understanding and application in daily work.

|  | Description of Risk | Likelihood of Risk | Potential Impact of Risk | Risk Mitigation Plan/Actions |
| --- | --- | --- | --- | --- |
| Risks affecting realization of Project Objectives | Potential challenges in engaging with private sector, in coordination with unions, due to sensitivities around labor issues and differing perspectives. | High | High | Capitalizing on Partners’ vision of creating horizontal relationships and dialogue with various actors and partners to reach a common goal, Mexico United 2026 will continue working to create intentional relationships with civil society organizations (CSOs), unions and the private sector in order to advance on project goals. Also, a communications and outreach plan and partnerships with unions with extensive experience in Mexico will guarantee the mitigation of risks. |
|  | Potential economic downfall lead to social, economic, and political crisis, policy shifts, etc. | Medium | Medium | The project will be competing with multiple priorities but planning ahead will allow us to continue building confidence with stakeholders. Partners will constantly review the design of the project and establish contact with the implementing organizations and key stakeholders, to assess if any adjustments are necessary and to be able to implement appropriate and relevant strategies and actions with the specific contexts of the country and regions. |
|  | Change in political cycle in Mexico and the US at a state level. Elections to come in Mexico, and the states of Jalisco and Nuevo Leon on June 2, 2024. | Medium | Medium | Partners will leverage contacts with the Government of Mexico (relevant entities such as Instituto Mexicano de la Juventud, IMJUVE) to give program priorities a voice in the country and establish clear lines of communication to quickly adjust implementation activities to suit changes in government priorities. |
|  | Changes in Mexican government labor and human rights policies. | Medium | Medium | Partners will be in communication with entities of the Government of Mexico and with human rights and labor rights organizations, to discuss and analyze possible changes in these policies and their impacts on individuals, groups and communities, to make the necessary adjustments to the strategies and project activities. |
| Risks affecting realization of Project Outcomes/ Outputs | Precarious security situation due to mafias associated with real estate, drug trafficking cartels and organized crime threats, particularly in Monterrey and Mexico City. | High | High | The measures contemplated in the Security Plan to minimize risks or mitigate their effects. In addition, some activities will be held virtually, to mitigate personal security risks. Furthermore, we established partnerships with local entities with extensive experience in Mexico, including Centro de Reflexión y Acción Laboral (CEREAL) in Guadalajara, Red de Mujeres Sindicalistas (RMS) and Centro de los Derechos del Migrante (CDM) in Mexico City; organizations that know the specific contexts of the cities and will help in the planning and execution of in person activities, making sure they are carried out in safe conditions for the participants. |
|  | Human rights defenders, human rights organizations, journalists and stakeholders refuse to participate in the training and awareness activities. | Low | Medium | With the lessons learned in the first phase of the project and the results achieved, there is knowledge of the interest that these actors have in participating in the meetings, events and training activities organized by the project. However, to ensure that the targets established in the M&E Plan are achieved, Partners will hold various meetings with implementing organizations and stakeholders to talk about the importance of carrying out these actions and support the dissemination campaign, through the appropriate channels to reach the target population. |
|  | Obstacles in the ability of Mexican host cities to ensure effective implementation of their human rights plans (limited financial and human resources). | Medium | Low | The project will hold various forums with local and national stakeholders to discuss priorities, risks and opportunities regarding the 2026 FIFA World Cup and the human rights plans of each host city and add different key labor actors to the activities of the Mexico United 2026 Network, for which Partners will hold outreach meetings and maintain communications with them. |
| Risks affecting Organization | Lack of experience of the organizations in the implementation of activities. | Low | Medium | Partners´ internal capacity building mechanisms, Standard Operating Procedures (SOPs) in place, extensive experience, and our internal Risk Assessments to our implementing partners. |
| Risks affecting Safety and Security of Personnel | General security risks, such as earthquake, medical emergencies and/or accidents, harassment/bullying, contact with armed groups, armed attack, harassment or shootings, illegal checkpoints, theft, and threatening phone calls. | Low | High | Partners protocols (SOPs), the measures contemplated in the Security Plan to minimize risks or mitigate their effects. and compliance with applicable local regulations. Some measures are following basic safety and security measures in the workplace; maintaining an emergency directory with staff contact information and emergency contacts; updating local emergency organizations’ contact information to receive support during emergencies, in particular hospitals, ambulances, air evacuation, etc.; organization of awareness courses and establishment of internal complaint mechanisms; avoid traveling to areas recently impacted by actions or violence on the part of armed groups; stay at hotels that are in safe areas or that have an adequate level of security, geographical location, and low level of risk; be attentive to any variations in regular routes or checkpoints when traveling by land; avoid dangerous areas considered unsafe, and avoid answering unknown calls. |