Monitoring and Evaluation (M&E) Narrative

Overview. Partners of the Americas (POA) is committed to developing and implementing a rigorous M&E system. POA has extensive experience developing M&E plans, and therefore comfortable to lead the process in close coordination and collaboration with USDOS-DRL. POA’s monitoring strategy integrates the use of a database on implementation monitoring: implementation of common indicators and project indicators related to proposed outputs and activities; testing the use of key project outcomes; and contextual factors and stakeholder interventions. Monitoring will also include comparison of progress against plans and budget; participation of stakeholders in the project implementation process; and sustainability of project activities.

POA has demonstrated capacity to successfully comply with USG-funded M&E requirements under multiple contractual mechanisms with USDOS, USDOL, and USAID, spanning over 40 years and multiple countries, including Brazil, Guyana,  Ecuador, Panama, Paraguay, Colombia, and Costa Rica (where we work as a sub-grantee and our major role is the provision of M&E technical assistance). POA has vast experience designing and implementing databases, collaborating with external contractors and donors to carry out Midterm and Final Evaluations, and reporting on project performance.

The M&E Plan will not only allow the project to monitor results, but also to address the issues of “how” and “why” the changes occurred. The project will use the M&E Plan as a management tool to monitor products and key outcomes, manage the project based on results, and evaluate the project effectiveness based on results and measurable impact. The uniformity and consistency of data collection procedures is critical for the success of the intervention and the M&E Plan will help to ensure that standard procedures, terms and definitions are used correctly, in all locations, at all times.

The main goal of the project is to strengthen Mexico’s capacity to identify, prevent and mitigate the impacts of the United 2026 games on the realization of labor rights and human rights guarantees. To achieve this, the project has five objectives:

O1: Increase workers’ knowledge of labor law, and ability to understand the applicability of labor regulations and international labor standards relevant to the United 2026 games.

Activity 1: Expand educational programs led by labor rights organizations in Mexico, with experience in popular education methods, to train workers on protections under Mexican labor law, international labor standards, business and human rights frameworks relevant to the United 2026 games and the risks of the games for Mexican workers.

The project will use training attendance lists to track the number of workers and labor rights stakeholders receiving training (Output 1.1.1 and Output 1.1.2). Attendance lists will be a simple and efficient way of informing the project about its training targets, while also allowing the project to verify that the participants have complied with the percentage of assistance required for them to count towards the achievement of the indicator. Additionally, event agendas and summaries, as well as participant attendance lists will inform the project of the awareness raising events under this objective (Output 1.1.3). The event agendas and summaries will inform on the specific topics included in each event and the participant attendance lists will document the reach of this activity for the intended target group. Additionally, a pre- and post-survey will be used to measure the increase in workers knowledge as a result of project intervention (Outcome 1.1.1). The pre- and post-survey will be a clear way to measure the initial knowledge of workers regarding labor rights and protections, and how these answers differ once they have received training from the project.

The project will use the finalized training component document developed with assistance from the project to track the number of components created (Output 1.2.1). This will be a clear way of assessing if new trainings components were in fact developed for labor rights organizations. In turn, training component integration plans will inform on the institutionalization of the new training components within the labor rights organizations educational programs (Output 1.2.2 and Outcome 1.2.1). The integration plans will not only include a guide on how the components will be integrated but also include information on follow-up and verification of their successful implementation.

POA will closely monitor COVID-19 in target regions. Under this activity, if necessary, the training for labor rights organizations will be modified to virtual platforms, which POA has substantial experience executing.

O2: Increase engagement and coordination between labor rights organizations, the private sector, and democratic, independent unions on the UHRS and around pre-games planning of United 2026 events, including the implementation of the human rights strategy in each host city and ways that the Government of Mexico, FIFA, and the Mexican National Soccer Federation will address and mitigate labor rights risks associated with the games.

Activity 2: Establish and facilitate a civil society labor advisory network in Mexico

The project will use civil society advisory network and Working group attendance lists to monitor the output and outcomes under this activity (Output 2.1.1 and Outcomes 2.1.1.and 2.1.2). The attendance lists will be an efficient way of informing the project about the number of labor rights stakeholders engaged in the civil society labor advisory network and the percentage of these stakeholders that are part of civil society organizations. The attendance lists will be an efficient way to verify that the participants have complied with the indicator requirements such as the number and percentage of meetings they must attend to be counted.

The project will use local committee attendance lists to monitor the number of labor rights stakeholders participating in local committees and the percentage of them that regularly attend the meetings (Output 2.2.1 and Outcome 2.2.1). The attendance lists will be an efficient way of informing the project about its local committee meeting targets, while also allowing the project to verify that the participants have complied with the indicator requirements such as the number and percentage of meetings they must attend to be counted.

If large in-person gatherings are not permitted or not safe due to COVID-19, POA will hold virtual meetings for the broader advisory network and convene small meetings for the working groups that adhere to all safety regulations.

O3: Strengthen the capacity of civil society actors, independent unions, and workers to monitor and report labor and human right abuses, to prepare to effectively document violations, and make strategic use of reporting and enforcement mechanisms related to the operation of the games

Activity 3: Develop training programs for human rights and labor rights defenders on monitoring, case development, and filing processes for existing grievance and conciliation procedures, and assist with the planning and implementation of alternative grievance procedures

Under this activity, the project will use training attendance lists to track the number of human and labor rights defenders receiving training (Output 3.1.1). Attendance lists will be a simple and efficient way of informing the project about its training targets, while also allowing the project to verify that the participants have complied with the percentage of assistance required for them to count towards the achievement of the indicator. In turn, event agendas and summaries, in addition to participant attendance lists, will inform the project on the number of training events conducted in target areas with assistance from the project (Output 3.1.2). Not only will these agendas, summaries, and attendance lists serve as supporting documentation for the implementation of the events, but they will also inform the project on the topics included within each event and the stakeholders and workers in attendance. Additionally, the project will utilize a pre and post-survey to understand the percentage increase in human rights and labor rights defenders that understand the existing alternative grievance procedures (Outcome 3.1.1). The pre-survey will help the project understand which areas these defenders need the most reinforcement in, allowing for the post-survey results to achieve the expected outcome. Finally, filing reports will aid the project in understanding the percentage increase in human and labor rights defenders filing for existing and alternative grievance and conciliation procedures (Outcome 3.1.2). The filing reports will also monitor the types of grievance and conciliation procedures being filed, helping to better understand the recurring violations.

POA will monitor the situation of COVID-19 and, if needed, trainings will be modified to a virtual format to comply with safety regulations. If the health situation allows, the project will carry out trainings in small groups with health and safety regulations.

Activity 4: Strengthen collaboration between civil society and journalists to monitor and report on labor rights impacts during the lifecycle of the games, including tracking violations and complaints submitted to grievance channels

Under this activity, the project will use training attendance lists to monitor the expected output and outcome. The attendance lists will assist the project in monitoring the number of journalists that receive training (Output 4.1.1), as well as the percentage of journalists that use this training to report on labor rights issues relevant to United 2026 (Outcome 4.1.1). The attendance lists will include a space where each journalist can indicate which media platform they work for, helping to understand the reach of the project across different types of media formats. Additionally, journalists that attended the training and subsequently developed a news piece on the subject, will also serve to measure the effectiveness of the trainings.

Regarding COVID-19 and health concerns related to in-person meeting, the awareness raising component of this activity can be carried out completely remotely. Additionally, POA will leverage its experience with virtual trainings to provide the training for journalists via a virtual platform.

O4: Increase awareness among the general public of Mexico’s commitments to human rights in regard to the United 2026 games.

Activity 5: Provide technical assistance to civil society to develop a media campaign to socialize information of labor rights risks in preparation for the United 2026 games.

The project will use meeting attendance lists to track the number of stakeholders included in the development of the media campaign (Output 5.1.1). Attendance lists will be a simple and efficient way of informing the project about its training targets, while also allowing the project to verify that the participants have complied with the percentage of assistance required for them to count towards the achievement of the indicator.

The project will use training agendas and summaries, as well as participant attendance lists, to inform the project regarding the information sessions organized by the project under this objective (Output 5.2.1). The event agendas and summaries will inform on the specific topics included in each training. Additionally. The training attendance list will report on the number of stakeholders that participated in the information sessions (Output 5.2.2). A pre- and post-survey will be used to measure the percentage increase in civil society stakeholders, private sector, and democratic union representatives’ understanding regarding the United 2026 Human Rights Strategy (Outcome 5.2.1). The pre- and post-survey will be a clear way to measure the initial knowledge of stakeholders and representatives regarding the Strategy, and how these answers differ once they have received training from the project.

POA will monitor the situation of COVID-19 in each of the target regions. If in-person information sessions are not possible, the project will rely heavily on the virtual sessions.

Roles and Responsibilities. The Program Specialist, with support from the Program Coordinator and the participation of sub-grantees, will direct the development and implementation of the M&E Plan, collection, storage, retrieval, and analysis of all data used to measure common and special performance indicators reported to USDOS-DRL. The Program Coordinator and Program Specialist will closely integrate all project areas so that they reinforce overall program interventions while providing needed evidence-based information for program improvements as well as for future planning. Additionally, the Program Specialist will coordinate with sub-grantees, sharing the data collection strategies and tools to be used in tracking project indicators, as well as monitoring and collecting the data gathered.

Data Security. POA recognizes that confidentiality of Personally Identifiable Information (PII) and other sensitive data is of vital importance. POA will safeguard all data, including all data exchanges conducted over the life of the project and PII, in a manner consistent with Federal law. Partners will provide training for all staff and project partners before activities begin. Trainings will be led by the Project Specialist. Employees will also be asked to sign agreement to follow POA confidentiality and security standards for handling sensitive data. Employees will be trained to understand the particularities to protect PII, and procedures to ensure that information is kept confidential. POA will incorporate security controls to protect PII, such as information of respondents to project surveys. The data will be encrypted and passwords will be used for employees authorized to access the data for legitimate purposes only. The devices used to store the data will have security software installed, and with secure wi-fi access. Devices that contain sensitive data are configured so that users cannot download any software or change the security settings without approval from POA IT Specialists. An 'auto-destroy function' will be added to devices that contain sensitive data in case it is reported stolen or missing. Based on best practices implementing other USG funded projects, POA will perform data quality control in a monthly basis.

Internal / External Evaluation. POA proposes to include an External Midterm Evaluation for the project to provide a timely assessment of progress and challenges, allowing enough time to incorporate and implement recommendations to improve the effectiveness of project interventions. The Midterm Evaluation will assess project implementation, progress toward meeting objectives, and project outcomes, as well as track the progress of project activities against up-to-date planning and project lifetime targets. POA will provide the evaluator with all the required information and logistical support needed and ensure that Midterm Evaluation recommendations are applied in a timely manner.

Addressing Barriers to Equal Participation. When collecting sensitive data, such as information about religious minorities, women, LGBTI persons, persons with disabilities, racial and ethnic minorities, and indigenous communities, POA is committed to respecting the sensitivities that this data collection requires. Project staff and sub-grantees will make sure to inform the participants that provision of such information is optional and that if it is indeed shared, the data will be used confidentially for project M&E purposes.