Applicant Name: Partners of the Americas (Partners)

Country/Countries of Performance: Paraguay

Project Title: Ñangareko Hağua (“To Protect Ourselves” in Guaraní)

Budget for Five-Year Implementation Period in USD: 2,500,000

Base Period Budget by Anti-Trafficking Element: 100% Protection

Cost Share: N/A

Contact Name: Macarena Jiménez Granda

Contact Email and Phone: mjimenez@partners.net, +595981455477

Problem Statement: One-third of trafficking in persons (TIP) victims in Paraguay are adult, often rural men [1]. These men are primarily exploited through forced labor in the Chaco region’s cattle sector [2], or trafficked to neighboring countries to work in agriculture [3], garment manufacturing [4], and cigarette factories [5]. The rate of men abducted from Paraguay’s border region with Brazil and Argentina and forced to work in illegal industries [6] is growing. Adding to these emerging risks is the construction of the Bioceanic Highway, which is expected to increase risk of trafficking both domestically and regionally [7].

The Paraguayan government’s response remains inadequate to these growing issues. Adult male victims, a particularly vulnerable group among trafficking victims, lack access to specialized shelters and institutional support available to women, children, and adolescents. This leaves male victims with insufficient access to care and protection, increasing their vulnerability to further exploitation. The failure of the Operational Secretariat in charge of the National Program to Prevent and Combat Human Trafficking (Article 47, Law No. 4788/2012) to lead actions for male victims exposes critical gaps in Paraguay’s anti-trafficking efforts. The government continues to rely on temporary solutions and lacks a comprehensive approach. While Standard Operating Procedures (SOPs) for victim support exist, they are neither well-known nor widely implemented by authorities. Furthermore, non-specialized shelters that could assist male victims are under-resourced and lack capacity. Systemic deficiencies further hinder Paraguay’s response in enforcement and resource allocation.

Project Description: Partners of the Americas (POA) presents Ñangareko Hağua (“To Protect Ourselves” in Guaraní), a project with the goal to strengthen protection services, particularly among adult male victims of trafficking, and build the capacity of non-specialized shelter staff to provide trauma-informed and victim-centered care for victims of human trafficking. POA proposes a five-year implementation period, structured into four progressive phases that allow installation, pilot testing, expansion, and long-term institutionalization of services.

This timeline enables the project to: (i) conduct a more robust institutional analysis and negotiation process; (ii) pilot and refine the male shelter model before full-scale implementation; (iii) sustain iterative capacity-building cycles for government institutions and non-specialized shelters; and (iv) ensure sustainability through gradual government ownership.

POA will organize implementation into four phases:

- Phase 1 (Year 1): Project installation, institutional analysis, mapping, and initial capacity-building.

- Phase 2 (Year 2): Development, pilot testing, and revision of the Adult Male Victim Care Manual and SOPs.

- Phase 3 (Years 3–4): Expansion of services, strengthening of the alternative shelter network, and continuous inter-institutional coordination.

- Phase 4 (Year 5): Consolidation of institutional commitments, sustainability measures, and transition of operational responsibilities to government partners.

POA will target three project objectives: 1) Increase comprehensive services for adult trafficking victims, particularly men, through the provision of shelter, trauma-informed mental health counseling, and medical and legal assistance; 2) Enhance and implement the use of existing protection SOPs to provide trauma-informed and victim-centered care to adult victims of trafficking; and 3) Build the capacity of non-specialized shelters to support adult male trafficking victims. Our vision is to create a future where comprehensive, trauma-informed protection services are accessible to all victims of human trafficking in Paraguay, particularly adult male victims, ensuring their reintegration into society with dignity, equality, and the opportunity for a better life. Through formalized institutional frameworks and local-driven support systems, we envision a Paraguay where no trafficking survivor is left without the care and assistance they deserve.

### To meet the proposed objectives, POA will work closely with the Inter-Institutional Board to Prevent and Combat Human Trafficking (referred to as the Board) and relevant government agencies, ensuring sustainability. The project will target both national and local public sector and civil society actors, building their capacity to protect adult male trafficking victims. It will also work at the local level to enhance the ability of local services to support adult male TIP survivors. Project methodologies will be survivor-informed, incorporating the leadership and perspectives of survivors to ensure their needs and interests are represented.

### POA has 60 years of experience implementing U.S. Government-funded programs, with multiple programs focused on prevention, protection, and prosecution of human trafficking cases in Paraguay. For this project, POA has identified two qualified key personnel to oversee management and implementation: Macarena JiménezAndrea Ingolotti, Project Coordinator, and Aurora Figueredo, Technical Specialist.

O1: Increase comprehensive services for adult trafficking victims, particularly men, through the provision of shelter, trauma-informed mental health counseling, and medical and legal assistance.

Activity 1.1: Identify Relevant Institution to Provide Care for Adult Male Victims of Trafficking. POA will collaborate with the Board to identify the most suitable entity to provide shelter and comprehensive services for adult male trafficking victims. Such identification will include a detailed analysis of the legal mandate of each institution that forms part of the Board and its capacity to provide protection and care services tailored to male victims of trafficking. This institutional assessment will occur throughout Year 1, allowing sufficient time for consultations, feasibility analysis, and consensus-building within the Board.

These discussions will evaluate the technical requirements, resources, and budget needed to implement the center, ensuring it meets the unique needs of this group.

### Activity 1.2: Sign Agreements with Governmental Institutions to Create Shelter. Once the appropriate institution is identified, a formal agreement will be signed to establish a shelter for adult male victims of trafficking. During Years 1–2, the selected institution will progressively formalize the support network that will include relevant governmental institutions such as the Ministries of Interior, Social Development, Health, and Housing, formalizing their commitment to supporting the shelter for male trafficking victims. The project will develop partnerships with these governmental institutions, emphasizing the importance of coordination to ensure the project's success and continuity. An operational plan will be created for and refined during the pilot phase (Year 2), outlining clear steps for its development. Advocacy efforts will focus on drafting the agreement, which will include a budget allocation provided by the project for the creation of the center, and a sustainability plan, identifying the human and financial resources required to maintain the shelter post-project. This agreement will ensure the sustainability of the shelter beyond the project. In addition to providing housing, the shelter will offer trauma-informed mental health counseling, medical and legal assistance, and technical training and job placement livelihood services.

### Activity 1.3: Establish Adult Male Trafficking Victims Shelter. The project will establish a shelter for adult victims of trafficking. POA will train the entity selected to operate the shelter using a comprehensive care methodology developed from international best practices, evidence-based approaches, and lessons learned from previous trafficking victim support initiatives, which will be tailored to the specific needs of adult male trafficking victims. This methodology will be progressively adapted and pilot-tested during Years 2–3 to meet the needs of adult male trafficking victims.

### Shelter implementation will follow a phased approach:

- Pilot operation (Year 2): initial implementation to test and validate protocols, refine service delivery, and calibrate the adapted care model.

- Operational adjustment (Year 3): revisions based on lessons learned and Monitoring, Evaluation, Research, and Learning (MERL) findings.

- Full-scale implementation (Years 4–5): expansion of services, institutionalization, and quality-control mechanisms.

### The project will offer comprehensive services including legal assistance, mental health support, medical care, and reintegration programs (family reunification, housing, and livelihoods). The shelter will be equipped with psychologists, social workers, occupational support professionals, and security personnel. As part of the project’s inclusive approach, trafficking survivors will be engaged as collaborators, contributing to the development and evaluation of services, with fair compensation for their contributions. Shelter services will prioritize victims’ needstrengthening their capacity to make informed decisions in a safe, non-revictimizing environment.

### This activity is closely tied to Activity 4, where a comprehensive care manual will be developed to guide the shelter’s operations, and Activity 5, where staff will be trained on implementing the care methodology. The manual will form the foundation for shelter operations, ensuring all care services are delivered according to best practices. Training sessions will equip shelter staff with the necessary skills to apply this methodology effectively, ensuring the shelter operates efficiently and consistently with the project’s overall goals.

### A contingency plan if establishing a completely new male shelter is not feasible is provided on page 12 of this proposal.

### Activity 1.4: Develop an Adult Male Trafficking Victim Care Manual. POA will develop a Comprehensive Adult Male Trafficking Victim Care Manual, anchored in a human rights framework. The manual will focus on critical principles such as non-revictimization, victim-centered counseling, confidentiality, and informed consent. It will provide a holistic care model covering the entire continuum of care with the following stages of intervention: i) entry into the shelter, ii) identification with the victimized person of their potential, capacities, and personal, family, community, and institutional resources for life planning iii) development of a “Life Plan”, and iv) implementation of the Life Plan.

### The Manual will be developed, pilot-tested, and refined over a multi-year process, drawing on the Manual for the Care of Female Victims (approved by the Ministry of Women under Resolution N° 061/2021) as a technical reference, while ensuring the creation of a methodology specifically tailored to adult male victims. Across Years 1-2, POA will engage in strategic consultations with the Public Ministry, the Ministry of the Interior, the Ministry of Social Development, and the Ministry of Labor, Employment, and Social Security, to inform the initial design. This will be followed by pilot implementation in Year 3 and final validation in Year 4, incorporating lessons learned from the shelter’s operational experience and MERL findings.

### Additionally, POA will employ a survivor-centered approach, consulting with male trafficking survivors to prioritize their perspectives and input in its development. Following these consultations, the Manual will be submitted to the Sub-Commission for Assistance and Care for Victims of Trafficking for review and final adjustments, ensuring alignment with national frameworks and victim care standards. Furthermore, the project will institutionalize this manual by the entity responsible for managing the shelter, embedding it into the operational protocols and ensuring its sustained application and periodical revision throughout the project’s final years.

### Activity 1.5: Train Stakeholders on the Adult Male Trafficking Victim Care Manual. Once the Manual is finalized, POA will conduct targeted training sessions for officials from relevant institutions on its implementation. These trainings will leverage the Referral Mechanism for the Care of Victims of Human Trafficking, developed by POA through the Ñande Ko'é project. The training will cover key topics such as victim-centered approaches, specific vulnerability factors affecting adult men, intervention principles, care protocols (including SOPs detailed under Activities 6 and 7), and victim certification. These trainings will not be one-time activities but will be offered through recurring annual cycles to ensure institutional continuity and retention of knowledge. The shelter's technical staff will receive specialized training to develop work plans, establish institutional relationships with the Public Ministry, and implement the methodology outlined in the manual. This training will include the use of registry systems and documentation sources to ensure effective service delivery and accountability.

O2: Enhance and implement the use of existing protection SOPs to provide trauma-informed and victim-centered care to adult victims of trafficking.

Activity 2.1: Increase the Board’s Inter-Institutional Coordination Capacity.

POA will work with the Board to become an effective coordinating body, as mandated under Law No. 4788/12. This effort will focus on training Board officials and member institutions to adopt and implement victim care SOPs, ensuring a cohesive and well-coordinated response to trafficking cases. Key activities, including quarterly coordination meetings with the Board and its member institutions will support a continuous cycle of review, implementation, and improvement of SOPs. The project will also convene a #DeTrataSeTrata (It´s All About Trafficking) forum to revise and adjust SOPs as mandated under Law No. 4788/2012. The revision of SOPs will follow an annual cycle (Years 1–4), allowing the Board to update procedures based on pilot results, inter-institutional feedback, and evolving national policies. Additionally, monthly meetings of the Sub-Commission for Assistance and Care for Victims of Trafficking will monitor project progress and ensure consistent follow-up on the implementation of SOPs.

POA will facilitate an exchange of experiences with a neighboring country that has successfully established a shelter for adult male trafficking victims. The exchange will provide insight on best practices for managing shelters and offering holistic care for male victims. Visits, technical discussions, and workshops will help the Board integrate lessons into Paraguay's framework, improving coordination and service delivery. This cross-regional collaboration will provide the Board with tangible strategies to implement long-term, sustainable solutions for trafficking victim care.

The project aims to engage Argentina as the neighboring country to participate in this exchange.  As a Tier 1 country in the 2024 Trafficking in Persons Report, Argentina meets the minimum standards for the elimination of trafficking and has shown consistent, significant efforts in combatting the issue at both the governmental and societal levels, particularly along its extensive border with Paraguay. Argentina's sustained commitment and success in anti-trafficking measures make it a crucial ally in the fight against human trafficking, offering valuable expertise, resources, and strategies that can enhance Paraguay's efforts to address the issue. Additionally, Argentina's National Secretariat for Childhood, Adolescence, and Family (SENAF) provides shelter services for adult male trafficking victims, alongside a network of non-specialized shelters available to them. Argentina also operates a program that supports trafficking survivors' reintegration into the labor market, with the third cohort entirely comprised of male survivors. By exchanging experiences, Argentina can offer insights into their initiatives that address the specific needs of male trafficking victims, equipping Paraguay with the strategies to better serve this vulnerable group.

Activity 2.2: Train Relevant Institution Staff on Existing SOPs for Victim Care.

POA will facilitate focused training sessions on the Referral Mechanism and the SOPs specific to each institution involved in victim care. These sessions will identify coordination SOPs among key government institutions, enhancing resource efficiency and improving the effectiveness of responses to human trafficking cases. Training will occur through annual refreshers and follow-up technical assistance visits to ensure sustained institutionalization across all five years.

By improving agency coordination, the project will contribute to the establishment of a unified approach to addressing human trafficking. Additionally, the project will emphasize trauma-informed care, training service providers to recognize and address the long-term effects of trauma on victims. The Referral Mechanism for Victim Care will also be updated to align with the latest institutional protocols and validated through the Inter-institutional Committee to Prevent and Combat Human Trafficking. Following this, key institutions will receive training on the updated mechanism, ensuring compliance with Law 4788/2012.

O3: Build the Capacity of Non-Specialized Shelters to Support Adult Male Trafficking Victims.

Activity 3.1: Map Existing Organizations Providing Shelter or Similar Services.

Currently, there are no shelters in Paraguay serving adult male victims of human trafficking. POA will work closely with the Board to develop a comprehensive map of organizations offering shelter and care services for vulnerable men, with a particular focus on rural and adult male victims. Mapping will evaluate each organization's capacity, including an analysis of internal regulations and criteria for inclusion and exclusion. The mapping will be updated annually to reflect institutional changes, allowing the network to evolve throughout the five-year implementation period. Results will be presented to the Sub-Commission for Assistance and Care for Victims of Trafficking for review and validation. Based on findings, an operational directory will be created, providing the necessary information to facilitate coordinated actions among service providers. The shelters identified through this process, which could include those assisting individuals affected by addiction or extreme poverty, will be integrated into a network capable of providing immediate care for adult male trafficking victims in Paraguay. While full mapping will occur during project implementation, an initial mapping has already identified the following non-specialized shelters that POA could engage to strengthen their capacity to support male trafficking victims:

- The state-funded Centro de Residencias de Deshabituación y Rehabilitación de Larga Estancia (Residential Center for Long-Term Detoxification and Rehabilitation), located in the town of Piribebuy in the Department of Cordillera.

- The privately funded Comunidad Terapéutica El Camino (El Camino Therapeutic Community), located in the town of Itacurubí de la Cordillera in the Department of Cordillera.

- The privately funded Hogar San José (San José Home), located in the city of Limpio in Paraguay’s Central Department.

- The privately funded Fundación Auxilio de los Cristianos (Christian Aid Foundation), located in the capital city of Asunción in Paraguay’s Central Department.

- The privately funded Hogar de Cristo (Christ Home), located in the capital city of Asunción in Paraguay’s Central Department.

- The privately funded Centro Misional Madre Teresa de Calcuta (Mother Teresa of Calcutta Mission Center), located in the city of Ciudad del Este in the Department of Alto Paraná.

- The privately funded Espacio de Protección de la Pastoral Migrante (Migrant Pastoral Protection Space), located in the capital city of Asunción in Paraguay’s Central Department.

Activity 3.2: Provide Technical Assistance for Internal Regulatory Adjustments in Alternative Shelters. The project will engage identified shelters to assess and adjust their internal regulations, allowing them to accommodate adult male victims of trafficking. Initial outreach will gauge their current capacity and identify barriers that limit their ability to support male victims. Following a detailed analysis of each shelter’s policies and protocols, the project will provide tailored technical assistance to amend their regulations, ensuring compliance with local laws and best practices for trafficking victim services. Technical assistance will be provided in waves (Years 2–4), allowing shelters to incorporate changes gradually and sustainably. In addition, staff will receive specialized training in trauma-informed care, specifically addressing the needs of underserved adult male trafficking victims. To ensure effectiveness and sustainability, the project will establish monitoring and follow-up systems to support the implementation of these regulatory changes. The shelters will be integrated into a broader referral network, creating new pathways for male victims to access care.

Activity 3.3: Train Staff at Identified Establishments for Proper Case Handling.

POA will implement a comprehensive training methodology for staff at shelters and care centers that serve socially vulnerable adult males and trafficking victims. The training will focus on trauma-informed and victim-centered care, ensuring staff can handle cases sensitively and under established procedures. This process will involve the creation of tailored training content that covers proper case management, human trafficking awareness, and the importance of inter-institutional coordination. Training cycles will recur annually, ensuring that new staff and turnover do not weaken service capacity over the duration of the project. The technical teams at key identified care centers will be trained to correctly receive, support, and refer cases, following the established referral mechanisms and protocols. This initiative will strengthen the capacity of service providers to offer appropriate and effective care for male trafficking victims.

Activity 3.4: Develop a Network of Alternative Shelters. The project will identify and consolidate a network of alternative shelters that can provide comprehensive services in coordination with Ministry of Labor programs. The network will be established and strengthened progressively across Years 2–5, incorporating lessons learned from the pilot shelter and refining coordination mechanisms over time. The network will be designed to ensure that victims, particularly adult males, have access to immediate care and long-term support for reintegration into society. The project will host regional meetings to introduce the victim care methodology tailored for male victims. Meetings will serve to discuss key obstacles and institutional adjustments necessary for effective inter-institutional coordination. Capacity-building initiatives will be implemented for the shelters identified in Activity 8, ensuring they are well-prepared to offer victim care and access to employment-related opportunities.

The project’s MERL plan will use a comprehensive, rigorous approach aligned with TIP Office requirements. Total MERL costs represent 9.05% of the project budget. POA will collaborate with the TIP Office to design MERL activities. A robust process will be implemented to establish baseline values for Common Performance Indicators and unique project indicators through quantitative and qualitative methodologies. This will involve collecting reliable data via surveys, interviews, and document reviews, ensuring that progress and outcomes reflect the realities of project beneficiaries and stakeholders. The project will implement a comprehensive monitoring system to collect data for all indicators regularly. MERL activities will follow a five-year structure including: a baseline assessment (Year 1), a Midterm Evaluation (Year 3), and Final Evaluation (Year 5) and annual learning reviews to inform SOP and manual adjustments. The system will include digital tools for monitoring key activities and outcomes, such as services provided to victims, staff training, and the impact on the social reintegration of male trafficking victims. Dedicated MERL staff will oversee and coordinate data collection and analysis activities to ensure consistency and accuracy throughout the project lifecycle​.

Sustainability Plan. The sustainability plan for the Ñangareko Hağua project ensures that resources developed through the project, as well as those leveraged from previous initiatives, will be proactively used by stakeholders and beneficiaries beyond the project's period of performance.

Throughout the five-year period, POA will gradually transfer leadership, operational responsibilities, and technical oversight to government institutions, ensuring long-term uptake of the male shelter model and alternative shelter network.

The Manual will be embedded progressively embedded into operational protocols, with government adoption expected between Years 4–5 after full pilot validation.

Institutionalization of the Adult Male Trafficking Victim Care Manual: The Adult Male Trafficking Victim Care Manual will serve as a foundational resource for sustaining victim-centered, trauma-informed care. Developed in consultation with key government agencies and trafficking survivors, the manual will align with national victim care standards and be embedded into the operational protocols of the entity managing the shelter. This ensures that best practices in victim support remain institutionalized beyond the project’s lifespan.

To ensure effective and sustained use of the manual, POA will train relevant government officials, shelter staff, and other stakeholders on its implementation. These trainings will build institutional knowledge and technical expertise, covering victim-centered approaches, intervention principles, and case management protocols. By leveraging the Referral Mechanism for the Care of Victims of Human Trafficking from the Ñande Ko’é project, training efforts will strengthen coordination among institutions responsible for victim protection. The involvement of the Sub-Commission for Assistance and Care for Victims of Trafficking in reviewing and validating the manual guarantees alignment with national frameworks and policies, reinforcing long-term government ownership of victim care services.

Government Institutionalization and Knowledge Transfer: The project will work closely with the Paraguayan government to ensure the institutionalization of care services for male trafficking victims. SOPs for Victim Care developed and enhanced through the project will be institutionalized and actively utilized by stakeholders and beneficiaries beyond the project’s period of performance. The project will achieve this by embedding SOPs into the work of the Inter-Institutional Board to Prevent and Combat Human Trafficking, strengthening the Board’s capacity to implement them, and training government officials for long-term sustainability.  POA will provide training sessions for government officials and service providers on the implementation of the SOPs, along with the Referral Mechanism for the Care of Victims of Human Trafficking, guaranteeing that officials are equipped to maintain a standardized and victim-centered approach to trafficking cases beyond the project’s duration.

Building the Capacity of Non-Specialized Shelters: The project will ensure the long-term sustainability of care for adult male trafficking victims by equipping non-specialized shelters with the policies, processes, tools, and knowledge necessary to continue providing trauma-informed care beyond the project’s duration. These shelters will be integrated into an alternative shelter network, creating a lasting framework for service provision. Staff will receive specialized training on victim-centered care and the implementation of SOPs refined and developed with the Board, ensuring they have the capacity to maintain and expand services for male trafficking victims even after the project concludes.

Commitment/Buy-in from Key Government Institutions. POA has engaged key institutions—including the Public Ministry, the Ministry of the Interior, the Ministry of Social Development, and the Ministry of Labor, Employment, and Social Security—to inform them about the potential project and request letters of support as a demonstration of their commitment to collaboration. However, Paraguay’s current political climate, shaped by Law 7363/2024, which regulates the control, transparency, and accountability of non-profit organizations, has created tension between the government and civil society organizations. Consequently, government institutions are hesitant to sign formal commitments until projects receive official funding and approval. Despite this, given POA’s strong track record of successfully implementing projects in Paraguay and fostering collaboration with key government agencies, we are confident that once the project is officially awarded, we will secure formal commitments from these Ministries.

Contingency Plan if establishing a completely new male shelter in the country is not feasible. If establishing a completely new shelter for male victims in the country is not feasible, the project will implement a contingency plan consisting of two key strategies:

- Refocusing efforts on enhancing the capacity of non-specialized shelters by investing additional resources into training and capacity-building activities. This will ensure that these shelters are equipped with the necessary knowledge, tools, and skills to effectively serve male trafficking victims, enabling them to continue providing support long after the project's conclusion.

- Collaborating with the government to establish a comprehensive process for assisting male trafficking victims by creating an integrated services network. This network will bring together key government institutions, including the Ministry of Labor, Ministry of Public Health, and Ministry of Social Development. It will define the roles and responsibilities of each institution in providing essential services to male trafficking victims, such as trauma-informed mental health counseling, medical and legal assistance, and ad-hoc shelter solutions. This collaborative approach will ensure that male victims have access to a coordinated and holistic support system.

This percentage is aligned with the findings of an ongoing study conducted by Grupo Luna Nueva on the use of ICTs in the recruitment of TIP victims. The study reveals an increase in male victims from 17% to 30% between 2021 and 2024.

The Board serves as an advisory body to the National Government in this area and is the coordinating entity for actions carried out by the Paraguayan State under the National Strategy for the Fight against Human Trafficking (Article 44 of Law No. 4788/12).