## Partners of the Americas

## Budget Narrative

### Introduction

In this section, Partners of the Americas (POA) provides a detailed explanation of the budget line items and the methods used to determine costs associated with implementing the proposed project strategy. POA has established sound financial management and internal control systems, ensuring expenditures are reasonable, allowable, and classified in accordance with generally accepted accounting principles (GAAP). POA uses cloud-based accounting software called Sage Intacct and is subject to an annual Single Audit. The Finance and Administration (F&A) department is staffed with professionals with over 40 years of combined experience in finance and accounting, auditing, and managing financial reporting for federal grants, contracts, and cooperative agreements. The F&A department comprises a Chief Financial Officer (CFO), Director of Compliance for Grants and Contracts, and two Senior Finance Officers. The F&A team works closely with project staff at POA HQ and in-country staff to monitor spending, ensure that all costs are reasonable and allowable, and support project staff to implement the project in accordance with USG rules and regulations (particularly 2 CFR 200), local laws, as well as POA’s internal policies. Our F&A department also reviews spending with project directors monthly and assists with the oversight of contracts, end-of-project reporting, and other aspects of project monitoring.

POA uses a robust and cost-effective strategy to determine cost allocation in accordance with USG cost principles, local laws, and internal policies. Our proposed budget for this project was developed by conducting thorough price analyses to identify realistic and fair market values for all projected expenses. Our budget estimates were also calculated based on past experience in implementing effective and cost-efficient USG-funded programs.

M&E Budget

POA believes that M&E is a critical component for successful programmatic implementation; therefore, POA has allotted approximately 9.05% ($226,185) of the total budget to M&E-related activities.

| M&E Budget |  |
| --- | --- |
| Personnel Costs - M&E Coordinator (100% LOE) | $ 116,891 |
| Fringe Benefits - M&E Coordinator (100% LOE) | $ 41,227 |
| Customize M&E Database for Project | $ 4,468 |
| M&E Materials | $ 4,604 |
| M&E Training and Coordination Meetings | $ 2,708 |
| Mid-term Evaluation | $ 27,040 |
| Final Evaluation | $ 29,246 |
| Total M&E Budget | $ 226,185 |
| Percentage of M&E Budget | 9.05% |

Personnel

POA will follow U.S. and local labor laws for all employees identified in this proposal. Salaries are based on comparable organizations and projects, information gathered in-country, market analysis, and other data. Proposed salaries are also consistent with those paid to other personnel engaged in similar work within and outside of POA. Level of effort (LOE) budgeted is based on the scope of the program proposed. POA has applied a 5% yearly increase to account for inflation and for merit increases for all for staff which is consistent with POA policies. All staff listed, with the exception of the Project Manager, will be based in Paraguay.

Project Coordinator: The Project Coordinator, Macarena Jiménez, with an annual salary of $116,160 (or $9,680 per month), will dedicate 50% of her time to Ñangareko Hağua. This position is budgeted for twelve (12) months per year in Years 1–5, with a 5% annual increase to account for inflation and merit. The Project Coordinator will be based in Asunción, Paraguay, and will lead the implementation of Ñangareko Hağua, overseeing all technical, administrative, and financial components of the project. The total estimated cost is $320,929.

Technical Specialist: The Technical Specialist, Aurora Figueredo, with an annual salary of $57,600 or $4,800/month will dedicate 50% of their to time to Ñangareko Hağua and will be based in Asuncion, Paraguay. This is budgeted at nine (9) months in Year 1, twelve (12) months in Years 2-4 and six (6) months in Year 5 with a 5% increase each additional year to account for inflation and merit. Additionally, she will coordinate with stakeholders and serve as a Trafficking in Persons (TIP) expert for the development of tools and resources. The total estimated cost is $134,435.

M&E Coordinator: The M&E Coordinator (TBD), with an annual salary of $24,000 or $2,000/month will dedicate 100% of their to time to Ñangareko Hağua and will be based in Asuncion, Paraguay. This is budgeted at nine (9) months in Year 1, twelve (12) months in Years 2-4 and eight (8) months in Year 5 with a 5% increase each additional year to account for inflation and merit. The total estimated cost is $116,891.

Administration and Finance Officer: Based in Paraguay, the Administration and Finance Officer with an annual salary of $26,400 or $2,200/month will dedicate 50% of their to time to Ñangareko Hağua. This is budgeted at nine (9) months in Year 1, twelve (12) months in Years 2-4 and eight (8) months in Year 5 with a 5% increase each additional year to account for inflation and merit. This position will implement financial management systems and controls to ensure compliance, transparency, and effective utilization of resources. The total estimated cost is $64,290.

Project Manager (HQ): Based in Washington DC, the Project Manager with an annual salary of $66,804 or $5,567/month will dedicate 30% of their to time to Ñangareko Hağua. This position is budgeted for twelve (12) months per year in Years 1–5, with a 5% annual increase to account for inflation and merit. The Project Manager is responsible for the backstopping function for the project, providing technical oversight, directly supervising the Project Coordinator, providing daily support to in-country staff, assisting with the preparation of reports and other deliverables, overseeing compliance with US Department of State (USDOS) rules and regulations and POA’s policies, and ensuring to on-time reporting to USDOS, among other tasks. The total estimated cost is $110,740.

Fringe Benefits

In Paraguay, POA staff have a fringe rate of 35.27% charged on total salary. This includes the required benefits in Paraguay and based on POA policy as follows:

- Social Security (Employer) – 16.5%

- Aguinaldo (13th month) – 8.33%

- Annual Leave- 15 days per year – 5.77%

- Severance for Dismissal – 4.17%

- Life Insurance – 0.5%

Project Coordinator: In accordance with labor laws, POA has budgeted a 35.27% rate on the salary of the Project Coordinator to account for fringe benefits. The total estimated cost is $113,192.

Technical Specialist: In accordance with labor laws, POA has budgeted a 35.27% rate on the salary of the Technical Specialist to account for fringe benefits. The total estimated cost is $47,415.

M&E Coordinator: In accordance with labor laws, POA has budgeted a 35.27% rate on the salary of the M&E Coordinator to account for fringe benefits. The total estimated cost is $41,227.

Administration and Finance Officer: In accordance with labor laws, POA has budgeted a 35.27% fringe rate on the Administration and Finance Officer’s base salary. The total estimated cost is $22,675.

Project Manager (HQ): In accordance with POA’s personnel policy and NICRA letter, POA has charged a 23.47% fringe rate on the base salary of the Project Manager. Fringe benefits include insurance, mandatory taxes, pension, and other employee benefits. The total estimated cost is $25,991.

Travel

- All travel costs after Year 1 include a 4% increase for inflation for locally purchased goods/services in Paraguay which is based on the expected inflation rate from the Banco de la República del Paraguay.

HQ Staff International Travel

International Airfare (Washington DC to Asuncion, Paraguay): POA is budgeting for airfare for the Project Manger to fly from Washington, DC to Asuncion, Paraguay for one (1) trip per year for life of the project. The purpose of the trip is for project management activities, capacity building and training, compliance spot checks, and oversight and monitoring. Based on average market price flight, POA estimates $2,000/trip. Round trip rates are based on coach/economy class airfares and compliance with Fly America. The total estimated cost for five (5) trips is $10,833.

Ground Transportation: Based on prior experience POA estimates $50/trip for ground transportation for a total of five (5) trips for the life of the project. Ground transportation includes transport to and from airports and some local transportation. The total estimated cost is $1,896.

Lodging in Asuncion: POA is budgeting lodging at a rate of $95/night in Asuncion and surrounding areas for a total of 35 nights (an average of seven nights per trip) for the life of the project. The lodging rate is based on hotel quotes, market research and an average reduced rate of the USG allowable rate. The total estimated cost is $3,602.

M&IE in Asuncion: POA is budgeting meals and incidental expenses at a rate of $81/day in Asuncion for a total of 35 days (an average of seven days per trip) for the life of the project. The per-diem rate is in accordance with POA policies and is based on an average reduced rate of USG allowable per-diems. The total estimated cost is $3,071.

Local Staff In-Country Travel

Lodging in Chaco, Ciudad del Este, Caaguazú, and Alto Paraná: POA is planning for the Project Coordinator, Technical Specialist, and/or M&E Coordinator to travel to the implementing regions. Lodging is budgeted at $85 per night, for an average stay of three nights per trip. POA anticipates three (3) trips in Year 1 and six (6) trips per year in Years 2–5. The lodging rate is based on hotel quotes, market research, and a reduced average rate aligned with USG allowable limits. The total estimated cost is $7,522.

M&IE in Chaco, Ciudad del Este, Caaguazú, and Alto Paraná: POA is planning for the Project Coordinator, Technical Specialist, and/or M&E Coordinator to travel to the implementing regions. M&IE is budgeted at $54 per day, for an average stay of three (3) days per trip. POA anticipates three (3) trips in Year 1 and six (6) trips per year in Years 2–5. The per-diem rate is in accordance with POA policies and is based on a reduced average rate aligned with USG allowable per-diems. The total estimated cost is $4,779.

Ground Transportation: POA is budgeting transportation costs for travel from Asunción to the implementing regions (Chaco, Ciudad del Este, Caaguazú, and Alto Paraná), as well as local transportation within these areas for meetings, site visits, trainings, and other program activities. Transportation is estimated at $750 per trip. POA anticipates three (3) trips in Year 1 and six (6) trips per year in Years 2–5. The total estimated cost is $22,123.

International Travel - Participants Exchange of Experience on Best Practices for Managing Shelters (Activity 2.1)

International Airfare (Asuncion, Paraguay to Argentina and/or Chile): POA will work to increase the project’s inter-institutional capacity by facilitate an exchange of experiences with a neighboring country that has successfully established a shelter for adult male trafficking victims. POA is budgeting airfare for the three (3) participants in these exchanges to fly round-trip from Asuncion, Paraguay to locations in Argentina and/or Chile. These costs are based on average market price flight, POA estimates POA estimates $350/trip with three (3) trips in Year 2 and three (3) trips in Year 3 for a total estimated cost of $2,228.

Ground Transportation: Based on prior experience POA is estimating ground transportation in Argentina and Chile at $50/trip with three (3) trips in Year 2 and three (3) trips in Year 3. Ground transportation includes transport to and from airports and some local transportation. The total estimated cost is $318.

Lodging in Chile/Argentina: POA is budgeting lodging at a rate of $110 per night, with twelve (12) nights planned in Year 2 and twelve (12) nights planned in Year 3. The lodging rate is based on hotel quotes, market research, and a reduced average aligned with USG allowable rates. The total estimated cost is $2,801.

M&IE in Chile/Argentina: POA is budgeting meals and incidental expenses at a rate of $100 per day in Chile/Argentina, with an average trip length of four (4) days. A total of twelve (12) days are planned in Year 2 of the project and twelve (12) days in Year 3. The per-diem rate complies with POA policies and is based on a reduced average aligned with USG allowable per-diems. The total estimated cost is $2,546.

Domestic Travel - Participants of Coordination Meetings to Develop a Network of Alternative Shelters (Activity 3.4)

Ground Transportation to/from Asuncion: The program will host regional meetings to create and consolidate a network of alternative shelters capable of providing comprehensive services, including victim care methodologies specifically tailored for male victims. POA anticipates hosting one (1) meeting in Year 1 and two (2) meetings per year in Years 2–4. Ground transportation is budgeted at $250 per participant, covering travel from each participant’s place of origin to Asunción and return, as well as necessary local transportation. POA estimates ten (10) participants per meeting. The total estimated cost is $18,732.

Lodging in Asuncion: POA is budgeting lodging for participants attending the meetings at a rate of $95 per night (plus inflation). Lodging is estimated for ten (10) participants per meeting, with one (1) night of lodging per participant. POA anticipates one (1) meeting in Year 1 and two (2) meetings per year in Years 2–4. The lodging rate is based on hotel quotes, market research, and a reduced average aligned with USG allowable rates. The total estimated cost is $7,118.

M&IE in Asuncion: POA is budgeting meals and incidental expenses for its victim care and methodology meetings at a rate of $81/day (plus inflation) in Asuncion for one (1) day per participant and a total of ten (10) days in Year 2 and twenty (20) days in Years 2-4. The per-diem rate is in accordance with POA policies and is based on an average reduced rate of USG allowable per-diem. The total estimated cost is $6,069.

Supplies

All supplies will be procured locally, in Paraguay, in accordance with standard procurement practices, as a means to eliminate shipping and handling costs.

Office Supplies: Based on experience with similar programs in Paraguay, POA is estimating $90/month for the purchase of program specific office supplies and training materials. Additionally, the cost will cover items such as masks, gel, alcohol, and hand sanitizer to ensure the safety of staff and the population that they interact with during the development of activities. POA is budgeting for ten (10) months in Year 1 and twelve (12) months in Years 2-5. The total estimated cost is $5,670.

Laptop Computers & Software: POA plans to procure five (5) laptop computers and accompanying software, at $1,200/unit. These computers will be purchased for the Project Coordinator, Technical Specialist, M&E Coordinator, Administration and Finance Officer and Project Manager in Year 1. The total estimated cost is $6,000.

Contractual

Activity 1.3: Establish Adult Male Trafficking Victims Shelter

TIP Shelter Manager: POA will contract a TIP Shelter Manager to oversee the daily operations of the shelter that provides care and protection to adult male trafficking victims. Responsibilities will include staff supervision, logistical oversight, and coordination with legal service providers. The Shelter Manager’s primary role is to ensure that survivors receive the support and services they need—such as life skills training—in a safe, secure, and compassionate environment. This consultancy is budgeted at a rate of $1,950 per month. The Shelter Manager will be hired for three (3) months in Year 1 and twelve (12) months per year in Years 2–4. The total estimated cost is $81,817.

Psychological Counselors for TIP Shelter: POA plans to contract psychological counselors as consultants for the development and implementation of mental health support, resources, and reintegration programs, such as group therapy sessions, for the adult male trafficking victims at the TIP shelter. Based on the LOE and taking into account previously contracted rates, a monthly rate of $925 will be charged. POA is budgeting for three (3) months in Year 1 and twelve (12) months per year in Years 2–4.  The total estimated cost is $38,811.

Social Workers for TIP Shelter: POA plans to contract social workers as consultants for the development and implementation of resources and reintegration programs for the adult male trafficking victims at the TIP shelter. Based on the LOE and taking into account previously contracted rates, a monthly rate of $1,500 will be charged. POA is budgeting for three (3) months in Year 1 and twelve (12) months per year in Years 2–4.  The total estimated cost is $62,936.

Occupational/Education Support for TIP Shelter: POA plans to contract occupational/educational support for the development and implementation of resources and reintegration programs for the adult male trafficking victims at the TIP shelter. Based on the LOE and taking into account previously contracted rates, a monthly rate of $925 will be charged. POA is budgeting for three (3) months in Year 1 and twelve (12) months per year in Years 2–4.   The total estimated cost is $38,811.

Legal Counsel for TIP Shelter: POA plans to contract legal counsel for the legal documentation and assistance with Identification, birth certificates, or immigration papers for the adult male trafficking victims at the TIP shelter. Based on the LOE and taking into account previously contracted rates, a monthly rate of $685 will be charged. POA is budgeting for three (3) months in Year 1 and twelve (12) months per year in Years 2–4. The total estimated cost is $28,741.

Medical Counsel for TIP Shelter: POA plans to contract medical counsel such as medical staff for any unforeseen health issues or emergencies regarding the adult male trafficking victims at the TIP shelter. Based on the LOE and taking into account previously contracted rates, a monthly rate of $685 will be charged. POA is budgeting for three (3) months in Year 1 and twelve (12) months per year in Years 2–4. The total estimated cost is $28,741.

Activity 1.4: Develop an Adult Male Trafficking Victim Care Manual

Consultant to develop Adult Male Trafficking Victim Care Manual: POA plans to contract a specialized consultant to develop the Adult Male Trafficking Victim Care Manual. POA estimates an average level of effort of twenty-five (25) consultancy days at a rate of $360 per day in Year 1. The total estimated cost for this consultancy is $9,000.

Activity 1.5: Train Stakeholders on the Adult Male Trafficking Victim Care Manual

Consultant to train on Adult Male Trafficking Victim Care Manual: POA plans to contract a consultant to deliver training sessions on the Adult Male Trafficking Victim Care Manual developed under the project. POA estimates twelve (12) consultancy days at a daily rate of $360 in Year 1. The total estimated cost for this consultancy is $4,320.

Activity 2.2: Train Relevant Institution Staff on Existing SOPs for Victim Care

Consultant to deliver trainings on Existing SOPs: POA plans to contract a consultant to deliver training sessions on existing Standard Operating Procedures (SOPs) for victim care under Activity 2.2. The consultancy is budgeted at a daily rate of $360, with an estimated level of effort of ten (10) days in Year 1 and twenty (20) days per year in Years 2–5. The total estimated cost for this consultancy is $35,398.

M&E

Midterm Evaluation: POA plans to contract an independent external evaluator to conduct the project’s midterm evaluation in Year 3. This evaluation will assess progress toward objectives, identify implementation challenges, and provide actionable recommendations to strengthen project performance for the remaining years. The estimated cost for the midterm evaluation is $27,040.

Final Evaluation: POA also plans to contract an independent external evaluator to carry out the final evaluation in Year 5. This evaluation will measure overall project effectiveness, impact, sustainability, and alignment with expected outcomes, providing evidence-based findings for future programming. The estimated cost for the final evaluation is $29,246.

Other Direct Costs

Banking and Cash handling fees & Fiscal Reviews: Based on prior experience, banking, cash handling fees and fiscal reviews are estimated to cost $75/month for nine (9) months in Year 1, and twelve (12) months in Years 2-5 for a total cost of $4,650.

Courier/fees services: Based on prior experience, courier fees/services for all project related activities are estimated to cost $35/month for nine (9) months in Year 1, and twelve (12) months in Years 2-5 for a total cost of $2,170.

Communication Costs: Based on prior experience, POA is estimating $120/month for communication costs for the project office in Asunción. The cost is intended to cover remote work while traveling in the field as necessary for printing, data, phone, internet, and other communication costs. POA is budgeting for nine (9) months in Year 1 and twelve (12) months in Years 2-5 for a total cost of $7,440.

Legal Fees: POA is estimating legal fees at $550/year, for Years 1-5 of the project and is based upon similar projects in the region. The total estimated is $2,979.

Office Space: Based on market quotes in Asunción, POA is estimating $1,250/month for an office space. POA estimates nine (9) months in Year 1 and twelve (12) months in Years 2-5 for a total cost of $77,495.

Subscriptions, Timekeeping and Expense Reporting Platform: POA is budgeting for timekeeping, expense reporting and subscriptions to various work-related digital platforms at a rate of $103/year for nine (9) months in Year 1 and twelve (12) months in Years 2-5. The final cost is $6,406.

Objectives and Activities

O1: Increase comprehensive services for adult trafficking victims, particularly men, through the provision of shelter, trauma-informed mental health counseling, and medical and legal assistance.

Activity 1.1 Identify Relevant Institution to Provide Care for Adult Male Victims of Trafficking

Meetings with the Board to assess feasibility and requirements for TIP Shelter: POA is budgeting for a total of four (4) meetings in Year 1 and two (2) meetings per year in Years 2–5. In Year 1, these meetings will focus on assessing the feasibility, technical requirements, resources, and budget needed to establish the shelter and ensure it meets the unique needs of this vulnerable group. From Year 2 onward, the meetings will serve to monitor progress and provide ongoing oversight. Based on similarly sized meetings under prior projects, POA estimates a cost of $135 per meeting. The total estimated cost is $1,732.

Activity 1.2: Sign Agreements with Governmental Institutions to Create Shelter

Venue and A/V for Signing event: POA is budgeting $900 per event to cover venue and A/V costs related to the establishment of a shelter for adult male trafficking victims. POA anticipates one (1) event in Year 1 to support the initial establishment process, and an additional event in Year 4 to formalize the institutionalization of the shelter. The total estimated cost is $1,912.

Refreshments/Coffee Break for Signing Event: POA is budgeting $17/person to cover the costs of refreshments and coffee breaks during these events and estimates 30 attendees in Year 1 and in Year 4. The total estimated cost is $ 1,084.

Materials and Printing for signing event: POA is estimating a lump sum cost of $200/year to cover the costs of procuring material for one (1) signing event during Year 1 and another during Year 4. The total estimated cost is $425.

Activity 1.3: Establish Adult Male Victims of Trafficking Shelter

POA is proposing costs to cover 3,25 years of the shelter, after which the costs will be covered by the government agency as part of the sustainability and transition planning of the project.

Rent and Utilities for TIP Shelter: Based off quotes, POA is estimating $2,150/month for the renting and the acquisition of all utilities needed in order to establish a shelter for adult victims of trafficking. The cost is intended to cover the rent, maintenance, insurance, utilities, and emergency protocols costs. POA is budgeting for three (3) months in Year 1 and twelve (12) months in Year 2-4 for a total cost of $90,209.

Furniture and Furnishings for TIP Shelter: POA is budgeting for the purchase of all the necessary furniture to equip the TIP shelter including the sleeping accommodations (bed, mattress, bedding, blankets, dresser, etc.), and contributions to setup the kitchen and laundry room amenities. The shelter will have ten (10) rooms at a cost of $875/room based upon quotes and research. The total estimated cost is $8,750.

Personal Hygiene Products for TIP Shelter: POA is budgeting personal hygiene (toiletries, soap, shampoo, toothpaste, toothbrushes, and other hygiene products) products at $125/person for thirty (30) beneficiaries during Years 1-4. The total estimated cost is $15,924.

Food and Groceries for TIP Victims: POA is estimating $165/month to procure food and groceries for ten (10) beneficiaries during three (3) months in Year 1, and ten (10) beneficiaries during twelve (12) months in Years 2-4. The total cost is $69,230.

Essential Needs (Clothing) and Medications for TIP Shelter: POA is budgeting for the clothing and medications (pain relievers, first aid supplies) as necessary at an estimated cost of $85/person for thirty (30) beneficiaries during Years 1-4. The total estimated cost is $10,828.

Operational Supplies for TIP Shelter: Operational Supplies (cleaning products, sanitary items, paper, etc.) are estimated to cost $175/month for three (3) months in Year 1, and twelve (12) months in Years 2-4 for a total cost of $7,343.

Security Contractor and Security Systems for TIP Shelter: Security services, the acquisition and installation of security systems are estimated to cost $1,500/month for three (3) months in Year 1 and twelve (12) months in Years 2-4. The cost includes security systems (CCTV, security alarm), emergency protocols, fire extinguishers and smoke detectors, and on-site security personnel (24/7). The total estimated cost is $69,236.

Cleaning & Maintenance for TIP Shelter: Cleaning and maintenance services are estimated at $750 per month for three (3) months in Year 1 and twelve (12) months per year in Years 2–4. The cost includes routine cleaning of common areas and bedrooms, waste management, basic facility upkeep, minor repairs, and periodic deep cleaning to ensure a safe, hygienic, and trauma-informed environment for adult male trafficking victims. These services are essential to maintaining shelter operations in accordance with health, safety, and protection standards. The total estimated cost is $31,468.

Health, Wellness, & Rehabilitation (Vaccinations, Medications, Health Assessment, etc.) for TIP Shelter: These services are estimated at $750 per month for three (3) months in Year 1 and twelve (12) months per year in Years 2–4. The cost includes routine and emergency medical care, initial and periodic health assessments, vaccinations, essential medications, psychological first aid, and referrals for specialized care when needed. It also covers wellness and rehabilitation support such as basic therapeutic services, follow-up consultations, and health supplies to ensure the physical and emotional well-being of adult male trafficking victims. The total estimated cost is $31,468.

Catering/Chef Services for TIP Shelter (excludes food): These services are estimated at $700 per month for three (3) months in Year 1 and twelve (12) months per year in Years 2–4. The cost includes professional chef and catering services to prepare nutritionally balanced meals for shelter residents; menu planning tailored to health, cultural, and dietary needs; safe food handling and kitchen hygiene practices; and the daily management of meal schedules. The total estimated cost is $29,370.

Transport (fuel and transport of victims): This service is estimated at $350 per month for three (3) months in Year 1 and twelve (12) months per year in Years 2–4. The cost includes fuel, routine vehicle use, and transportation of survivors to essential services such as medical appointments, legal consultations, psychosocial support, and reintegration activities. It also covers local transport needed for case management follow-up and coordination with relevant institutions to ensure continuity of care. The total estimated cost is $14,685.

Activity 1.4: Develop an Adult Male Trafficking Victim Care Manual

Develop Comprehensive Adult Male Trafficking Victim Care Manual: POA is estimating a one-time cost of $5,000 in Year 1 for the development of a comprehensive adult male trafficking victim care manual that will have a human rights framework. It addresses the unique needs of adult male trafficking victims and includes strategies for providing trauma-informed care, legal assistance, and reintegration support. It will focus on critical principles such as non-revictimization, victim-centered counseling, confidentiality, and informed consent. The total estimated cost is $5,000.

Survivor Inclusion Compensation: POA is estimating $1,000/person for the survivor inclusion compensation in the development of the comprehensive adult male trafficking victim care manual. This cost covers the compensation given to survivors or persons with lived experience of human trafficking that contribute or are meaningfully included in the design, implementation, and/or evaluation of the project. POA estimates five (5) people in Year 1 for a total cost of $5,000.

Printing of Manual: POA is budgeting the printing of the Manuals at a unit cost of $25, with an estimated 250 copies in Year 1 and 200 copies in Year 2. The total estimated cost $11,450.

Activity 1.5: Train Stakeholders on the Adult Male Trafficking Victim Care Manual

Venue and A/V for Training on Victim Care Manual: POA is budgeting $900 per event to cover venue rental and A/V services for trainings on the Victim Care Manual. These costs include the rental of an appropriate training space, audio-visual equipment, and on-site technical support. POA anticipates one (1) training event per year in Years 1–5, for a total estimated cost of $4,875.

Refreshments/Coffee Break for Training on Victim Care Manual: POA is budgeting $17 per person to cover the cost of refreshments and coffee breaks for participants attending the training on the Victim Care Manual. POA estimates 50 participants per training event, with one (1) event per year in Years 1–5. The total estimated cost is $4,604.

Materials and Printing for Training on Victim Care Manual: POA is estimating a lump sum cost of $600/event to cover the costs of purchasing and printing materials, such as notebooks, pens, and victim care manuals, for the training on the Victim Care Manual. For five (5) years, POA estimates a total cost of $3,250.

O2: Enhance and implement the use of existing protection SOPs to provide trauma-informed and victim-centered care to adult victims of trafficking.

Activity 2.1: Increase the Board’s Inter-Institutional Coordination Capacity

Board’s Inter-Institutional Coordination Meetings: POA is estimating $95/meeting to cover the costs meeting the Board and its member institutions to streamline responses and monitor the progress of the project. POA estimates three (3) meetings in Years 1-5 for a total cost of $3,468.

Activity 2.2: Train Relevant Institution Staff on Existing SOPs for Victim Care

Updating of the Mechanism of Attention to Victims of Human Trafficking, according to the updated protocols of the institutions: POA estimates a one-time cost of $3,000 to update the mechanism of attention to victims of human trafficking to meet the updated protocols of the institutions. This will help identify coordination SOPs among key government institutions, enhancing resource efficiency and improving the effectiveness of responses to human trafficking cases. The total estimated cost is $3,000.

Printing of updated document: POA is budgeting the printing of the updated document at a unit cost of $15, with an estimated 250 copies in Year 1 and 100 copies in Year 2. The total estimated cost $5,310.

Venue and A/V for Training on SOPs for Victim Care: POA is estimating $750/training to cover the costs of a venue and A/V for training on the SOPs for victim care. These costs include rent of venue and A/V services provided by staff. POA estimates two (2) trainings in Years 1-4 and one (1) training in Year 5 at a total cost of $8,124.

Refreshments/Coffee Break for Training on SOPs for Victim Care: POA is estimating $17/person to cover the costs of refreshments/coffee breaks for people at the training on SOPs for victim care. POA estimates 15 people per training in Years 1-5 at a total cost of $1,381.

Materials and Printing for Training on SOPs for Victim Care: POA is estimating a lumpsum cost of $500/training to cover the costs of purchasing and/or printing materials for the training on SOPs for victim care. POA estimates a total cost of $5,416 for ten(10) trainings in Years 1-5.

O3: Build the Capacity of Non-Specialized Shelters to Support Adult Male Trafficking Victims.

Activity 3.1: Map Existing Organizations Providing Shelter or Similar Services

Meetings with Stakeholders to Map Existing Organizations Providing Shelter: POA is estimating $200/meeting to cover the cost of meeting with stakeholders to map existing organizations that are already providing shelter or similar services to the project. POA estimates five (5) meetings in Year 1 at a total cost of $1,000.

Activity 3.2: Provide Technical Assistance for Internal Regulatory Adjustments in Alternative Shelters

Legal Review for Adjustments to Internal Regulations: POA is estimating $320/day to cover the cost of legal reviews of each shelter for adjustments to internal regulations. POA estimates forty (40) days in Year 1 at a total cost of $12,800.

Meetings with Shelters to Provide Assistance and Review of Regulatory Adjustments: POA is estimating $250/meeting to cover the cost of meetings with the shelters to aid and review the regulatory adjustments. POA estimates fifteen (15) meetings with alternative shelters in Year 1 and fifteen (15) meetings with alternative shelters in Year 2 at a total cost of $7,650.

Activity 3.3: Train Staff at Identified Establishments for Proper Case Handling

Trainings for Staff on Proper Case Handing and Methodology: POA is estimating $500/training to cover the costs of training staff on proper case handling and methodology. POA estimates five (5) trainings per year for Years 2-5 at a total cost of $11,041.

Activity 3.4: Develop a Network of Alternative Shelters

Venue and A/V for Coordination Meetings to Develop a Network of Alternative Shelters: POA is estimating $500/meeting to cover the costs of a venue and A/V for coordination meetings to consolidate a network of alternative shelters. POA estimates four (3) meetings per year in Years 2-5 for a total cost of $6,624.

Refreshments/Coffee Break for Coordination Meetings to Develop a Network of Alternative Shelters: POA is budgeting $17/person to cover the costs of refreshments and coffee breaks during the coordination meetings. POA estimates 15 people per year during Years 2-5. The total estimated cost is $1,126.

Materials and Printing for Coordination Meetings to Develop a Network of Alternative Shelters: POA is estimating a lumpsum cost of $300/meeting to cover the costs of procuring material for three (3) coordination meetings per year during Years 2-5. The total estimated cost is $3,975.

Monitoring & Evaluation

Customize M&E Database for Project: POA is budgeting for a one-time cost of $4,468 in Year 1 for the customization of the M&E Database for the project. The total estimated cost is $4,468.

M&E Materials: Based on prior experience on similar sized programs, POA is budgeting $850/year throughout the life of the project for expenses associated with M&E materials. The total estimated cost is $4,604.

M&E Training and Coordination Meetings: POA is budgeting $500/meeting for one (1) meeting per year in Years 1-5 for monitoring and evaluation of the project. The total estimated cost is $2,708.

Indirect Costs

While POA’s approved NICRA permits an overhead rate of 28.28% on total direct costs, we have elected to apply a reduced indirect rate to enhance the cost effectiveness of our project. Specifically, POA is applying a 20% indirect cost rate on all direct costs. POA’s senior management approved this approach, and it reflects our commitment to responsible stewardship of project resources without compromising operational integrity. In preparing the budget, POA has minimized administrative and support costs for managing the project to the extent possible to maximize the funds available for project activities while still ensuring overall award compliance and capacity building for implementing partners.

| Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- |
| $66,655 | $93,631 | $101,095 | $99,464 | $55,822 | $416,667 |

Total project costs:

Year 1: $399,930

Year 2: $561,786

Year 3: $606,568

Year 4: $596,784

Year 5: $334,932

Project Grand Total: $2,500,000