## Original
Project Title: Ñangareko Hağua - Partners of the Americas
Activity | Responsible | 2025 | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030
|  | Oct-Dec | Jan-Mar | Apr-June | July-Sept | Oct-Dec | Jan-Mar | Apr-June | July-Sept | Oct-Dec | Jan-Mar | Apr-June | July-Sept | Oct-Dec | Jan-Mar | Apr-June | July-Sept | Oct-Dec | Jan-Mar | Apr-June | July-Sept
Objective 1: Increase comprehensive services for adult trafficking victims, particularly men, through the provision of shelter, trauma-informed mental health counseling, and medical and legal assistance.
Activity 1.1: Identify Relevant Institution to Provide Care for Adult Male Victims of Trafficking. | Partners, Project Coordinator and Technical Specialist
Activity 1.2: Sign Agreements with Governmental Institutions to Create Shelter. | Partners, Project Coordinator and Technical Specialist
Activity 1.3: Establish Adult Male Victims of Trafficking Shelter. | Project Coordinator and Technical Specislist
Activity 1.4: Develop an Adult Male Trafficking Victim Care Manual. | Technical Specialist and Technical Consultants
Activity 1.5: Train Stakeholders on the Adult Male Trafficking Victim Care Manual. | Technical Specialist and Technical Consultants
Objective 2: Enhance and implement the use of existing protection SOPs to provide trauma-informed and victim-centered care to adult victims of trafficking.
Activity 2.1: Increase the Board’s Inter-Institutional Coordination Capacity. | Partners, Project Coordinator and Technical Specialist
Activity 2.2: Train Relevant Institution Staff on Existing SOPs for Victim Care. | Technical Specialist and Technical Consultants
Objective 3: Build the Capacity of Non-Specialized Shelters to Support Adult Male Trafficking Victims.
Activity 3.1: Map Existing Organizations Providing Shelter or Similar Services. | Project Coordinator and Technical Specialist
Activity 3.2: Provide Technical Assistance for Internal Regulatory Adjustments in Alternative Shelters. | Technical Specialist and Technical Consultants
Activity 3.3: Train Staff at Identified Establishments for Proper Case Handling. | Technical Specialist and Technical Consultants
Activity 3.4: Develop a Network of Alternative Shelters. | Partners, Project Coordinator and Technical Specialist
Monitoring and Evaluation (General)
Conduct M&E Training with project staff | Partners, Project Coordinator and M&E Coordinator
Conduct baseline assessment | Partners, Project Coordinator and M&E Coordinator
Hold coordination meetings with relevant stakeholders to monitor project progress and make adjustments | Partners, Project Coordinator and M&E Coordinator
Monitor project activities | Partners, Project Coordinator and M&E Coordinator
Conduct Midterm Evaluation | Partners, Project Coordinator and M&E Coordinator
Conduct Final Evaluation | Partners, Project Coordinator and M&E Coordinator
Closing of project activities | Partners, Project Coordinator and M&E Coordinator