# Partners of the Americas Inc.

# Food for Progress Program Nigeria

# C-2 – FY 2025 BUDGET NARRATIVE

| Program | Food for Progress |
| --- | --- |
| Country | Nigeria |
| Fiscal Year | 2025 |
| Organization | Partners of the Americas, Inc. (UEI: DD5WNYRUYFE5) |
| Point of Contact | Carmen Pena, cpena@partners.net |

Section 1: General Explanatory Comments

Partners of the Americas Inc. (POA) will implement a four-year Food for Progress (FFPr) Program project in Nigeria. The total federal award amount is $26,360,000. This includes commodity ($20,610,000), freight ($4,750,000), and administrative costs (cash portion) ($1,000,000). The total operating budget (grand total costs) for this project is $12,716,554.54, which includes $347,715.54 in cost share. POA expects interest on proceeds to be $578,839. The budget narrative describes the operating budget and does not describe the commodity and freight portions of Federal funding.

Gross Monetization Proceeds*	$11,368,839

CCC Admin Funds	 $1,000,000

Cost Share	$347,715.54

Total	$12,716,554.54

*Including anticipated interest

| Summary of Total Project Operating Budget (Includes Cost Share) |  |
| --- | --- |
| Administration | $2,116,753.69 |
| Activities | $9,164,710.13 |
| ICR on Administration | $317,513.05 |
| ICR on Activities | $1,117,577.66 |
| Total | $12,716,554.54 |

| Summary of Total Indirect Costs Applied (excludes Cost Share) |  |
| --- | --- |
| Total Administration Direct Costs | $2,116,753.69 |
| Total Activities Direct Costs Less Subawards | $6,254,850.54 |
| Total Activities Direct Costs Subawards Only | $2,562,144.05 |
| Indirect Costs Applied on Administration 15% | $317,513.05 |
| Indirect Costs Applied on Activities Less Subaward 15% | $938,227.58 |
| Indirect Costs Applied on Activities Subaward Only 7% | $179,350.08 |
| Total Indirect Costs | $1,435,090.72 |

| Summary of M&E (Monitoring & Evaluation) Budget (Excluding M&E Personnel & Travel) |  |
| --- | --- |
| Evaluations (Baseline, Midterm, & Final) | $485,000 |
| Monitoring Guidelines Creation & Printing | $2,000 |
| Monitoring Guidelines Revision & Printing | $3,000 |
| Monitoring Guidelines Staff Training on Indicators and Data Collection/Analysis | $10,000 |
| M&E Database Platform Subscription (includes training) | $33,500 |
| Total M&E Budget | $533,500 |
|  | 4.31% |

POA considers Monitoring & Evaluation (M&E) a vital element for the effective implementation of programs; consequently, POA has allocated 4.31% ($533,500) of the total operating budget (excluding cost share) to M&E-related activities. In the field, POA will employ a dedicated M&E Director and Specialist, each committed at 100% Level of Effort (LOE) throughout the five-year duration of the project. Furthermore, POA will establish a comprehensive system for M&E assessment, tracking, and dependable data collection. This system will encompass costs related to external third-party evaluations, a specialized study, training on M&E guidelines, licensing and deployment of M&E software, and site visits for data collection. Additionally, POA will leverage its prior experience in data collection by providing materials, tools, and other resources to support staff in managing M&E aspects of the project.

# Budget Assumptions and Cost Escalations

POA has established a local hire pay scale for Nigeria in accordance with market rates for the level of experience and education required. The salary scale for local hires was established based on comparable organizations and projects, information gathered from in-country consultants, online research, and market analysis for similar positions and experience levels. POA has applied a 5% increase to account for inflation and a 5% increase for merit-based salary increases for all Home Office (HO), and Cooperating Country National (CCN) staff after Year 1 (Y1), in accordance with POA policy. Actual annual increases will range from 1%-5% and are based on an annual performance review. Expenses for travel, supplies, and office expenses include a yearly escalation for inflation after Y1. Inflation is estimated at 5% annually after Y1.

Local travel costs for both international and domestic in-country transportation are budgeted based on local prevailing transportation rates. For international and domestic in-country lodging, it is based on market prices, POA’s experience, and are set well below the U.S. Department of State Standardized Regulations (DSSR) per diem rates and the General Services Administration (USA rates). Meals and incidentals (M&IE) for international (non-US) and domestic in-country travel is based on a reduced rate of the DSSR M&IE diem thresholds and in accordance with POA policy. M&IE for travel to the US is based on a reduced amount of the GSA per diem thresholds and in accordance with POA policy. International air travel is budgeted based on the prevailing cost of roundtrip economy-class tickets for the proposed routes and will be Fly America Act compliant.

# Financial Capacity

POA has implemented rigorous financial management and internal control systems specifically designed to support the detection and prevention of fraud, waste, and abuse of U.S. Government resources. These systems include segregation of duties, multi-level review and approval processes, real-time expenditure tracking, automated alerts for irregularities, and periodic internal checks. POA uses Sage Intacct, a secure, cloud-based accounting platform that ensures transparent, auditable, and timely financial reporting. This enables automated workflows, role-based access controls, and detailed documentation of all transactions, which help identify anomalies, enforce compliance, and deter misuse of funds. To further reinforce accountability, POA is subject to an annual Single Audit under 2 CFR 200 Subpart F and conducts routine internal reviews and spot checks at both home office and field levels. All staff with financial responsibilities receive regular training on fraud prevention, U.S. Government cost principles, and POA’s internal policies. Preventive measures include monthly financial reviews with project directors, oversight of procurement and subawards, ongoing reconciliation of accounts, and detailed documentation of all expenditures. These processes create multiple checkpoints that enable early detection of discrepancies or noncompliance. The Finance and Administration (F&A) department is staffed by experienced professionals with over 50 years of experience in financial oversight. This team works with project and country teams to monitor spending, confirm the allowability and allocability of costs, and ensure full compliance with 2 CFR 200, local regulations, and POA’s policies.

# Cost Application Methodology

POA uses a robust and cost-effective strategy to determine cost allocation in accordance with USG cost principles, local laws, and internal policies. Our proposed budget for this project was developed by conducting thorough price analyses to identify reasonable, realistic, and fair market values for all projected expenses. Our budget estimates were also calculated based on past experience implementing effective and cost-efficient USG-funded programs. POA follows U.S. and local labor laws to determine salary and fringe benefits for all employees in this application.

While POA’s approved NICRA permits an overhead rate of 28.28% on total direct costs, we have elected to apply a reduced indirect rate to align with the NOFO’s administrative cost limitations and enhance the cost competitiveness of our application. Specifically, POA is applying a 15% indirect cost rate on all direct costs except subawards, to which a reduced 7% indirect cost rate is applied to maximize direct activities. This rate, well below our NICRA, covers the minimal, distinct costs of subaward monitoring and compliance required under 2 CFR 200.331-333, including risk monitoring and auditing of subrecipients. This approach was approved by POA’s senior management and reflects our commitment to responsible stewardship of project resources, ensuring costs remain allowable, allocable, and reasonable without compromising operational integrity. POA acknowledges that this reduced indirect cost rate is binding. POA will continue to use this rate throughout the life of project.

In preparing the budget, POA has minimized administrative and support costs for managing the project to the extent possible to maximize the funds available for project activities while still ensuring overall award compliance and capacity building for implementing partners. As a result, 71.28% of the operating budget will be directed towards activities and 28.72% to administration and indirect costs.

# Budget Components and Project Implementation

The proposed budget is designed to ensure cost-effective, compliant, and high-impact implementation of the FFPr Nigeria project. Budget estimates are based on thorough price analysis and verified prior costs from similar donor-funded programs and were developed in alignment with 2 CFR 200, local regulations, and POA’s policies. The budget reflects a disciplined approach to resource allocation, ensuring cost realism, fairness, and strong return on investment.

Activity 1 increases agricultural productivity and trade through livestock production by increasing technical capacity, access to finance, and use of ICT. The project adequately funds training through a subaward to USSEC. The funding will boost productivity, improve feed formulation, and access to finance for poultry and aquaculture farmers. Activity 2 improves trade finance capacity to increase US exports to Nigeria through capacity building with US exporters and Nigerian importers/financial institutions and targeted grants. Funding supports training, conferences, grants, and pilot financing. Activity 3 expands trade by reducing non-tariff trade barriers. Funding supports key SPS system updates, audits, and action plan development. To meet USDA cost expectations, POA applies a reduced indirect cost rate, directing over 70% of the budget to project activities. The grant mechanism is structured to maximize return on investment by mandating the purchase of US equipment and inputs and requiring a minimum of 50% in co-investment.

# Cost Effectiveness

The POA budget is structured by activity to support the project's three core components, focusing on cost-effectiveness and operational efficiency. FFPr Nigeria’s budget was designed to minimize waste, leverage existing investments, and capitalize on government and private sector interest. The project will work with existing local service providers with proven expertise and equipment to deliver livestock productivity training, ensuring technical rigor and resource optimization. Additionally, the project uses USSEC’s existing high-quality poultry and aquaculture technical packages, leading to cost effectiveness. Collaborating with agribusinesses using contract farming or out-grower schemes allows POA to target pre-vetted, high-potential producers, enhancing impact and saving time. FFPr Nigeria will also provide larger grants to integrated companies to increase operational efficiencies, avoiding giving small grants to producers. The project also benefits from the FFPr Nigeria consortium’s established relationships in Nigeria, enabling swift re-engagement with key stakeholders like the Ministry of Agriculture, financial institutions, and agricultural service providers, minimizing start-up and admin costs.

All budgeted costs are reasonable, necessary, allocable, and directly aligned with the Plan of Operations. Each cost is justified in terms of its necessity for project success. They are supported by quotes, research, and POA’s local experience to ensure fair market value. This ensures that resources are utilized responsibly, promoting transparency and accountability in expenditures.

# Anticipated Interest Earned

FFPr Nigeria expects that interest accrued on monetization proceeds will be $578,839 over the life of the project (LOP) based on an investment of the fund in an interest-bearing account with Bank of America. Based on current quotes, the compounding interest rate for a separate interest-bearing savings account with Bank of America is 2.50%.

# Management of Monetization Proceeds

Payment will be secured and received from the buyer(s) through an irrevocable Letter of Credit from trusted banks. Upon receipt, funds will be deposited into a separate U.S.-based, interest- bearing USD account managed by POA’s CFO, with secondary control held by POA’s CEO/President. Disbursement will occur only upon approval from the Senior Program Director, via funding request, and after review by the CFO. Monetization proceeds will be released solely for immediate, approved project needs. The CFO oversees award administration, accounting, internal controls, and financial reporting, with compliance support from the Grants and Contract Compliance Unit, which conducts spot checks and annual internal audits. POA also undergoes an annual external audit covering all accounts and fund disbursements.

# Section 2: Administration

Total Administration Costs: $2,434,267 ($1,434,267 in monetization, $1,000,000 in CCC funds, $0 in cost share)

- Total Direct Costs: $2,116,754 ($1,247,189 in monetization, $869,565 in CCC funds)

- Total Indirect Costs: $317,513 ($187,078 in monetization, $130,435 in CCC funds

Salaries/Personnel - Total $363,547 ($98,892 monetization, and $264,655 in CCC funds) Cooperating Country National (CCN) – Chief of Party. Budgeted at 50% LOE in Y1 and 5% LOE in Y 2-4, the Chief of Party (COP) will be a Nigerian national and seasoned agribusiness professional a minimum of 8 years of experience in agribusiness value chain development, food systems, market systems, and private sector agricultural initiatives. The position is budgeted to remain on the project through the LOP and will oversee a team of experts and support staff, prepare reports and work plans, and align project initiatives. The COP is a key personnel position with a monthly base salary of $9,583. POA conducted due diligence to verify experience, prior salary, and compensation history to determine a reasonable salary. Additionally, the salary falls within POA’s standard salary scale for COPs.

CCN Staff. CCN staff include the following:

Technical Director: oversees and integrates technical approaches across poultry, aquaculture, trade finance, and non-tariff barrier activities. Adapts strategies to field conditions, leads cross-sector collaboration, and ensures high-quality assistance that supports sustainable livestock growth and expands US exports.

Technical Lead: Activity 2 US Exports: focuses on expanding market access by promoting trade finance tools, organizing buyer connections, and using ICT to link US producers with Nigerian buyers.

Technical Lead: Activity 2 Access to Finance Specialist: concentrates on improving credit availability and financial tools for producers and agribusinesses, supporting contract farming models and strengthening trade facilitation.

Communications/Strategic Partnerships Manager: develops outreach and engagement strategies connecting government, private sector, and producers to share project knowledge and sustain impact. Builds partnerships and promotes achievements through media while ensuring USDA-compliant, transparent communications.

M&E Director: leads overall monitoring strategies, integrating data from all activities to assess project impact and guide adaptive management with comprehensive reports and evaluations.

M&E Specialist: handles day-to-day data collection, indicator tracking, and data quality assurance, providing timely insights to support decision-making and ensure consistent performance measurement.

Finance & Administration (F&A) Director (Key Personnel): leads overall financial planning, budgeting, and compliance, ensuring project funds in the field office are efficiently allocated to priority activities while adhering to USG and local regulations.

Accountant: handles daily financial transactions, verifies expenditures, and maintains accurate records to support transparent and compliant financial management.

Administration/ HR Manager: manages recruitment, oversees staff retention, manages the office, and serves as the logistic coordinator for field operations.

Grants & Contracts Manager: oversees sub-grants and contracts to ensure partners deliver services in line with USDA regulations, maintaining fiscal stewardship and program quality through effective grant management.

Compliance & Procurement Specialist: manages procurement and compliance processes, ensuring timely acquisition of necessary inputs and equipment while strictly following USG, USDA, and local laws to support uninterrupted project implementation.

Driver: provides safe and reliable transportation for project staff and materials, ensuring timely support for field activities and operational continuity.

CCN staff salary is distributed between Administrative and Activities as appropriate for each role. The proposed salary rates align with market research, benchmarking analysis, and local in-country consultations.

Home Office (HO) Staff. POA HO salary rates are based on the current annual salaries of staff, POA’s salary matrix, and industry benchmarking surveys.

The Senior Vice President of Programs will lead the POA HO team, provide executive oversight and strategic direction to ensure alignment with donor priorities and organizational objectives. This person will be the key liaison with USDA/FAS for high-level communications, risk management, and issue escalation, and serve as a Washington, D.C. point of contact with government officials in Nigeria. This role ensures donor relations are proactively managed, program strategies stay aligned with priorities, and organizational policies and compliance frameworks are upheld. By reviewing major deliverables and validating staffing and budget decisions, the Senior Vice President promotes transparent decision-making and protects against fraud, waste, and abuse.

The Senior Program Director, who leads POA’s Agriculture and Food Security unit, manages both the HO and field teams involved in the project’s interventions and technical support. This director does not oversee POA’s entire USDA portfolio, as other units like Education, which manages programs such as McGovern-Dole requiring different technical expertise and operate independently. The Senior Program Director serves as the primary HO technical lead and counterpart to the Chief of Party and Technical Director. This position is dedicated to technical leadership, overseeing program performance, ensuring timely approvals of work plans and monitoring & evaluation (M&E) indicators, and coordinating troubleshooting efforts to maintain steady progress. This role also mentors technical leads and engages key U.S. and Nigerian stakeholders to align policies and resources specifically with the program’s goals. As POA manages subawards entirely out of HO, this position will oversee the technical management of the two subawards under this FFPr program. This includes tracking targets for subaward technical implementation, reviewing monitoring and evaluation (M&E) data for accuracy and consistency, and leads narrative report writing to fulfill USDA reporting requirements.

The Associate Director will serve as the primary day-to-day support to the field team and assists with achieving programmatic, financial, and administrative backstopping. The Associate Director focuses on day-to-day operational support and coordination of implementation schedules, deliverables, and technical workstreams. Serves as the vital link between project teams and POA’s compliance, contracts, and technical units, ensuring timely support. This position supports M&E data cleanup and provides review and training on administrative and contractual matters related to the two subawards under this program. The Associate Director also contributes to knowledge management, and learning agenda execution, providing detailed operational oversight that enables senior leaders to concentrate on strategic and technical leadership.

The Compliance and Contracts Director, serves as the programmatic lead for regulatory compliance, procurement, vendor vetting, policy development and revision, and contracting. Ensuring that all project activities adhere to 2 CFR 200 and USDA/FAS-specific requirements, oversees audit readiness, and provides ongoing training to field teams to mitigate compliance risks. The role also ensures that subrecipient performance is monitored for compliance with federal guidelines, providing corrective actions as needed. This position is particularly critical given the difficult compliance operating conditions in Nigeria. For that reason, this position is budgeted at a higher level of effort.

The Finance, HR, and Administration Home Office Support ensures smooth operational support aligned with project priorities. Their responsibilities include budgeting, grant reporting, record retention, field and home office expense report auditing, vendor management, HO payroll processing, training for HO and FO on HR and financial functions, processes, and policies, and general administrative/logistical support to sustain both field and home office functions. This role combines multiple functions into a blended salary. All efforts will be directly aimed at the program and will be properly documented. As such, the direct charge reflects the specific time devoted solely to project activities, distinguishing these efforts from general organizational support, and ensuring that costs are reasonable, properly allocated, and consistent with federal expectations.

# Fringe Benefits – Total $95,688 ($26,907 in monetization, and $68,781 in CCC funds) Fringe Benefits CCN Nigeria

Fringe benefits for CCN staff are budgeted at 29.60%. These percentages are based on local labor law, in-country required benefits, and POA's fringe benefit policy. This includes:

    - 10.00% - Pension (applicable to employers with more than fifteen employees)

    - 1.00% - National Social Insurance Trust Fund (NSITF) (Work Injury Insurance)

    - 1.00% - Industrial Training Fund (ITF)

    - 5.77% - 21 days of annual leave a year

    - 8.33% - 1 month of severance for every year of service

    - 0.50% - Life insurance

    - 3.00% - Private health insurance

Total CCN Fringe Administrative Benefits = $50,042

Fringe Benefits – HO

POA charges HO fringe benefit costs in accordance with POA’s personnel policy and its

NICRA letter. POA has budgeted a 23.47% fringe rate on HO salaries. Fringe benefits include insurance, mandatory taxes, pension, and other employee benefits. Total HO Fringe Benefits are $45,646. Fringe benefits percentage breakdown is as follows:

| HO/USN Fringe Breakdown | Percentage |
| --- | --- |
| U.S. Payroll Taxes | 7.86% |
| Medical Insurance | 9.04% |
| Life Insurance | 0.14% |
| AD&D and Disability Insurance | 0.16% |
| Retirement Pension | 6.17% |
| Transportation Benefits | 0.10% |

  - Travel – Total $240,863 ($180,727 in monetization and $60,136 in CCC funds) International Travel ($45,267). POA HO staff will undertake 9 international trips from Washington, DC to Nigeria during the LOP, with three trips in Y1 and 2 trips in Y2-Y4. The additional trip in Y1 is planned to facilitate a rapid project start-up. These trips will focus on monitoring, oversight, and providing technical guidance. Conversely, Nigeria staff will make 12 international trips to the USA during the same period to hold meetings and participate in technical trainings and conferences, with at least 6 of these trips involving COP and Technical Director travel to HO in Washington, DC. The total estimated cost is $45,267 for 21 international flights ($1,800/fight for 6 flights in Y1 and 5 flights annually in Y2-Y4). Flight costs are based on current quotes for economy airfare, complying with the Fly America Act. Additionally, POA is budgeting ground transport for HO Project Management travel in Nigeria, estimated at $150/trip (3 trips/year in Y1 and 2 trips/year in Y2-Y4), and ground transport for Nigeria staff travel in the US, estimated at $250/trip (3 trips/year in Y1-Y4).

Local Travel ($43,446). POA estimates $43,446 for administrative local travel carried out by CCN staff. This includes roundtrip domestic airfare ($250/trip) and local transport ($30/trip) for a total of 36 trips/year in Y1-Y4 for program oversight, training and events, and M&E and data collection. Local travel rates are based on POA’s internal travel policy and represent a reasonable local rate in Nigeria. Flight costs are based on current quotes for economy airfare, complying with the Fly America Act.

Vehicle Fuel ($2,136). POA estimates the cost for fuel for 1 vehicle to be $50/month. The total cost estimate for 39 months is $2,136. This is based on POA’s experience implementing similar projects in the region.

Per Diem & Lodging (150,014). POA is estimating $29,871 in lodging & M&IE for HO Project Management travel to Nigeria ($311/day for 30 days in Y1, and for 20 days in Y2-Y4) as well as other travel related expenses ($150/trip) for 3 trips/year  in Y1 and 2 trips in Y2-Y4. Visa costs at ($160/visa) are budgeted for 6 HO staff over the LOP. Other travel related expenses include fees estimated for roundtrip baggage and required immunizations. Lodging & M&IE for Nigeria staff travel to the US is estimated at $263/day, for a total of 21 days/year in Y1-Y4. Visa costs for these trips are estimated at $185/trip, and other travel related expenses at $150/trip, for a total of 3 trips/year in Y1-Y4. Additionally, POA is budgeting for lodging and M&IE for domestic travel associated with training, M&E, and data collection at a rate of $146/day, for a total of 144 days/year in Y1-Y4. Lodging/travel expenses based on market quotes; per diem on reduced DSSR/GSA rates.

# Professional Services/Contractual – Total $992,893 ($641,326 in monetization, and 351,567 in CCC funds)

Monetization Agent Fee ($180,193). The Monetization Agent fee is estimated at 1.67% of monetization proceeds received for $180,193, based on provider quote and contract.

Monetization Impact Assessment ($60,000). POA estimates $60,000 for a monetization impact assessment to evaluate the market impact of the monetization. Based on cost for assessment paid in Nigeria under prior USDA program.

Support Services ($219,200). POA has included expenses related to support services over the life of the program. These costs are directly attributable to the project. POA included single audit fees ($52,000). These audit fees are allocable to a particular Federal award if the goods or services involved are chargeable or assignable to that award in accordance with the relative benefits received. This single audit fee is a portion of the total single audit cost that is directly related to the FFPr Nigeria program. Therefore, it can be charged directly to the project, proportionately, as costs are allocated based on each award’s share of total Federal expenditures during the audited period. This audit is required under 2 CFR 200 Subpart F and directly supports the project by ensuring financial integrity, compliance with federal regulations, and accurate reporting of project funds, making the cost reasonable, allowable, and allocable. The cost represents approximately 15% of the annual audit cost. Other support services include payroll and accounting fees ($96,000); legal fees ($12,000); IT services and management ($24,000); security services, risk assessments, and security assessments, ($4,000). POA has also included expenses for short-term administrative support consultants ($31,200) to support LOP administration. These experts support critical functions including establishing financial and HR systems, guiding local hiring and regulatory compliance as needed throughout LOP, and identifying necessary local services needed over LOP to ensure a compliant and effective project. The rate for administrative support consultants is based on a daily rate of $520 and an average of 15 days a year. These highly qualified US-based consultants have over 5 years of project administration experience. The proposed rate aligns with market rates for similar services and prior costs paid by POA.

Evaluations ($485,000). POA estimates external evaluation fees for the Baseline, Midterm, and Final Evaluations to be $150,000, $160,000, and $175,000, respectively. POA will host an open procurement to select an external evaluator for the evaluations. POA will consider factors such as the soundness of the proposal, unique capabilities, cost, schedule, technical competency, and experience in Nigeria.

Monitoring Guidelines Development ($15,000). POA will develop, translate, and print M&E guidelines at a one-time cost of $2,000. To support adaptation, $1,000/year is budgeted in Y2-4 for revisions, translation, and reprinting. A specialized Humentum trainer will conduct staff training on project-specific M&E tools, guidelines, indicators, and data analysis, including updates. A total of $2,500 is budgeted annually to cover the trainer fee and carry out the training regularly to ensure staff are fully equipped to implement, monitor, and report on project activities effectively for an LOP total of $10,000.

M&E Database ($33,500). POA is budgeting for a cloud-based project-specific M&E database subscription under a service contract to manage project data and reporting efficiently. The total cost includes a one-time platform setup fee of $5,500, an annual $6,500 subscription fee (covering hosting, maintenance, and technical support), and an additional $500/year for ongoing user training and system updates provided by the database service provider. The $500 training component is part of the service package and covers periodic virtual sessions and updates delivered by the provider to ensure staff can effectively use new features and reporting functions. The $500/year is the fee for the trainer. To be more sustainable, POA has opted for a cheaper M&E platform than originally proposed that also includes a longer data retention period after the project ends.

# Equipment – Total $60,000 ($0 in monetization and $60,000 in CCC funds)

POA plans to purchase one 4x4 vehicle. Based on local quotes, POA estimates the cost at $60,000, including customs, taxes, and import fees. POA will follow USDA procurement guidelines and sourcing requirements. POA conducted a buy versus lease analysis and found it more cost- effective to purchase the vehicle given frequent travel for data collection, trainings, and site visits.

# Office – Total $276,326 ($229,221 in monetization and $47,105 in CCC funds)

HQ Office ($18,749). POA estimates HO banking & cash handling fees ($12,930) and IT/communications stipends for HO staff ($5,819). The HO banking & cash handling fees cover project-related banking transactions, including ACH/wire transfer fees, monthly bank maintenance fees, and other fees directly related to maintaining monetization proceeds and HO project transactions. POA's policy provides HO staff with an IT/communications stipend to cover reasonable costs associated with remote work, including personal cellphone, internet, and electricity to work remotely. This stipend is a direct project cost rather than an overhead expense because it directly supports staff whose time is charged to the project and ensures staff can maintain consistent communication, access project systems, and perform project duties efficiently. POA does not provide staff with organization-owed cell phones, mobile data plans, or office workspace. To reduce HO operational costs for rent, POA’s HO staff work remote. This stipend is required to ensure consistent internet and data connectivity given the remote nature of our HO operations. The stipend is applied proportionally to each project based on staff level of effort as shown in the table below.

| Staff Position | Monthly Stipend | LOE % | Total Monthly Amount |
| --- | --- | --- | --- |
| Senior Vice President of Programs | $50 | 5% | $2.50 |
| Senior Program Director | $50 | 25% | $12.50 |
| Associate Director | $50 | 100% | $50.00 |
| Compliance & Contracts Director | $50 | 25% | $12.50 |
| Finance, HR, & Administration Home Office Support | $50 | 70% | $35.00 |

Nigeria Office ($257,577). POA estimates the cost of its in-country office in Lagos to be $257,577. Nigeria-specific office expenses include communications costs (internet, phone, data); office rent (POA will rent a coworking space: shared offices providing desks, meeting rooms, and amenities) as a more cost-effective option that includes fully equipped work environments that reduce overhead and administrative burdens. This setup supports efficient project operations by allowing teams to focus on work without managing office infrastructure. POA is also budgeting other Nigeria-office expenses including courier fees/services & postage; recruitment/procurement advertising; meeting expenses for key stakeholder meetings outside of Lagos, specifically in Abuja (hourly rate for space & equipment); accounting platform (Sage Intacct and QuickBooks); and licenses & subscriptions for program management. Nigeria office expenses also include banking & cash handling fees. Estimated rates are based on POA’s regional experience and current market rates.

# Supplies – Total $15,669 ($5,323 in monetization and $10,346 in CCC funds)

Appliances ($8,687). POA plans to purchase 12 desktop/laptop computers for CCN staff at $600/laptop based on local quotes from Nigerian marketplace, JUMIA. POA is also budgeting for 2 all in one printers, photocopiers, and scanners; 1 projector and videoconferencing equipment; and office furniture for the Lagos office including shelves, filing cabinets and a safe for office storage. Based on market prices in Nigeria, estimated costs are $8,687.

Office Supplies ($6,982). The monthly consumable office supply cost is estimated at $135. The costs cover all necessary office supplies such as notebooks, pens, calculators, office bags, clip files, registers, photocopy paper, flip chart paper, markers, transparency paper, flip chart boards, etc. POA estimates are based on past experience with projects of similar size and market research.

# Other – Total $71,769 ($64,794 in monetization and $6,975 in CCC funds)

Training, Workshops, Conference and Registration Fees ($18,000). POA plans for three training, workshop, conference, and registration fees/year in Y1-Y4, at an estimated cost of

$1,500/training. Costs will cover registration for project staff to attend trainings on USG Rules and Regulations, program management, and technical conferences. These trainings, workshops, and conferences are aimed at building the technical and operational capacity of POA project staff to improve implementation of the project. The total estimated cost is $18,000.

Repair & Maintenance ($7,112). POA estimates repair and maintenance at $7,112 for the LOP. This includes equipment office repairs/maintenance ($4,310), and vehicle maintenance ($2,802).

Insurance ($46,657). POA estimates insurance, including property and liability insurance ($43,101) specific to the Nigeria office. The property & liability insurance protects the organization and staff against potential claims arising from project operations, including accidents, third-party damages, cybersecurity attacks, employment liability, and other risks, ensuring compliance with local regulations and safeguarding project assets and personnel. This is only the portion of the insurance which is specifically allocable to the Nigeria office. Additionally, annual vehicle registration ($108) and vehicle insurance ($3,448) is budgeted for a total of $46,657. This is based on current quotes for each insurance type.

# Indirect Costs – Administration – Total $317,513 ($187,078 for monetization and

$130,435 for CCC)

POA has elected to apply reduced indirect cost rates for administration costs to enhance cost competitiveness and ensure alignment with USDA’s expectations regarding administrative efficiency. A 15% indirect cost rate is applied to total direct administration costs, totaling $317,513 over LOP. All rates and applications are compliant with POA’s NICRA and U.S. government cost principles 2 CFR 200.414. This cost strategy prioritizes programmatic impact by ensuring that the majority of resources flow directly to field-level interventions.

# Section 3: Activities

Total – $10,282,288 ($9,934,572 in monetization and $347,716 in cost share)

    - Total Direct Costs: $9,164,710 ($8,816,994 in monetization funds and $347,716 in cost share)

    - Total Indirect Costs: $1,117,578 ($1,117,578 monetization funds)

# Activity 1: Increase Agricultural Productivity & Trade through Livestock Production – Total $3,479,474 ($3,439,474 in monetization funds and $40,000 in cost share)

## Salaries/Personnel – $645,471

CCN Staff – COP. The COP is budgeted at 20% LOE in Y1-Y3, and 30% in Y4, remaining throughout the LOP. The COP will be a Nigerian national and seasoned agribusiness professional with a minimum of 8 years of experience. The COP provides project oversight and management and maintains technical standards. The COP’s salary is distributed between Administration and Activities.

CCN Staff. The majority of CCN staff are budgeted to remain on the project throughout the LOP. CCN staff salaries are distributed between Administrative and Activities as appropriate for each role. The proposed salary rates align with market research, benchmarking analysis, and local in- country consultations that were conducted by POA.

HO Staff. POA HO salary rates are based on the current annual salaries of staff, POA’s salary matrix, and industry benchmarking surveys. The POA HO team will be led by the Senior Vice President of Programs and provide executive oversight and strategic direction to ensure alignment with donor priorities and organizational objectives. The Senior Program Director, who manages the HO and project teams involved in the project’s interventions, will provide technical oversight and support. The Associate Director will serve as the primary day-to- day support to the field team and assists with achieving programmatic, financial, and administrative backstopping. They will be supported by the Compliance and Contracts Director who serves as the programmatic lead for regulatory compliance, procurement, vendor vetting, policy development and revision, and contracting. The Finance, HR and Administration Home Office Support ensures smooth operational support aligned with project priorities.

## Fringe Benefits – Total $180,247

See Section 2.2 for details regarding Benefit rates.

## Travel – Total $81,799

Local Travel ($39,320). POA is estimating $13,716 in local transportation (taxis/Ubers) related to Activity 1, at $300/month for 42 months during the LOP. This budget will be utilized when the project vehicle is unavailable. POA is also budgeting $25,604 in domestic airfare and local transportation for staff to travel from Lagos to target regions for trainings under Activity 1, at

$250/trip for airfare and $30/trip in local transportation for 12 trips in Y1 and 24 trips/year Y2- Y4. These costs enable staff to deliver targeted training and technical assistance directly to livestock producer groups in key rural areas, supporting hands-on capacity building, improving livestock productivity, and facilitating access to trade finance. Local travel is vital to ensuring engagement with decentralized communities and achieving the activity’s goal of strengthening producer organizations and market linkages.

Vehicle Fuel ($2,563). POA estimates fuel for project vehicles at $60/month for 39 months over LOP. Rate is based on POA’s documented experience implementing similar USDA projects.

Per Diem & Lodging ($39,915). POA estimates lodging and M&IE for staff attending the trainings under Activity 1 at $80/day in lodging and $66/day in M&IE for 3 days/trip for 12 trips in Y1 and 24 trips/year in Y2-Y4.

## Professional Services/Contractual – Total $408,000

Contract for Nationwide Poultry Consumption Campaign ($400,000). POA will hire a consumer campaigns firm under a public relations contract to design and accompany the dissemination of a poultry consumption campaign in Y2-Y4. The campaign is a public awareness and behavior change activity directly linked to project objectives by promoting behavior change and increasing domestic demand for poultry. This will in turn strengthen market opportunities for U.S. agricultural exports. POA estimates $80,000 in Y2 and $160,000/year in Y3-Y4. This contract estimate is based on POA’s prior experience implementing similar campaigns.

Security Services, Risk Assessments, & Security Assessment ($8,000). POA will contract a firm to provide security services and conduct risk and security assessments under Activity 1 to ensure the well-being of staff and program participants, at $2,000/year throughout the LOP.

## Equipment – Total $0

None.

## Office – Total $0

None.

## Supplies – Total $0

None.

## Other – Total $2,123,957

Subrecipient: US Soybean Export Council (USSEC) ($2,123,957). POA will issue a subaward to USSEC to leverage its existing innovative and high-quality training technical packages to build the capacity of livestock producers and professionals. USSEC will lead the implementation of training to boost poultry and fish productivity, and to improve feed formulation. USSEC brings deep regional experience in Nigeria and expertise in differentiating, elevating preference, and securing market access for the use of US soy in aquaculture and livestock feed in 80 countries worldwide.

## Indirect Costs - $346,005

POA has elected to apply reduced indirect cost rates for Activity 1 to enhance cost competitiveness and ensure alignment with USDA’s expectations regarding administrative efficiency. A 15% indirect cost rate is applied to total direct activity costs (excluding subawards), totaling $197,328 over the life of the activity. For direct subaward costs, a further reduced rate of 7% is applied, totaling $148,677. All rates and applications are compliant with POA’s NICRA and US government cost principles 2 CFR 200.414. This cost strategy prioritizes programmatic impact by ensuring that a majority of resources flow directly to field-level interventions.

## Cost Share – Total $40,000

Public & Private Sector Support for Nationwide Poultry Consumption Campaign ($40,000). USSEC currently conducts a “Right to Protein” consumer campaign aimed at increasing consumption of animal products in Nigeria. FFPr Nigeria will scale the campaign, by aiming to increase the per capita consumption of poultry in Nigeria and in return drive US exports that serve the industry. USSEC will contribute cost share by providing training manuals and modules (~ 60%), as well as by directly investing additional funds to expand the campaign’s reach and impact (~ 40%). Estimated cost share from in-kind contributions were estimated based on USSEC’s experience developing and providing similar training modules. Cost share will total $8,000 beginning in Y2 and $16,000 spent in both Y3 & Y4 for a total of $40,000.

# Activity 2: Improve Trade Finance Capacity to Increase US Exports to Nigeria – Total

$4,590,116 ($4,282,400 in monetization and $307,716 in cost share)

## Salaries/Personnel – Total $1,470,861

CCN Staff – COP. The COP is budgeted at 20% LOE in Y1, 55% in Y2-3, and 60% in Y4, remaining throughout the LOP. The COP will be a Nigerian national and seasoned agribusiness professional with a minimum of 8 years of experience. The COP provides project oversight and management and maintains technical standards. The COP’s salary is distributed between Administration and Activities.

CCN Staff. The majority of CCN staff are budgeted to remain on the project throughout the LOP. CCN staff salaries are distributed between Administrative and Activities as appropriate for each role. The proposed salary rates align with market research, benchmarking analysis, and local in- country consultations that were conducted by POA.

HO Staff.  POA HO salary rates are based on the current annual salaries of staff, POA’s salary matrix, and industry benchmarking surveys. The POA HO team will be led by the Senior Vice President of Programs and provide executive oversight and strategic direction to ensure alignment with donor priorities and organizational objectives. The Senior Program Director, who manages the HO and project teams involved in the project’s interventions, will provide technical oversight and support. The Associate Director will serve as the primary day-to- day support to the field team and assists with achieving programmatic, financial, and administrative backstopping. They will be supported by the Compliance and Contracts Director who serves as the programmatic lead for regulatory compliance, procurement, vendor vetting, policy development and revision, and contracting. The Finance, HR and Administration Home Office Support ensures smooth operational support aligned with project priorities.

## Fringe Benefits – Total $409,128

See Section 2.2 for details regarding Benefit rates.

## Travel – Total $153,215

International Travel ($31,005). POA is estimating 50% of the costs (50% covered by participant) for US-Nigeria international airfare for American farmers, ranchers, and agricultural professionals to attend buyer conferences in Nigeria. International airfare is estimated at $900/trip for 10 trips/year in Y2-Y3 for a total of $19,373. POA is also estimating $11,633 in international airfare from the US to Nigeria for the Trade Finance and Export Consultant at $1,800/trip for 1 trip/year in Y1 and Y4, and 2 trips/year in Y2-Y3. Flight costs are based on current quotes for economy airfare complying with the Fly America Act.

Local Travel ($40,290). POA is estimating $13,716 in local transportation (taxis/Ubers) related to Activity 2, at $300/month for 42 months during the LOP. POA is also budgeting $25,604 in domestic airfare and local transportation for staff to travel from Lagos to target regions for trainings under Activity 2, at $250/trip for airfare and $30/trip in local transportation for 12 trips in Y1 and 24 trips/year in Y2-Y4. Local transportation is also included for the Trade Finance and Export Consultant while traveling in Nigeria at $150/trip for 1 trip/year in Y1 and Y4, and 2 trips/year in Y2-Y3. This budget will be used when project vehicle is unavailable and is based on POA’s internal travel policy, which reflects reasonable rates in each country. Flight costs are based on current quotes for economy airfare in compliance with Fly America Act.

Vehicle Fuel ($2,563). POA estimates fuel for the project vehicle at $60/month for 39 months over the LOP. The transport will be for implementation of Activity 2. The rate is based on POA’s documented experience implementing similar projects in the region.

Per Diem & Lodging ($79,357). POA is budgeting lodging and M&IE for staff attending trainings under Activity 2 at $80/day in lodging and $65.5/day in M&IE for 3 days/trip for 12 trips in Y1 and 24 trips/year in Y2-Y4. POA will cover 50% of lodging and M&IE for American farmers, ranchers, and agricultural professionals attending the buyer conferences. These are estimated at $90/day in lodging and $65/day in M&IE for a total of 7 days/trip for 10 trips/year in Y2-Y3, with participants covering the remaining 50%. Additionally, lodging and M&IE is budgeted for the Trade Finance and Export Consultant at $180/day in lodging and $130.5/day in M&IE for 7 days/trip for 1 trip/year in Y1 and Y4, and 2 trips/year in Y2-Y3.

## Professional Services/Contractual – Total $312,540

Contract for Trade Finance Capacity Building ($201,000). POA will contract a firm to build capacity of American producers and Cooperators in trade finance starting at $33,500 in 1, followed by $67,000/year in Y2-Y3 and $33,500 in Y4. The firm will provide training that combines trade finance education with Nigeria-specific market guidance on competitive pricing, transaction execution, and realistic return-on-investment expectations. This contract specifically will contribute to Activity 2.1.1: Deliver Trade Finance Capacity Building for American Producers and Cooperators within Activity 2. The Senior Program Director is responsible for coordinating and supervising the scope of work and overall activities related to this element with the firm.

## Expert Consultant on Trade Finance & Exports ($103,540)

POA will hire an US expert Trade Finance & Exports Consultant throughout the life of the agreement (LOA) to provide training and deliver workshops on Access to Finance for US Exports to Nigeria in Y1 at a rate of $620/day for 40 days in Y1; 45 days/year in Y2-3; and 37 days in Y4, for a total cost of $103,540. The proposed daily rate is estimated based on documented project management experience.

## Security Services, Risk Assessments, & Security Assessment ($8,000)

POA will contract a firm to provide security services and conduct risk and security assessments under Activity 2 at yearly rate of $2,000 during LOP to ensure the well-being of staff and program participants at a total cost of $8,000.

## Equipment – Total $0

None.

## Office – Total $0

None.

## Supplies – Total $15,545

Webinar Platform (Zoom) for Trainings ($15,545). POA is budgeting for Zoom platform fees for virtual trainings held under Activity 2, at an estimated rate of $340/month for 6 months in Y1 and 12 months/year from Y2-Y4. Rates are based on current market quotes.

## Other – Total $1,921,111

Trainings & Meetings ($176,111)

One-Day Workshops for Nigerian Banks and Importers on FAS Program ($3,438). POA is budgeting for 2 one-day workshops in Y1 for Nigerian banks and importers on key programs like USDA GSM-102. Estimated at $15/person for lunch/refreshments, $5/person for workshop materials, and $1,039/day for venue rental, for 30 participants and 4 staff.

One-Day Workshops for Nigerian Banks and Importers on Foreign Currency Risk ($3,438). POA is budgeting for 1 one-day workshop per year in Y2-Y3 for Nigerian banks and importers to manage foreign currency exchange risks. Estimated at $15/person for lunch/refreshments,

$5/person for workshop materials, and $1,039/day for venue rental, for 30 participants and 4 staff.

Three-Day Buyer Conferences ($150,000). POA is budgeting for one three-day buyer conference per year in Y2 and Y3 to forge connections between American exporters and Nigerian importers. Each conference will host approximately 375 participants for an average per-participant cost of $67/day over the three days. Estimated at $75,000/conference, this will include venue rental and conference setup, coffee breaks, interpretation and translation services, promotional materials and event visibility, domestic and international travel support for targeted buyers (service provider to assist with coordinating local ground transportation, airport transfers, and hotel arrangements for participants), and event planning services (service contract to an event management firm to handle logistics, registration, and on-site support). This event estimate was based on POA’s prior experience implementing similar sized events.

| Cost Category | Estimated Cost (per conference) |  |
| --- | --- | --- |
| Venue Rental & Setup |  | $30,000 |
| Coffee Breaks |  | $7,000 ($6.22/day/participant) |
| Interpretation & Translation |  | $8,000 |
| Promotional Materials & Event Visibility |  | $10,000 |
| Domestic & International Travel Support |  | $10,000 |
| Event Planning Services |  | $10,000 |
| Total |  | $75,000 |

One-Day Workshop for Institutions, Ministries, and Private Sector ($1,824). POA is budgeting for a one-day workshop in Y1 to identify and prioritize financing solutions for Nigerian buyers/importers. Estimated at $15/person for lunch/refreshments, $5/person for workshop materials, and $1,044/day for venue rental, for 35 participants and 4 staff.

Ongoing Technical Assistance for Access to Local Trade Finance ($17,411). POA is budgeting for 1 training in Y1, 11 trainings in Y2, and 12 trainings in Y3 to provide technical assistance to key importers to ensure uptake of local trade finance, as well as to provide targeted training to recipients of small grants to leverage grants to access other existing financing. Estimated at $15/person for lunch/refreshments, $5/person for workshop materials, and $517/day for venue rental, for 18 participants and 2 staff.

Agribusiness Grants ($1,300,000). POA is budgeting for a co-investment grant mechanism for agribusinesses with existing out-grower schemes and/or distribution networks in poultry and aquaculture value chains. Each grant will average $50,000, each  will require a co-investment of at least 20%.  ,

Depending on the grantees' capacity to directly acquire commodities, equipment, and/or technology, the grant may be provided as an in-kind grant or as cash grant. "In-kind grant” refers to a grant implementation approach where POA uses USDA project funds to directly purchase eligible U.S.-origin commodities, supplies and/or agricultural inputs, or technologies on behalf of the grantee, rather than providing the grantee with cash to make these purchases themselves. This mechanism ensures proper use of USDA funds, achieves greater cost efficiency through bulk or consolidated procurement. In these cases, POA would manage the full procurement process, identifying suppliers, obtaining quotes, and purchasing the goods directly using USDA funds. The procured supplies or technologies would then be delivered to the grantee as a contribution equivalent to the grant value.

The grants mechanism will support four broad areas: (1) aggregate importers for bulk U.S. commodity purchases; (2) build facilities and distribution for perishable goods; (3) provide financing to boost U.S. commodity and equipment purchases; and (4) offer technical support to improve productivity and input use. POA plans to award 26-30 grants from Y2- Y4 with an estimated $325,000 awarded in Y2, $650,000 in Y3, and $325,000 in Y4. With twice as many grants to manage, the home office must dedicate additional resources to ensure each grant is properly vetted, contracts are accurately executed, and funds are used efficiently and in compliance with program requirements.

Small Grants for Producers & Processors ($442,000). POA is budgeting for a small grant mechanism for small and medium-scale poultry and aquaculture producers and processors. Each grant will average $13,000 and will not require a co-investment to increase the range of eligible applicants. However, recipients will be required to attend access to ongoing local financing trainings as a condition of their award, which will enable them to leverage their grants to access additional financing. The small grants mechanism will support three purposes: (1) adoption of good agricultural practices and U.S. agri-technologies to enable recipients to improve input, on-farm infrastructure, and equipment; (2) expand use of ICT solutions to improve poultry and aquaculture productivity and/or trade readiness; and (3) test emerging ICT technologies in low-risk environments. POA plans to award 34 grants from Y2-Y3, with an estimated $221,000 awarded in each year.

## Communications ($3,000)

POA is estimating costs for the transparent release and outreach of grant-related solicitations through digital and print distribution, maximizing response among local and regional stakeholders. This includes $1,000/year in Y2-Y4 for Co-Investment Agribusiness Grants RFPs and Small Grants for Producers & Processors RFPs.

## Indirect Costs - $642,360

POA has elected to apply reduced indirect cost rates for Activity 2 to enhance cost competitiveness and ensure alignment with USDA’s expectations regarding administrative efficiency. A 15% indirect cost rate is applied to total direct activity costs (excluding subawards), totaling $642,360 over the life of the activity. All rates and applications are compliant with POA’s NICRA and U.S. government cost principles 2 CFR 200.414. This cost strategy prioritizes programmatic impact by ensuring that the majority of resources flow directly to field-level interventions.

    - Cost Share – Total $307,716

# Co-Investment Agribusiness Matching from the $1,300,000 in Grants ($260,000)

Private sector agribusinesses that receive an agribusiness grant will be required to provide co-investment. A portion of which POA estimates as cost share. The total estimated co-investment on these grants is $260,000. Grant recipients will be required to provide a minimum of 20% co-investment (matching funds) relative to their grant amounts. This requirement will be a condition of their grant agreements specifying co-investment terms, with monitoring through regular progress reports and financial documentation reviews. The $260,000 estimate is based on projected grant sizes and recipient capacities to provide this level of matching contribution. Non-compliance with co-investment requirements may lead to suspension or withholding of grant disbursements.

# [PENDING] Buyer Conferences for American Farmers, Ranchers and Agricultural Professionals (Nigeria-USA) - 50% of Cost ($47,716)

Partner organizations contribute 50% of costs in Y2-Y3, covering: Round Trip Travel: 10 trips/year at $900/trip (Total: $19,373); Lodging & M&IE: 70 days/year at $155/day (Total: $23,392); and Ground Transportation: 10 trips/year at $75/trip (Total: $1,614). Partner organizations will also cover the full portion of their multi-entry visa fees for Nigeria-US at 10 trips/year at $155/trip (Total: $3,336) for a complete total of $47,716.

# Activity 3: Expand Trade by Reducing Non-Tariff Trade Barriers – Total $1,095,120 ($1,095,120 in monetization funds)

## Salaries/Personnel – Total $471,181

CCN Staff – COP. The COP is budgeted at 10% LOE in Y1, 20% in Y2-Y3,and 5% in Y4, remaining throughout the LOP. The COP will be a Nigerian national and seasoned agribusiness professional with a minimum of 8 years of experience. The COP provides project oversight and management and maintains technical standards. The COP’s salary is distributed between Administration and Activities.

CCN Staff. The majority of CCN staff are budgeted to remain on the project throughout the LOP. CCN staff salaries are distributed between Administrative and Activities as appropriate for each role. The proposed salary rates align with market research, benchmarking analysis, and local in-country consultations that were conducted by POA.

HO Staff. POA HO salary rates are based on the current annual salaries of staff, POA’s salary matrix, and industry benchmarking surveys. The POA HO team will be led by the Senior Vice President of Programs and provide executive oversight and strategic direction to ensure alignment with donor priorities and organizational objectives. The Senior Program Director, who manages the HO and project teams involved in the project’s interventions, will provide technical oversight and support. The Associate Director will serve as the primary day-to- day support to the field team and assists with achieving programmatic, financial, and administrative backstopping. They will be supported by the Compliance and Contracts Director who serves as the programmatic lead for regulatory compliance, procurement, vendor vetting, policy development and revision, and contracting. The Finance, HR and Administration Home Office Support ensures smooth operational support aligned with project priorities.

## Fringe Benefits – Total $128,713

See Section 2.2 for details regarding Benefit rates.

## Travel – Total $49,039

Local Transportation ($26,518). POA is estimating $13,716 in local transportation (taxis/Ubers) related to project implementation activities under Activity 3, at $300/month for 42 months over the LOP. This budget will only be used if the project vehicle is unavailable. POA is also budgeting

$12,802 in roundtrip domestic airfare and local transportation for staff to travel from Lagos to implementing regions for trainings under Activity 3. Airfare is estimated at $250/trip and local transportation at $30/trip for 6 trips in Y1 and 12 trips/year in Y2-4. Local travel rates are based on POA’s internal travel policy and represent a reasonable local rate in Nigeria. Flight costs are based on current quotes for economy airfare, complying with the Fly America Act.

Vehicle Fuel ($2,563). POA estimates fuel for the project vehicle at $60/month for 39 months over the LOP. The rate is based on POA’s documented experience with projects in the region.

Per Diem & Lodging ($19,957). POA is budgeting for lodging and M&IE for staff traveling for trainings under Activity 3, estimated at $80/day in lodging and $66/day in M&IE for 3 days/trip for 6 trips in Y1 and 12 trips/year in Y2-4. Lodging is based on market quotes; per diem on reduced DSSR rates.

## Professional Services/Contractual – Total $8,000

Security Services, Risk Assessments, & Security Assessment ($8,000). POA will contract a firm to provide security services and conduct risk and security assessments under Activity 3 to ensure the well-being of staff and program participants, at $2,000/year in Y1-Y4.

## Supplies – Total $0

None.

## Other – Total $438,187

Subrecipient CABI: $438,187: CABI will work with the Government of Nigeria to harmonize trade policies to boost US exports. CABI will leverage its connections to key Nigerian regulatory bodies to increase US export efficiency. This includes conducting a national review of harmonization with key science-based SPS standards and identifying opportunities to improve compliance. CABI brings deep technical expertise in harmonizing trade standards, developing risk-based inspection protocols, and building the institutional capacity of food safety authorities.

## Indirect Costs - $129,213

POA has elected to apply reduced indirect cost rates for Activity 3 to enhance cost competitiveness and ensure alignment with USDA’s expectations regarding administrative efficiency. A 15% indirect cost rate is applied to total direct activity costs (excluding subawards), totaling $98,540 over the life of the activity. For direct subaward costs, a further reduced rate of 7% is applied, totaling $30,673. All rates and applications are compliant with POA’s NICRA and US government cost principles 2 CFR 200.414. This cost strategy prioritizes programmatic impact by ensuring that the majority of resources flow directly to field-level interventions.

## Cost Share – Total $0

None.