OGSM: FFE-522-2025/004-00-A

COUNTRY: HONDURAS

THE AGREEMENT BETWEEN

THE GOVERNMENT OF THE UNITED STATES OF AMERICA AND

PARTNERS OF THE AMERICAS

FOR THE PROVISION OF AGRICULTURAL COMMODITIES AND FINANCIAL AND TECHNICAL ASSISTANCE THROUGH THE MCGOVERN-DOLE INTERNATIONAL FOOD FOR EDUCATION AND CHILD NUTRITION PROGRAM

AMENDMENT I

Agreement No. OGSM: FFE-522-2025-004-00, dated September 23, 2025, between the Foreign Agricultural Service and Partners of the Americas, is hereby amended as follows:

- By deleting Part III, Item III, Paragraph C(1) of the Agreement and replacing it with the following:

“C. (1) The budget approved by FAS for this agreement consists of the Budget Summary, Attachment

C-1, and Attachment C-2, Budget Narrative, which are attached hereto and made a part of this agreement. The Recipient will expend any funds generated from a sale of the donated commodities that is otherwise permitted under this agreement (hereinafter referred to as the "sale proceeds"), FAS-provided funds, and funds provided as voluntary committed cost sharing or matching contributions, only for costs as specified in the line items in Attachment C-1. The Recipient may expend such funds only up to the amounts specified in the line items in Attachment C-1; except that, in accordance with 7 CFR section 1599.12(h), the Recipient may make adjustments between direct cost line items in Attachment C-1 without further approval, subject to the limitation in 7 CFR section 1599.12(h)(2), provided that: (a) the total amount of such adjustments does not exceed ten percent of the Grand Total Costs, excluding any voluntary committed cost sharing or matching contributions, in Attachment C-1, and (b) regardless of the total amount of adjustments, the Recipient must obtain prior approval from FAS for any adjustments that involve actions that require prior approval pursuant to 2 CFR part 200.”

- By deleting Attachment C-1 and replacing it with Attachment C-1 Modification I.

- By Adding Attachment C-2 Budget Narrative.

All other provisions of the agreement remain the same.

This amendment shall be effective upon signature by both parties.

In witness whereof, the representatives of the parties, duly authorized for the purpose, have signed this amendment.

| FOR THE GOVERNMENT OF |  |  |  | FOR |  |
| --- | --- | --- | --- | --- | --- |
| THE UNITED STATES OF AMERICA |  |  |  | Partners of the Americas |  |
| By: |  | ______________________________ |  | By: | ______________________________ |
|  |  | Mark Slupek |  |  | John McPhail |
| Title: |  |  |  | Title: |  |
|  |  | Deputy Administrator |  |  | President & CEO |
|  |  | Global Programs |  |  |  |
|  |  | Foreign Agricultural Service, |  |  |  |
|  |  | U.S. Department of Agriculture |  |  |  |
| Date: | ______________________________ |  |  | Date: | ______________________________ |

ATTACHMENT C - 1 
Budget Summary
MODIFICATION I

Program:  MGD
Country of Operation: Honduras
Implementing Organization: Partners of the Americas
Fiscal Year: 2025
Agreement Number: FFE-522-2025/004-00-A

Total Amount of Federal Funds Obligated

| Funding Source | Funding Year | Commodity Cost (FFPr and MGD Only) | Freight Cost (FFPr and MGD Only) | Administrative Costs (cash portion) | Total Federal Funding Obligated |
| --- | --- | --- | --- | --- | --- |
| Local and Regional Procurement (LRP) | 2025 | $0.00 | $0.00 | $4,000,000.00 | $4,000,000.00 |
| McGovern - Dole (Food For Education) | 2025 | $9,958,720.00 | $2,511,080.00 | $23,530,200.00 | $36,000,000.00 |

Project Operating Budget

| ExpenseType |  | Monetization Proceeds | FAS Funds | Cost Share | Total w/out Cost Share | Total w/Cost Share |
| --- | --- | --- | --- | --- | --- | --- |
| Administration |  |  |  |  |  |  |
|  | Supplies | $0.00 | $82,190.64 | $0.00 | $82,190.64 | $82,190.64 |
|  | Equipment | $0.00 | $53,000.00 | $0.00 | $53,000.00 | $53,000.00 |
|  | Travel | $0.00 | $368,758.30 | $0.00 | $368,758.30 | $368,758.30 |
|  | Professional Services | $0.00 | $1,182,800.00 | $0.00 | $1,182,800.00 | $1,182,800.00 |
|  | Benefits | $0.00 | $2,027,170.96 | $0.00 | $2,027,170.96 | $2,027,170.96 |
|  | Salaries | $0.00 | $5,286,497.76 | $0.00 | $5,286,497.76 | $5,286,497.76 |
|  | Other | $0.00 | $646,819.51 | $0.00 | $646,819.51 | $646,819.51 |
| Total Administration |  | $0.00 | $9,647,237.17 | $0.00 | $9,647,237.17 | $9,647,237.17 |
| Activities |  |  |  |  |  |  |
|  | Capacity Building: Local and Regional Level | $0.00 | $365,869.91 | $11,500.00 | $365,869.91 | $377,369.91 |
|  | Capacity Building: National Level | $0.00 | $425,854.90 | $0.00 | $425,854.90 | $425,854.90 |
|  | Develop Public-Private Partnerships to Support School Feeding Sustainability | $0.00 | $462,935.92 | $21,000.00 | $462,935.92 | $483,935.92 |
|  | Expand Use of US Commodities in Honduras School Feeding Program | $0.00 | $89,328.66 | $4,980.00 | $89,328.66 | $94,308.66 |
|  | Training: Teachers and Administrators | $0.00 | $2,400,715.18 | $0.00 | $2,400,715.18 | $2,400,715.18 |
|  | Building/Rehabilitation: Wells and water stations/systems | $0.00 | $520,716.18 | $182,500.00 | $520,716.18 | $703,216.18 |
|  | Distribution: School supplies and materials | $0.00 | $407,143.18 | $0.00 | $407,143.18 | $407,143.18 |
|  | Enrollment campaigns | $0.00 | $629,594.49 | $0.00 | $629,594.49 | $629,594.49 |
|  | Provide School Meals | $0.00 | $658,976.11 | $187,000.00 | $658,976.11 | $845,976.11 |
|  | Training: Commodity management | $0.00 | $357,568.95 | $0.00 | $357,568.95 | $357,568.95 |
|  | Training: Good health and nutrition practices | $0.00 | $1,056,867.11 | $0.00 | $1,056,867.11 | $1,056,867.11 |
| Total Activities |  | $0.00 | $7,375,570.59 | $406,980.00 | $7,375,570.59 | $7,782,550.59 |
| Commodity and Food Purchases (LRP only) |  |  |  |  |  |  |
| Commodity Procurement |  |  | $3,282,393.11 | $0.00 | $3,282,393.11 | $3,282,393.11 |
| Food Vouchers |  |  | $0.00 | $0.00 | $0.00 | $0.00 |
| Cash Transfers |  |  | $0.00 | $0.00 | $0.00 | $0.00 |
| Total Commodity Procurement |  |  | $3,282,393.11 | $0.00 | $3,282,393.11 | $3,282,393.11 |
| ITSH |  |  |  |  |  |  |
|  | Supplies | $0.00 | $2,450.00 | $0.00 | $2,450.00 | $2,450.00 |
|  | Internal Transportation | $0.00 | $381,450.00 | $0.00 | $381,450.00 | $381,450.00 |
|  | Warehouse | $0.00 | $588,336.00 | $0.00 | $588,336.00 | $588,336.00 |
|  | Travel | $0.00 | $37,600.88 | $0.00 | $37,600.88 | $37,600.88 |
|  | Professional Services | $0.00 | $213,600.00 | $0.00 | $213,600.00 | $213,600.00 |
|  | Benefits | $0.00 | $460,008.22 | $0.00 | $460,008.22 | $460,008.22 |
|  | Salaries | $0.00 | $953,187.37 | $0.00 | $953,187.37 | $953,187.37 |
| Total ITSH |  | $0.00 | $2,636,632.47 | $0.00 | $2,636,632.47 | $2,636,632.47 |
| Total Direct Costs |  | $0.00 | $22,941,833.34 | $406,980.00 | $22,941,833.34 | $23,348,813.34 |
| ICR on Administration |  | $0.00 | $1,929,447.43 |  | $1,929,447.43 |  |
| ICR on Commodity Procurement |  | $0.00 | $656,478.62 |  | $656,478.62 |  |
| ICR on Activities |  | $0.00 | $1,475,114.12 |  | $1,475,114.12 |  |
| ICR on ITSH |  | $0.00 | $527,326.49 |  | $527,326.49 |  |
| Total Indirect Costs |  | $0.00 | $4,588,366.66 |  | $4,588,366.66 |  |
| Anticipated Program Income |  |  |  |  |  | $0.00 |
| Grand Total Costs |  | $0.00 | $27,530,200.00 | $406,980.00 | $27,530,200.00 | $27,937,180.00 |
| Total Amount of Federal Award (Total Federal Funds Obligated plus Cost Share): $40,406,980.00 |  |  |  |  |  |  |

C-2 Budget Narrative

Agreement Number: FFE-522-2025/004-00

| Program | McGovern Dole |
| --- | --- |
| Country | Honduras |
| Fiscal Year | 2025 |
| Organization | Partners of the Americas, Inc. (UEI: DD5WNYRUYFE5) |
| Point of Contact | Carmen Peña, cpena@partners.net |

  - General Explanatory Comments

Partners of the Americas Inc. (POA) will implement a six-year McGovern Dole (MGD) Program project in Honduras. The total federal award amount is $40,000,000. This includes commodity ($9,958,720), freight ($2,511,080), and operating budget ($27,530,200). The total project operating budget includes $406,980 in cost share. The following budget narrative describes the operating budget and does not describe the commodity and freight portions of Federal funding.

- USDA/FAS Funding:	$27,530,200

- Total Cost Share	                 $406,980

- Total Project Operating Budget	$27,937,180

| Summary of Total Project Operating Budget (Includes Cost Share) |  |
| --- | --- |
| Administration | $9,581,237.17 |
| Activities | $7,782,550.59 |
| Commodity Procurement | $3,282,393.11 |
| ITSH | $2,702,632.47 |
| ICR on Administration | $1,916,247.43 |
| ICR on Activities | $1,475,114.12 |
| ICR on Commodity Procurement | $656,478.62 |
| ICR on ITSH | $540,526.49 |
| Total | $27,937,180 |

Cost Escalations (Including Salary Increases)

POA has applied a 5% increase to account for inflation and a 5% increase for merit-based salary increases for all Headquarters (HQ), and Cooperating Country National (CCN) staff after Year 1 (Y1), in accordance with POA policy. Actual annual increases will range from 1%-5% and are based on an annual performance review. Expenses for travel, supplies, and office expenses include a yearly escalation of inflation after Y1. Inflation is estimated at 5% annually after Y1.

Cost Share

Cost share for the award is $406,980 and includes warehouses, parent contributions, and community stakeholder contributions for the sustainability of WASH stations under Activities 1, 5,8, 10 and 11 which aim to expand investments in school feeding and education. A detailed breakdown of the cost share is as follows:

- Warehouse Fees total $162,000

  - 36 warehouses * $100/month * 9 months * 5 years = $162,000

- Volunteer Parent Labor total $25,000

  - Valued at $50 per parent ($25 per hour * 2 hours) * 100 parents * 5 years = $25,000

- Public & Private Sector Material Contributions for WASH Stations total $132,500

  - $265 in donated materials per WASH station * 500 schools = $132,500

- Volunteer Time for Maintenance of WASH Stations total $50,000

  - 100 community members * 4 hours/year * 5 years * $25/hour = $50,000

- Annual Volunteer Recognition Events total $11,500

  - $2,300  per event * 5 annual events = $11,500

- Venue & A/V Equipment for Validation Workshops total $6,000

  - $1,500 per workshop * 2 workshops/year in Y2 and Y3 * 2 years = $6,000.

- Venue & A/V Equipment Meetings on CSR Activation Platform total $15,000

  - $250/meeting * 12 meetings * 5 years = $15,000

- Workshop to Present Study Findings total $4,980

  - $2,490/event * 2 events total = $4,980

By including cost share POA seeks to stimulate shared investment in the project to maximize impacts and generate sustainability.

Program Income Summary

MGD Honduras does not expect to generate Program Income under the project.

Summary of Indirect Rates Applied

| ICR Category | Direct Category Subtotal | ICR Applied (20%) |
| --- | --- | --- |
| ICR on Administration | $9,581,237.17 | $1,916,247.43 |
| ICR on Activities | $7,375,570.59 | $1,475,114.12 |
| ICR on Commodity Procurement | $3,282,393.11 | $656,478.62 |
| ICR on ITSH | $2,702,632.47 | $540,526.49 |
| Total Costs | $22,941,833.33 | $4,588,366.66 |

Prevention of Fraud, Waste, and Abuse

POA has implemented rigorous financial management and internal control systems specifically designed to support the detection and prevention of fraud, waste, and abuse of U.S. Government resources. These systems include segregation of duties, multi-level review and approval processes, real-time expenditure tracking, automated alerts for irregularities, and periodic internal checks. POA uses Sage Intacct, a secure, cloud-based accounting platform that ensures transparent, auditable, and timely financial reporting. This enables automated workflows, role-based access controls, and detailed documentation of all transactions, which together help identify anomalies, enforce compliance, and deter misuse of funds. To further reinforce accountability, POA is subject to an annual Single Audit under 2 CFR 200 Subpart F, and conducts routine internal reviews and spot checks at both headquarters and field levels. All staff with financial responsibilities receive regular training on fraud prevention, U.S. Government cost principles, and POA’s internal policies. Preventive measures include monthly financial reviews with project directors, oversight of procurement and subawards, ongoing reconciliation of accounts, and detailed documentation of all expenditures. These processes create multiple checkpoints that enable early detection of discrepancies or noncompliance. The Finance and Administration (F&A) department, staffed by experienced professionals with over 50 years of experience in financial oversight. This team works with project and country teams to monitor spending, confirm allowability and allocability of costs, and ensure full compliance with 2 CFR 200, local regulations, and POA’s policies. POA’s current NICRA, approved by USAID, sets an indirect cost rate of 28.28%. For this Agreement, POA is voluntarily committing to a reduced indirect cost rate of 20% to maximize direct program funding. POA affirms that the decision to charge a reduced rate is made solely by POA and that FAS/USDA did not encourage or otherwise influence POA’s decision to charge a reduced rate. POA acknowledges that 20% is the indirect cost billing rate currently applicable under this award, unless modified by mutual agreement in the event that POA receives a revised NICRA approved by its Cognizant Agency.

Summary of Monitoring & Evaluation Budget

| Summary of M&E (Monitoring & Evaluation) Budget (Excluding M&E Personnel & Travel) |  |
| --- | --- |
| Evaluations (Baseline, Midterm, & Final) | $485,000 |
| 2 Special Studies: (1) Feasibility of Integrating CSB+ into the National Feeding Program & (2) Sustainability & Institutional Readiness Study = | $250,000 |
| Monitoring Guidelines Creation, Translation & Printing | $10,000 |
| Monitoring Guidelines Revision, Translation & Printing | $10,000 |
| Monitoring Guidelines Staff Training on Indicators and Data Collection/Analysis | $36,000 |
| M&E Database Platform Subscription (includes training) | $39,000 |
| Total M&E Budget | $830,000 |
| Total Budget % Dedicated to M&E (Excluding Cost Share) | 3.01% |

Summary of the Local and Regional Procurement (LRP) Budget

POA’s Local and Regional Procurement (LRP) budget is $4,000,000 or approximately 10 percent of the federal obligation of $40,000,000. The table below provides a summary of the costs that contribute to the LRP portion of the award.

| Summary of Local and Regional Procurement Budget |  |
| --- | --- |
| Salaries/Personnel (from Administration) | $0 |
| Benefits (from Administration) | $0 |
| Salaries/Personnel (from ITSH) | $34,358.71 |
| Benefits (from ITSH) | $16,581.52 |
| Internal Transportation | $0 |
| Warehouse | $0 |
| Commodity Procurement | $3,282,393.11 |
| ICR on Administration | $0 |
| ICR on ITSH | $10,188.05 |
| ICR on Commodity and Food Purchases | $656,478.62 |
| Total LRP Budget | $4,000,000 |
| Total Budget % Dedicated to LRP | 10% |

Cost Effectiveness

POA's budget has been developed considering cost-effectiveness to support and achieve key objectives. The project’s budget components were designed to build long-term human capital and leverage private sector resources. The project is cost-effective, namely because of the demand- based nature of activities and interest from the government and private sector, in support of activities. All costs within the budget are deemed reasonable, allocable, and necessary to project implementation for MGD Honduras as they directly related to the activities outlined in the Plan of Operations and contribute to achieving the project's components efficiently and effectively. Prices are based on quotes, research, and POA experience to determine their fair market value. This ensures that resources are utilized responsibly, promoting transparency and accountability.

  - Administration

Administration Costs: $11,497,484.61 ($11,497,484.61 in USDA/FAS funds, $0 in cost share)

- Direct Costs: $9,581,237.17 ($9,581,237.17 in USDA/FAS funds, $0 in cost share)

- Indirect Costs: $1,916,247.43

    - Salaries/Personnel - Subtotal $5,286,497.76

| Position *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Chief of Party* (CCN) | 71 | 100% | $9,583 | $10,882 | $772,637.64 |
| Deputy Chief of Party* (CCN) | 71 | 100% | $6,500 | $7,381 | $524,049.20 |
| Communications Specialist (CCN) | 64 | 50% | $1,500 | $1,700 | $54,388.37 |
| M&E Director (CCN) | 69 | 100% | $4,583 | $5,205 | $369,521.87 |
| M&E Specialist (CCN) | 65 | 100% | $2,000 | $2,288 | $148,693.34 |
| M&E Officer (CCN) | 54 | 100% | $1,250 | $1,418 | $75,170.52 |
| Finance & Administration Director (CCN) | 69 | 100% | $5,000 | $5,697 | $393,114.77 |
| Contracts & Compliance Manager (CCN) | 68 | 100% | $2,633 | $2,995 | $203,679.57 |
| Grants & Procurement Specialist (CCN) | 60 | 100% | $1,500 | $1,699 | $101,947.90 |
| Grants & Procurement Officer (CCN) | 53 | 100% | $1,000 | $1,135 | $60,136.42 |
| Finance Officer (CCN) | 68 | 100% | $1,250 | $1,422 | $96,683.34 |
| Accountant (CCN) | 60 | 100% | $1,000 | $1,147 | $68,794.11 |
| Operation & HR Manager (CCN) | 68 | 100 % | $1,800 | $2,047 | $139,224.01 |
| Administrative Assistant (1) (CCN) | 56 | 100% | $750 | $853 | $47,766.74 |
| Administrative Assistant (2) (CCN) | 56 | 100% | $750 | $853 | $47,767.74 |
| Driver – (1) (CCN) | 60 | 100% | $500 | $573 | $34,397.05 |
| Driver – (2) (CCN) | 60 | 100% | $500 | $573 | $34,397.05 |

| Vice President of Programs (USN) | 72 | 35% | $13,500 | $15,304 | $385,668.46 |
| --- | --- | --- | --- | --- | --- |
| Program Director (USN) | 72 | 90% | $12,500 | $ 14,171 | $918,258.23 |
| Compliance & Contracts Director (USN) | 72 | 20% | $9,167 | $10,392 | $149,642.08 |
| Associate Director (USN) | 72 | 100% | $7,500 | $8,502 | $612,172.15 |
| Senior Program Officer | 72 | 5%* | $5,917 | $672 | $48,389.19 |
| Subtotal |  |  |  |  | $5,286,497.76 |

    - Fringe Benefits & Allowances – Subtotal $2,027,170.96

According to POA’s internal organization policies, CCN is defined as “An individual - employee who is a cooperating country citizen, or a non-cooperating country citizen lawfully admitted for permanent residence in the cooperating country.”

Fringe Benefits CCN – Honduras ($1,530,984.63)

Fringe benefits for CCN staff are budgeted at 48.26% of their total salary and are based on local labor law, in-country required benefits, and POA’s fringe benefit policy. This includes:

      - 8.50% - Honduran Social Security Institute (IHSS)

      - 1.00% - Vocational Training Institute (INFOP)

      - 1.50% - Pensión Régimen de Aportaciones Privadas (RAP)

      - 5.77% - 15 days of annual leave a year

      - 8.33% - 1 month of severance for every year of service

      - 8.33% - 13th Month

      - 8.33% - 14th Month

      - 0.5% - Life insurance

      - 6% - Private health insurance

Fringe Benefits – HQ ($496,186.34)

POA charges fringe benefit costs in accordance with POA’s personnel policy and its NICRA letter. POA has charged a 23.47% fringe rate on HQ salaries. Fringe benefits include insurance, mandatory taxes, pension, and other employee benefits.

    - Travel – Subtotal $368,758.30

According to POA’s organizational policy, POA provides a reduced per diem based on the applicable U.S. State Department and General Services Administration rates as stated below. This does not include any necessary deductions or exclusions. The reduction for international travel is 90% reduced per diem and local travel 50% reduced per diem.

International Travel ($110,133.85)

HQ Staff Travel – International ($71,232.35): POA HQ staff will make 24 international trips during the LOP from Washington, DC to Honduras during the period of performance. The purpose of the trips will be to provide monitoring, oversight, and technical guidance. This includes airfare tickets (24 trips * $800 per trip + $2,566 for inflation in Y2-Y6 = $21,766), lodging and M&IE ($78.30 M&IE per day + $150 lodging per day) * 7 days per trip * 24 trips +$5,126.60 for inflation in Y2-Y6 = $43,481), local transportation ($120 per trip * 24 trips + $385 for inflation in  Y2-Y6 = $3,265), and other related travel expenses to cover items such as travel visas ($100 per trip * 24 trips + 321 for inflation in Y2-Y6 = $2,721).

Honduras Staff Travel – International ($38,901.50): Honduras staff, mainly the Chief of Party (COP) and Deputy Chief of Party (DCOP), will make 12 international trips during the LOP from Honduras to Washington, DC. This includes airfare tickets (12 trips * $800 per trip +$1,283 for inflation in Y2-Y6 = $10,883), lodging and M&IE (($82.80 M&IE per day + $180 lodging per day) * 7 days per trip * 12 trips + $2,950.80 for inflation in Y2-Y6= $25,026), local transportation ($120 per trip * 12 trips +$192 for inflation in Y2-Y6 = $1,632), and other related travel expenses to cover items such as travel visas ($100 per trip *12 trips + $160 for inflation in Y2-Y6 = $1,360).

Local Travel ($258,624.45)

Honduras Staff Travel – Domestic (Tegucigalpa-Intibucá) ($129,159.07): POA estimates staff will need to complete 36 total trips per year, or 3 trips per month, for program oversight, to attend trainings and meetings/events, as well as perform M&E and data collection. This estimates about 216 trips for 4 nights and 4 days over the life of the program. The estimate includes vehicle fuel expenses ($120 per month * 58 months + $989 for inflation in Y2-Y6 = $7,949), local transportation ($55 per trip * 216 trips + $1,588 for inflation in Y2-Y6 = $13,468), and lodging and M&IE ($40 M&IE per day + $70 lodging per day) * 4 days per trip *216 trips +$12,702 for inflation in Y2-Y6 = $107,742).

Honduras Staff Travel – Domestic (Tegucigalpa-La Paz) ($129,465.38): POA estimates staff will need to complete 36 total trips per year, or 3 trips per month, for program oversight, to attend trainings and meetings/events, as well as perform M&E and data collection. This estimates about 216 trips for 4 nights and 4 days over the life of the program. The estimate includes vehicle fuel expenses ($120 per month * 60 months + $1,055 for inflation in Y2-Y6 = $8,255), local transportation ($35 per trip * 216 trips +$1,010 for inflation in Y2-Y6 = $8,570), and lodging and M&IE ($40 M&IE per day + $75 lodging per day) * 4 days per trip * 216 trips + $13,280 for inflation in Y2-Y6 = $112,640).

    - Professional Services/Contractual – Subtotal $1,116,800.00

Professional Services ($286,800.00): POA has included the following expenses related to support services over the life of the program:

      - Audit Costs ($30,000): The cost of local program-specific audit costs as required by Honduran law, estimated at $5,000 per year for 6 years ($5,000/year * 6 years = $30,000).

      - Legal Fees ($42,000): POA will use legal services to negotiate contracts, obtain labor contract council, and other legal services as needed, estimated at $7,000 per year for 6 years ($7,000/year * 6 years = 42,000).

      - Security Services, Risk Assessments, and Security Assessments ($120,000): The cost of security services for in-country staff and activities is estimated at $20,000 per year for 6 years ($20,000/year * 6 years = $120,000).

      - Start-up Consultant ($64,800): POA will contract start-up consultants to ensure the rapid start of the project, supporting the operational start of the project. POA is estimating a daily rate of $600 per day for a total of 108 days during Y1 ($600/day * 108 days = $64,800). Given their technical expertise, the consultants will be highly qualified with 5+ years of specialized experience in technical topics. The rate is in line with market rates for these types of consultants based either in the U.S. or other international locations and is consistent with prior rates paid for similar consultants, with the specialized experience required by the deliverable. The start-up consultants will support with developing key USDA deliverables, such as the Work Plan, Evaluation Plan, Performance Monitoring Plan, Revised Budget, Commodity Procurement & Delivery Plan, Terms of Reference for the Baseline and Market Studies, and Communications & Marketing Plan. They will also support the development of scopes of work for staffing positions, staff recruitment, and the operational start-up of POA’s Honduras Country Office.

      - Market Study ($30,000): POA is budgeting for an external consultant to lead the project’s initial market study and establish the framework for the annual market study updates, at a rate of $400 per day for 75 days in Y1 ($400/day * 75 days = $30,000).

Evaluations and Other Assessments ($735,000.00): POA estimates external evaluation fees for the Baseline, Midterm, and Final Evaluations to be $150,000, $160,000, and $175,000, respectively. POA will host an open procurement to select an external evaluator for the evaluations. POA will consider factors such as the soundness of the proposal, unique capabilities, cost, schedule, technical competency, and experience in Honduras POA will conduct two separate special studies: In Y1 and Y3, POA will conduct a two-phased special study on Sustainability & Institutional Readiness. In Y3 and Y4, POA will conduct a special study on Feasibility of Integrating CSB+ into the National School Feeding Program. POA estimates $125,000 for each special study ($125,000 per study * 2 studies = $250,000.)

Monitoring Guidelines Development ($56,000.00): POA will develop M&E guidelines, including the cost of creating, translating, and printing at a one-time rate of $10,000 in Y1. As part of its adapting and learning process, POA also estimates $2,000 per year starting in Y2 ($2,000 for Y2 – Y6 estimated $10,000) for any revisions to the guidelines, including translation and printing over LOP. Once the Guidelines have been developed, POA will provide training to all staff on indicators and data collection/analysis, including ongoing training for existing and updated guidelines, for a total of $36,000 ($6,000 per year * 6 years = $36,000).

M&E Database ($39,000.00): POA is budgeting for a cloud-based M&E database/platform subscription fee, including training, to accurately track project data and M&E across regions and activities. The M&E database and training cost is estimated at $6,500 per year in Y1-Y6, for a total of $39,000 ($6,500/year * 6 years = $39,000).

    - Equipment – Subtotal $53,000.00

POA plans to purchase one 4x4 specialized vehicle ready for rural areas. Based on local quotes, POA estimates the cost at $53,000/vehicle, including customs, taxes, and import fees. POA will follow USDA procurement guidelines. POA conducted a buy vs. lease analysis and found it more cost-effective to purchase vehicles given the frequent travel for data collection, trainings, and site visits to locations 4+ hours from the capital city.

    - Office Supplies – Subtotal $82,190.64

Furniture and Hardware ($60,498.37): POA plans to purchase 37 desktop/laptop computers (estimated at $1,280/computer for a total of $47,360.00), 2 all-in-one printer/photocopier/scanner (estimated at $350 per unit for a total of $700.00), 1 projector (estimated at $738.37), 39 desks (estimated at $150 per desk for a total of $5,850.00), 39 chairs (estimated at $50 per chair for a total of $1,950.00), 2 meeting tables (estimated at $250 per table for a total of $500.00), 3 shelves for office storage (estimated at $100 per shelf for a total of $300.00), 5 filing cabinets (estimated at $250 per cabinet for a total of $1,250.00), 2 fireproof safes (estimated at $225 per safe for a total of $450.00), and 2 A/C units for the office (estimated at $700 per unit for a total of $1,400.00). Estimated costs are based on market prices in Honduras for a total of $60,498.37.

General Supplies ($21,692.27): The budgeted monthly office supply costs are estimated at $300 per month for 66 months, plus $1,892 for inflation in Y2-Y6. The costs cover all necessary office supplies such as notebooks, pens, calculators, office bags, clip files, registers, photocopy paper, flip chart paper, markers, transparency paper, flip chart boards, etc. POA estimates are based on past experience with projects of similar size and market research.

    - Other Direct Costs – Subtotal $646,819.51

Office in Tegucigalpa ($284,217.61): The estimated subtotal cost of the capital city project office for Y1-Y6. The costs for the office, rented solely for the proposed project, including the following costs for 6 years:

      - Communications Costs (Internet, Phone, Data): $300 per month * 66 months + $2,638 for inflation in Y2-Y6 = $22,438.23.

      - Office Rent: $2,500  per month * 66 months + $21,985 for inflation in Y2-Y6 = $186,985.27.

      - Office Utilities (Electricity and Water): $350 per month * 66 months + $3,078 for inflation in Y2-Y6 = $26,177.94.

      - Office Cleaning: $50 per month * 66 months + $440 for inflation in Y2-Y6 = $3,739.71.

      - Security Services: $600 per month * 66 months + $5,276 for inflation in Y2-Y6 = $44,876.47.

Satellite Office in Intibucá ($19,072.50): The estimated subtotal cost of the Intibucá satellite project office for Y1-Y6 is based solely on communications costs (internet, phone, data) for local staff: $255 per month * 66 months + $2,242 for inflation in Y2-Y6 = $19,072.50.

Satellite Office in La Paz ($19,072.50): The estimated subtotal cost of the La Paz satellite project office for Y1-Y6 is based solely on communications costs (internet, phone, data) for local staff: $255 per month * 66 months + $2,242 for inflation in Y2-Y6 = $19,072.50.

General Local Office Costs ($257,730.14): The estimated subtotal general costs of the project offices for Y1-Y6. This includes the following costs for 6 years:

      - Banking and Cash Handling Fees: $125 per month * 66 months + $1,099 for inflation in Y2-Y6 = $9,349.26.

      - Courier fees/services/Postage: $10 per month, * 66 months + $88 for inflation in Y2-Y6 = $747.94.

      - Recruitment/Procurement Advertising: $400 per year * 6 years + $321 for inflation in Y2-Y6 = $2,720.77.

      - Meeting Expenses: $375 per month * 66 months + $3,298 for inflation in Y2-Y6 = $28,047.79.The meeting room rental space based on an hourly rate of $25/hour for up to 15 hours a month. The hourly rate may include the room rental, A/V equipment,  and other material costs.

      - Payroll Processing and Local Accounting Books Preparation: $400 per month * 66 months + $3,518 for inflation in Y2 – Y6 = $29,917.64.

      - Licenses & Subscriptions (Microsoft 365, Adobe, Replicon, & PandaDoc): $1,996 per month * 66 months + $17,553 for inflation in Y2-Y6 = $149,289.04.

      - Training, Workshops, Conference and Registration Fees: $6,000 per year * 6 years + $1,658 for inflation in Y2 – Y6 = $37,657.69. POA staff will participate in global or regional school feeding and education events such as the Global Child Nutrition Forum or the Annual Conference of the Comparative and International Education Society.

Repair & Maintenance ($26,935.57): POA estimates equipment and office repair costs for Y1-Y6 including the following:

      - Equipment and Office Repairs and Maintenance: $1,500 per year for 6 years ($1,500 per year * 6 years + $1,203 =  $10,202.87) .

      - Vehicle Maintenance/repairs/spare parts: $830 per vehicle per year (3 vehicles) for 6 years ($830/year * 3 vehicles * 6 years + $1,972.71 for inflation in Y2-Y6 = $16,732.71 subtotal.

Insurance and Fees ($39,791.19): POA estimates insurance costs for Y1-Y6 including the following:

      - Vehicle Registration Fee: $1,150 per vehicle per year ($1,150 * 3 vehicles * 6 years + $2,766.60 for inflation in Y2-Y6 = $23,466.60).

      - Vehicle Insurance: $800 per vehicle per year ($800 * 3 vehicles * 6 years + $1,924.59 for inflation in Y2-Y6 = $16,324.59).

2.9 Indirect Costs – Administration – Subtotal $1,916,247.43

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $1,916,247.43.

  - Activities

Subtotal: $9,257,664.71 ($8,850,684.71 in USDA/FAS funds and $406,980.00 in cost share)

- Subtotal Direct Costs: $7,782,550.59 ($7,375,570.59 in USDA/FAS funds and $406,980.00 in cost share)

- Subtotal Indirect Costs: $1,475,114.12

Activity 1: Provide School Meals – Subtotal $658,976.11 ($845,976.11 with $187,000 in cost share)

    - Salaries/Personnel – Subtotal $295,496.60

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary** | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Nutrition and Health Specialist | 63 | 25% | $1,500 | $1,690 | $26,611.97 |
| Nutrition Officer (1) | 54 | 85% | $1,000 | $1,132 | $51,965.96 |
| Nutrition Officer (2) | 54 | 85% | $1,000 | $1,132 | $51,965.96 |
| School Feeding Specialist | 57 | 40% | $1,500 | $1,676 | $38,203.34 |
| Food Aid Monitors (1) | 57 | 85% | $1,000 | $1,140 | $55,220.47 |
| Food Aid Monitors (2) | 57 | 85% | $1,000 | $1,140 | $55,220.47 |
| Education & Community Engagement Specialist | 63 | 10% | $1,500 | $1,703 | $10,577.67 |
| Education & Community Engagement Officer | 51 | 10% | $1,000 | $1,124 | $5,730.76 |

| Subtotal | $295,496.60 |
| --- | --- |

    - Fringe Benefits – Subtotal $142,606.66

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $295,496.60 * 48.26% = $142,606.66.

    - Travel – Subtotal $20,872.84

      - Vehicle Fuel ($8,255.29): POA estimates vehicle fuel for the 2 vehicles to cost $120 per month for 60 months of the project to support project staff implement and oversee interventions under Activity 1 The total amount for vehicle fuel is calculated at $120 per month * 60 months + $1,055 for inflation in Y2-Y6 - $8,255.

      - Local Travel ($12,617.55): POA estimates additional general expenses for project staff implementing and overseeing interventions under Activity 1. This includes local transportation ($35 per trip * 12 trips + $56 for inflation in Y2-Y6 = $476.13), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 2 days per trip *12 trips +369 for inflation in Y2-Y6 = $3,128.88). POA estimates staff will need to complete 30 total trips during the LOP for the School Feeding Manager to check storerooms and monitor trainings. This estimates 2 nights and 2 days per trip. The estimate includes local transportation ($35 per trip * 30 trips  + $140 for inflation in Y2-Y6 = $1,190.33), and lodging and M&IE (($40 M&IE per day + $75 lodging per day) * 2 days per trip * 30 trips +$922 for inflation in Y2-Y6 = $7,822.20).

    - Professional Services / Contractual – Subtotal $200,000.00

- Contract for Mancomunidad Assistance Support ($200,000.00): POA will issue limited service contracts to mancomunidades to finance technical assistance and staff time for mentoring producer groups and coordinating deliveries. Under these contracts, mancomunidades will identify and prepare local producer organizations and cooperatives to supply eggs, fruits, and vegetables to schools. POA is budgeting for a total of 20 contracts (2 in Y1, 4 in Y2-Y5, and 2 in Y6) valued at $10,000 each. $10,000/contract * 20 contracts = $200,000.00.

    - Indirect Costs – $131,795.22

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $131,795.22.

    - Cost-Share – $187,000.00

Warehouse Fees ($162,000.00): Commodities will be transported from the central warehouse to the 36 municipal warehouses, after which they will be distributed to the corresponding school warehouses as needed. The rent of each warehouse is valued at $100 per month. Each municipality will contribute by covering warehouse rental during the school year for 9 months per year, totaling $32,400 annually (36 warehouses * $100/month * 9 months/year * 5 years = $162,000). Over five years, this amounts to $162,000.

Volunteer Parent Labor - Receive & Transport Commodities - Parents’ Time on Transportation and Food Preparation ($25,000.00): Each year from Y2-Y6, 100 parents will volunteer to deliver commodities from municipalities to schools. Valued at $50 per parent ($25 per hour * 2 hours) * 100 parents * 5 years = $25,000. Their involvement reduces transport costs and fosters community ownership, making the program more sustainable.

Activity 2: Distribution: School Supplies and Materials – Subtotal $407,143.18

    - Salaries/Personnel – Subtotal $80,048.38

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary** | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Education Director | 65 | 10% | $4,583 | $5,184 | $33,695.67 |
| Education Specialist | 59 | 10% | $2,500 | $2,802 | $16,534.10 |
| Education Officer | 57 | 10% | $1,000 | $1,125 | $6,413.64 |
| Education & Community Engagement Specialist | 62 | 10% | $1,500 | $1,706 | $10,577.67 |
| Education & Community Engagement Officer | 51 | 10% | $1,000 | $1,124 | $5,730.30 |
| Private Sector Specialist | 63 | 5% | $1,500 | $1,690 | $7097.00 |
| Subtotal |  |  |  |  | $80,048.38 |

    - Fringe Benefits – Total $38,631.35

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $80,048.38 * 48.26% = $38,631.35.

    - Travel – Total $10,245.45

      - Vehicle Fuel ($4,127.65): POA estimates vehicle fuel for the 2 vehicles to cost $60 per month for 60 months of the project to support project staff implement and oversee interventions under Activity 2. The total amount for vehicle fuel is calculated at $60 per month * 60 months + $528 for inflation in Y2-Y6 - $4,128.

      - Local Travel for Implementation of Activity 2 ($3,605.01): POA estimates additional general expenses for project staff implementing and overseeing interventions under Activity 2. This includes local transportation ($35 per trip * 12 trips = + $56 for inflation in Y2-Y6 $476.13), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 2 days per trip *12 trips +369 for inflation in Y2-Y6 = $3,128.88).

      - Local Travel for Overseeing Distribution of Materials ($2,512.79): POA estimates staff will need to complete 63 total trips for staff to oversee the distribution of materials. This estimates local transportation ($35 per trip * 63 trips + $308 for inflation in Y2-Y6 = $2,512.79).

    - Supplies – Total $278,218.00

POA will print and distribute activity books in local languages to target schools as follows:

      - Activity Books for Grades 1-3: estimated at $4 per book * 7,787 books per year in Y1-Y4 * 4 years = $124,584.00.

      - Activity Books for Grades 4-6: estimated at $1 per book   *10,250 books per year in Y1-Y4 * 4 years = $41,000.00.

      - Activity Books for Grades 7-9: estimated at $2 per book * 31,367 books in Y2 = $62,734.00.

      - Game-Based Guides for Grades 3-6: estimated at $1 per guide * 49,900 books total (7,000 books in Y1 and 14,300 books annually in Y2-Y4) = $49,900.00.

    - Indirect Costs – $81,428.64

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $81,428.64.

Activity 3: Training: Teacher and Administrators – Subtotal $2,400,715.18

    - Salaries/Personnel – Total $129,595.27

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary** | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Education Director | 65 | 20% | $4,583 | $5,184 | $67,391.34 |
| Education Specialist | 59 | 20% | $2,500 | $2,802 | $33,068.21 |
| Education Officer | 57 | 20% | $1,000 | $1,125 | $12,827.28 |
| Education & Community Engagement Specialist | 62 | 10% | $1,500 | $1,706 | $10,577.67 |
| Education & Community Engagement Officer | 51 | 10% | $1,000 | $1,124 | $5,730.76 |
| Subtotal |  |  |  |  | $129,595.27 |

    - Fringe Benefits – Subtotal $62,542.68

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $129,595.27 * 48.26% = $62,542.68.

    - Travel – Subtotal $146,104.24

      - Vehicle Fuel ($9,869.12): POA estimates vehicle fuel for the 2 vehicles to cost $150 per month for 57 months of the project to support project staff implement and oversee interventions under Activity 3. The total amount for vehicle fuel is calculated at $150 per month * 57 months + $1,319 for inflation in Y2-Y6 = $9,869.12.

      - Local Travel for Implementation of Activity 3 ($3,605.01): POA estimates additional general expenses for project staff implementing and overseeing interventions under Activity 3. This includes local transportation ($35 per trip * 12 trips + $56 for inflation in Y2-Y6 = $476.13), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 2 days per trip *12 trips + $369 for inflation in Y2-Y6= $3,128.88).

      - Travel for Master Trainings ($58,281.59): POA estimates travel costs for Master Trainings drawing participants from central government departments and regional trainers based in La Paz and teacher coaches selected from local government staff. The estimate includes local transportation ($35 per trip * 10 participants and 2 staff members * 17 trainings + $558 for inflation in Y2-Y6 = $7,697.57), and lodging and M&IE ($40 M&IE per day + $75 lodging per day) * 2 days per trip * 204 trips +$3,664 for inflation in Y2-Y6 = $50,584.02).

      - Travel for Teacher Coaches Curriculum Based Training ($52,976.99): POA estimates travel costs for teacher coaches' curriculum-based training. The estimate includes local transportation ($35 per trip * 15 participants * 12 trainings + $697 for inflation in Y2-Y6= $6,996.96), and lodging and M&IE ($40 M&IE per day + $75 lodging per day) * 2 days per trip * 180 trips $4,580 for inflation in Y2-Y6 = $45,980.03).

      - Travel for Teacher Curriculum Based Training ($13,684.00): POA estimates travel costs for staff to oversee teacher application of improved strategies learned through the curriculum- based training. The estimate includes local transportation ($35 per trip * 5 staff * 9 trainings + $232 for inflation Y2-Y6 = $1,807.32), and lodging and M&IE ($40 M&IE per day + $75 lodging per day) * 2 days per trip * 45 trips + $1,527 for inflation in Y2-Y6 = $11,876.68).

      - Travel for Administrator Training ($7,687.53): POA estimates travel costs for staff to oversee administrator training within the Master Training Program. The estimate includes local transportation ($35 per trip * 5 staff * 5 trainings + $140 for inflation in Y2-Y6 = $1,015.33), and lodging and M&IE ($40 M&IE per day + $75 lodging per day) * 2 days per trip * 25 trips + $922 for inflation in Y2-Y6 = $6,672.00).

    - Other – Total $2,062,473.00

      - Master Level Training ($2,652.00): POA will facilitate 17 Master Level Trainings from Y1 through Y6 for target project schoolteachers. Each training will last for 1 day and will host 10 participants and 2 staff members. The estimated cost of $156 per training includes refreshments ($8 per person * 12 attendees = $96) and training materials ($5 per person *12 attendees = $60) The total cost is calculated as follows: $156/training * 17 trainings = $2,652.00.

      - Teacher Coaches Curriculum Based Training ($2,808.00): POA will facilitate 12 Teacher Coaches Curriculum Based Trainings from Y1 through Y6 for target project schoolteachers. Each training will last for 1 day and will host 18 participants. Estimates include refreshments ($8 per person * 18 attendees = $144) and training materials ($5 per person *18 attendees = $90), for a total of $234 per training. The total cost is calculated as follows: $234/training * 12 trainings = $2,808.00.

      - Teacher Curriculum Based Training ($138,060.00): POA will facilitate 2 Teacher Curriculum Based Trainings per year from Y2 through Y5, and one final training in Y6, for target project schoolteachers (9 trainings total). Each training will last for 1 day and will host 1,175 participants and 5 staff members. Estimates include refreshments ($8 per person * 1,180 attendees = $9,440) and training materials ($5 per person * 1,180 attendees = $5,900), for a total of $15,340 per training. The total cost is calculated as follows: $15,340/training * 9 trainings = $138,060.00.

      - Administrator Training ($22,230 ): POA will facilitate 1 Administrator Training per year from Y2 through Y6 for target school administrative staff (5 trainings total). Each training will last for 1 day and will host 337 participants and 5 staff members. Estimates include refreshments ($8 per person * 342 attendees = $2,736) and training materials ($5 per person * 342 attendees = $1,710), for a total of $4,446 per training. The total cost is calculated as follows: $4,446 per training * 5 trainings = $22,230.00.

      - Subrecipient: FEREMA ($1,896,723.00) – (UEI: NY8TFD4ZL3C3): POA is proposing the Ricardo Ernesto Maduro Andreu Education Foundation (FEREMA) as a subrecipient, a Honduran nonprofit with over 25 years of experience supporting policy development and implementing programs to address critical challenges in the national education system. FEREMA will be responsible for providing technical assistance and oversight for teacher capacity building in targeted instruction and remediation under this activity. The estimated cost for FEREMA is $95,925 in Y1, $555,960 in Y2, $583,758 in Y3, $612,946 in Y4, and $48,134 in Y5, for a total cost of $1,896,723.00. The following is a breakdown of FEREMA’s costs under Activity 3:

        - Salaries (includes LOE for Project Coordinator, Education Officers, Preschool Specialist, Logistics Officer, Financial Specialist, and Financial and Accounting Assistant) =$366,134

        - Fringe 37% = $135,470

        - Travel (includes local transportation (flights & taxis), M&IE, & lodging) = $391,421

        - Professional Services/Contractual (includes specialized trainers and coaches, nutrition technicians/mobilizers, and graphic design) = $586,238

        - Supplies (includes portion of office supplies, laptops, project, printer) = $24,138

        - Other Direct Costs (includes training and workshop costs (venue, refreshments, materials), portion of the following: licenses, office communications, postage, bank fees, and legal costs) = $145,923

        - Indirect Cost 15% = $247,139

Pursuant to 2 C.F.R. § 200.320(c)(2) and consistent with FAR 6.302-1, POA requests approval to engage FEREMA as a sole-source subrecipient under the USDA McGovern-Dole Honduras project. POA conducted market research through consultation with the Ministry of Education, engagement with donor groups, and an independent review of national education organizations, which confirmed that FEREMA is the only Honduran institution with the technical capacity and readiness to implement an evidence-based targeted instruction approach to reduce learning loss and improve literacy outcomes. FEREMA received direct training from Pratham, the international pioneer of the Teaching at the Right Level (TaRL) methodology, and began adapting TaRL to the Honduran education system, providing support to update the GANE guides, making it uniquely qualified to deliver targeted instruction and remediation at scale. This specialized expertise is further reinforced by FEREMA’s more than 25 years of experience in education policy development and program implementation, its proven record of training teachers and administrators, and its ability to convene multi-sectoral stakeholders, including private sector partners, to support education reform. No other local entity combines this unique technical expertise and institutional credibility; engaging an alternative partner would require substantial investments in training and capacity-building, resulting in higher costs and reduced effectiveness. A noncompetitive award to FEREMA is therefore in the best interest of the U.S. Government, ensuring efficient, cost-effective implementation of McGovern-Dole interventions—particularly Objective 2: Strengthening access to quality education and improving literacy outcomes for school-aged children through teacher, administrator, and community training on pedagogy and quality instruction.

    - Indirect Costs – $480,143.04

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $480,143.04.

Activity 4: Enrollment Campaign – Subtotal $629,594.49

    - Salaries/Personnel – Total $181,211.70

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary** | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Education Director | 65 | 20% | $4,583 | $5,184 | $67,391.34 |
| Education Specialist | 59 | 20% | $2,500 | $2,802 | $33,068.21 |
| Education Officer | 57 | 20% | $1,000 | $1,125 | $12,827.28 |
| Communications Specialist | 64 | 10% | $1,500 | $1,700 | $10,877.67 |
| Communications Officer | 48 | 60% | $1,000 | $1,131 | $32,584.55 |
| Education & Community Engagement Specialist | 62 | 15% | $1,500 | $1,706 | $15,866.51 |
| Education & Community Engagement Officer | 51 | 15% | $1,000 | $1,124 | $8,596.14 |
| Subtotal |  |  |  |  | $181,211.70 |

    - Fringe Benefits – Subtotal $87,452.77

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $181,211.70 * 48.26% = $87,452.77.

    - Professional Services/Contractual – Subtotal $44,000.00

Early Warning Systems Consultant ($4,000.00): POA will hire a consultant to help expand Honduras’ Early Warning System (SART) to prevent school dropout in Intibucá and La Paz, where coverage is limited despite national policy. The consultant will provide services in Y2 for 1 month, estimated at $4,000 per month ($4,000/month *1 months = $4,000.00).

Contract for Social Behavior Change Campaign ($40,000.00): POA will hire a firm to design and carry out a mass media social behavior change campaign to boost student enrollment and retention. The firm will conduct the campaign beginning in Y2 and continue through Y6, estimated at $8,000 per year ($8,000/year * 5 years = $40,000.00).

    - Supplies – Subtotal $23,000.00

- Printing, Signage, and Awareness Materials for Early Warning Systems ($5,000.00): POA is budgeting for printing, signage, and awareness materials related to Early Warning Systems in Y2 and Y3. The total estimated cost per year for these materials is $2,500 ($2,500/year * 2 years = $5,000.00).

- Alternative Education Kits ($18,000.00): POA will purchase and distribute 3,000 (600 per year) alternative education kits estimated at $6 per kit to at-risk students between Y1 through Y6 (600 kits/year * 5 years *$6/kit = $18,000.00).

    - Travel – Subtotal $71,664.62

      - Vehicle Fuel ($9,631.18): POA estimates vehicle fuel for the 2 vehicles to cost $140 per month for 60 months of the project to support project staff implement and oversee interventions under Activity 4. The total amount for vehicle fuel is calculated at $140 per month * 60 months + $1,231 for inflation in Y2-Y6 = $9,631.18.

      - Travel for Community Engagement ($62,033.44): POA is budgeting local travel for an estimated 12 Community Engagement trips per year (72 trips total) for 2 project staff throughout the life of project. Estimated costs include local transportation ($35 per trip * 72 trips * 2 staff  + $674 for inflation in Y2-Y6 = $5,713.61) and lodging and M&IE ($40 M&IE per day + $75 lodging per day) * 3 days per trip * 72 trips * 2 staff + $6,640 for inflation in Y2-Y6 = $56,319.84).

    - Other – Subtotal $222,265.40

- Subrecipient: FEREMA (UEI: NY8TFD4ZL3C3) ($208,065.40): POA is proposing FEREMA as a subrecipient to expand access to Honduras’ national play-based model in 102 pre-primary classrooms by providing training to volunteer educators on child development, nutrition, and age- appropriate pedagogy. In addition, FEREMA will provide ongoing coaching and host parenting workshops on school readiness and early stimulation. The estimated cost for FEREMA is $10,523 in Y1, $60,987 in Y2, $64,037 in Y3, $67,239 in Y4, and $5,280 in Y5 for a total cost of $208,065.40. The following is a breakdown of FEREMA’s costs under Activity 4:

  - Salaries (includes LOE for Project Coordinator, Education Officers, Preschool Specialist, Logistics Officer, Financial Specialist, and Financial and Accounting Assistant) =$40,164

  - Fringe 37% = $14,861

  - Travel (includes local transportation (flights & taxis), M&IE, & lodging) = $42,938

  - Professional Services/Contractual (includes specialized trainers and coaches, nutrition technicians/mobilizers, and graphic design) = $64,309

  - Supplies (includes portion of office supplies, laptops, project, printer) = $2,648

  - Other Direct Costs (includes training and workshop costs (venue, refreshments, materials), portion of the following: licenses, office communications, postage, bank fees, and legal costs) = $16,007

  - Indirect Cost 15% = $27,139

- Training for Principals on Early Warning Systems ($14,200.00): POA will deliver two 2-day trainings per year in Y2-Y3 (4 trainings total) on Early Warning Systems to school principals. Each training will be attended by 75 participants at an estimated cost of $3,550 per training, calculated as follows:

  - Printed materials for each training are estimated at $5 per attendee per day ($5* 75 attendees * 2 days = $750)

  - Lunch/refreshments for each training are estimated at $8 per attendee per day ($8 & 75 attendees * 2 days = 1,200)

  - Venue costs for each training are estimated at $800/day ($800 * 2 days = 1,600).

The total cost is calculated as follows: $3,550/training * 4 trainings total = $14,200.00.

    - Indirect Costs – $125,918.90

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $125,918.90.

Activity 5: Building/Rehabilitation: Wells and Water Stations/Systems – Subtotal $703,216.18 ($520,716.18 with $182,500 in cost share)

    - Salaries/Personnel – Subtotal $114,153.35

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary** | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Nutrition and Health Specialist | 63 | 25% | $1,500 | $1,690 | $26,611.97 |
| WASH Officer | 57 | 100% | $1,000 | $1,125 | $64,136.42 |
| Education & Community Engagement Specialist | 62 | 10% | $1,500 | $1,706 | $10,577.67 |
| Education & Community Engagement Officer | 51 | 10% | $1,000 | $1,124 | $5,730.76 |
| Private Sector Specialist | 63 | 5% | $2,000 | $2,253 | $7,096.53 |
| Subtotal |  |  |  |  | $114,153.35 |

    - Fringe Benefits – Subtotal $55,090.41

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $114,153.35 * 48.26% = $55,090.41.

    - Supplies – Subtotal $258,200.00

      - Food Preparation and Storage Items for Schools ($100,200.00): POA will assess need for supplies in target schools. In Y2 and Y3, POA will procure and distribute key food preparation and storage items such as scales and shelving to improve the safety and efficiency of school meals. Costs are estimated at $300 per school for a total of 334 schools per year: 167 in Y2 and 167 in Y3.  $300/school *334 schools = $100,200.00.

      - Behavior-Centered Design Handwashing Stations ($48,000.00): POA will pilot behavior- centered design handwashing stations in 80 schools throughout the life of project (20 schools per year in Y2-Y5), estimated at $600 per school ($600/station * 80 schools = $48,000.00). These stations will serve to promote consistent handwashing among students.

      - Rainwater Harvesting Systems ($60,000.00): Over the four  years, POA will install 40 rainwater harvesting systems in schools without piped water to address chronic water shortages. The costs per system are estimated at $1,500 ($1,500/system * 40 schools = $60,000.00).

      - Maintenance for Existing Handwashing Stations ($50,000.00): POA will support schools with maintaining/servicing existing handwashing stations. This is estimated at $100 per school for 100 schools per year in Y1 through Y5 (500 schools total). $100/school * 500 schools = $50,000.00.

    - Travel – Subtotal $20,292.42

      - Vehicle Fuel ($13,759): POA estimates vehicle fuel for the 2 vehicles to cost $200 per month for 60 months of the project to support project staff implement and oversee interventions under Activity 5. The total amount for vehicle fuel is calculated at $200 per month * 60 months + $1,759 for inflation in Y2-Y6 = $13,758.82.

      - Local Travel for Implementation of Activity 5 ($3,605.01): POA estimates additional general expenses for project staff implementing and overseeing interventions under Activity 5. This includes local transportation ($35 per trip * 12 trips + $56 for inflation in Y2-Y6 = $476.13), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 2 days per trip * 12 trips + $369 for inflation in Y2-Y6 = $3,128.88).

      - Travel for Capacity Building Sessions on Water Systems Maintenance ($2,928.58): POA is budgeting local travel for 10 trips in Y1-Y5 to conduct capacity building sessions on water systems maintenance. Estimated costs include local transportation ($35 per trip * 10 trips + $37 for inflation in Y2-Y5= $386.79) and lodging & M&IE ($40 M&IE per day + $75 lodging per day) * 2 days per trip * 10 trips + $242 for inflation in Y2-Y5= $2,541.79).

    - Other – Subtotal $72,980.00

      - Capacity Building Sessions on Water Systems Maintenance ($3,380.00): POA will conduct 5 one-day capacity building sessions, one per year in Y1-Y5, to train school staff on water systems maintenance. Each training will include 50 school staff and 2 POA staff members. Training costs include the following:

        - Printed materials for each session are estimated at $5 per attendee ($5* 52 attendees * 5 sessions = $1,300)

        - Lunch/refreshments for each session are estimated at $8 per attendee ($8* 52 attendees

* 5 sessions = $2,080)

Total cost for five sessions: $1,300 for printed materials + $2,080 for lunch/refreshments = $3,380.00

      - Small Grants to School Meals Committees for Initial Soap Provision ($69,600.00): POA will provide small grants to schools receiving behavior-centered design handwashing stations and rainwater harvesting systems. There will be 100  grants in Y1 and 120 grants per year in Y2-Y5, for a total of 580 grants. Each grant, estimated at $120 each, will cover the initial provision of soap for these stations and systems. $120/grant * 580 grants = $69,600.00.

    - Indirect Costs –$104,143.24

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $104,143.24.

    - Cost Share –$182,500.00

Public & Private Sector Material Contributions for WASH Stations ($132,500.00): Community stakeholders, members, and private sector companies will contribute materials such as soap and hand towels for the operationalization of the school WASH stations (100 stations per year in Y1-Y5 for a total of 500 WASH Stations). POA estimates $132,500 ($265 in donated materials per WASH station * 500 schools = $132,500.00).

Volunteer Time for Maintenance of WASH Stations ($50,000.00): A total of 100 community members will volunteer 4 hours per school per year in Y1-Y5 to maintain the WASH stations. Valued at $25 per hour, this contribution totals $50,000 (100 community members * 4 hours/year * 5 years * $25/hour = $50,000.00). Their involvement fosters community ownership, making the program more sustainable.

Activity 6: Training: Good Health and Nutrition Practices – Subtotal $1,056,867.11

    - Salaries/Personnel – Subtotal $211,787.41

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary** | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Education Director | 65 | 20% | $4,583 | $5,184 | $67,391.34 |
| Education Specialist | 59 | 20% | $2,500 | $2,802 | $33,068.21 |
| Education Officer | 57 | 20% | $1,000 | $1,125 | $12,827.28 |
| Nutrition and Health Specialist | 63 | 15% | $1,500 | $1,690 | $15,967.18 |
| Nutrition Officer (1) | 54 | 15% | $1,000 | $1,132 | $9,170.46 |
| Nutrition Officer (2) | 54 | 15% | $1,000 | $1,132 | $9,170.46 |
| School Feeding Specialist | 57 | 15% | $1,500 | $1,676 | $14,326.25 |
| Food Aid Monitors (1) | 57 | 7% | $1,000 | $1,140 | $4,547.57 |
| Food Aid Monitors (2) | 57 | 7% | $1,000 | $1,140 | $4,547.57 |
| Communications Specialist | 64 | 15% | $1,500 | $1,700 | $16,316.51 |
| Communications Officer | 48 | 15% | $1,000 | $1,131 | $8,146.14 |
| Education & Community Engagement Specialist | 62 | 10% | $1,500 | $1,700 | $10,577.67 |
| Education & Community Engagement Officer | 51 | 10% | $1,000 | $1,131 | $5,730.76 |
| Subtotal |  |  |  |  | $211,787.41 |

    - Fringe Benefits – Subtotal $102,208.61

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $211,787.41 * 48.26% = $102,208.61.

    - Professional Services/Contractual – Subtotal $158,500.00

Social Behavioral Change Consultant ($18,000.00): POA will hire a consultant to help lead a school- and community-based social behavioral change campaign aimed at reducing health-related absences. The consultant will provide services in Y1 for 2 months and in Y2 for 4 months, estimated at $3,000 per month ($3,000/month * 6 months = $18,000.00).

Contract for Social Behavior Change Campaign ($25,000.00): POA will hire a firm to design the messaging and produce content for a social behavior change campaign to reduce health-related school absences. The firm will design and produce the content for the campaign in Y1, estimated at $25,000.00.

Contract for School Based Environmental Nudges ($67,500.00): POA will hire a firm to design environmental nudges, including visual cues for handwashing, hygienic food handling, healthy eating, and illness prevention, as part of its social behavior change campaign. The firm will conduct the campaign in Y2-Y5 at $15,000 per year, and Y6 at $7,500 ($15,000 * 4 years +$7,500 * 1 year = $67,500.00).

Enumerators & Behavior Monitors ($48,000.00): POA will hire 16 enumerators, one per municipality, to collect data and monitor behavior change among participants of SBC campaigns. Each enumerator will be contracted for one month each in Y1 through Y3 at a rate of $1,000 per month (16 enumerators* 1 month* $1,000* 3 years = $48,000.00).

    - Supplies – Subtotal $37,000.00

      - Development & Printing of Guidance for Scaling ($1,000.00): POA is estimating $1,000 in Y4 for printing guidance on training materials from interactive learning sessions to scale up and sustain the training model.

      - School Based Environmental Nudges Materials ($36,000.00): POA is estimating $8,000 per year in Y2 through Y5, and $4,000 in Y6 ($8,000 *4 years + $4,000), to purchase materials needed for the school based environmental nudges. This will include visual posters and signage to place across schools.

    - Travel – Subtotal $34,765.07

      - Vehicle Fuel ($10,319.12): POA estimates vehicle fuel for the 2 vehicles to cost $150 per month for 60 months of the project to support project staff implement and oversee interventions under Activity 6. The total amount for vehicle fuel is calculated at $150 per month * 60 months + $1,319 for inflation in Y2-Y6 = $10,319.12.

      - Local Travel for Implementation of Activity 6 ($3,605.01): POA estimates additional general expenses for project staff implementing and overseeing interventions under Activity 6. This includes local transportation ($35 per trip * 12 trips + $56 for inflation in Y2-Y6 = $476.13), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 2 days per trip * 12 trips + $369 for inflation in Y2-Y6 = $3,128.88).

      - Travel for Sustaining Messaging Trainings ($11,714.34): POA is budgeting local travel for two staff members to travel to trainings to sustain messaging from social behavior change campaigns across participating schools in Y1 – Y5. Estimated costs include local transportation ($35 per trip * 8 trips per year in Y1-Y5 (40 trips total)  + $147 in inflation for Y2-Y5 = $1,547.18), and lodging & M&IE ($40 M&IE per day + $75 lodging per day) * 40 trips * 2 staff + $967 for inflation in Y2-Y5  = $10,167.16).

      - Travel for Community Mobilization and Outreach Events ($9,126.60): POA is budgeting local travel for staff to travel to community mobilization and outreach events across participating school communities. Estimated costs include local transportation ($35 per trip * 32 trips + $85 for inflation in Y2 and Y3 = $1,205.40) and lodging and M&IE ($40 M&IE per day + $75 lodging per day) * 2 days per trip * 32 trips + $561 for inflation in Y2 and Y3 = $7,921.20).

    - Other – Subtotal $512,606.03

      - Trainings on Sustaining Messaging ($8,840.00): From Y1 through Y5, POA will conduct 20 one-day training sessions, 4 per year, to sustain messaging from social behavior change campaigns across participating schools. Each training will include 32 attendees plus 2 staff members. Training costs include the following:

        - Printed materials for each session are estimated at $5 per attendee ($5* 34 attendees * 20 trainings = $3,400).

        - Lunch/refreshments for each session are estimated at $8 per attendee ($8* 34 attendees

* 20 trainings = $5,440).

Total cost for 20 trainings: $3,400 for printed materials + $5,440 for lunch/refreshments = $8,840.

      - Community Mobilization and Outreach Events ($11,193.00): POA will hold 16 community mobilization and outreach events, 8 in Y2 and 8 in Y3. Each event will include 48 attendees plus 2 staff members. The events will include the following costs:

        - Printed materials for each event are estimated at $5 per attendee ($5* 50 attendees *16 events = $4,000).

        - Lunch/refreshments for each event are estimated at $8 per attendee ($8* 50 attendees

*16 events = $6,400).

Total cost for 16 events: $4,000 for printed materials + $6,400 for lunch/refreshments + $793 for inflation = $11,193.00.

      - Subrecipient: FEREMA ($492,573.03) – (UEI: NY8TFD4ZL3C3): POA is proposing FEREMA as a subrecipient. Under Activity 6, FEREMA will conduct interactive, school- based nutrition education sessions to strengthen the knowledge and behaviors of teachers, caregivers, and parents. The estimated cost for FEREMA is $24,911 in Y1, $144,381 in Y2,

$151,600 in Y3, $159,180 in Y4, and $12,500 in Y5 for a total cost of $492,573.03. The following is a breakdown of FEREMA’s costs under Activity 6:

  - Salaries (includes LOE for Project Coordinator, Education Officers, Preschool Specialist, Logistics Officer, Financial Specialist, and Financial and Accounting Assistant) =$95,084

  - Fringe 37% = $35,181

  - Travel (includes local transportation (flights & taxis), M&IE, & lodging) = $101,651

  - Professional Services/Contractual (includes specialized trainers and coaches, nutrition technicians/mobilizers, and graphic design) = $152,244

  - Supplies (includes portion of office supplies, laptops, project, printer) = $6,269

  - Other Direct Costs (includes training and workshop costs (venue, refreshments, materials), portion of the following: licenses, office communications, postage, bank fees, and legal costs) = $37,896

  - Indirect Cost 15% = $64,249

    - Indirect Costs – $211,373.42

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $211,373.42 .

Activity 7: Training: Commodity Management – Subtotal $357,568.95

    - Salaries/Personnel – Subtotal $67,802.66

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary** | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Policy & Sustainability Specialist | 37 | 10% | $1,500 | $1,778 | $6,577.91 |
| Nutrition and Health Specialist | 63 | 10% | $1,500 | $1,690 | $10,644.79 |
| School Feeding Specialist | 57 | 25% | $1,500 | $1,676 | $23,877.09 |
| Food Aid Monitors (1) | 57 | 8% | $1,000 | $1,140 | $5,197.22 |
| Food Aid Monitors (2) | 57 | 8% | $1,000 | $1,140 | $5,197.22 |
| Education & Community Engagement Specialist | 62 | 10% | $1,500 | $1,700 | $10,577.67 |
| Education & Community Engagement Officer | 51 | 10% | $1,000 | $1,131 | $5,730.76 |
| Subtotal |  |  |  |  | $67,802.66 |

    - Fringe Benefits – Subtotal $32,721.57

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. POA Fringe Benefits CCN Staff: $67,802.66 * 48.26% = $32,721.57.

    - Travel – Subtotal $7,044.72

      - Vehicle Fuel Expense ($3,439.71): POA estimates vehicle fuel for the 2 vehicles to cost $50 per month for 60 months of the project to support project staff implement and oversee interventions under Activity 7. The total amount for vehicle fuel is calculated at $50 per month * 60 months + $440 for inflation in Y2-Y6 = $3,439.71.

      - Local Travel for Implementation of Activity 7 ($3,605.01): POA estimates additional general expenses for project staff implementing and overseeing interventions under Activity 7. This includes local transportation ($35 per trip * 12 trips +$56 for inflation in Y2-Y6 = $476.13), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 2 days per trip *12 trips + $369 in inflation for Y2-Y6 = $3,128.88).

    - Professional Services/Contractual – Subtotal $250,000.00

Contract to Certify School Food Handlers ($250,000.00): POA intends to contract an institution, such as Zamorano University, to co-develop a national School Food Handler Certification to certify school food handlers. The certification will consist of a 20-hour modular course available in-person and online, estimated at $62,500 per certification, held annually from Y1-Y4 ($62,500 * 4  = $250,000.00).

    - Indirect Costs –$71,513.79

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $71,513.79.

Activity 8: Capacity Building: Local and Regional Level – Subtotal $377,369.91 ($365,869.91 with $11,500 in cost share)

    - Salaries/Personnel – Subtotal $126,706.98

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary** | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Policy & Sustainability Specialist | 37 | 20% | $1,500 | $1,778 | $13,155.83 |
| Education Director | 65 | 10% | $4,583 | $5,184 | $33,695.67 |
| Education Specialist | 59 | 10% | $2,500 | $2,802 | $16,534.10 |
| Education Officer | 57 | 10% | $1,000 | $1,125 | $6,413.64 |
| Nutrition and Health Specialist | 63 | 5% | $1,500 | $1,690 | $5,322.39 |
| School Feeding Specialist | 57 | 5% | $1,500 | $1,676 | $4,775.42 |
| Communications Specialist | 64 | 10% | $1,500 | $1,700 | $10,877.67 |
| Communications Officer | 48 | 10% | $1,000 | $1,131 | $5,430.76 |
| Education & Community Engagement Specialist | 62 | 10% | $1,500 | $1,700 | $10,577.67 |
| Education & Community Engagement Officer | 51 | 10% | $1,000 | $1,131 | $5,730.76 |
| Private Sector Specialist | 63 | 10% | $2,000 | $2,253 | $14,193.05 |
| Subtotal |  |  |  |  | $126,706.98 |

    - Fringe Benefits – Subtotal $61,148.79

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $126,706.98 * 48.26% = $61,148.79.

    - Travel – Subtotal $22,671.15

      - Vehicle Fuel ($6,879.41): POA estimates vehicle fuel for the 2 vehicles to cost $100 per month for 60 months of the project to support project staff implement and oversee interventions under Activity 8. The total amount for vehicle fuel is calculated at $100 per month * 60 months + $879 for inflation in Y2-Y6 = $6,879.41.

      - Local Travel for Implementation of Activity 8 ($3,605.01): POA estimates additional general expenses for project staff implementing and overseeing interventions under Activity 8. This includes local transportation ($35 per trip * 12 trips +$56 for inflation in Y2-Y6 = $476.13), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 2 days per trip *12 trips + $369 for inflation in Y2-Y6 = $3,128.88).

      - Stipend for Local Travel for Annual Volunteer Recognition Events ($1,450.48): POA estimates

$50 per trip as a stipend for staff traveling to the Annual Volunteer Recognition Events, with 5 trips planned per year in Y2 through Y6 ($50 * 25 trips total +$200 for inflation in Y2-Y6 = $1,450.48).

      - Local travel for Digital School Meal Monitoring System Trainings ($10,736.25): POA estimates holding one training in Y2 to build the capacity of schools in the use of the tool. The estimate includes local transportation for 10 master trainers ($55 per trip* 10 trips in Y2 + $28 for inflation = $577.50), and lodging and M&IE (($44 M&IE per day + $150 lodging per day) * 5 days per trip *10 trips + $459 for inflation = $10,158.75).

    - Professional Services/Contractual – Subtotal $120,000.00

Consultant to Develop Step-by-Step Recipe and Demonstration Guides ($10,000.00): POA will hire a consultant for 4 months in Y1 at $2,500 per month ($2,500 per month * 4 months = $10,000.00) to develop recipe cards and demonstration guides to help integrate recipe-based nutrition education into the MOE’s Escuela para Padres. The monthly rate assume 20 days a month (4 weeks *5 days) x $125 daily rate = 2,500/month.

Video Editing and Design Consultant for Recipe Demos ($20,000.00): POA will hire a consultant for 4 months in Y1 and one month per year in Y2 through Y5 at $2,500 per month ($2,500 per month * 8 months total = $20,000.00). The monthly rate assume 20 days a month (4 weeks * 5 days) x $125 daily rate = 2,500/month. The consultant will edit videos and develop recipe demos for recipe-based nutrition education.

IT Consultant to Design Modules for Digital School Meal Monitoring System ($30,000.00): POA will hire an IT consultant for 10 months in Y2 and Y3 at $1,500 per month to design and develop training modules for the digital school meal monitoring system ($1,500 per month * 20 months total = $30,000.00). The monthly rate assume 20 days a month (4 weeks * 5 days) x $75 daily rate = 1,500/month.

Develop a Platform to Monitor the Delivery of Rations ($60,000.00): POA will hire a firm to develop a platform to digitize school meal monitoring in their existing system to track food deliveries, stocks, attendance, and meals served at the school level. POA estimates to hire a firm for $60,000.00 in Y2, this is based on POA’s prior experience implementing similar contracts. The estimated breakdown for the fixed price contract is as follows:

- System design & requirements analysis = $10,000

- Software development & customization = $35,000

- Testing & quality assurance = $5,000

- Security & data protection and compliance = $5,000

- Project management = $5,000

    - Supplies – Subtotal $24,000.00

      - Basic Package of Materials ($24,000.00): POA will develop a basic package of materials, including printable recipe cards, nutrition tips, and demonstration guides, to distribute to 3,000 parents (750 per year) starting in Y2 at $8 per package ($3,000 * 8 = $24,000.00).

    - Other – Subtotal $11,343.00

      - Digital School Meal Monitoring System Training: conducted in 50 pilot schools in Year 2 at $393/training = $393.00

      - Annual Volunteer Recognition Event ($10,950.00): POA will hold annual volunteer recognition events in Y2 through Y6 at $2,190 per event for 125 attendees and 5 staff members. Costs include:

        - Printed materials for each session are estimated at $5 per attendee ($5 * 130 attendees

= $650).

        - Lunch/refreshments for each session are estimated at $8 per attendee ($8* 130 attendees = $1,040).

        - Venue costs are estimated at $500 per event.

$2,190 * 5 events (1 annually from Y2-Y6) = $10,950.00.

    - Indirect Costs – $73,173.98

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $73,173.98.

    - Cost Share – $11,500.00

Annual Volunteer Recognition Events ($11,500.00): From  Y2 to Y6, local government and private sector partners will contribute to the annual volunteer recognition events by contributing additional supplies, travel stipends, and speakers, valued at $2,300 per event ($2,300 per event * 5 annual events = $11,500.00).

Activity 9: Capacity Building: National Level – Subtotal $425,854.90

    - Salaries/Personnel – Subtotal $108,822.24

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Policy & Sustainability Specialist | 37 | 30% | $1,500 | $1,778 | $19,733.74 |
| Education Director | 65 | 10% | $4,583 | $5,184 | $33,695.67 |
| Education Specialist | 59 | 10% | $2,500 | $2,802 | $16,534.10 |
| Education Officer | 57 | 10% | $1,000 | $1,125 | $6,413.64 |
| Nutrition and Health Specialist | 63 | 5% | $1,500 | $1,690 | $5,322.39 |
| School Feeding Specialist | 57 | 5% | $1,500 | $1,676 | $4,775.42 |
| Education & Community Engagement Specialist | 62 | 5% | $1,500 | $1,700 | $5,288.84 |
| Education & Community Engagement Officer | 51 | 5% | $1,000 | $1,131 | $2,865.38 |
| Private Sector Specialist | 63 | 10% | $2,000 | $2,253 | $14,193.05 |
| Subtotal |  |  |  |  | $108,822.24 |

    - Fringe Benefits – Subtotal $52,517.61

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $108,822.24 * 48.26% = $52,517.61.

    - Travel – Subtotal $14,915.04

      - Vehicle Fuel ($4,127.65): POA estimates vehicle fuel to cost $60 per month for 60 months of the project to support project staff oversee interventions under Activity 9. The total amount for vehicle fuel is calculated at $60 per month * 60 months + 528 for inflation in Y2-Y6 = $4,128.

      - Local Travel for Implementation of Activity 9 ($3,605.01): POA estimates additional general expenses for project staff implementing and overseeing interventions under Activity 9. This includes local transportation ($35 per trip * 12 trips + $56 for inflation in Y2-Y6 = $476.13), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 2 days per trip * 12 trips + $369 for inflation in Y2-Y6 = $3,128.88).

      - Travel to Support the Decentralization of PNAE ($4,364.88): POA estimates travel expenses to support project staff working to decentralize PNAE activities, for a total of 9 trips in Y6. This includes local transportation ($35 per trip * 9 trips + $87 for inflation = $402.03), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 3 days per trip * 9 trips + $858 for inflation = $3,962.85).

      - International Travel by Consultant ($2,817.50): An international consultant will travel to Tegucigalpa and Intibucá in Y1 to conduct cost analyses to inform PNAE scaling. Costs include one round-trip flight from USA to Honduras ($800.00), local transportation ($50 per day * 10 days = $500.00), lodging and M&IE in Tegucigalpa (($43.50 M&IE per day + $150 lodging per day) * 5 days = $967.50), and lodging and M&IE in Intibucá (($40 M&IE per day + $70 lodging per day) * 5 days = $550.00).

    - Professional Services/Contractual – Subtotal $213,000.00

Contract for Certification in Local Procurement for School Feeding ($154,800.00): POA will contract Zamorano University or a comparable accredited institution to co-develop and institutionalize a certificate in Local Procurement for School Feeding. This formal course will professionalize the role of mancomunidades officials and other local actors in transparent and efficient management of food procurement. The certificate program will be developed and piloted in Y1-Y6, formally accredited by Y3. POA is estimating a total of $25,800 per year from Y1-Y6 for this contract ($25,800/year * 6 years = $154,800.00).

International Consultant to Conduct Cost Analysis to Inform PNAE Scaling ($12,000.00): POA will hire a consultant to develop step-by-step recipe and demonstration guides for 20 days in Y1 at a daily rate of $600 per day (20 days * 600/day = $12,000.00).

Consultant to Review Legal Framework and Advocacy ($27,000.00): POA will hire a consultant to review legal framework and advocacy in Y2 through Y3 estimated for 45 days per year at a daily rate of $300 per day (90 days total * $300/day = $27,000.00).

Graphic Design of Roadmap for Decentralized PNAE Operations ($1,200.00): POA will hire a consultant to lead the graphic design of the Roadmap for Decentralized PNAE Operations in Y4 for 10 days at a base daily rate of $120 per day (10 days * $120/day = $1,200.00).

Contract to Document and Replicate Best Practices for National Scale-Up ($18,000.00): POA will hire a firm to document and replicate best practices for the National Scale-Up strategy in Y3 estimated at $3,000 per month for 6 months (6 months * $3,000/month = $18,000.00).

    - Supplies – Subtotal $3,000.00

Toolkit Supplies ($3,000.00): POA will print the Practical Knowledge Toolkits developed under this activity for a total of $3,000.00 in Y4.

    - Other – Subtotal $33,600.00

Validation Meetings ($6,000.00): POA will hold monthly meetings to validate findings of the Cost Analysis to inform PNAE scaling in Y2 and Y3 at $250 per meeting for 12 meetings per year. (24 meetings total * $250/meeting = $6,000.00).

Two-Day Workshop on Proposed Graduation Strategy ($27,600.00): POA will hold 2 two-day workshops per year on the proposed graduation strategy in Y1 through Y6 (2 two-day workshops per year * 6 years = 12 two-day workshops total). Each workshop will host 50 participants at an estimated cost of $2,300 per workshop. Costs include:

        - Printed materials for each session are estimated at $5 per attendee per day ($5 * 50 attendees * 2 days = $500).

        - Lunch/refreshments for each session are estimated at $8 per attendee per day ($8* 50 attendees *2 days = $800).

        - Venue costs are estimated at $500 per event per day ($500 * 2 days = $1,000).

        - Total cost per two-day workshop: $500 for printed materials + $800 for lunch/refreshments + $1,000 for venue costs = $2,300

The total cost is estimated as: 2 two-day workshops per year * 2,300 per workshop * 6 years = $27,600.00.

    - Indirect Costs –$85,170.98

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $85,170.98.

Activity 10: Develop Public-Private Partnerships to Support School Feeding Sustainability – Subtotal $483,935.92 ($462,935.92 with $21,000 in cost share)

    - Salaries/Personnel – Subtotal $223,765.60

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Policy & Sustainability Specialist | 37 | 30% | $1,500 | $1,778 | $19,733.74 |
| Education Director | 65 | 10% | $4,583 | $5,184 | $33,695.67 |
| Education Specialist | 59 | 10% | $2,500 | $2,802 | $16,534.10 |
| Education Officer | 57 | 10% | $1,000 | $1,125 | $6,413.64 |
| Nutrition and Health Specialist | 63 | 10% | $1,500 | $1,690 | $10,644.79 |
| School Feeding Specialist | 57 | 5% | $1,500 | $1,676 | $4,775.42 |
| Communications Specialist | 64 | 15% | $1,500 | $1,700 | $16,316.51 |
| Communications Officer | 48 | 15% | $1,000 | $1,131 | $8,146.14 |
| Education & Community Engagement Specialist | 62 | 5% | $1,500 | $1,700 | $5,288.84 |
| Education & Community Engagement Officer | 51 | 5% | $1,000 | $1,131 | $2,865.38 |
| Private Sector Specialist | 63 | 70% | $2,000 | $2,253 | $99,351.37 |
| Subtotal |  |  |  |  | $223,765.60 |

    - Fringe Benefits – Subtotal $107,989.28

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $223,765.60 * 48.26% = $107,989.28.

    - Professional Services/Contractual – Subtotal $115,200.00

Consultant for Developing Public-Private Partnerships (PPP) to Strengthen School Feeding Services  ($24,000.00): POA will hire a consultant to develop a strategy to incorporate  public, corporate, and philanthropic financing to support school feeding at $3,000 per month for 4 months in Y1 and 4 months in Y2 (8 months total). $3,000/month * 8 months = $24,000.00. The monthly rate assume 20 days a month (4 weeks * 5 days) x $150 daily rate = 3,000/month.

Legal Advisor for Activities ($2,400.00): POA will hire a legal advisor to support with municipal mapping and needs assessments, co-development of partnership MOUs, cost-sharing templates, and recognition strategies. POA is estimating a rate of $300 per day for 8 days in Y2 ($300/day * 8 days = $2,400.00).

IT Consultant to Support CSR Activation Platform ($9,000.00): POA will hire an IT consultant for the development of the CSR Activation Platform at $3,000 per month for 3 months in Y1 ($3,000 / month * 3 months = $9,000.00). The monthly rate assume 20 days a month (4 weeks * 5 days) x $150 daily rate = 3,000/month.

Graphic Designer for CSR Platform ($1,800.00): POA will hire a graphic designer to create high- quality campaign content (videos, infographics, school profiles) for the CSR platform, estimated at $120 per day for 15 days in Y1 ($120/day * 15 days = $1,800.00).

Creative Content Production ($78,000.00): POA will hire a firm to produce engaging content to engage the Honduran Diaspora in school feeding support, estimated at $6,500 per month for 4 months per year in Y3 through Y5 (3 years total). $6,500/ month * 4 months/year * 3 years = $78,000.00.

    - Travel Costs – Subtotal $8,339.04

      - Vehicle Fuel ($4,127.65): POA estimates vehicle fuel for the 2 vehicles to cost $60 per month for 60 months to support project staff oversee interventions under Activity 10. The total amount for vehicle fuel is calculated at $60 per month * 60 months + 528 for inflation in Y2-Y6 = $4,127.65.

      - Local Travel for Implementation of Activity 10 ($3,605.01): POA estimates additional general expenses for project staff implementing and overseeing interventions under Activity 10. This includes local transportation ($35 per trip * 12 trips + $56 for inflation in Y2-Y6 = $476.13), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 2 days per trip * 12 trips + $369 for inflation in Y2-Y6 = $3,128.88).

      - Local Travel for Capacity Building Meetings for Municipal Staff and Business Leaders ($606.38): POA will hold 2 capacity building meetings in Y3 for Municipal Staff and Business Leaders. Travel costs include local transportation ($55 per trip * 2 trips + $11 for inflation = $121.28) and lodging and M&IE (($40 M&IE per day + $70 lodging per day) * 2 days per trip *2 trips + $45 for inflation = $485.10).

    - Other– Subtotal $7,642.00

      - Validation Workshops ($2,656.00): POA will hold 2 validations workshops per year in Y2 and Y3 (4 workshops total) for 25 attendees and 3 staff (28 attendees per workshop) at an estimated rate of $664 each. Costs per workshop include:

        - Printed materials for each session are estimated at $5 per attendee ($5* 28 attendees = $140).

        - Lunch/refreshments for each session are estimated at $8 per attendee ($8* 28 attendees

= $224).

        - Venue costs are estimated at $300 per event

        - Total cost per workshop: $140 for printed materials + $224 for lunch/refreshments + $300 for venue costs = $664

The total cost is calculated as: 4 workshops total * $664 per workshop = $2,656.00

      - Capacity Building Meetings for Municipal Staff and Business Leaders ($486.00): POA will hold 2 meetings in Y3 for 10 attendees and one staff member (11 people total per meeting) at an estimated rate of $243 per workshop . Costs include:

        - Printed materials for each session are estimated at $5 per attendee ($5* 11 attendees * 2 events = $110).

        - Lunch/refreshments for each session are estimated at $8 per attendee ($8* 11 attendees

* 2 events = $176).

        - Venue costs are estimated at $100 per event ($100 * 2 events = $200).

        - Total cost for two meetings: $110 in printed materials + $176 for lunch/refreshments + $200 for venue costs = $486.00.

      - Meetings on the CSR Activation Platform ($4,500.00): POA will organize monthly meetings in Y2 through Y6 at $75 each for 60 meetings to review and discuss the Corporate Social Responsibility Activation Platform. Total costs are calculated as: $75/meeting * 60 meetings = $4,500.00.

    - Cost Share –$21,000.00

Venue & A/V Equipment for Validation Workshops ($6,000.00): Local stakeholders will contribute venue & A/V equipment for the validation workshops valued at $1,500 per workshop in Y2 and Y3. $1,500 per workshop * 2 workshops/year in Y2 and Y3 * 2 years = $6,000.00.

Venue & A/V Equipment Meetings on CSR Activation Platform ($15,000.00): Local stakeholders will contribute venue and A/V equipment for the meetings on the CSR activation platform valued at $250 per meeting for 12 meetings in Y2 through Y6 (5 years total). $250/meeting * 12 meetings * 5 years = $15,000.00.

    - Indirect Costs –$92,587.18

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $92,587.18.

Activity 11: Expand Use of U.S. Commodities in Honduras’ School Feeding Program – Subtotal $94,308.66 ($89,328.66 + $4,980 in cost share)

    - Salaries/Personnel – Subtotal $54,237.07

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary** | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Policy & Sustainability Specialist | 37 | 10% | $1,500 | $1,778 | $6,577.91 |
| Nutrition and Health Specialist | 63 | 5% | $1,500 | $1,690 | $5,322.39 |
| School Feeding Specialist | 57 | 5% | $1,500 | $1,676 | $4,775.42 |
| Education & Community Engagement Specialist | 62 | 5% | $1,500 | $1,700 | $5,288.84 |
| Education & Community Engagement Officer | 51 | 5% | $1,000 | $1,131 | $2,865.38 |
| US Commodity Logistics Specialist | 65 | 20% | $2,000 | $2,262 | $29,407.13 |
| Subtotal |  |  |  |  | $54,237.07 |

    - Fringe Benefits – Subtotal $26,174.81

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $54,237.07 * 48.26% = $26,174.81.

    - Travel – Subtotal $6,356.78

- Vehicle Fuel ($2,751.76): POA estimates vehicle fuel for the 2 vehicles to cost $40 per month for 60 months of the project to support project staff implementation and oversee interventions under Activity 11 ($40/month * 60 months + $352 for inflation in Y2-Y6 = $2,751.76).

- Local Travel for Implementation of Activity 11 ($3,605.01): POA estimates additional general expenses for project staff implementing and overseeing interventions under Activity 11. This includes local transportation ($35 per trip * 12 trips + $56 for inflation in Y2-Y6= $476.13), and lodging and M&IE (($40 M&IE per day + 75 lodging per day) * 2 days per trip * 12 trips + $369 for inflation in Y2-Y6 = $3,128.88).

    - Other – Subtotal $2,560.00

Workshop to Present Study Findings ($2,560.): POA will conduct one workshop in Y3 and one in Y6 (2 workshops total) to present the findings of the Special Study targeting the integration of CSB+ and eggs into the National Feeding Program. The workshops will host 60 stakeholders each at an estimated rate of $1,280 per workshop. Costs include:

        - Printed materials for each session are estimated at $5 per attendee ($5* 60 attendees = $300).

        - Lunch/refreshments for each session are estimated at $8 per attendee ($8* 60 attendees

= $480).

        - Venue costs are estimated at $500 per event.

2 workshops total * $1,280/workshop = $2,560.00.

    - Indirect Costs –$17,865.73

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $17,865.73.

    - Cost Share –$4,980.00

Workshop to Present Study Findings ($4,980.00): In Y2 and Y6, local government and private sector partners will contribute to the annual volunteer recognition events by contributing additional supplies, travel stipends, and speakers, valued at $2,490 per event. 2 events total * $2,490/event = $4,980.00.

  - Commodity and Food Purchase – Subtotal $3,938,871.73

- Subtotal Direct Costs: $3,282,393.11

- Subtotal Indirect Costs: $656,478.62

    - Commodity Procurement – Subtotal $3,282,393.11

|  | Egg | Fruits |  | Vegetables |  |  | TOTAL |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MT | Cost | MT | Cost | MT | Cost | MT | Cost |
| Y1 | 202 | $354,933 | 150 | $63,000 | 100 | $67,000 | 452 | $484,933 |
| Y2 | 202 | $372,680 | 150 | $66,150 | 100 | $70,350 | 452 | $509,180 |
| Y3 | 202 | $391,314 | 150 | $69,458 | 100 | $73,868 | 452 | $534,639 |
| Y4 | 202 | $410,880 | 150 | $72,930 | 100 | $77,561 | 452 | $561,371 |
| Y5 | 202 | $431,424 | 150 | $76,577 | 100 | $81,439 | 452 | $589,439 |
| Y6 | 202 | $452,995 | 120 | $64,325 | 100 | $85,511 | 422 | $602,830 |
| Subtotal | 1,210 | $2,414,226 | 870 | $412,439 | 600 | $455,728 | 2,680 | $3,282,393 |

    - Indirect Costs – Commodity and Food Purchases –$656,478.62

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $656,478.62.

  - Internal Transportation, Storage, and Handling (ITSH) – Subtotal $3,243,158.96

- Subtotal Direct Cost: $2,702,632.47

- Subtotal Indirect Cost: $540,526.49

    - Salaries/Personnel – Subtotal $953,187.37

| Position (All CCN) *Key personnel | Months | LOE | Base Monthly Salary | Average Monthly Salary | Salary Subtotal |
| --- | --- | --- | --- | --- | --- |
| Supply Chain Manager | 67 | 100% | $5,000 | $5,636 | $377,589.14 |
| In-Country Logistics Specialist | 65 | 100% | $2,000 | $2,262 | $147,035.66 |
| US Commodity Logistics Specialist | 65 | 80% | $2,000 | $2,262 | $117,628.52 |
| Warehouse Manager | 64 | 100% | $1,250 | $1,416 | $90,647.28 |
| Warehouse Officer (1) | 56 | 100% | $1,000 | $1,132 | $63,412.70 |
| Warehouse Officer (2) | 56 | 100% | $1,000 | $1,132 | $63,412.70 |
| LRP Technical Specialist | 56 | 100% | $1,500 | $1,669 | $93,461.36 |
| Subtotal |  |  |  |  | $953,187.37 |

    - Fringe Benefits – Subtotal $460,008.22

POA calculated benefits for CCN staff at 48.26% of the employees’ base salary. See the detailed breakdown in Section 2.2. Fringe Benefits CCN Staff: $953,187.37 * 48.26% = $460,008.22.

    - Travel – Subtotal $37,600.88

      - Vehicle Fuel Expense ($10,319.12): POA estimates vehicle fuel for the 2 vehicles to cost $150 per month for 60 months of the project to support project staff implement and oversee ITSH related activities. The total amount for vehicle fuel is calculated at $150 per month * 60 months + 1,319 for inflation in Y2-Y6 = $10,319.12.

      - Local Travel ($27,281.76): POA is estimating 63 trips of 3-days each for ITSH activities. This estimate includes local transportation ($35 per trip * 63 trips + $308 for inflation = $2,512.79) and lodging and M&IE(($40 M&IE per day + $75 lodging per day) * 3 days * 63 trips + $3,034  for inflation in Y2-Y6 = $24,768.97).

    - Internal Transportation – Subtotal $381,450.00

      - Internal Transportation – US Commodities ($351,200.00): $40/MT to transport 8,780 MT during Y1-Y6 ($40/MT * 8,780 MT = $351,200.00).

      - Internal Transportation – Eggs ($30,250.00): $25/MT to transport 1,210  MT during Y1-Y6 ($25/MT * 1,210 MT = $30,250.00).

    - Professional Services/Contractual – Subtotal $279,600.00

Warehouse Cleaning & Repairs ($18,600): POA is estimating warehouse cleaning and repair services for the upkeep of the warehouse at a rate of $300 per month for 62 months through the LOP ($300/month * 62 months = $18,600.00).

Phytosanitary and Other Permits ($15,000.00): POA is estimating phytosanitary and other permits to facilitate commodity movement from the port and within the country at $2,500 per year in Y1 through Y6 ($2,500/year * 6 years = $15,000.00).

Clearing Agent for Customs/Customs Clearance Services ($180,000.00): POA is budgeting for customs clearance services at $30,000 per year in Y1 through Y6 ($30,000/year * 6 years = $180,000.00).

Commodity Management, Warehouse, and Logistics Consultant ($54,000): POA is budgeting for a local expert to advise on the setup and location of the project warehouses at a rate of $600 per day for 90 days in Y1 ($600/day * 90 days = $54,000).

Call Forward Consultant ($12,000): POA is budgeting for a consultant to support the first call forward process at a rate of $600 per day for 10 days per year in Y1 and Y2 ($600/day * 10 days/year * 2 years = $12,000).

    - Warehouse – Subtotal $588,366.00

      - Warehouse Rental and Security Costs ($367,004.00): POA is estimating $66,728 per year in Y1-Y5 and $33,364 in Y6 to cover warehouse and security costs for 6 years to safeguard and distribute U.S. commodities throughout the LOP ($66,728/year * 5 years + $33,364 = $367,004.00).

      - Preventative Fumigation (Main & Secondary Warehouse) ($77,400.00): POA is budgeting $12,900 per year to conduct annual preventative fumigation at the project’s main and secondary warehouse. The total estimated cost is $77,400.00 ($12,900/year * 6 years = $77,400. POA estimates the yearly rate of $12,900 based on the $8,900 for the main warehouse + $4,000 for the secondary warehouse.

      - Regular Fumigation (Main & Secondary Warehouse) ($49,600.00): In addition to annual preventative fumigation, POA will also conduct regular fumigation at the main and secondary warehouse three times annually in Y1-Y5, and once in Y6 (16 times total), at an estimated cost of $3,100 per fumigation. The total cost is calculated as follows: $3,100 per fumigation * 16 times total = $49,600.00.

      - Municipality Fumigation Kits ($5,400.00): POA will provide one fumigation kit per municipality each year to 36 municipalities over the LOP at an estimated rate of $25  per kit ($25  per kit * 36 municipalities * 6 years = $5,400.00). The kits will be used by the municipalities to manage their warehouses and ensure safekeeping of commodities.

      - Unloading and Stowage ($16,500.00): POA is budgeting for commodity unloading and stowage at a rate of $3,000 per year for Y1 and Y5, and $1,500 in Y6 ($3,000/year * 5 years + $1,500 for Y6 = $16,500.00).

      - Repacking of  Commodities Materials for Schools ($46,872.00): POA will provide school repackaging materials for commodities to 1,953 schools each year over the LOP at a rate of $4  per unit ($4  per unit * 1,953 schools * 6 years = $46,872.00).

      - Take Home Ration Packaging ($23,400.00): POA is budgeting to provide take home ration packaging to approximately 1/3 of schools each year (1/3 * 1,953 schools ≈ 650), for a total of 650 packaging kits per year at $6/kit ($6/kit * 650 kits/year * 6 years = $23,400.00). Take-home rations will be repackaged using safe, durable materials appropriate for food commodities.

      - Printing Material for Warehouse Safety Signs ($2,160.00): POA will develop and print 36 municipality warehouse safety signs each year for the project and municipality warehouse. Each sign is estimated to cost $10 per unit ($10 per unit * 36 municipalities * 6 years = $2,160.00).

    - Supplies – Subtotal $2,450.00

Tablets for Warehouse ($2,450.00): POA will purchase 7 tablets in Y1 at $350 each for project staff managing the warehouse (7 tablets *$350/tablet = $2,450.00). The tablets will be used to record inventory data, track commodity movements, and support real-time reporting to strengthen warehouse management and traceability under the project.

    - Indirect Costs – ITSH –$540,526.49

In accordance with POA’s reduced indirect cost application of 20% for this proposal, indirect costs are estimated at $540,526.49.