Annex B: POA Work Plan

Anticipated Start Date: January 1, 2024

| Project to Improve Adherence to International Labor Standards in the Agricultural Sector in Ecuador | Responsible Organization | Year 1 (2024) |  |  |  | Year 2 (2025) |  |  |  | Year 3 (2026) |  |  |  | Year 4 (2027) |  |  |  | Deliverables |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q 3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |
| Project Startup, Management, and Closeout |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initial kick-off meeting with USDOL | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deploy staff from POA HQ to travel to El Oro and Cotopaxi to lead initial start-up activities | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobilize key staff and formalize contracts with all local staff | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide Awardee contact information and written notice to USDOL that key personnel have begun to work on the project | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Open bank account | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Set in place financial and administrative systems | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Meet government officials and local counterpart organizations to build relations; review goals and expectations; and agree on activities, indicators, targets, and expected results | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Formalize scopes of work and contractual documents with all partner organizations | POA, INDES & partner organizations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop project communication plans | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit draft CMEP and Project Document | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit final CMEP (including data collection tools and final TPR Annex A with indicator targets) and Project Document | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit Federal Financial Report (FFR) Standard Form (SF) 425 | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit full Technical Progress Report (TPR) | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit equipment and Real Property Inventory List to Grant Officer | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit Government Property Inventory Disposition Request; inventory list of all real property, equipment with an acquisition value of > USD 5,000 per unit, and supplies if aggregate value < USD 5,000 | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Set in place a plan to prepare all close-out documents per the Closeout Document Checklist, including Final Technical Report Final Quarterly FFR/SF-425; Closeout Financial Form; Recipient’s Release Form; Recipient’s Assignment of Refunds, Rebates, and Credits Form; and Government Property Closeout Inventory Certification within 120 days after the end of the project | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 1: Increased capacity of government officials to enforce labor laws specifically related to child labor, forced labor, occupational safety and health and other labor rights in the agricultural sector. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Assess labor law enforcement institutions, processes, and services | POA & GADs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | •6 Consejos and 6 Juntas capacity building plans developed and routinely monitored •Services and opportunities guide created for 6 cantons •Sustainable child labor tracking system tested, refined, and in use in 6 cantons •Training curricula developed and institutionalized for MOL, MOA, prosecutors/police, Ombudsman Offices, schools, health providers, and for GADs, Consejos, and Juntas) |
| 1.2 Strengthen intersectoral coordination by re-invigorating referral mechanisms and strengthening Consejos and Juntas | POA & GADs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 Develop government capacity building strategy applying assessment results | POA & GADs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 Develop, deliver, and institutionalize tailored capacity building for government officials | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5 Strengthen digital child labor tracking and public reporting/accountability | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6 Partner with GADs to integrate enforcement processes and capacity building into local community development plans and budgets | POA & GADs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7 Disseminate successes | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 2: Increased worker knowledge about Child Labor, Forced Labor, Occupational Safety, and other labor rights in the agricultural sector. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Assess rural workers’ information needs, work experiences, and trusted organizations | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | •Producer associations and other trusted government and civil society actors trained to reach workers with rights information in each canton •Coordinated multi-sectoral awareness-raising campaigns reach rural workers in each canton, including institutionalized government outreach •Social dialogue platforms established and institutionalized in each canton |
| 2.2 Train and facilitate selected multisectoral partners to develop, implement, and monitor strategic, inclusive awareness-raising campaigns targeting rural workers | POA, INDES & partner organizations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 Institutionalize training | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 Establish and convene neutral spaces for bipartite and tripartite social dialogue | POA, INDES & stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5 Train small, medium, and large employers to engage workers, understand workers’ rights, and monitor rights compliance in their supply chains | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6 Partner with GADs to integrate the above training and awareness-raising, and social | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7 Generate new opportunities for learning among civil society, workers, government, private sector, and others. | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.8 Assess changes in rural workers’, business, and government officials’ knowledge, skills, and practices | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.9 Assess changes in rural workers’, business, and government officials’ knowledge, skills, and practices. | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 3: Increased worker access to remediation of labor law violations within the agricultural sector. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 Undertake Remediation Constraints and Opportunities Analysis | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | •Analysis of grievance reporting and remediation process constraints and opportunities •Grievance and remediation pilots inclusively designed, tested, and results disseminated •Large companies engaged to strengthen remediation among staff and in prioritized sectors •Anonymous reporting platform rolled out |
| 3.2 Validate analysis and select pilot mechanism designs | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 Engage partners to design, plan, implement, and monitor pilot solutions | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 Finalize and institutionalize proven grievance and restitution mechanisms | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5 Develop and integrate an anonymous reporting platform | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.6 Engage medium and large producers to address violations in their workplaces and supply chains | POA & INDES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring & Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish data collection system | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct annual data quality assessment | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop project-level child labor and forced labor definitions | POA & USDOL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct and finalize baseline study that will include need assessment | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop and finalize the CMEP in close collaboration with USDOL | POA & USDOL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Standard Operating Procedures for data collection, data quality assurance, management, and analysis. | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Train staff, sub-grantees/partners on CMEP, Standard Operating Procedures, and the data collection system | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review and update the proposed project strategy, CMEP, and indicators to determine whether any modifications are needed after new information from Needs assessment and mapping about the project’s implementing environment, intended project targets or targeted geographic areas | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit Sustainability Strategy | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work with USDOL and contractor and to carry out external Midterm Evaluation | POA & USDOL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit agreed upon follow-up action plan based on interim evaluation (or interim review) recommendations | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work with USDOL and contractor and to carry out external Final Evaluation | POA & USDOL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit Disposition of Evaluation Recommendations Tracker (DERT) | POA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |