## FY23
Activity | 2023 | [39 empty] | 2024
| Mar |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  | Sept
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Program Promotion and Communications
Alumni Webinar Series promoting previous experiences
Promotional Materials Posted on Social Media
Bi-Weekly Coordination Meeting with ECA
Outreach to Embassies and Consulates in Target Countries
Outreach to Chapters and Affiliate Organizations
Annual Education and Culture 2023 Video Developed
Annual Education and Culture 2023 Video Publicized
Travel Grants
Newsletters and Social Media engagement
Pre-Launch
Open Application
Application Cycle Deadline
Eligibility Review
Internal Review
DOS Review
Embassies Review
Participant Onboarding and Visa Interviews
Participant Travel
Sub-Awards
Open Competition
Deadline for Applications
Eligibility Review
Internal/External Review
DOS Review
Embassies Review
Participant Notification and Onboarding
Program Implementation
What Works
Virtual Workshops and Roundtables
Coordination Meeting with POA and DOS
Draft Agenda shared with ECA, WHA, and Embassy
Peer Learning Event Implementation