Partners of the Americas

John Ogonowski and Doug Bereuter Farmer-to-Farmer Program

NOFO Number: 7200AA23RFA00006 - Phase II Full Application

Caribbean Basin Region

Prime Organization Name: Partners of the Americas

Prime Organization Business Status: 501(c)3 Nonprofit

Prime Tax Identification Number: 52-0848769

Unique Identity Number: DD5WNYRUYFE5

Prime Contact Name and Position: Michael Moscarelli, Chief Operating Officer, Partners of the Americas

Prime Contact Email Address and Phone: mmoscarelli@partners.net  202.637.6214

Alternate Contact Name and Position: Sheila Posas, Senior Director, Agriculture and Food Security, Partners of the Americas

Alternate Contact Email Address and Phone: sposas@partners.net 202-427-2420

Prime Complete Business Mailing Address:

1424 K Street NW

Suite 700

Washington DC 20005

Sub Organization Name: None

# Michael Moscarelli

17 July 2023

Chief Operating Officer

# Partners of the Americas

TABLE OF CONTENTS

Executive Summary	1

Program Description	3

Program Strategy	3

Rationale for Proposed Region and Selected Core Countries	3

Proposed Approach and Planning Process	3

Development Goals and Objectives	4

Expected Relationships with USAID Mission and In-Country Stakeholders:	4

Responding to Requests for Associate Awards and Mission Buy-ins	5

Addressing Gender and Environmental Concerns	6

Country F2F Project Design	6

Host Selection	7

Results Planning	9

Life of Project Targets	9

Monitoring, Evaluation, and Learning (MEL) Plan	9

Critical Implementation Issues	10

Implementation and Management Plan	11

Implementation Plan	11

Volunteer Recruitment and Support	11

Volunteer Orientation. 	13

Volunteer Logistical and Technical Support	13

Post-Assignment Follow-up and Support to Hosts	14

Returned Volunteer Outreach Activities	14

Continuous Learning and F2F Community of Practice Participation.	15

Management Plan	15

Management Structure and Approach	15

Overview of the Senior Director and Key Personnel Positions	17

ANNEX LIST

Annex 1: Proposed Year One Work Plan

Annex 2: Life of Project Work Plan

Annex 3: CV for the Proposed F2F Program Director

Annex 4: CVs for Proposed F2F Country Directors

Annex 5: Past Performance References

Annex 6: Branding Strategy and Marketing Plan

Annex 7: Budget Spreadsheet in Excel

Annex 8: Budget Narrative

ACRONYM LIST

AOR		Authorized Representative

AVOP 		Agricultural Volunteer Opportunity Program

CABPRO	Goats for Prosperity Project

CDCS		Country Development Cooperation Strategy

CSO		Civil Society Organization

F2F		Farmer-to-Farmer

HQ		Headquarters

LOP		Life of Project

M&E		Monitoring and Evaluation

MEL		Monitoring, Evaluation, and Learning

NGO		Non-Governmental Organization Community of practice

POA		Partners of the Americas

SMART	Specific, Measurable, Agreed, Realistic, Time-bound

SOW		Scope of Work

USAID	United States Agency of International Development

USAID/RFS	USAID Bureau for Resilience and Food Security

USG		United States Government

# EXECUTIVE SUMMARY

Climate change threatens the agriculture sector of the Caribbean Basin. More frequent and severe droughts, extreme weather events, damaging storm surges, and rising sea levels increase water scarcity, soil degradation, and the prevalence of pests and diseases, among other adverse effects. This jeopardizes crop yields, livelihoods, and food security throughout the Basin. Loss of livelihoods due to the effects of climate change disproportionately impacts marginalized groups such as Indigenous peoples and women. Thus, the United States Agency of International Development (USAID) investments in innovations that increase adaptive capacity, productivity, and competitiveness are critical to increasing the resilience of the Caribbean’s most vulnerable and marginalized populations.

Partners of the Americas (POA) will leverage 32 years of Farmer-to-Farmer (F2F) program implementation experience, an integrated cloud-based F2F recruitment and Monitoring and Evaluation (M&E) system, and a database of 1,500+ highly skilled volunteers, to implement the 2023-2028 F2F Caribbean Basin Program. During the five-year, $7.5M program, POA will carry out 380 F2F volunteer assignments to the Dominican Republic, Guatemala, Guyana, and Jamaica to increase climate adaptation and resilience (Exhibit 1). F2F volunteers will provide technical assistance to 11,400 beneficiaries (52% women, 35% youth, and 10% Indigenous peoples), leading to $3.57M in increased annual gross sales, $1.07M in increased net annual income, and 42,000 hectares under improved management.

| Exhibit 1: F2F Caribbean Basin Development Objectives |  |  |  |
| --- | --- | --- | --- |
| Program Development Objective: |  | Increase climate adaptation and resilience of vulnerable and marginalized groups in the agriculture sector |  |
| Country | F2F Country Project |  | F2F Country Project Objective |
| Jamaica | Climate-Smart Agriculture |  | Increase adaptive capacity and resilience through the use of inclusive climate-smart agriculture practices. |
|  | Indigenous & Youth Agribusiness Development |  | Increase access to finance and agribusiness skills among at-risk youth and Maroon populations, including women. |
| Guyana | Climate-Smart Horticulture |  | Increase adaptive capacity and resilience through inclusive climate-smart fruit and vegetable production practices. |
|  | Hinterland Agribusiness Development |  | Increase access to finance and agribusiness entrepreneurial skills among Indigenous populations in the Hinterlands. |
| Dominican Republic | Watershed Management |  | Increase resilience through sustainable livelihoods, improved practices, and enhanced watershed governance. |
|  | Border Region Livelihoods & Resilience |  | Increase inclusive agricultural livelihood opportunities and adaptive capacity along the DR/Haiti border. |
| Guatemala | Nutrition-Sensitive Agriculture |  | Increase resilience and household nutrition through crop diversification and improved agricultural practices. |
|  | Watershed Management |  | Increase resilience through sustainable livelihoods, improved practices, and enhanced watershed governance. |

The 2023-2028 F2F Caribbean Basin Program will focus on increasing the climate adaptation and resilience of vulnerable and marginalized groups in the agriculture sector, and engaging women, youth, indigenous and marginalized populations throughout F2F activities. Proposed Country F2F Projects aim to address specific climate threats in each country, while targeting groups that are most impacted by climate change. POA will also seek to collaborate with key government and community-level entities involved in climate and weather monitoring and modeling activities to inform F2F assignments, trainings, and share key resources with host organizations and local partners.

Before developing Country F2F Projects, POA will conduct inclusive development analyses, gender analyses, participatory rural appraisals and needs assessments as part of the Country F2F Project design. Furthermore, the F2F Caribbean Basin Program will identify and select new and diverse host organizations to reach more women, youth, indigenous and other marginzalied groups; target recruitment efforts to diversify sources of  volunteers with diverse backgrounds and expertise; and leverage data and technology throughout activities to improve technical assistance and maximize impacts.

POA proposes a lean and efficient staffing plan to implement the 2023-2028 F2F Caribbean Basin Program while ensuring effective use of resources. Based in Washington, DC, POA’s Headquarters (HQ) staff will include a Program Director (key personnel), Program Manager, Technical Officer, and Recruiter with responsibility over programmatic and financial program activities. Each POA field office will include one Country Director (key personnel), one administrative assistant, and one to two field officers. Given the four core countries mentioned above are in POA’s FY19-23 F2F Caribbean Basin Program, POA will retain the majority of those staff to accelerate start-up and implementation.

During Q1 of FY24, POA will focus on start-up activities, beginning with hiring and onboarding staff, finalizing and submitting eight Country F2F Projects for USAID and USAID Mission approval, and procuring a project vehicle for the Dominican Republic. Furthermore, POA will update volunteer orientation materials, country operational manuals, and the M&E database and protocols, begin collecting host baseline data, and develop Scopes of Work (SOWs). In early Q2, POA will hold a kick-off workshop to train POA HQ and Field Staff on federal rules and regulations, general program management, host profiles, SOWs, volunteer recruitment and logistics, monitoring and data collection, cross-cultural awareness, and volunteer support, among other topics. Following the workshop, POA expects to carry out initial F2F volunteer assignments and become fully operational in Q2 of FY24.

Throughout implementation, POA will actively engage with USAID Missions, local partners, and other USG-funded programs to identify priorities and maximize efforts. Additionally, POA will participate in F2F Community of Practice activities, including to share lessons learned, best practices, and innovative tools to improve F2F implemenation.

# PROGRAM DESCRIPTION

## Program Strategy

Rationale for Proposed Region and Selected Core Countries: The proposed core countries for the 2023-2028 F2F Caribbean Basin Program are the Dominican Republic, Guatemala, Guyana, and Jamaica. However, POA remains flexible to work in other countries, as requested by USAID. POA has a legal presence in each proposed country. POA selected the Caribbean Basin Region for two main reasons: 1) It is a priority for the F2F Program, as the region is included in the United States (US) Farm Bill; and 2) With nearly 60 years of experience working throughout the Caribbean Basin Region, POA has developed an intimate and unique understanding of nuances in the Region’s cultures and agriculture sectors. The specific core countries of the proposed program were strategically selected based on need, alignment with United States Government (USG) priorities, and opportunity to leverage efficiencies that maximize the impact of USG funding.

## Strategy for Effective Use of Voluntary Technical Assistance: The F2F Caribbean Basin Program will use voluntary technical assistance to strengthen beneficiaries’ climate adaptation and resilience. F2F volunteers will train hosts in climate-smart agriculture and natural resource management practices, providing tailored recommendations to sustainably increase stakeholder productivity, competitiveness, and food security. For example, a volunteer may train a Kaqchikel women’s group in Guatemala in designing an intercropping system with annual and perennial crops to ensure consistent availability of fruits and vegetables for household consumption and sale. This training would not only increase the community’s climate resilience, but also empower indigenous women to be leaders and key decision-makers in agriculture, specifically climate-smart agriculture.

Furthermore, F2F volunteers will train trainers to create a multiplier effect. For example, a volunteer may train Ministry of Agriculture extension agents in the Dominican Republic to install and maintain drip irrigation systems. These extension agents will then work with local farmers navigating water scarcity issues to install drip irrigation systems that maximize “crop per drop.” Volunteer assistance also expands beyond on-farm production. A volunteer in Jamaica may work with the Trelawny Town Maroon Cooperative in Cockpit Country to improve dry storage of ginger and turmeric to reduce postharvest losses from increased humidity. POA will leverage the wide range of F2F volunteer technical assistance, following nine guiding principles (Table 2) to maximize impact and reach diverse stakeholders.

## Proposed Approach and Planning Process

Aligning with the USAID Climate Strategy 2022-2030, and embedding considerations of gender issues and impacts, POA adopted nine guiding principles that informed the proposed approach and planning process (Exhibit 2).

| Exhibit 2: F2F Caribbean Basin Approach and Planning Process: Guiding Principles |  |
| --- | --- |
| Guiding Principle | Definition |
| Advance Gender Equity | Provide women with equal access to technical assistance, knowledge, and innovations where household livelihoods are predominantly agriculture-based |
| Reduce Emissions | Catalyze urgent mitigation from energy, land use, and other key emissions sources |
| Build Resilience | Strengthen the resilience of populations vulnerable to climate impacts |
| Mobilize Finance | Increase the flow of and equitable access to finance to support adaptation |
| Partner with IPLCs | Partner with Indigenous peoples and local communities to lead climate action |
| Amplify Crucial Voices | Enable and empower women, youth, and other marginalized and/or under-represented groups to lead climate action |
| Transform Key Systems | Advance transformation of key systems and essential services to enhance resilience |
| Improve Governance | Strengthen responsive, transparent governance for effective climate action |
| Work Across Assistance Types | Strengthen the coordination of humanitarian, development, and peacebuilding assistance to address climate impacts |

## Development Goals and Objectives

Aligning with the overall F2F objectives, POA’s F2F Caribbean Basin Program will seek to increase climate adaptation and resilience of vulnerable and marginalized groups in the agriculture sector. The primary goal of the F2F Caribbean Basin Program is to is to generate rapid, sustained, and broad-based economic growth in the targeted agricultural sectors of selected countries, while also focusing on critical environmental and natural resource management issues impacting agriculture sectors.

A secondary goal of the program is to increase the US public’s understanding of international development issues and programs, as well as international understanding of the US and US development programs. Additionally, the F2F Caribbean Basin Program will align with the development goals and objectives defined in 1) USAID Missions’ Country Development Cooperation Strategy; 2) USAID Climate Strategy 2022-2030; 3) Feed the Futures’ Gender Integration Framework and Women’s Empowerment in Agriculture Index; 4) USAID’s Youth in Development Policy and Policy on Promoting the Rights of Indigenous People; 5) 2023 US Farm Bill; 6) US Government Global Food Security Strategy 2022-2026; and 7) Biden Administration’s Executive Order on Tackling the Climate Crisis at Home and Abroad. POA will further align program activities with USAID Mission and local government priorities, and identify ways to collaborate with other USG-funded projects to maximize resources and impacts.

Expected Relationships with USAID Mission and In-Country Stakeholders:

POA prioritizes its relationship with USAID Missions and strives to complement objectives within their Country Development Cooperation Strategy (CDCS). Throughout F2F program implementation, POA regularly communicates and connects with USAID Missions to ensure that they are engaged in activities and can indicate their interests, priorities, concerns, and opportunities. F2F will also collaborate with other in-country projects to maximize the impact of USG assistance while avoiding duplication of efforts. Additionally, as detailed below, POA promotes buy-ins to USAID Missions and responds to Associate Award requests to expand F2F activities and fund projects in their areas of interest. POA also collaborates with host country governments (often the Ministry of Agriculture), local non-governmental organizations (NGOs), civil society organizations (CSOs), and private service providers. Working with and through these local stakeholders strengthens local capacity and increases human capital, laying a foundation of sustained support that hosts and beneficiaries can build on after the F2F program ends.

Cabras para la Prosperidad (CABPRO)

POA implements the $2M CABPRO project – $1M funded by USAID/ Guatemala through the F2F buy-in mechanism and $1M private matching funds from Guatemala’s Fundación Mario Lopez Estrada. CABPRO aims to improve food security and livelihoods in Guatemala's Western Highlands. The project supports 350 Indigenous Mam households to increase goat milk, poultry, egg, and vegetable production to combat chronic malnutrition and generate new economic opportunities. Over 40% of families have improved goat milk consumption, and 30% of families have increased protein consumption through poultry production. Notably, Mam women are more empowered through financial literacy skills, establishing 14 money-saving groups that have saved over $8,000 quetzals in just two months.

Responding to Requests for Associate Awards and Mission Buy-ins

POA will promote buy-ins to USAID Missions and respond to requests for Associate Awards to expand F2F activities and fund projects in their areas of interest. Buy-ins and Associate Awards may include complementary support and inputs such as equipment, grants, consultants, and volunteers. Since USAID Mission funding availability and program priorities will determine the availability of any Mission buy-ins, these are yet uncertain. If Mission funding becomes available, the Work Plan will be modified accordingly, and buy-in funding may be used for additional volunteer services or for complementary development inputs associated with and supporting the work of the F2F volunteers. For Application budgeting purposes, we have included $1,000,000 for buy-in funding as a separate line in the budget. If buy-in funding is available, implementation and targets will be increased accordingly.

Addressing Gender and Environmental Concerns

Gender Concerns: POA understands that each country experiences gender disparities in different ways across different agricultural value chains. For example, in Guatemala, women face a severe gender gap in terms of access to agriculture markets and value chains. Furthermore, in rural areas, about 57% of female agricultural workers do not directly earn a salary as they are considered “helpers” to their husbands, fathers, or brothers rather than regular workers. In Guyana, meanwhile, 90% of women heads of households who farm do not hold a title to their lands, making it nearly impossible to access loans to make investments in their farms. To better address barriers to women’s participation in different agricultural value chains across the Caribbean basin, POA will:

- Provide gender inclusion and intersectionality training to F2F field staff

- Identify, target and connect with women-led and women-focused groups across the Caribbean basin and the different value chains

- Consult and involve women as decision-makers throughout the process of designing Country F2F Projects and F2F activities

- Provide country and value chain-specific gender analysis materials to F2F Volunteers as part of the orientation process

- Conduct inclusive development analyses to assess barriers for women and other marginzalized groups.

- Continually assess Country F2F activities and Scopes of Work (SOWs) to ensure the activities align with each core country’s gender needs, risks, and inequalities

- Ensure that activities are available and accessible to women

- Ensure robust measurements of gender inclusion and indicators disaggregated by sex and intersectional identities across inputs, outcomes, and impact

POA will conduct inclusive development analyses in each target country following USAID’s guidance in Suggested Approaches for Integrating Inclusive Development Across the Program Cycle and in Mission Operations. Findings from the analyses will help identify barriers within the F2F “status quo” that can be amended to allow for greater participation from marginalized groups – for example, arranging trainings at times and with amenities that do not contribute to a burdensome workload for women.

Inclusive Development Analyses

Environmental Concerns: Aligning with the USAID Climate Strategy 2022-2030, the F2F Caribbean Basin Program is designed to increase climate adaptation and resilience of vulnerable and marginalized groups in the agriculture sector. Proposed Country F2F Projects aim to address specific climate threats in each country, while targeting groups that are most impacted by climate change. POA will also seek to collaborate with key government and community-level entities involved in climate and weather monitoring and modeling activities to inform F2F assignments, trainings, and share key resources with host organizations and local partners.

Country F2F Project Planning

POA brings 32 years of experience in Country F2F Project planning to this award. Details are found below and in the attached work plans. POA remains flexible in developing country-level F2F Program strategies and will adjust appropriately to meet specific USAID preferences. We recognize that the final selection of countries and country F2F project areas is subject to further consultations with and no-objection from the country USAID Mission. We will consult with Missions and with the F2F AOR to finalize plans for country programs and country F2F projects and will document these in Project Work Plans approved by the Authorized Representative (AOR), and will remain flexible to revise Country Projects as necessary throughout the Life of Project (LOP).

| Exhibit 3: F2F Caribbean Basin Development Objectives |  |  |  |
| --- | --- | --- | --- |
| Program Development Objective: |  | Increase climate adaptation and resilience of vulnerable and marginalized groups in the agriculture sector |  |
| Country | Country F2F Project |  | Country F2F Project Objective |
| Jamaica | Climate-Smart Agriculture |  | Increase adaptive capacity and resilience using inclusive climate-smart agriculture practices |
|  | Indigenous & Youth Agribusiness Development |  | Increase access to finance and agribusiness entrepreneurial skills among at-risk youth and Maroon populations, including women |
| Guyana | Climate-Smart Horticulture |  | Increase adaptive capacity and resilience through inclusive climate-smart fruit and vegetable production practices |
|  | Hinterland Agribusiness Development |  | Increase access to finance and agribusiness entrepreneurial skills among Indigenous populations in the Hinterlands |
| Dominican Republic | Watershed Management |  | Increase resilience through sustainable livelihoods, improved practices, and enhanced watershed governance |
|  | Border Region Livelihoods & Resilience |  | Increase inclusive agricultural livelihood opportunities and adaptive capacity along the DR/Haiti border |
| Guatemala | Nutrition-Sensitive Agriculture |  | Increase resilience and household nutrition through crop diversification and improved agricultural practices |
|  | Watershed Management |  | Increase resilience through sustainable livelihoods, improved practices, and enhanced watershed governance |

Country F2F Project Design: Based on initial assessments and reviews, the core countries proposed by POA are Guyana, Jamaica, the DR, and Guatemala, coupled with to-be-determined Flex assignments in other countries across the Caribbean Basin. As mentioned above, these proposed core countries face similar climate change risks and impacts. Each proposed Country F2F Project design addresses constraints within a specific commodity value chain, support sector, agroecological zone, geographic area, or beneficiary population (See Exhibit 2, above). These proposed Country F2F Projects align with USAID Mission strategies and objectives and draw on CDCSs, focus groups with critical public, private, and civil society stakeholders, and supplemental desk research.

Upon award, POA will complete the full analysis and design of Country F2F Projects during three months of implementation. The analysis will be based on primary and secondary research. Primary research will include stakeholder interviews with a wide range of stakeholders from select geographic areas from the public, private, and civil society sectors, including small-scale farmers, farmer organizations, agribusinesses, export-oriented processors, government officials, local NGOs, research institutes, USAID Missions, Peace Corps, and the World Bank. Secondary research will include a literature review of NGO reports, project documents, and US and host country government documents. Country Projects will be assessed in terms of whether volunteer technical assistance can achieve desired results. POA remains flexible to revise Country Projects as necessary.

As detailed in Year One Work Plan, Annex 1, POA will develop eight Country F2F Project Strategies in FY24 as quickly as possible to facilitate rapid start-up. A full LOP Work Plan is depicted in Annex 2. Prior to developing complete F2F country projects, POA will reconvene with the target country’s USAID Mission and conduct a robust sector analysis, including inclusive development analyses, participatory rural appraisals, needs assessments with potential hosts, USG and host country priorities, and possible impact areas, among other factors.

Host Selection: Hosts are the foundation of an impactful F2F Program. With 32 years of experience implementing F2F Programs, POA has developed and refined its approach to selecting hosts that maximizes impact and value. POA will tap into its network of existing hosts to expedite project startup, while also seeking new motivated hosts with a willingness to learn, make improvements, and achieve sustainable results.

A New Cohort of F2F Hosts

In the 2018-2023 program cycle, many of POA’s hosts graduated from needing assistance. A select cohort of experienced F2F hosts will continue in the 2023-2028 program cycle to help expedite start-up. However, POA  anticipates over 75% of hosts will be new to receiving F2F technical assistance.

POA’s host identification approach includes in-country networking, promoting F2F using media outreach, sub-sector consultations with local governments, and special events like agricultural fairs. POA also generates interest from prospective hosts through broad dissemination of best practices and volunteer recommendations.

POA’s extensive F2F experience demonstrates that F2F success relies heavily on the selection of hosts that can learn and apply new knowledge and disseminate it to others. Hosts are selected based on criteria including: potential to show results, degree of interaction with the selected value chain or support sector, ability to identify and clearly state technical assistance needs, willingness to participate in the design of a multi-year plan with specific goals, support for the active participation of women and minority populations, use of democratic principles in operations, and commitment to supporting F2F activities. POA’s hosts typically include producer groups, local NGOs, small- and medium-scale producers, agribusinesses, educational institutions, agro-processors, and marketing organizations.

With many hosts from the 2018-2023 program cycle graduating, the 2023-2028 cohort of hosts will combine a select group of experienced F2F hosts, which will expedite program activity at start-up, with intensively recruited new hosts. The new hosts, representing new geographic areas and an inclusive population subset, will make up approximately 75% of the anticipated host cohort. POA will prioritize women-led hosts, as well as Indigenous peoples, youth, and other marginalized groups in the agriculture sector.

POA recognizes the critical importance of engaging female hosts throughout F2F programming and particularly in response to changing climate and weather patterns. Despite being heavily involved in agriculture and postharvest activities, women are often more vulnerable than their male counterparts due to not having the same socioeconomic standing and opportunities. For instance, many women, in addition to securing income for their families, are tasked with providing food, water, and firewood for their households. Being stretched so thin leaves them and their children extremely vulnerable to food shortages caused by the impacts of changing climates. Research indicates, however, that female farmers and heads of households take a greater interest in climate issues and adaptation measures than males. POA targets 52% female beneficiaries and ensures that activities do not have unintended negative impacts on women.

Host Plans: POA strategically selects hosts so as to work with them over several years to build their capacity in a manner that fosters sustainable positive change. Field staff and hosts work together to determine what types of assistance are needed, considering support available from other local and international programs. They develop an operational plan to sequence the assignments over time to build upon each other, maximizing efficiency and effectiveness. Operational plans contain clearly defined objectives, anticipated impact, complementary inputs that the host can provide, and volunteers' role in helping the host achieve its goals. Plans are regularly revisited, revised, and adapted to meet changing needs in dynamic, complex environments. To do this, hosts and field staff, in collaboration with other stakeholders, conduct periodic analyses of volunteer interventions, recommendations, results to date, and host goals. As the program progresses, new SOWs are identified, and hosts may request assistance in areas not previously anticipated.  F2F will also work to connect hosts with complementary support.

Exhibit 4: POA’s Host Assessment Process

## Results Planning

POA’s F2F Program will have substantive and sustainable economic impacts while focusing on gender equity and environmental sustainability. The proposed program focuses on strengthening value chains, building the capacity of local organizations, and improving resilience.

Life of Project Targets: POA has set ambitious but feasible LOP targets that maximize program outcomes and impacts while maintaining cost-effectiveness (See Annex 2). Indicators and targets will be defined upon implementation, but initial estimates are included in the attached Work Plan. In addition to standard performance and impact indicators, POA intends to develop custom indicators to better measure the unique impacts at a country and project level. Custom indicators will be developed in conjunction with Country Project Strategies during Q1. Based on initial analyses and current work, illustrative custom indicators could include the percentage of new host organizations and the percentage of indigenous persons trained. Other custom indicators may be used as a proxy to measure resilience and adaptation to climate change. POA will confirm targets for Standard F2F Program Performance and Impact Indicators in the Project Monitoring, Evaluation, and Learning Plan incorporated in the Life of Project Work Plan after consultations with the USAID AOR and other F2F implementing partners.

Monitoring, Evaluation, and Learning (MEL) Plan:

A critical USAID ally in developing the F2F Access Database, POA is a leader in MEL systems application for F2F. POA’s existing cloud-based F2F database is designed to leverage digital solutions for MEL, including mobile data collection tools, and to facilitate complete and timely data collection, monitoring, and analysis. POA has had the opportunity to improve its F2F database and data collection tools over the years, increasing efficiency and accuracy in measuring results and enhancing organizational capacity and learning. POA will further augment its tools and capacity with new gender-inclusive approaches to data collection, such as indicators disaggregated by sex and intersectional identities.

POA's F2F Caribbean Basin Program will employ a participatory approach to MEL to promote inclusivity and sustainability and ensure F2F activities are responsive, impactful, and representative of the realities of the target communities. POA will actively engage key stakeholders—e.g., host organizations, local community members, and partners—throughout data collection and assessment activities to seek feedback and monitor results to inform decision-making and improve F2F program activities. Participatory techniques include conducting focus groups, participatory mapping, gender role analyses, and feedback and action sessions to gain valuable insights into host needs, experiences, and priorities. Through this approach, POA will ensure that the voices and concerns of diverse groups, such as women, youth, and marginalized communities, are heard and addressed throughout the life of program. Additionally, POA will promote ownership, empowerment, and inclusivity, leading to sustainable and inclusive outcomes.

Critical Implementation Issues: POA has experience responding to issues while maintaining focus on overall program objectives. A case in point is POA’s response to the COVID-19 crisis. While the pandemic created many implementation challenges for F2F, it also opened the door to dynamic F2F programming, such as the remote-paired model. POA continues to apply this model even after the pandemic ended due to the its success in enabling US volunteers with limited ability to travel to participate in the program, as well as facilitating long-term virtual support to host organizations.

As described in more detail in the implementation management section below, POA’s F2F program will address critical factors such as gender equity, diversity, and environmental impact. The M&E system will capture data on these issues for monitoring and decision-making purposes.

Environment: Throughout implementation, POA will ensure compliance with USG and local environmental laws, including USAID environmental regulations regarding pesticide and/or GMO use, and comply with the F2F Program Pesticide Evaluation Report and Safer Use Action Plan (PERSUAP). In compliance with the terms of the FY24-28 Initial Environmental Examiniation for the F2F Program and of the PERSUAP, POA staff will conduct environmental screenings of individual volunteer assignments and ensure the provision of mitigation plans as indicated necessary. POA will provide environmental updates, including PERSUAP reporting, in each semi-annual and annual report. Staff will also conduct random spot checks of assignments, possibly including interviews with hosts and volunteers, across all six program countries to ensure compliance.

Gender: POA’s Caribbean Basin F2F Program strategy will prioritize inclusive agricultural development, actively engaging women, youth, indigenous groups, and/or other marginalized groups throughout F2F activities. By including diverse participants, POA will provide more effective assistance and create lasting impact. POA will have a deliberate focus on addressing the specific needs and self-identified barriers of these marginalized groups, leveraging existing inclusive development analyses and conducting supplementary studies to build on existing research and data.

Public Outreach: In recent years, volunteer recommendations and other information has been widely disseminated through various avenues, including “how-to” videos posted on YouTube, radio broadcasts, and social media platforms such as Facebook and Twitter. Additionally, volunteer assignments are often coordinated to coincide with events where volunteers serve as guest speakers, which can help reach new audiences. These outreach activities not only disseminate volunteer information more widely, but also generate interest and inquiries about F2F, which is a great way to expand the program’s reach in each country. The FY24-28 Program will continue leveraging lessons learned from these experiences. POA’s M&E system will also measure public outreach – publications, speaking engagements, social media, etc. – as this is one of the program's goals per the Farm Bill.

# IMPLEMENTATION AND MANAGEMENT PLAN

Implementation Plan

POA’s implementation and management plan for effectively and efficiently carrying out the F2F Program is based on careful analysis of HQ and field capacity and context while incorporating lessons learned and best practices from 32 years of F2F program implementation. During Year One, the program will focus on expedited start-up activities, including staffing, Country F2F Project design, monitoring and evaluation (M&E), and training (See Annex 2, Life of Project Work Plan). The implementation and management plan covers the entire F2F volunteer process, from host selection, needs assessments, and planning, to volunteer recruitment and support. It ensures high-impact assignments are carried out by well-qualified volunteers with extensive opportunities for and participation by women, minorities, and first-time volunteers. The plan also provides details on country-level collaboration with key partners, in-country outreach, continuous learning, and program improvement, including participation in an F2F Community of Practice.

Volunteer Recruitment and Support: POA has a comprehensive volunteer management system refined over 32 years of efficient and effective volunteer recruitment and support. This system, combined with POA’s proven volunteer selection and orientation methodology, has consistently yielded high-quality volunteers that maximize the potential impact of a given assignment. In many organizations, volunteers are deployed because they are highly skilled and respected as content or technical experts. Yet these skills alone will not result in the most impactful volunteer assignments. POA’s volunteers not only boast significant technical expertise, but are also equipped with tools and knowledge to maximize adult learning. Furthermore, POA orients volunteers to host realities, enabling them to tailor their training appropriately. Most importantly, POA prioritizes women and minorities in volunteer recruitment.

Using LinkedIn Recruiter for Innovative, Efficient, and Inclusive Recruitment

By using filters, optimized keyword searches, and strategic InMail messaging, POA increased response rates by over 300%, effectively sourcing volunteer candidates from 850 million professionals on LinkedIn. For example, POA received 1 response for every 25 emails using traditional recruitment methods; with LinkedIn Recruiter, POA receives an average of 9 replies to every 13 InMails. LinkedIn Recruiter also facilitates inclusive recruitment by notifying when gender ratios in searches are unbalanced and enabling filters for location, skills, and other professional or demographic characteristics to ensure diverse and equitable representation in candidate pools.

Volunteer Scope of Work (SOW) Development: High-quality assignments depend on high-quality SOWs. F2F is a demand-driven program. Consequently, volunteer SOWs are developed based on host needs identified during the planning process described in the Country F2F Project Planning (Host Selection) section above. Once the host operational plan is finalized, specific two to three week-long SOWs are created. These SOWs include in-depth, technical, project-level details for each assignment, including host information, assignment purpose, expected results, and deliverables, desired volunteer qualifications, inputs, and resources, recommended preparation, and an assignment itinerary. POA’s long history of F2F volunteer program management has shown that this methodology consistently yields high-quality SOWs and results in high-impact assignments.

Volunteer Recruitment: Volunteer recruitment is carried out by POA Headquarters (HQ) staff and collaborating US partners. POA utilizes the most cutting-edge digital technologies, including a cloud-based F2F recruitment management information system developed during the 2018-2023 cycle. POA’s in-house F2F recruiting staff leverage new technologies, networks, and databases, along with LinkedIn Recruiter, to inclusively target highly qualified professionals for F2F volunteer assignments. These innovations expand our reach to new populations and ensure POA brings top talent to each F2F assignment.

In addition, volunteers are screened for characteristics that make them more suitable to work in a development setting, such as flexibility, ability to adapt training material to local context, language proficiency (when possible), and cultural sensitivity.

POA follows a 4-prong approach, see Exhibit 5, that levels the field for first-time volunteers and women, youth, and minority groups, builds local capacity through paired assignments, and empowers host participation in volunteer selection, often leading to the fielding of women or other minorities.

Exhibit 5: POA’s Approach to Inclusive Volunteer Recruitment

In addition, POA boasts a database of 1,500+ highly skilled volunteers and a robust network of US universities, Minority Serving Institutions like Historically Black Colleges and Universities and Hispanic-Serving Institutions, agribusinesses, cooperatives, and civil society organizations. Examples include land grant universities in 45 states, the US Department of Agriculture’s Cooperative Extension Service network, veterans’ programs, Future Farmers of America, 4-H Clubs, women’s farmer associations, national and regional organic farmers’ associations, beekeepers’ associations, and US importers and distributors of organic products.

POA seeks to increase opportunities for female volunteers. Having set a minimum target of 55% female volunteers for our program, we will conduct targeted outreach and communications with female majority organizations (including female farming organizations and associations) and at female-oriented events (such as Women in Agriculture conferences) to develop partnerships and raise awareness of opportunities with F2F. Furthermore, POA has also developed specific orientation materials to prepare female volunteers for possible gender-based biases and undesired attention during their assignments. While gender equity has been a focus of USAID and F2F implementers in recent years, POA will continue to use innovative approaches to ensure that gender equity considerations are embedded across all F2F processes and activities. POA also seeks to increase participation of minorities in the F2F Program. POA’s robust network contains a multitude of Minority Serving Institutions, such as Historically Black Colleges and Hispanic-serving organizations, where POA will specifically target and conduct outreach to establish and recruit from a more diverse pool of volunteers.

Additionally, in the interest of increasing public understanding of international development, POA will seek to balance new and repeat volunteers by setting a goal of 65% new volunteers. This approach will allow effective repeat volunteers to build on past experiences and established relationships with hosts, while providing new volunteers with opportunities to share their expertise and innovative ideas, gaining international experience and expanding awareness of international development issues and programs among the US public.

## Volunteer Orientation: After a host selects a vetted F2F volunteer candidate for an assignment, POA provides the candidate with orientation materials and digital copies of previous volunteers’ trip reports. Technical orientation materials and supplemental training include guidance on conducting effective assignments and writing concise, appropriate trip reports and host recommendations. Other orientation materials include medical, insurance, emergency contact information, entry/exit requirements, airport pickup information, lodging details, and per diem rates. To ensure that volunteers are well-prepared to conduct an effective and enjoyable assignment, POA facilitates three live videoconference orientations:

- The F2F recruiter provides a pre-departure orientation focused on assignment objectives and expected deliverables, logistics, financial compliance, and outstanding volunteer questions;

- The field staff provide an orientation focused on effective teaching methods, local culture, host learning styles, environmental regulations, and safety and security; and

- The field staff organize a meeting with the volunteer and host organization(s) to set expectations and maximize the effectiveness of the in-person assignment.

While this orientation method has been successful during decades of implementation, POA continuously strives to improve and will explore new ways to prepare volunteers, such as including country and value chain-specific gender analysis materials to F2F Volunteers to ensure gender sensitive technical assistance.

Volunteer Logistical and Technical Support: In preparation for a volunteer visit, field staff arrange an assignment itinerary comprised of field visits, stakeholder meetings, and training sessions. Field staff coordinate the itinerary logistics, including lodging and transportation, to ensure that the visit goes according to plan. In addition, staff and volunteers have the support of professional travel and health services through POA’s travel agency and travel insurance provider. Finally, field staff have contact information for providers and are trained in responding to emergencies, including but not limited to: communicating emergency plans and use of the communication chain, and maintaining close relationships with local hosts and US Embassies.

During the assignment, POA’s staff and local organizations provide assistance and support to the volunteer, such as access to equipment, transportation and meals, translation services, technical information on agricultural conditions, homestays, and more. These connections allow volunteers a greater degree of understanding of conditions and a richer cross-cultural experience. POA’s lasting ties to local institutions also ensure that volunteer efforts initiated during their in-country stays will continue over time.

At the end of an assignment, F2F volunteers provide tailored Specific, Measurable, Agreed, Realistic, and Time-bound (SMART) recommendations to hosts. They also prepare detailed trip reports that integrate technical data, host information, interventions, recommendations, immediate outcomes observed, and suggestions for follow-up. These reports are a useful tool for project M&E and provide context and valuable information for field staff and future volunteers offering supplemental support and follow-up visits to hosts. Finally, before the end of the assignment, field staff and volunteers hold debriefing sessions with hosts and other relevant stakeholders. These meetings provide an opportunity to review volunteer observations, recommendations, and accomplishments. It is also an opportunity to receive critical feedback on program design and assumptions to refine future assignments.

Innovating. Adapting. Leading.

Faced with the challenges of the Covid-19 pandemic, POA leveraged virtual and paired assignments to continue activities in the 2018-2023 F2F program cycle to reach broader populations. Once global travel restrictions were lifted, POA quickly developed a Covid-19 Safety Protocol and step-by-step guidelines to safely resume in-person assignments. As the first F2F implementer to resume in-person assignments, POA shared lessons learned and resources with the F2F Community of Practice, supporting their transition back to fielding in-person assignments.

Post-Assignment Follow-up and Support to Hosts: Upon returning to the US, POA’s HQ staff hold a debriefing phone call with the volunteer, offering an opportunity for open dialogue on their experience and suggestions for program improvement. During the call, POA encourages the volunteer to continue engaging with the host remotely to clarify recommendations and provide additional support. Volunteers also provide feedback through a survey designed to improve program quality, effectiveness, and the volunteer experience. Furthermore, to achieve F2F’s secondary goal, volunteers supply outreach materials, such as photos for social media and blog posts. POA staff often professionalize blog posts to create success stories for distribution to USAID and other audiences.

POA’s Experience Mentoring F2F Implementing Partners from 2018-2023

As a leader in the F2F Community of Practice, POA hosted a F2F Regional Meeting in Jamaica in 2020 for F2F implementing partners that were off to delayed Year One start-ups. Over the course of one week, POA HQ and field staff drew on 32 years of F2F Program implementation experience to train six organizations in key administrative and programmatic aspects of F2F implementation. Training topics included work planning, host identification, scope work development, M&E, volunteer management, and more. Likewise, in the 2023-2028 Program Cycle, POA is once again ready to support new and veteran implementing partners to optimize processes and procedures to achieve a rapid start-up and smooth implementation.

Returned Volunteer Outreach Activities: POA’s volunteers have always done an excellent job of reaching out to share their experiences. This is partly due to our organizational structure and the tools for public outreach that POA provides. POA will continue to support our volunteers and partnering organizations with public outreach and specifically seek to increase our social media efforts. Staff will also be involved in public outreach efforts, attending meetings with organizations working in international agriculture, keeping local media informed when volunteers are in-country, and keeping the program blog site up to date. POA has also been active on LinkedIn, Instagram, BlogSpot, and several USAID Missions have retweeted F2F stories or engaged with us. Our LinkedIn account boasts over 1,800 connections and serves to maximize outreach activities to increase F2F visibility and support recruitment. POA’s F2F blog address is https://f2fpoa.blogspot.com/, our LinkedIn account is https://www.linkedin.com/in/farmertofarmer-partners, and our Instagram account is @f2fpoa.

## Continuous Learning and F2F Community of Practice Participation.

## POA is a learning organization. Quarterly, POA conducts formative evaluations to document lessons learned and best practices, which POA then disseminates to field offices and the larger F2F Community of Practice. POA plans to hold regional workshops to build staff capacity to maximize program efficiency and effectiveness. For example, workshops held in previous F2F programs ensured that staff were fully trained in M&E system changes and best practices, briefed regarding new processes and policies to improve internal controls, provided training to leverage new technology, and gave staff a forum to share challenges and solutions. During the FY23-28 F2F Program, POA will hold at least three regional workshops.

In the 2023-2028 program cycle POA will enthusiastically participate in the Community of Practice to share best practices, provide guidance and information to other implementers, share challenges and lessons learned, and participate and assist in planning and facilitating committee meetings, Implementing Partner Meetings, evaluations, special studies, and other events. USAID recognized POA’s long history of contributions to the Community of Practice by awarding POA the F2F Agricultural Volunteer Opportunity Project – an umbrella support program for all F2F implementers and USAID. The program currently plans and facilitates Community of Practice meetings and events, compiles shared resources and platforms to access them, and increases the participation of field staff during annual meetings and events.

POA will continue to participate actively in the F2F Community of Practice to share good practice and seek ways to enhance program efficiencies and effectiveness and achieve common goals across the program. For this purpose, POA plans to provide project resources for activities mutually agreed to by the community of practice and will incorporate any specific activities in the Project Work Plans.

Management Plan

## Management Structure and Approach

POA will implement a lean and efficient staffing plan to implement the 2023-2028 F2F Caribbean Basin Program while ensuring effective use of resources. Combined, POA HQ and field staff bring nearly 120 years of cumulative experience implementing F2F Programs in Latin America and the Caribbean. Based in Washington, DC, POA’s HQ staff will include a Program Director, Program Manager, Technical Officer, and Recruiter with responsibility over programmatic and financial program activities. HQ staff will also oversee field staff, develop reports, and communicate with USAID and the USAID Missions in each country.

POA’s F2F Program Director provides overall management and strategic leadership of the program, supervises the Program Manager and Country Directors, liaises with USAID Bureau for Resilience and Food Security  (USAID/RFS), and is the contact point for the F2F Community of Practice. The Program Manager oversees the day-to-day operations, trains staff, develops technical reports, has financial oversight of the program, and supervises the Technical Officer and Recruiters. The Technical Officer leads MEL activities and monitors progress toward LOP targets while supporting field staff in developing effective scopes of work (SOW) and ensuring high-quality assignment deliverables. In addition, one recruiter will conduct outreach to diverse sources of volunteers, liaise with field staff to identify and select highly experienced volunteers and arrange travel logistics for assignments.

Guyana, Jamaica, Guatemala, and the Dominican Republic will each have an in-country Country Director and three supporting field staff. Country Directors will lead the development of Country Project Strategies, data collection, performance monitoring, host selection, and develop and maintain positive relationships with USAID Mission staff and other local stakeholders. Field staff will coordinate assignment planning and communications with hosts, provide in-country logistical support for volunteer assignments, and provide input for program reports.

POA continuously mentors and trains F2F staff. POA gives field staff latitude to make decisions on program activities while ensuring they align with the country project strategy and the overarching development goals and objectives of F2F. POA will provide training and tools, including regional workshops, online training, and various toolkits, to assist them with program management in-country. Specific training and follow-up support will include federal rules and regulations, general program management, host profiles, SOWs, volunteer recruitment and logistics, impact monitoring and data collection, cross-cultural awareness, and volunteer support. POA leverages technology including cell phone calling, Teams messaging and calls, and Outlook email to facilitate cross-country communications to enable home and field-based staff to interact even when staff are in the field. It also allows field staff to bring questions and concerns directly to the appropriate person.

Exhibit 6: F2F Caribbean Basin Program Staffing Structure

Managing Efficiently: POA has leveraged and learned from its 32 years of F2F experience to devise and revise systems that streamline implementation and enhance management. It is this first-hand knowledge and existing techniques and tools perfected over time that POA brings to the F2F Caribbean Basin Program to efficiently and effectively implement F2F. Beyond those mentioned previously, e.g., recruitment-related and host selection, other experience-driven, management-enhancing tools include:

- Workshops with the entire team in Years One, Three, and Five to reinforce training; discuss improvements to tools, systems, and processes; review lessons learned; and plan assignments and activities for the year ahead.

- Cloud-based M&E database that allows field staff to upload data offline and improves accuracy and real-time reporting.

- Robust volunteer network + LinkedIn Recruiter for more efficient and diverse recruitment of volunteers.

- Digital technologies to manage volunteer logistics and streamline reporting, such as cloud-based file sharing, digital signing, and online forms that speed response and feed directly into a database

- Communications tools to continuously communicate with field staff; streamline planning and management of F2F activities

- Remote meeting with the entire F2F team monthly and bi-weekly with each country office to coordinate and plan assignments

- Host operational plans and tentative SOWs developed early on to help with assignment planning (recruiters have an idea of types of volunteers to identify; can book assignments months in advance; helps to mitigate any potential interruptions in the future and quickly adjust as needed.

Staffing and Key Personnel

Overall staffing and staffing relationships are described above under Management Approach and Structure, page 15. Personnel filling key positions in the POA F2F organizational structure are:

- Gustavo Galdo, HQ F2F Program Director

- Jermaine Joseph, Guyana Country Director

- Rafael Marte Aracena, Dominican Republic Country Director

- Marsha Johnson, Jamaica Country Director

- Jose Cano, Guatemala Country Director

Overview of the Senior Director and Key Personnel Positions

Below is a summary table of the descriptions of the key positions and staff identified to date. Full CV for the Program Director can be found in Annex 3 and Full Country Director CVs can be found in Annex 4.

Headquarters Senior Director

Senior Director at 5% LOE will focus specifically on providing overarching leadership on F2F from HQ and developing strong relationships with local partners, USAID, and USAID Missions to identify opportunities for collaboration, including with USAID Mission buy-ins and associate awards.

Headquarters F2F Program Director*

POA anticipates that Gustavo Galdo will be the F2F Program Director working out of headquarters at 70% LOE. Mr. Galdo has over 20 years of international agricultural development experience, including three years of experience managing the 2021-2025 Farmer-to-Farmer Venezuela Food Security Activity. Under this $18M activity, he has supervised a team of over 100 staff and volunteers operating in 5 states in Venezuela. He holds an undergraduate degree and a Master's of Science in Civil Engineering.

Guyana Country Director*

In Guyana, POA anticipates that Jermaine Joseph will be the Country Director. He holds a Bachelor’s degree in Public Management and an additional Diploma in Agriculture Science. He has over 20 years of work experience in the agricultural sector and community development, specializing in stakeholder development and community building in the agriculture sector. Mr. Joseph also has prior experience with POA as F2F Country Deputy Director from 2018-2023.

Dominican Republic Country Director*

In the Dominican Republic, POA anticipates Rafael Aracena will be the Country Director. He holds a Bachelors degree in Engineering and Agricultural Crop Production and a Master’s of Business Administration. He has served under the Farmer-to-Farmer project in the Dominican Republic as a Field Officer and managed volunteers in technical assignments throughout the country. He has recently led a team of 8 as the Chief of Party for the Resilient Agriculture Activity funded by USAID. Mr. Aracena is fluent in Spanish and English.

Jamaica Country Director*

In Jamaica, POA anticipates that Marsha Johnson will remain the Country Director. She holds a Bachelor’s degree from the University of West Indies in Kingston, Jamaica. She has been working with the agriculture sector and Agro-tourism sector in Jamaica for over 15 years and currently serves as the Farmer-to-Farmer Country Director under the 2018-2023 F2F Caribbean Basin Program.

Guatemala Country Director*

In Guatemala, POA anticipates that Jose Cano will remain the Country Director. He holds a Bachelor’s degree in agricultural production systems and has over 25 years of work experience in the agricultural sector in collaboration with government institutions, the private sector, and academia. Mr. Cano has worked in the agriculture sector for many years, including on several USAID-funded programs, and has practical expertise in agriculture, market systems, and rural development. He is the current Guatemala Country Director for the 2018-2023 F2F Caribbean Basin Program and is fluent in Spanish and English.

https://www.fao.org/3/ca4726en/CA4726EN.pdf

380 volunteers, without $1M in Mission buy-in.

Landa Ugarte, Ana; Salazar, Elizabeth; Quintana, Magali; Herrera, Molina Raul. USAID/Guatemala Gender Analysis Report. Prepared by Banyan Global, 2018.

FAO. 2023. Country gender assessment of the agriculture and rural sector – Guyana. Country Gender Assessment Series. Georgetown

The F2F Program Director will allocate a percentage of their time (estimated at 25%) to organizational development activities, such as business development, and/or other POA projects, in accordance with POA policies. This LOE reflects a more accurate projection of time that the F2F Program Director will dedicate to the Program.