800-Parque Explora

Juntos Aprendemos Budget Narrative

Subaward Modification No. 7

This budget narrative was adjusted in March 2024, according to an overall budget realignment a no cost extension until August 31, 2026 and a ceiling reduction by USD 475,000.

Background:

Modification No. 7 is, among other changes, modifying the ceiling amount of the subaward by USD 475,000 from USD $6,818,381 to USD $6,343,381. This reduction is due to changes in the project structure since Parque Explora will no longer be in charge of the Project’s communications strategy , which implies a decrease in this budget item; the new total amount will be enough to ensure the operation and achieve successfully the goals approved in the work plan.

Budget lines, after realignment will be as follows:

|  | Categories Categorias | Amount Monto | Leverage Apalancamiento | Total |
| --- | --- | --- | --- | --- |
| 1. | Personnel Personal | $2,365,110 $2,238,979 | $272,332 $474,112 | $2,637,441 $2,713,091 |
| 2. | Fringe Benefits Beneficios | $1,036,457 $1,119,100 | $129,699 $218,811 | $1,166,156 $1,337,911 |
| 3. | Travel Viajes | $659,970 $551,981 | $0 | $659,970 $551,981 |
| 4. | Equipment Equipo | $50,000 $0 | $0 | $50,000 $0 |
| 5. | Supplies Suministros | $58,128 $171,660 | $0 | $58,128 $171,660 |
| 6. | Contractual Contractual | $1,035,700 $1,093,512 | $0 | $1,035,700 $1,093,512 |
| 7. | Other Direct Costs Otros Costos Directos | $1,088,619 $682,551 | $0 | $1,088,619 $682,551 |
| 8. | Total Direct Costs Total Costos Directos | $6,293,983 $5,857,784 | $402,031 $692,922 | $6,696,014 $6,550,706 |
| 9. | Indirect Costs Costos Indirectos | $524,398 $485,597 | $40,203 $69,645 | $564,601 $555,242 |
| 10. | Total Costs Total Costos | $6,818,381 $6,343,381 | $442,234 $762,568 | $7,260,615 $7,105,948 |

No cost extension, leverage modification and budget realignment are included in the following budget lines details:

- Personnel

Total USAID amount decreased by USD $126,130

| 800-Parque Explora Initial Budget |  | 800-Parque Explora Realignment – Modification No. 7 |  |
| --- | --- | --- | --- |
| Total amount: | USD $2,637,441 | Total amount: | USD $2,713,091 |
| JA/USAID: | USD $2,365,110 | JA/USAID: | USD $2,238,979 |
| JA/Leverage: | USD $272,332 | JA/Leverage: | USD $474,112 |

- Reduction due to salary adjustment and elimination of positions.

- Leverage amount increases due to the new period of performance, since some management staff will support until the end.

- The approved budget line summarizes the financial aspects of the personnel for the project according with the approved WP for years 1, 2, 3 and 4, and expectations goals and closeout procedures in years 5, and 6.

- Level of effort (LOE) budgeted is based on the scope of the program and the current needs.

- Due to the current inflationary situation in Colombia:

  - 5.6% increase for inflation has been applied for all 800-PE/JA staff in 2022.

  - 13.12% increase for inflation has been applied for all 800-PE/JA staff in 2023.

  - 10% increase for inflation has been applied for all 800-PE/JA staff in 2024.

  - Estimates for 2025 and 2026 are projected at 4% average increase in accordance with projected inflation rate.

- All positions are required for the successful implementation of the activities, are according with the Work Plans approved and all positions are into the range of wages that Parque Explora use in all its projects.

- All recruitment processes of staff at all levels, are prior approved by POA/JA/RRHH.

Staff approvals can see on the following POA´ SharePoint link: Staff

# Fringe Benefits

Total USAID amount increased by USD $82,644

| 800-Parque Explora Initial Budget |  | 800-Parque Explora Realignment – Modification No. 7 |  |
| --- | --- | --- | --- |
| Total amount: | USD $1,166,155 | Total amount: | USD $1,337,911 |
| JA/USAID: | USD $1,036,456 | JA/USAID: | USD $1,119,100 |
| JA/Leverage: | USD $129,699 | JA/Leverage: | USD $218,811 |

- Increase amount does not exceed 10% of the total subaward for the life of the subgrant. The increase in this item is mainly due to the adjustment in the fringe percentage, since the original budget considered fringe benefits charging 40,364% of ordinary salaries and it really represents 52,76%.

- Leverage amount increases due to the new period of performance, since some management staff will support until the end.

- The approved budget line summarizes the social security system (pension, health, solidary pension fund, labor risks and payroll taxes (SENA, ICBF and Family Compensation Fund) related with all the personnel hired for the project (located in numeral 1 – Personnel). This budget line also includes all costs related with vacations, severance payments, among others, all according with the set of Colombian legal principles and rules that regulate the relationships between employer(s) and worker(s).

- Parque Explora has two types of fringe benefits:

  - Contributions caused by ordinary salaries, that represents the 52,76% and contributions, that includes the following percentages:

- 8.333% for severance payment per month

- 1% interest on severance payment per month

- 4.166% for vacation (15 days of vacation/265 working days a year) per month

- 8.333% bonus (prima legal de servicios or 13th & 14th month bonus) per month

- 8.5% health insurance per month

- 12% pension per month

- 1.43% profesional risks per month

- 4% Family Welfare Fund per month

- 3% for the Instituto Colombia Bienestar Familiar (ICBF) per month

- 2% for the Sistema de Aprendizaje National (SENA) per month

  - Contributions caused by integral salaries, that represents the 25,18%, includes only leveraged positions.

# Travel

Total USAID amount decreased by USD $107,989

| 800-Parque Explora Initial Budget |  | 800-Parque Explora Realignment – Modification No. 7 |  |
| --- | --- | --- | --- |
| Total amount: | USD $659,970 | Total amount: | USD $551,981 |
| JA/USAID: | USD $659,970 | JA/USAID: | USD $551,981 |
| JA/Leverage: | USD $0 | JA/Leverage: | USD $0 |

Assumptions: - Round trip rates are based on coach/economy class airfares and compliance with Fly America. - Per-diem rates and allowances are based on an average reduced rate of USG allowable per-diems. - Lodging rates are based on a hotel quotes, market research and an average reduced rate of the USG allowable rate. - All of the costs for travel after year one include a 4% increase to account for inflation.

- Reduction due to the elimination of travel lines initially included and that are not necessary in the execution of the program.

- The approved budget line summarizes costs related with travel expenses: airfare, land transportation, lodging, per diem for 800-PE/JA Direction Team, some transversal and technical positions of field personnel to oversee project activities, including, but no limited to, parents/students/teacher training activities, different kind of meeting with Education Secretaries, Advisory boards meetings, annual forums, national and international forums for Education Observatories, SMT, 2nd tier subgrantees meetings, local transportation for tutors, etc.

# Equipment

Total amount decreased by USD $50,000

| 800-Parque Explora Initial Budget |  | 800-Parque Explora Realignment – Modification No. 7 |  |
| --- | --- | --- | --- |
| Total amount: | USD $50,000 | Total amount: | USD $0 |
| JA/USAID: | USD $50,000 | JA/USAID: | USD $0 |
| JA/Leverage: | USD $0 | JA/Leverage: | USD $0 |

Assumptions: - All equipment (over $5,000) purchases will be made under the guidance of the POA, unless otherwise indicated. - To the extent possible, all equipment will be procured in Colombia, in accordance with standard procurement practices, to eliminate shipping and handling costs.

- Decrease amount does not exceed 10% of the total subaward for the life of the subgrant.

- The approved budget line only considered the acquisition of one (1) Vehicle for Field Office.

- The original budget included USD $50,000 for the purchase of one (1) vehicle following USAID procurement guidelines and sourcing requirements for the operations in Antioquia. However, Parque Explora has contracts with transportation providers that have very competitive rates for local mobility, and according to  technical activities of Juntos Aprendemos, a vehicle is not necessary.

- As of December 2023, Parque Explora has executed $0 in this item, with no need to acquire a vehicle in the future; therefore, this line will be deleted.

# Supplies

Total USAID amount increased by USD $113,532

| 800-Parque Explora Initial Budget |  | 800-Parque Explora Realignment – Modification No. 7 |  |
| --- | --- | --- | --- |
| Total amount: | USD $58,128 | Total amount: | USD $171,660 |
| JA/USAID: | USD $58,128 | JA/USAID: | USD $171,660 |
| JA/Leverage: | USD $0 | JA/Leverage: | USD $0 |

- Increase amount does not exceed 10% of the total for the life of the subgrant.

- Increase for expenses not initially contemplated, such as purchase and rental of computers, purchase of licenses, and endowment for employees required by law.

- As of December 2023, Parque Explora has executed $139,971 in this item, resulting in a balance of -$72,209, as more laptops and tablets and other kind of supplies were required for project staff. The value will be covered with realigned amounts in Supplies (Personal Protective Equipment), because of USAID instructions which indicate that Implementing Partners are no longer required to apply biosafety protocols to prevent risks or infections or present COVID-19, on May 11, 2023.

# Contractual

Total USAID amount increased by USD $57,812

| 800-Parque Explora Initial Budget |  | 800-Parque Explora Realignment – Modification No. 7 |  |
| --- | --- | --- | --- |
| Total amount: | USD $1,035,700 | Total amount: | USD $1,093,512 |
| JA/USAID – 2nd Tier Subawardees: | USD $1,000,000 | JA/USAID – 2nd Tier Subawardees: | USD $1,000,000 |
| JA/USAID –Security: | USD $35,700 | JA/USAID –Security: | USD $0 |
| JA/USAID –Rapid Response Fund: | USD $0 | JA/USAID – Rapid Response Fund: | USD $93,512 |

- Increase amount does not exceed 10% of the total subaward for the life of the subgrant.

- The budget line summarizes second tier subawards and the inclusion of rapid response fund not initially contemplated.

- Project demands and Juntos Aprendemos high-paced implementation require Parque Explora to rapidly respond to project needs. Parque Explora proposes $93,512 between 2023 and 2026, destined to cover, but not limited to, consultant services.

- All second tier subawardees processes are prior approved by POA/JA/HO.

- Second Tier Subawards process and approvals can be seen on the following POA´ SharePoint link: 2nd Tier SubAs

- The original budget included $35,700 for a Local Security Contract, however, POA proactively consolidated this contract in just one for all the operation of Juntos Aprendemos in Colombia.

- The value will be covered with realigned amounts in other direct costs.

# Other Direct Costs

Total USAID amount decreased by USD $406,068

| 800-Parque Explora Initial Budget |  | 800-Parque Explora Realignment – Modification No. 7 |  |
| --- | --- | --- | --- |
| Total amount: | USD $1,088,619 | Total amount: | USD $682,551 |
| JA/USAID: | USD 1,088,619 | JA/USAID: | USD $682,551 |
| JA/Leverage: | USD $0 | JA/Leverage: | USD $0 |

- Reduction due to the suppression of communications expenses, holding of national fairs and actions related that were initially considered and were eliminated.

- The budget line summarizes all costs related with F&A (audits, bank fees, translations costs, etc.) and logistics related with objectives and subactivities: trainings, tutoring session’s needs – educational guides, fungible materials, etc, workshops needs (spaces, refreshments, lunchs, etc), and MEL needs.

OTHER RELATED COSTS:

# De Minimis Rate:

Total USAID amount decreased by USD $38,801

| 800-Parque Explora Initial Budget |  | 800-Parque Explora Realignment – Modification No. 7 |  |
| --- | --- | --- | --- |
| Total amount: | USD $564,601 | Total amount: | USD $555,242 |
| JA/USAID: | USD $524,398 | JA/USAID: | USD $485,597 |
| JA/Leverage: | USD $40,203 | JA/Leverage: | USD $69,645 |

- This decrease is due to the reduction in the total ceiling.

- Initial budget included a negotiated Minimis Rate by 10%. Indirect Costs will be applied upon budget realignment approval at the same rate. A summary of these charges as follows:

|  | Year |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 800-Parque Explora | Y1 USD | Y2 USD | Y3 USD | Y4 USD | Y5 USD | Y6 USD | TOTAL USD |
| (10% De Minimis Rate) – USAID | $16,897 | $151,905 | $83,619 | $89,330 | $94,478 | $49,368 | $485,597 |
| (10% De Minimis) – Leverage | $0 | $7,712 | $14,455 | $18,258 | $19,396 | $9,825 | $69,645 |

- Leverage per year (without De Minimis Rate)

|  | Year |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 800-Parque Explora | Y1 USD | Y2 USD | Y3 USD | Y4 USD | Y5 USD | Y6 USD | TOTAL USD |
| Leverage* | $0 | $70,308 | $147,829 | $182,575 | $193,957 | $98,254 | $692,922 |

* Leverage increase due to the extra time of some positions during the extension.

- Total USAID amount per year

| 800-Parque Explora Initial Budget |  | 800-Parque Explora Realignment – Modification No. 7 |  |
| --- | --- | --- | --- |
| Year 1 | USD $940,973 | Year 1 | USD $187,345 |
| Year 2 | USD $1,335,822 | Year 2 | USD $1,849,073 |
| Year 3 | USD $1,823,999 | Year 3 | USD $1,135,004 |
| Year 4 | USD $1,841,035 | Year 4 | USD $1,144,382 |
| Year 5 | USD $876,552 | Year 5 | USD $1,234,831 |
| Year 6 | USD $0 | Year 6 | USD $792,746 |
| TOTAL | USD $6,818,381 | TOTAL | USD $6,343,381 |

Employees earning integral salary, 70 percent of salary will be the basis to calculate contributions to the social security system.

Current Inventory can be seen on the following POA´ SharePoint link: Inventory

“Year” refers to the Juntos Aprendemos Program Year, January-December, except for Year One (August – December 2021) and Year Six (January – August 2026).

“Year” refers to the Juntos Aprendemos Program Year, January-December, except for Year One (August – December 2021) and Year Six (January – August 2026).