BUDGET NARRATIVE

| Program | Food for Progress |
| --- | --- |
| Country | Mauritania |
| Fiscal Year | 2023 |
| Organization | Partners of the Americas, Inc. |
| Point of Contact | Michael Moscarelli, mmoscarelli@partners.net |

I. General Explanatory Comments benefit

Partners of the Americas Inc. (POA) will implement a five-year Food for Progress (FFPr) Program project in Mauritania. The total federal award amount is $35,550,000. This includes commodities ($28,250,000), freight ($5,900,000), and administrative costs (cash portion) ($1,400,000). The total operating budget (grand total costs) for this project is $15,600,000; this includes $200,000 in cost share. POA expects interest on proceeds to be $7,878. The following budget narrative describes the operating budget and does not describe the commodity and freight portions of Federal funding. The narrative is set up per the NOFO guidance and subsequent amendments. Please see the following summaries below, as requested on pages 81 & 82 of the NOFO.

Gross Monetization Proceeds	  $14,000,000

CCC Admin Funds	 $1,400,000

Interest	  $7,878

Cost Share	$600,000

Total 	   $16,007,878

Total Project Operating Budget (including cost share and interest) $16,007,878

| Summary of Total Project Operating Budget (Includes Cost Share) |  |
| --- | --- |
| Administration | $3,487,244.80 |
| Activities | $8,723,886.20 |
| ICR on Administration | $986,192 |
| ICR on Activities | $2,410,555 |
| Total | $16,007,878 |

POA aims to maximize funding going towards direct program activities. POA’s operating budget (including cost share) directs 57% of the funds to program activities, and 43% is for administration and indirect costs.

Summary of POA Indirect Rates Applied 		$3,396,747

| Summary of Total Indirect Costs Applied |  |
| --- | --- |
| Total Administration Direct Costs | $3,487,244.80 |
| Total Activities Direct Costs | $8,523,886.20 |
| Indirect Costs Applied on Administration 28.28% | $986,192 |
| Indirect Costs Applied on Activities 28.28% | $2,410,555 |
| Total Indirect Costs | $3,396,747 |

Summary of M&E Budget						 $965,500

| Summary of M&E Budget (Excluding M&E Personnel & Travel) |  |
| --- | --- |
| Evaluations (Baseline, Midterm, & Final) | $485,000 |
| Impact Evaluation | $200,000 |
| Special Study | $200,000 |
| Monitoring Guidelines Creation, Translation & Printing | $10,000 |
| Monitoring Guidelines Revision, Translation & Printing | $8,000 |
| Monitoring Guidelines Staff Training on Indicators and Data Collection/Analysis | $30,000 |
| M&E Database Platform Subscription (includes training) | $32,500 |
| Total M&E Budget | $965,500 |
| Total Budget % Dedicated to M&E (Excluding Cost Share) | 6.26% |

POA believes that M&E is a critical component for successful programmatic implementation; therefore, POA has allotted approximately 6.26% ($965,500) of the total budget (excluding cost share) to M&E-related activities. In the field, POA will have a dedicated M&E Director and an M&E Specialist with 100% LOE throughout the 5 years of the project. In addition to these staff, POA will implement a robust system for M&E evaluation, tracking, and reliable data collection. This includes costs for M&E external third-party evaluations, a special study, M&E guidelines training, license and implementation of M&E software, and M&E data collection site visits. In addition, POA will bring its prior experience in data collection to help train staff. POA will provide its training materials, tools, and other resources to help staff with the M&E aspects of the project. These resources will be offered to the project at no cost to USDA.

Budget Assumptions and Cost Escalations

POA has established a local hire pay scale for Mauritania in accordance with market rates for the level of experience and education required. The salary scale for local hires was established based on comparable organizations and projects, information gathered from in-country consultants, online research, and market analysis for similar positions and experience levels. POA has applied a 4% increase to account for inflation and merit-based salary increases for all U.S. Nationals (USN)/Third Country Nationals (TCN) staff, Headquarters (HQ), and Cooperating Country National (CCN) staff after Year 1 (Y1), in accordance with POA policy. Actual annual increases will range between 1%-5% and are based on an annual performance review.

Expenses for travel, office supplies & personal protective equipment, and office expenses include a yearly escalation for inflation after Y1. Inflation is estimated at 4% annually after Y1.

All equipment (over $5,000) purchases will be made under the guidance of POA, unless otherwise indicated. To the extent possible, all equipment will be procured in Mauritania, in accordance with standard procurement practices, to eliminate shipping and handling costs. Travel costs for domestic in-country travel and per diem rates are budgeted based on local prevailing transportation, and lodging costs in Mauritania are based on a reduced rate of the U.S. Department of State per diem thresholds. International air travel is budgeted based on the prevailing cost of economy-class tickets for the proposed routes and will be Fly America Act compliant. The international lodging and per diem rates budgeted are based on a reduced U.S. Department of State lodging rate and POA’s prior experience.

Financial Capacity

POA has established sound financial management and internal control systems, ensuring expenditures are reasonable, allowable, and classified in accordance with generally accepted accounting principles (GAAP). POA uses cloud-based accounting software and is subject to an annual single audit. The Finance and Administration (F&A) department is staffed with professionals with over 100 years of combined experience in finance and accounting, auditing, and managing financial reporting for federal grants, contracts, and cooperative agreements. The F&A department comprises a Chief Financial Officer (CFO), Controller, Deputy Controller, Director of Compliance for Grants and Contracts, Budget Analyst, Accounts Payable Finance Officer, and two Senior Field Finance Officers. The F&A team works closely with project staff at POA HQ and in-country staff to monitor spending, ensure that all costs are reasonable and allowable, and support project staff to implement the project in accordance with USG rules and regulations (particularly 2 CFR 200), local laws, as well as POA’s internal policies. Our F&A department also reviews spending with project directors monthly and assists with the oversight of contracts, end-of-project reporting, and other aspects of project monitoring.

Cost Application Methodology

POA uses a robust and cost-effective strategy to determine cost allocation in accordance with USG cost principles, local laws, and internal policies. Our proposed budget for this project was developed by conducting thorough price analyses to identify reasonable, realistic, and fair market values for all projected expenses. Our budget estimates were also calculated based on past experience implementing effective and cost-efficient USG-funded programs. POA follows U.S. and local labor laws to determine salary and fringe benefits for all employees identified in this proposal. Indirect Costs have been applied in accordance with POA’s most recent NICRA agreement approved by our cognizant agency, USAID. In preparing the budget, POA has minimized administrative and support costs for managing the project to the extent possible to maximize the funds available for project activities while still ensuring overall award compliance and capacity building for implementing partners. As a result, 57% of the operating budget, including cost share, will be direct towards activities and 43% to administration and indirect costs.

Budget Components and Project Implementation

FFPr Mauritania’s budget allocated to each activity will allow for effective project implementation. POA’s budget uses rigorous evidence and references previous costs of similar projects implemented in Mauritania by donors such as the World Bank, the United Nations International Fund for Agriculture Development, and USAID. Activity 1 will appropriately fund demonstration sites for farmers and cover associated training costs, a contract with 6th Grain (a US-based GIS and remote sensing company) to produce high-impact agricultural data and introduce and improve new and innovative irrigation solutions for farmers. Activity 2 will promote regenerative agriculture with agropastoralists through training on horticulture production, planting Horticulture Tree Buffer Zones that mitigate desertification, and conducting Social and Behavior Change radio and in-person “Farmer Field Days” activities and outreach. The budget for these activities will ensure sufficient resources flow toward training, tree planting, and communications campaigns. Activity 3 will invest in agro-dealers and women’s cooperatives “Agribusiness hubs, Private Agriculture Service Provider certification program, agriculture school’s improvement, Outgrower Model contract farming development, launch the Mauritanian Ag Expo, and build governments capacity to support agriculture and sustain investment. The budget will allow for all these activities to be implemented effectively; for example, building the Private Agriculture Service Provider certificate program considers the cost of designing the program, room, and board for trainees, and start-up funds for graduates. Activity 4 optimizes USDA’s investment by incentivizing significant cost share opportunities. POA will work with the Global Cold Chain Alliance to build an investment portfolio for post-harvest capacity investment. This market study will reveal a suite of investment options in post-harvest storage and processing through appropriate project cost share input. POA is confident that all activities are appropriately funded to ensure quality implementation of proposed activities.

Cost Effectiveness

In compliance with the NOFO requirements, POA's budget is organized by activity and apportions costs for implementing the project's four activities. The budget has been developed considering cost-effectiveness to support and achieve the key objectives. The project’s budget components were designed to build long-term human capital and leverage private sector resources. The project is cost-effective, namely because of the demand-based nature of activities and interest from the government and private sector to support and sustain activities. Up-front expenditure on innovative research and market studies will provide the project with precise information on how to meet the needs of beneficiaries. Studies and information made available through the project will incentivize the private sector to co-invest in activities and ensure the long-term viability of any USDA investment. Funds will be dispersed with precision, deferring to data-driven spending decisions. POA anticipates that funds spent on new linkages will exponentially increase agriculture sector output and two-way trade, creating an excellent return on investment for all stakeholders.

Anticipated Interest Earned

FFPr Mauritania expects that interest accrued on monetization proceeds will be $7,878 over the life of the project (LOP) based on an investment of the fund in an interest-bearing account with Bank of America. Based on current quotes, the compounding interest rate for a separate interest-bearing savings account with Bank of America is 0.03%.

Management of Monetization Proceeds

Payment will be secured and received from the buyer(s) through an irrevocable Letter of Credit from a bank(s) acceptable to POA. Upon receipt of payment, the funds will be deposited into a separate U.S.-based interest-bearing U.S. dollar account under the supervision of POA’s CFO, who will be responsible for the disbursement of funds once approval has been received from the President & CEO. Funds from the monetization proceeds will only be disbursed when an immediate cash need for project activities and prior approval from the President & CEO is obtained. POA’s CFO and Controller oversee core functions related to award administration, accounting, internal controls, and financial reporting, with additional compliance support from the Grants and Contract Compliance Unit. The Grants and Compliance Unit will conduct periodic compliance spot checks and annual internal audits with POA and contractors. Annually POA undergoes a formal external audit, in which all bank accounts and release of funds are tested.

II. Administration

Total Administration Costs: $4,473,437 ($3,073,437 in monetization, $1,400,000 in CCC funds, $0 in cost share)

- Total Direct Costs: $3,487,245 ($2,395,882 in monetization, $1,091,363 in CCC funds)

- Total Indirect Costs: $986,192 ($677,555 in monetization, $308,637 in CCC funds)

2.1 Salaries/Personnel - Total $824,514 ($340,514 monetization, and $484,000 CCC funds)

USN/TCN Staff. USN/TCN benefits are budgeted for the Chief of Party (COP) for five years over LOP. The COP will be an expatriate who has worked in Mauritania or other similar operating environments for over 15 years and has the necessary USG background, compliance, and technical expertise. The COP will oversee a team of experts and support staff, prepare reports and work plans, align project initiatives with in-country priorities, and ensure project compliance with federal regulations. The COP’s salary is distributed between Administrative and Activities. To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

CCN Staff. Budgeted at 100% LOE for all five years of the project, the Deputy Chief of Party (DCOP) will be a Mauritanian national with more than 10 years of experience working in Mauritania. The DCOP is responsible for ensuring technical quality in the design and implementation of project activities. Other CCN staff include 3 Technical Leads, Specialists for component 2, 3, and 4, 20 Extension Agents, M&E Director, M&E Specialist, F&A Director, Human Resource Manager, Contracts & Compliance Specialist, Accountant, Administrative Assistant, Security Guards, and 2 Drivers. The CCN staff salary is distributed between Administrative and Activities as appropriate for each role. The majority of CCN staff are budgeted to remain on the project throughout the life of the project, except for the 20 Extension Agents who will complete their work midway through Y3. The proposed salary rates align with market research, and local in-country consultations were conducted by POA. To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

Headquarters (HQ) Staff. POA HQ salary rates are based on the current annual salaries of staff, POA’s salary matrix, and industry benchmarking surveys. The POA HQ team will be led by the Senior Director of Agriculture & Food Security, who oversees the HQ team in the project’s interventions, providing compliance and technical support. The HQ Program Manager will serve as the primary day-to-day support to the field team. They will be supported by the HQ Monitoring, Evaluation, Research, and Learning (MERL) Senior Director and HQ Compliance Team who are not directly billed to the project, but are included in POA’s overhead cost rate (see NICRA letter). To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

2.2 Fringe Benefits – Total $406,405 ($140,988 in monetization, and $265,417 in CCC funds)

Fringe Benefits – HQ and USN/TCN

POA charges fringe benefit costs in accordance with POA’s personnel policy and its NICRA letter. POA has charged a 23.47% fringe rate on HQ and USN/TCN salaries. Fringe benefits include insurance, mandatory taxes, pension, and other employee benefits. Total Headquarters and USN/TCN Administrative Fringe Benefits = $154,154.

### Fringe Benefits CCN Mauritania

Fringe benefits for CCN staff are budgeted at 26.92% of their total salary and are based on local labor law, in-country required benefits, and POA’s fringe benefit policy. This includes:

- 13% - Social security CNSS (Caisse National de Sécurité Sociale)

- 2% - Medical CNSS (Caisse National de Sécurité Sociale)

- 5% - CNAM (Caisse Nationale d’Assurance Maladie)

- 6.92% - Annual leave 18 days (1.5 days per month of service)

Total CCN Fringe Administrative Benefits = $45,145.

Allowances – USN/TCN Staff

### Allowances for USN/TCN staff are budgeted at 50% of their total salary and are based on allowance rates from the U.S. Department of State Office of Allowance and POA USN/TCN fringe benefit policy. This includes:

- 15% Cost of Living Adjustment

- 35% Post Hardship

Additionally, POA is budgeting for the following allowances which are part of POA’s standard fringe benefit package for ex-pat COPs:

- Housing allowance: POA is budgeting $1,600/month based on the U.S. Department of State housing allowance and market research for housing in a secure location with on-site security and Wi-Fi for the ex-pat COP. The house will be made ready and furnished.

- Reallocation & demobilization allowance: POA is budgeting $30,000/year in Y1 and Y5. Per POA's ex-pat fringe benefit policy this allowance is intended to cover COP's initial flight to Mauritania, excess baggage, movement of household goods - shipment for land/sea container, and customs and taxes.

- Annual home of record and rest & recuperation (R&R) trips: POA is budgeting for roundtrip airfare at $1,700/trip for the ex-pat COP to take either annual home of record or R&R trip each year as allowable under the Foreign Affairs Manual (FAM).

The above allowances are reasonable given that they are in accordance with POA’s fringe benefit policy for expatriates and are in alignment with the benefits allotted by the U.S. Department of State and the FAM. Given the challenging operating context and security concern in Mauritania, POA believes that these benefits are reasonable and must be provided to attract and retain a top experienced COP candidate to oversee the project.

Total USN/TCN Administrative Allowances = $207,106.

2.3 Travel – Total $208,538 ($170,975 in monetization and $37,563 in CCC funds)

International Travel ($64,454)

POA HQ staff will make 20 international trips to Mauritania during the period of performance. The purpose of the trips will be to provide monitoring, oversight, and technical guidance. The total HQ staff international travel cost (airfare) estimate is $36,831.

Mauritania staff will make 15 international trips during the period of performance. The purpose of the trips will be to hold meetings, attend technical training, and attend conferences. The Chief of Party and the DCOP will each make at least 3 international trips to HQ in Washington, DC. The total Mauritania staff international travel cost (airfare) estimate is $27,623.

Local Travel ($28,977)

POA estimates $9,479 in local ground transportation for 35 trips for HQ and Mauritania staff international travel.

POA estimates $19,499 in local ground transportation for Mauritania staff to make 180 domestic trips over LOP. The purpose of the trips will be to attend trainings and meetings as well as perform M&E and data collection.

Motorcycle and Vehicle Fuel ($7,522)

POA estimates the administrative cost for fuel expense for 2 vehicles and 20 motorcycles to be $150/month. The total vehicle fuel cost estimate is $7,522.

Per Diem ($107,584)

International Travel – HQ Staff: POA estimates $26,713 in lodging, meals, incidental expenses (M&IE), and other travel costs (visa, insurance, etc.). POA estimates lodging at $97/night and M&IE at $72/day for 20 trips of 7 days each. POA also estimates $1,083 in other travel related costs, estimated at $50/trip for 20 trips.

International Travel – Mauritania Staff: POA estimates $20,035 in lodging and M&IE, and other travel costs (visa, insurance, etc.). POA estimates lodging at $110/night and M&IE at $59/day for 15 trips of 7 days each. POA also estimates $812 in other travel-related costs, estimated at $50/trip for 15 trips.

Local Travel – Mauritania Staff: POA estimates $60,836 in lodging at a rate of $43/night and M&IE, estimated at $35/day for 36 trips per year of 4 days each.

2.4 Professional Services/Contractual – Total $1,417,600 ($1,167,600 in monetization, and

$250,000 in CCC funds)

Professional Services

Monetization Agent Fee ($280,000)

The Monetization Agent fee is estimated at 2% of monetization proceeds received for $280,000.

Monetization Impact Assessment ($48,000)

POA estimates $48,000 for a monetization impact assessment to evaluate the market impact of the monetization.

Support Services ($124,100)

POA has included expenses related to support services over the life of the program. These costs are directly attributable to the project and include audit costs ($40,000); legal fees/services ($15,000); security services, risk assessments, and security assessments ($2,500); short-term technical advisors ($22,950), a start-up consultant ($21,150), and POA will contract Abdel Aziz Dahi to serve as a Technical Advisor of Trade Promotion & Strategic Partnership & Investment who is a Mauritanian national with more than 20 years of experience working at the highest levels of the Government of Mauritania ($22,500).

Evaluations

Evaluations ($685,000)

POA estimates external evaluation fees for the Baseline, Midterm, Final, and Impact Evaluations to be $150,000, $160,000, $175,000, and $200,000, respectively. POA will host an open procurement to select an external evaluator for the evaluations. POA will consider factors such as the soundness of the proposal, unique capabilities, cost, delivery schedule, technical competency, experience in Mauritania, etc. The Impact Evaluation is supplementary funds to collect additional impact evaluation data points on top of the Baseline, Midterm, and Final Evaluation.

Special Studies ($200,000)

POA proposes two special studies: 1) Horticultural Tree Buffer Zone Study and 2) Pastoralist Social Behavior Change Study. In Y2, POA will begin a study to assess the farm productivity and ecosystem impacts of incorporating horticulture buffer zones. In Y3, POA will begin the Pastoralist Social Behavior Change Study to determine what incentives, if any, increase pastoralists’ willingness to cultivate mango trees to diversify their income and food sources. Both studies will cost $100,000, totaling $200,000, and will each run for three years. POA will go through a competitive bidding process to select the contractors. POA will consider factors such as the soundness of the proposal, unique capabilities, cost, delivery schedule, technical competency, experience in Mauritania, etc.

Monitoring Guidelines Development ($48,000)

### POA will develop M&E guidelines, including the cost of creating, translating, and printing at a one-time rate of $10,000. As part of its adapting and learning process, POA also estimates $8,000 for any revisions to the guidelines, including translation and additional printing needed over LOP. Once the Monitoring Guidelines have been developed, POA will provide training to all staff on indicators and data collection/analysis, including ongoing training for existing and updated guidelines, for a total of $30,000.

M&E Database ($32,500)

### POA estimates M&E database platform subscription fees, including training, to accurately track project data across regions and activities. The total M&E database cost is $32,500.

2.5 Equipment – Total $130,000 ($130,000 in monetization and $0 in CCC funds)
POA plans to purchase two 4x4 specialized vehicles ready for the deserts and rural areas. Based on local quotes, POA estimates the cost at $65,000/vehicle, including customs, taxes, and import fees, for a total of $130,000. POA will follow USDA procurement guidelines and sourcing requirements. POA conducted a buy vs. lease analysis and found it more cost-effective to purchase vehicles given the frequent travel for data collection, trainings, and site visits to locations 4+ hours from the capital city. The title for this equipment will be retained by POA.

2.6 Office – Total $384,483 ($369,493 in monetization and $14,990 in CCC funds)

POA estimates the cost of its main in-country office in Nouakchott and a satellite office in Rosso to be $384,483. The costs include communications costs (internet, phone, data); office rent, utilities, and security; banking and cash handling fees; courier fees/services and postage; recruitment/procurement advertising; meeting expenses which are intended to cover the cost for any printing of materials for programmatic meetings, and room rental and A/V equipment rental as needed; payroll processing and local accounting books preparation; and licenses and subscriptions for program management. To estimate these costs, POA hired a local consultant in Mauritania to obtain quotes from local providers for these services to establish the average rate for each cost.

2.7 Supplies – Total $37,113 ($11,145 in monetization and $25,968 in CCC funds)

Appliances ($23,369)

POA plans to purchase 12 desktop/laptop computers; 2 all-in-one printers, a photocopier, and a scanner; 1 projector; and office furniture for the in-country offices, including desks, chairs, tables, shelves, filing cabinets, safes, and A/C units). Estimated costs are $23,369.

Office Supplies ($13,744)

The budgeted monthly office supply and personal protective equipment (PPE) costs are estimated at $250. The costs cover all necessary office supplies such as notebooks, pens, calculators, office bags, clip files, registers, photocopy paper, flip chart paper, markers, transparency paper, flip chart boards, etc. Additionally, the PPE costs are intended to include but are not limited to masks, gloves, hand sanitizer, antibacterial wipes, and other PPE that will keep staff and other participants safe. POA estimates are based on past experience and market research.

2.8 Other – Total $78,592 ($65,167 in monetization and $13,425 in CCC funds)

Training ($37,500)

POA plans for $7,500 in training, workshop, conference, and registration fees per year for the life of the project. The price is based on a registration or training fee of $1,500/event or training and 5 trainings/events per year. The costs will cover trainings, workshops, and/or courses on USG Rules and Regulations, program management, and technical conference and registration fees as necessary for the successful implementation of the project. The total for training is $37,500.

Maintenance ($28,093)

POA estimates equipment and office repairs and maintenance ($8,124), motorcycle maintenance ($6,500) (note: motorcycles to be purchased under specific activities), and vehicle maintenance ($13,469) to be a total of $28,093.

Insurance ($12,999)

POA estimates property and liability insurance ($2,708), motorcycle insurance ($8,124) (note: motorcycles to be purchased under specific activities), and vehicle insurance ($2,167) to be a total of $12,999.

2.9 Indirect Costs – Administration – Total $986,192 ($677,555 for monetization and

$308,637 for CCC)

In accordance with POA’s most recently approved NICRA, indirect costs are estimated at $986,192.

III. Activities

- Total $11,134,441 ($10,934,441 in monetization funds and $600,000 in cost share)

- Total Direct Costs: $8,723,886 ($8,523,886 in monetization funds and $600,000 in cost share)

- Total Indirect Costs: $2,410,555 ($2,410,555 in monetization funds)

Activity 1: Increase Production and Farmer Resiliency – Total $2,098,882 ($2,098,882 in monetization funds and $0 in cost share)

### 3.1.1 Salaries/Personnel – $955,939

USN/TCN Staff. USN/TCN benefits are budgeted for the Chief of Party (COP) for five years over LOP. The COP will be an expatriate who has worked in Mauritania or other similar operating environments for over 15 years and has the necessary USG background, compliance, and technical expertise. The COP will oversee a team of experts and support staff, prepare reports and work plans, align project initiatives with in-country priorities, and ensure project compliance with federal regulations. The COP’s salary is distributed between Administrative and Activities. To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

CCN Staff. Budgeted at 100% LOE for all five years of the project, the Deputy Chief of Party (DCOP) will be a Mauritanian national with more than 10 years of experience working in Mauritania. The DCOP is responsible for ensuring technical quality in the design and implementation of project activities. Other CCN staff include 3 Technical Leads, Specialists for component 2, 3, and 4, 20 Extension Agents, M&E Director, M&E Specialist, F&A Director, Human Resource Manager, Contracts & Compliance Specialist, Accountant, Administrative Assistant, Security Guards, and 2 Drivers. The CCN staff salary is distributed between Administrative and Activities as appropriate for each role. The majority of CCN staff are budgeted to remain on the project throughout the life of the project, except for the 20 Extension Agents who will complete their work midway through Y3. The proposed salary rates align with market research, and local in-country consultations were conducted by POA. To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

### 3.1.2 Fringe Benefits – Total $345,361

Benefits for USN/TCN staff are calculated at 23.47% of the employee’s base salary ($44,380). CCN Mauritania staff benefits are per local labor laws and are calculated at 26.92% of the employee’s base salary ($206,435).

Allowances for USN/TCN staff are calculated at 50% of their total salary ($94,546).

### 3.1.3 Travel – Total $149,457

Local Travel ($127,949)

POA estimates $5,549 in local transportation for trainings at $100/trip for 51 trips over the LOP. In addition, to make training accessible, POA estimates $122,400 for transport stipends for participants to attend trainings at $10/participant for 6,000 participants per year in Y1 and Y2,

Motorcycle and Vehicle Fuel Expenses ($8,525)

Vehicle fuel for technical leads and motorcycle fuel for 9 motorcycles used by the project’s extension agents under this activity is estimated at $170/month for 46 months.

Per Diem ($12,984)

POA estimates $12,984 in lodging at a rate of $43/night and M&IE at $35/day for trainings for 51 trips over LOP, each trip will be for 3 days.

### 3.1.4 Professional Services/Contractual – Total $428,825

### The contractor, 6th Grain, will implement GIS and remote sensing technologies to model crop production potential and develop a digital registry of farmers in Y1-Y2 for a total of $300,000. POA has selected 6th Grain to conduct these activities based on its world-class GIS and remote sensing capabilities with a presence in Mauritania. The contract cost will include the cost to develop a digital registry and provide training to Mauritanian officials.

### POA will contract two expert technical irrigation hydrology engineers to evaluate infrastructure installed by current and previous development projects to improve on-farm irrigation and large-scale infrastructure. These consultants will be contracted for 3 months each at $6,000/month. This is budgeted in Y1 for a total of $36,000. POA will select expert consultants through an open and competitive process.

### POA will contract a firm to provide security services and conduct risk and security assessments under activity 1 to ensure the well-being of staff and program participants for $35,000 over LOP. Under activity 1, POA anticipates contracting other short-term technical advisors to support development of innovative techniques to improve production at $29,700 over LOP. Additionally, POA will contract Abdel Aziz Dahi to serve as a Technical Advisor of Trade Promotion & Strategic Partnership & Investment who is a Mauritanian national with more than 20 years of experience working at the highest levels of the Government of Mauritania ($28,125).

### 3.1.5 Equipment – Total $0

### None.

### 3.1.6 Office – Total $0

### None.

### 3.1.7 Supplies – Total $45,300

### POA will procure seeds and tools in Y1-Y2 for demonstration plot set-up and maintenance with a unit cost of $3,750. POA will set up 2 plots in each of the 4 regions of implementation. The total is $30,000.

### POA will procure 9 motorcycles with a unit cost of $1,100 based on local quotes for use by the Extension Agents. The total is $9,900.

### POA will procure 9 tablets to assist with rural data collection with a unit cost of $600 based on market rates for use by the Extension Agents. The total is $5,400.

### 3.1.8 Other – Total $174,000

### POA will implement the following training activities:

Development of Technical Package (Design, Printing & Translation) ($18,000)

A one-time cost has been budgeted in Y1 for the development of the technical assistance packages. The cost associated with this includes design, printing, and translation into multiple languages.

Publish Report for On-farm Irrigation (Design, Printing & Translation) ($18,000)

A one-time cost has been budgeted in Y2 for the publication of a report on the evaluation of on-farm irrigation. The cost associated with this includes design, printing, and translation into multiple languages.

Publish Report for Large-Scale Water Infrastructure (Design, Printing & Translation) ($18,000)

A one-time cost has been budgeted in Y2 for the publication of a report on the solutions and findings for large-scale water infrastructure best practices. The cost associated with this includes design, printing, and translation.

Demonstration Plots for Drip and Innovative Irrigation Solutions (2 drips, 2 aspersion/sprinklers, and 2 valley pivot plots) ($120,000)

Demonstration plots for drip and innovative irrigation solutions are being budgeted in Y1-Y2. The plots will be used to demonstrate innovative irrigation techniques such as drip, sprinkler aspersion, and valley pivots. POA estimates the cost at $20,000/plot for 6 total demonstration plots. The cost will cover setup, design, and materials for the demonstration plots. Based on quotes from International Fund for Agricultural Development (IFAD), the drip irrigation kits (pumps, tubes, filter, etc.) will vary based on exact size, however, each is estimated at $16,000/kit. The plots will also require a fence which is estimated at $3,000 per hectare based on IFAD quotes. Additionally POA estimates $300/plot for fertilizer, $300/plot for seeds, and $400/plot for tool kits (shovels, hoes, etc.) to tend to the plots.

Activity 2: Promote Regenerative Agriculture with Agropastoralists – Total $1,825,819 ($1,825,819 in monetization and $0 in cost share)

### 3.2.1 Salaries/Personnel – Total $894,149

USN/TCN Staff. USN/TCN benefits are budgeted for the Chief of Party (COP) for five years over LOP. The COP will be an expatriate who has worked in Mauritania or other similar operating environments for over 15 years and has the necessary USG background, compliance, and technical expertise. The COP will oversee a team of experts and support staff, prepare reports and work plans, align project initiatives with in-country priorities, and ensure project compliance with federal regulations. The COP’s salary is distributed between Administrative and Activities. To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

CCN Staff. Budgeted at 100% LOE for all five years of the project, the Deputy Chief of Party (DCOP) will be a Mauritanian national with more than 10 years of experience working in Mauritania. The DCOP is responsible for ensuring technical quality in the design and implementation of project activities. Other CCN staff include 3 Technical Leads, Specialists for component 2, 3, and 4, 20 Extension Agents, M&E Director, M&E Specialist, F&A Director, Human Resource Manager, Contracts & Compliance Specialist, Accountant, Administrative Assistant, Security Guards, and 2 Drivers. The CCN staff salary is distributed between Administrative and Activities as appropriate for each role. The majority of CCN staff are budgeted to remain on the project throughout the life of the project, except for the 20 Extension Agents who will complete their work midway through Y3. The proposed salary rates align with market research, and local in-country consultations were conducted by POA. To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

### 3.2.2 Fringe Benefits – Total $313,823

Benefits for USN/TCN staff are calculated at 23.47% of the employee’s base salary ($36,865). Benefits for CCN Mauritania staff are in accordance with local labor laws and are calculated at 26.92% of the employee’s base salary ($198,421).

Allowances for USN/TCN staff are calculated at 50% of their total salary ($78,537).

### 3.2.3 Travel – Total $59,522

Local Travel ($38,013)

POA estimates $5,549 in local transportation for trainings at $100/trip for 51 trips over the LOP. In addition, to make training accessible, POA estimates $32,465 for transport stipends for participants to attend trainings at $10/participant for 1,000 participants per year from Y2-Y4.

Motorcycle and Vehicle Fuel Expenses ($8,525)

Vehicle fuel for technical leads and motorcycle fuel for 6 motorcycles used by the project’s extension agents under this activity is estimated at $170/month for 46 months.

Per Diem ($12,984)

POA estimates $12,984 in lodging at $43/night and M&IE at $35/day for trainings, for 51 trips over LOP, each trip will be for 3 days.

### 3.2.4 Professional Services/Contractual – Total $368,125

### POA will enter into four consultant/contractual agreements as follows:

### $30,000: To design materials for outreach and awareness campaigns to promote horticulture activities within agropastoral communities in Y1; the cost includes translation into multiple languages.

### $180,000: To disseminate outreach and awareness campaigns to promote horticulture activities within agropastoral communities in Y3-Y5.

### $50,000: To contract 5 nurseries in Mauritania and Senegal at $10,000/nursery to grow mango, lime, native acacia, and other tree species in Y1.

### $18,000: To create outreach and sensitization materials for Social Behavioral Change activities to promote horticulture activities within agropastoral communities in Y2-Y4.

Consultants and contractors will be selected based on a competitive bidding process. POA will take into consideration factors such as the soundness of the proposal, unique capabilities of the bidder, the amount of the bid, delivery schedule, technical competency, etc.

### POA will contract a firm to provide security services and conduct risk and security assessments under activity 2 to ensure the well-being of staff and program participants for $35,000 over LOP. Under activity 2, POA anticipates contracting other ad-hoc consultancy and advisory support services  on regenerative and climate-smart agriculture and classes for regional nutrition for which POA has budgeted $27,000 over LOP.

### PPOA will contract Abdel Aziz Dahi to serve as a Technical Advisor of Trade Promotion & Strategic Partnership & Investment who is a Mauritanian national with more than 20 years of experience working at the highest levels of the Government of Mauritania ($28,125).

### 3.2.5 Equipment – Total $0

### None.

### 3.2.6 Office – Total $0

### None.

### 3.2.7 Supplies – Total $10,200

POA will procure 6 motorcycles with a unit cost of $1,100 based on local quotes for use by the Extension Agents. The total is $6,600.

POA will procure 6 tablets to assist with rural data collection with a unit cost of $600 based on market rates for use by the Extension Agents. The total is $3,600.

### 3.2.8 Other – Total $180,000

Six Farmer Field Schools per year in Y2-Y4 have been budgeted to train 400 individuals in 20 communities. The trainings in the Farmer Field Schools will demonstrate economically feasible and culturally appropriate horticulture activities for adoption from agropastoral communities. Based on quotes from IFAD, the gravity irrigation kits (pumps, tubes, filter, etc.) will vary based on exact size, however, each is estimated at $7,000/kit. The plots will also require a fence which is estimated at $2,000 for the expected size. Additionally, POA estimates $500/plot for fertilizer, and $500/plot for seeds.

Activity 3: Improve the Agricultural-Enabling Environment – Total $1,995,172 ($1,995,172 in monetization and $0 in cost share.)

### 3.3.1 Salaries/Personnel – Total $890,638

USN/TCN Staff. USN/TCN benefits are budgeted for the Chief of Party (COP) for five years over LOP. The COP will be an expatriate who has worked in Mauritania or other similar operating environments for over 15 years and has the necessary USG background, compliance, and technical expertise. The COP will oversee a team of experts and support staff, prepare reports and work plans, align project initiatives with in-country priorities, and ensure project compliance with federal regulations. The COP’s salary is distributed between Administrative and Activities. To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

CCN Staff. Budgeted at 100% LOE for all five years of the project, the Deputy Chief of Party (DCOP) will be a Mauritanian national with more than 10 years of experience working in Mauritania. The DCOP is responsible for ensuring technical quality in the design and implementation of project activities. Other CCN staff include 3 Technical Leads, Specialists for component 2, 3, and 4, 20 Extension Agents, M&E Director, M&E Specialist, F&A Director, Human Resource Manager, Contracts & Compliance Specialist, Accountant, Administrative Assistant, Security Guards, and 2 Drivers. The CCN staff salary is distributed between Administrative and Activities as appropriate for each role. The majority of CCN staff are budgeted to remain on the project throughout the life of the project, except for the 20 Extension Agents who will complete their work midway through Y3. The proposed salary rates align with market research, and local in-country consultations were conducted by POA. To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

### 3.3.2 Fringe Benefits – Total $327,782

### Benefits for USN/TCN staff are calculated at 23.47% of the employees’ base salary ($44,380). Benefits for CCN Mauritania staff are in accordance with local labor laws and are calculated at 26.92% of the employees’ base salary ($188,856).

### Allowances for USN/TCN staff are calculated at 50% of their total salary ($94,546).

### 3.3.3 Travel – Total $233,828

Local Travel ($5,549)

POA estimates $5,549 in local transportation for trainings at $100/trip for 51 trips over the LOP.

Motorcycle and Vehicle Fuel Expenses ($7,522)

Vehicle fuel for technical leads and motorcycle fuel for 4 motorcycles used by the project’s extension agents under this activity is estimated at $150/month for 46 months.

Per Diem ($220,757)

POA estimates $12,984 in lodging at $43/night and M&IE at $35/day for trainings, for 51 trips over LOP, each trip will be for 3 days. In addition, POA estimates $207,774 in lodging and M&IE for Private Agriculture Service Providers (PASPs) Certification Program participants at $160/week for 50 participants to attend 8 weeks of training in Y2-Y4.

### 3.3.4 Professional Services/Contractual – Total $110,125

### POA will contract a consultant to develop the modules for the PASP Certification Program in Y1 for a total of $20,000. POA will select the consultant based on a competitive bidding process. POA will take into consideration factors such as the soundness of the proposal, unique capabilities of the bidder, the amount of the bid, delivery schedule, technical competency, etc.

### POA will contract a firm to provide security services and conduct risk and security assessments under activity 3 to ensure the well-being of staff and program participants for $35,000 over LOP. Under activity 3, POA anticipates contracting other ad-hoc consultancy and advisory support services to support the PASP course implementation for which POA has budgeted $27,000 over LOP.

### Additionally, POA will contract Abdel Aziz Dahi to serve as a Technical Advisor of Trade Promotion & Strategic Partnership & Investment who is a Mauritanian national with more than 20 years of experience working at the highest levels of the Government of Mauritania ($28,125).

### 3.3.5 Equipment – Total $0

### None.

### 3.3.6 Office – Total $0

### None.

### 3.3.7 Supplies – Total $6,800

POA will procure 4 motorcycles with a unit cost of $1,100 based on local quotes for use by the Extension Agents. The total is $4,400.

POA will procure 4 tablets to assist with rural data collection with a unit cost of $600 based on market rates for use by the Extension Agents. The total is $2,400.

### 3.3.8 Other – Total $426,000

Stipends for Student Internships ($144,000)

POA estimates $90,000 for student internship stipends for domestic internships at $6,000/stipend for 5 stipends per year from Y2-Y4. POA estimates $54,000 for student internship stipends for international internships at $18,000/stipend for 1 stipend per year from Y2-Y4. The internship stipends will help cover travel costs and participants’ time. The amount is based on entry-level salary for extension agents in Mauritania.

POA will implement the following small grant activities:

Small Grant to Increase Women's Cooperatives' Capacity to Function as Agro-dealers ($30,000)

POA will provide 10 grants to women cooperatives in the amount of $3,000 to improve their storage infrastructure and purchase key inputs for business start-ups.

POA will implement the following training activities:

Capacity Building Meetings to Increase Women’s Cooperatives’ Capacity ($44,000)

One capacity building meeting per quarter for 10 cooperatives has been budgeted to support them in functioning as Agribusiness Hubs. The meetings will take place in Y2 and Y3.

Capacity Building Meetings to Increase Existing Agro-dealers Capacity ($12,000)

Two capacity-building meetings per year for 3 cities have been budgeted to enhance the capabilities of promising or innovative early-stage agro-dealers. The meetings will take place in Y2 and Y3.

PASP Certification Program ($36,000)

POA is estimating $1,500 per week for 8 weeks each year for materials and venue costs for the implementation of the PASP Certification Program in Y2-Y4. The PASP certification program cost is based quotes from ISET on a venue rental cost (including A/V equipment) of $250/day x 5 days a week for a total of $1,250, plus an additional $250 for printing and other training materials a week.

Course on Agricultural Mechanization ($100,000)

One course on agriculture mechanization has been budgeted and split into Y1 and Y2. The estimated cost includes trainers, venue, food, materials, and transportation costs. The course will improve technical institutions’ capacity to educate students in agricultural mechanization. The cost for the course on agricultural mechanization was based on an estimated provided from CAT which was the cost for similar courses conducted in the region.

Develop Training Materials to Increase Women’s Cooperatives’ & Existing Agro-dealers Capacity (Printing & Translation) ($15,000)

POA will print and translate training materials into multiple languages to increase women’s cooperatives and existing agro-dealers capacity for a total of $15,000 in Y2.

Advertising to Facilitate Outgrower Models ($7,500)

POA will use advertising to reach farmers and private sector partners to facilitate outgrower models in the tomato and carrot value chains. The estimate is for $2,500 per year in Y2-Y4.

Annual Agriculture Expo Event ($37,500)

Each Expo will last 2 days and host roughly 3,000 attendees. The first Expo will be launched in Y2 and will be fully funded by the project. The second Expo in Y3 will be partly funded by the project as the responsibility is transferred to the National Horticulture Trade Association. Costs include venue rental, materials, booths, per diem, transportation, etc. POA estimated the cost based on prior experience convening similar size events in the different regions we implement. The breakdown of the cost include $10,000/day x 2 days for a total of $20,000 for venue and booth costs which can accommodate 3,000 attendees. POA budgeted an additional, $3,320 for materials, banners, flyers and other printed items, $1,680 for transportation ($30/day x 2 days) and per diem ($40/day x 2 days) for 12 staff to attend the event.

Activity 4: Build Capacity for Post-harvest – Total $3,204013 ($2,604,013 in monetization and $600,000 in cost share.)

### 3.4.1 Salaries/Personnel – Total $890,001

USN/TCN Staff. USN/TCN benefits are budgeted for the Chief of Party (COP) for five years over LOP. The COP will be an expatriate who has worked in Mauritania or other similar operating environments for over 15 years and has the necessary USG background, compliance, and technical expertise. The COP will oversee a team of experts and support staff, prepare reports and work plans, align project initiatives with in-country priorities, and ensure project compliance with federal regulations. The COP’s salary is distributed between Administrative and Activities. To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

CCN Staff. Budgeted at 100% LOE for all five years of the project, the Deputy Chief of Party (DCOP) will be a Mauritanian national with more than 10 years of experience working in Mauritania. The DCOP is responsible for ensuring technical quality in the design and implementation of project activities. Other CCN staff include 3 Technical Leads, Specialists for component 2, 3, and 4, 20 Extension Agents, M&E Director, M&E Specialist, F&A Director, Human Resource Manager, Contracts & Compliance Specialist, Accountant, Administrative Assistant, Security Guards, and 2 Drivers. The CCN staff salary is distributed between Administrative and Activities as appropriate for each role. The majority of CCN staff are budgeted to remain on the project throughout the life of the project, except for the 20 Extension Agents who will complete their work midway through Y3. The proposed salary rates align with market research, and local in-country consultations were conducted by POA. To account for annual salary increases, POA has increased the salary by 4% after Y1 through LOP.

### 3.4.2 Fringe Benefits – Total $327,610

### Benefits for USN/TCN staff are calculated at 23.47% of the employee’s base salary ($44,380). Benefits for CCN Mauritania staff are in accordance with local labor laws and are calculated at 26.92% of the employee’s base salary ($188,685).

### Allowances for USN/TCN staff are calculated at 50% of their total salary ($94,546).

### 3.4.3 Travel – Total $79,877

Local Travel ($44,546)

POA estimates $5,549 in local transportation for trainings at $100/trip for 51 trips over LOP, each trip will be for 3 days. In addition, POA estimates $38,998 for transport costs to international trade shows and events at $1,800 per trip for 4 trips per year over the LOP for a total of 20 trips. The $1,800/trip includes one international roundtrip airfare ($1,600 estimated), plus $200 for local ground transportation.

Motorcycle and Vehicle Fuel Expenses ($5,015)

Vehicle fuel for technical leads and motorcycle fuel for 1 motorcycle used by the project’s extension agent under this activity is estimated at $100/month for 46 months.

Per Diem ($30,316)

POA estimates $12,984 in lodging at $43/night and M&IE at $35/day for trainings, for 51 trips per year of 3 days each. In addition, POA estimates $17,332 in lodging at an average rate of $100/night and M&IE at an average of $60/day for trips to trade shows and events for 4 trips per year of 5 days each that will be held internationally.

### 3.4.4 Professional Services/Contractual – Total $524,275

### POA will contract a consultant to implement a Cold Chain Feasibility Study in Y1 and Y2 for a total of $350,000. POA will select the consultant based on a competitive bidding process. POA will take into consideration factors such as the soundness of the proposal, unique capabilities of the bidder, the amount of the bid, delivery schedule, technical competency, etc.

### POA will contract a firm to provide security services and conduct risk and security assessments under activity 4 to ensure the well-being of staff and program participants for $35,000 over LOP. Under activity 4, POA anticipates contracting other ad-hoc consultancy and advisory support services on  training of processors and agribusinesses in food safety practices, for which POA has budgeted $32,400 over LOP.

### Additionally, POA will contract Abdel Aziz Dahi to serve as a Technical Advisor of Trade Promotion & Strategic Partnership & Investment who is a Mauritanian national with more than 20 years of experience working at the highest levels of the Government of Mauritania ($106,875).

### 3.4.5 Equipment – Total $539,650

### For the equipment below, POA will issue a cash grant for the purchase, and the recipient will be responsible for procuring directly. However, POA plans to put stipulations into the grant mechanism for prior approval by POA before purchase, so there is oversight on these procurements to ensure they are competed competitively. Payment to the grant recipient will be made on a percentage reimbursement basis with the ability to withhold the final payment if the equipment is not available at the end of the project. Final reimbursement payments to the grant recipients will be made at the end of the project.

### 7

### The equipment will be titled under the recipient organization as they will be contributing substantially to the purchase. However, POA will issue grants with conditions on the equipment use, to ensure the equipment is available during LOP. Recipients will be expected to contribute about 50% of the cost, and POA will make this a requirement of the grant to be eligible for funding.

### Post-harvest Processing Equipment and Infrastructure ($150,000)

### POA plans to co-invest in export-scale processing infrastructure with local and foreign investors. The tenders are expected to be released in Y3.

### Co-invest in Small-Scale Processing Infrastructure for Cooperatives ($100,000)

### POA plans to co-invest in small-scale processing infrastructure with promising women’s cooperatives and medium- to large-scale farmers. A total of 10 cooperatives will receive $10,000 during Y2 and Y3.

### Large Scale Cold and Dry Storage Equipment and Infrastructure ($226,150)

### In Y2, POA plans to co-invest in large-scale cold and dry storage equipment and infrastructure with local and foreign investors based on the information gathered in the Cold Chain Feasibility Study.

### Transformation Equipment for Waste Reduction ($63,500)

### In Y3, POA plans to co-invest and provide equipment that will incentivize businesses that convert agricultural waste into biofuels, organic fertilizers, and compost products.

### 3.4.6 Office – Total $0

### None.

### 3.4.7 Supplies – Total $1,700

POA will procure 1 motorcycle with a unit cost of $1,100 based on local quotes for use by the Extension Agent.

POA will procure 1 tablet to assist with rural data collection with a unit cost of $600 based on market rates for use by the Extension Agent.

### 3.4.8 Other – Total $240,900

POA will implement the following small grant activities:

Small Grant to Cooperatives to Increase Small Scale Cold Storage Capacity ($200,000)

POA will provide 10 grants to women cooperatives of $20,000 to support purchasing on-farm cold and dry storage facilities and provide training.

Communications Costs to Release RFP to Co-invest in Export-Scale Processing Infrastructure ($1,000)

POA is estimating $1,000 in Y2 to cover communications costs related to the release of the Request for Proposals (RFP) to co-invest in export-scale processing infrastructure.

Communications Costs to Release RFP to Co-invest in Cold and Dry Storage ($1,000)

POA is estimating $1,000 in Y2 to cover communications costs related to the release of the RFP to co-invest in cold and dry storage.

Communications Costs to Release RFP to Innovative Waste Utilization Businesses ($500)

POA is estimating $500 in Y2 to cover communications costs related to the release of the RFP for innovative waste utilization businesses.

Investment Roundtables ($18,000)

At least one Investment Roundtable has been budgeted per year through the LOP to leverage the production data obtained through GIS/remote sensing to present it to relevant domestic and international private sector actors. Two roundtables will be held in Y3.

Food Safety Training for Farmers and Processors ($10,400)

Two trainings per year have been budgeted for food safety training for farmers and processors, including harvest, packaging, and storage. The trainings will take place in Y2 and Y3.

Event Registration for Trade Shows ($10,000)

POA estimates $500 per event registration to send groups, including agribusiness hubs, large-scale and domestic processors, and commercial farmers, to global food trade shows. POA is budgeting for 4 events per year through the LOP.

### 3.4.9 Cost-Share – Total $600,000

POA is proposing a total of $600,000 in cost share. Overall program value will be bolstered by these cost share contributions. Cost share will be realized in both in-kind and cash contributions. The types of costs that will be documented and counted as cost share will include:

- Venue Space for Investment Roundtables ($1,000): POA estimates venue space at $166.60 per roundtable based on prior experience, for a total of 6 roundtables. To obtain this cost share, POA plans to work with local investors and businesses to offer venue space for these roundtables.

- Cost Share for Post-Harvest Processing Equipment and Infrastructure ($210,000): POA expects to co-invest in export-scale processing infrastructure. The program will look for local and foreign investors to match USDA’s investment with private sector investment.

- Cost Share for Co-invest in Small-Scale Processing Infrastructure for Cooperatives ($50,000): POA will collaborate with promising women’s cooperatives and large-scale farmers to co-invest in small-scale processing infrastructure. POA intends to provide grants to 10 cooperatives. To be eligible for grant funding, cooperatives will be expected to offer co-investment of 50% of their award, equivalent to $5,000 per cooperative.

- Cost Share for Large Scale Cold and Dry Storage Equipment and Infrastructure ($339,000): POA has identified promising Mauritanian private sector partners interested in co-investing in large-scale cold and dry storage facilities.

### 3.5 Indirect Costs – Activities – Total $2,410,555

In accordance with POA’s most recently approved NICRA, indirect costs are 28.28% of direct activity costs. Total Indirect Costs on Activities: $2,410,555.

Total Estimated Costs: $16,007,878 ($14,007,878 in monetization and interest, $1,400,000 in CCC funds, $600,000 in cost share)