BUDGET NARRATIVE

| Program | Food for Progress |
| --- | --- |
| Country | Tunisia |
| Fiscal Year | 2024 |
| Organization | Partners of the Americas, Inc. (UEI: DD5WNYRUYFE5) |
| Point of Contact | Michael Moscarelli, mmoscarelli@partners.net |

I. General Explanatory Comments

Partners of the Americas Inc. (POA) will implement a five-year Food for Progress (FFPr) Program project in Tunisia. The total federal award amount is $24,850,000. This includes commodity ($19,350,000), freight ($4,000,000), and administrative costs (cash portion) ($1,500,000). The total operating budget (grand total costs) for this project is $17,305,226; this includes $305,226 in cost share. POA expects interest on proceeds to be $342,286. The budget narrative describes the operating budget and does not describe the commodity and freight portions of Federal funding.

Gross Monetization Proceeds*	  $15,500,000

CCC Admin Funds	 $1,500,000

Cost Share	$305,226

Total 	   $17,305,226

*including anticipated interest

| Summary of Total Project Operating Budget (Includes Cost Share) |  |
| --- | --- |
| Administration | $4,056,674 |
| Activities | $9,500,812 |
| ICR on Administration | $1,147,228 |
| ICR on Activities | $2,600,512 |
| Total | $17,305,226 |

| Summary of Total Indirect Costs Applied |  |
| --- | --- |
| Total Administration Direct Costs | $4,056,674 |
| Total Activities Direct Costs | $9,195,586 |
| Indirect Costs Applied on Administration 28.28% | $1,147,228 |
| Indirect Costs Applied on Activities 28.28% | $2,600,512 |
| Total Indirect Costs | $3,747,739 |

| Summary of M&E (Monitoring & Evaluation) Budget (Excluding M&E Personnel & Travel) |  |
| --- | --- |
| Evaluations (Baseline, Midterm, & Final) | $500,000 |
| Special Study on Carbon Assessment and Living Incomes | $280,000 |
| Conduct Rapid Complementary Cost-Benefit Analysis | $45,000 |
| Monitoring Guidelines Creation, Translation & Printing | $8,000 |
| Monitoring Guidelines Revision, Translation & Printing | $8,000 |
| Monitoring Guidelines Staff Training on Indicators and Data Collection/Analysis | $30,000 |
| M&E Database Platform Subscription (includes training) | $77,500 |
| Total M&E Budget | $948,500 |
| Total Budget % Dedicated to M&E (Excluding Cost Share) | 5.58% |

POA believes that M&E is a critical component for successful programmatic implementation; therefore, POA has allotted approximately 5.58% ($948,500) of the total budget (excluding cost share) to M&E-related activities. In the field, POA will have a dedicated M&E Director and an M&E Specialist with 100% LOE throughout the 5 years of the project. In addition to these staff, POA will implement a robust system for M&E evaluation, tracking, and reliable data collection. This includes costs for M&E external third-party evaluations, a special study, rapid complementary cost-benefit analysis, M&E guidelines training, license and implementation of M&E software, and M&E data collection site visits. In addition, POA will bring its prior experience in data collection to help train staff. POA will provide its training materials, tools, and other resources to help staff with the M&E aspects of the project. These resources will be offered to the project at no cost to USDA.

Budget Assumptions and Cost Escalations

POA has established a local hire pay scale for Tunisia in accordance with market rates for the level of experience and education required. The salary scale for local hires was established based on comparable organizations and projects, information gathered from in-country consultants, online research, and market analysis for similar positions and experience levels. POA has applied a 7% increase to account for inflation and a 5% increase for merit-based salary increases for all Headquarters (HQ), and Cooperating Country National (CCN) staff after Year 1 (Y1), in accordance with POA policy. Actual annual increases will range between 1%-5% and are based on an annual performance review.

Expenses for travel, supplies, and office expenses include a yearly escalation for inflation after Y1. Inflation is estimated at 7% annually after Y1.

All equipment (over $5,000) purchases will be made under the guidance of POA, unless otherwise indicated. To the extent possible, all equipment will be procured in Tunisia, in accordance with standard procurement practices, to eliminate shipping and handling costs.

Local travel costs for both international and domestic in-country transportation are budgeted based on local prevailing transportation rates. For international and domestic in-country lodging, it is based on market prices, POA’s experience, and are set well below the Department of State (foreign country rates) and General Services Administration (USA rates). Per diem for international (non-US) and domestic in-country travel is based on a reduced rate of the U.S. Department of State per diem thresholds and in accordance with POA policy. Per diem for travel to the US is based on a reduced amount of the GSA per diem thresholds and in accordance with POA policy. International air travel is budgeted based on the prevailing cost of roundtrip economy-class tickets for the proposed routes and will be Fly America Act compliant.

Financial Capacity

POA has established sound financial management and internal control systems, ensuring expenditures are reasonable, allowable, and classified in accordance with generally accepted accounting principles (GAAP). POA uses cloud-based accounting software called Sage Intacct and is subject to an annual Single Audit. The Finance and Administration (F&A) department is staffed with professionals with over 50 years of combined experience in finance and accounting, auditing, and managing financial reporting for federal grants, contracts, and cooperative agreements. The F&A department comprises a Chief Financial Officer (CFO), Controller, Director of Compliance for Grants and Contracts, Budget Analyst, Finance Officer, and two Senior Field Finance Officers. The F&A team works closely with project staff at POA HQ and in-country staff to monitor spending, ensure that all costs are reasonable and allowable, and support project staff to implement the project in accordance with USG rules and regulations (particularly 2 CFR 200), local laws, as well as POA’s internal policies. Our F&A department also reviews spending with project directors monthly and assists with the oversight of contracts, end-of-project reporting, and other aspects of project monitoring.

Cost Application Methodology

POA uses a robust and cost-effective strategy to determine cost allocation in accordance with USG cost principles, local laws, and internal policies. Our proposed budget for this project was developed by conducting thorough price analyses to identify reasonable, realistic, and fair market values for all projected expenses. Our budget estimates were also calculated based on past experience implementing effective and cost-efficient USG-funded programs. POA follows U.S. and local labor laws to determine salary and fringe benefits for all employees identified in this proposal. Indirect Costs have been applied in accordance with POA’s most recent NICRA agreement approved by our cognizant agency, USAID. In preparing the budget, POA has minimized administrative and support costs for managing the project to the extent possible to maximize the funds available for project activities while still ensuring overall award compliance and capacity building for implementing partners. As a result, 55% of the operating budget, including cost share, will be direct towards activities and 45% to administration and indirect costs.

Budget Components and Project Implementation

FFPr Tunisia’s budget allocated to each activity will allow for effective project implementation. POA’s budget uses rigorous evidence and references previous costs of similar projects implemented in Tunisia by donors such as the World Bank, the United Nations International Fund for Agriculture Development, and USAID. In Activity 1, POA will increase the use of climate-smart agriculture and water management by deploying a communications campaign, increasing producer organizations' capacity to spread key information, and leveraging a grants mechanism to support farmers in procuring equipment to make climate-smart adaptations. In Activity 2, POA will increase the productivity of the oasis agriculture system by boosting complementary crop production, creating, and disseminating technical packages for the target geographic regions, building producer organizational capacity, and scaling cold storage and processing enterprises through grants. In Activity 3, POA will increase the use of sustainable oasis agriculture system business models by reducing water costs, increasing the availability of mechanization equipment, creating market linkages for farmers and producer organizations, supporting producer organizations to achieve economies of scale, boosting date processing enterprises, certifying producer and exporters, leveraging the sustainable outgrower business model, and increasing famer and producer groups’ access to finance.

Activity 1 will appropriately fund a climate-smart agriculture communications campaign, producer organization digital extension trainings, and award grants to farmers to make climate-smart agriculture adaptations. Activity 2 will design and disseminate four technical packages for each target region, conduct training with producer organizations and private agriculture service providers, award grants and provide technical assistance to processors and secondary product enterprises, as well as fund cold storage for farmers and producer groups. The budget for these activities will ensure sufficient resources flow toward creating and deploying the technical package, conducting trainings, and processing and cold storage grants and technical assistance. Activity 3 will provide support to farmers to reduce water-related costs through technical assistance and grants, train producer organizations to achieve economies of scale, invest in youth mechanization enterprises, provide grants to women-led date processors, certify farmers and exporters. Activity 3 will increase access to finance by training farmers in key business skills, training financial institutions in measuring risk, and using GIS and remote sensing to measure farmer risk to increase lending through 6th Grain, a proposed subrecipient. The budget will allow for all these activities to be implemented effectively; for example, the grants mechanism will build in technical assistance that farmers will use to contract private agriculture service providers. This will ensure producers receive critical climate-smart technologies and the technical assistance needed to install them.

Cost Effectiveness

POA's budget is organized by activity and apportions costs for implementing the project's three activities. The budget has been developed considering cost-effectiveness to support and achieve the key objectives. The project’s budget components were designed to build long-term human capital and leverage private sector resources. The project is cost-effective, namely because of the demand-based nature of activities and interest from the government and private sector to support and sustain activities. Up-front expenditure on innovative market studies will provide the project with precise information on how to meet the needs of beneficiaries. Studies and information made available through the project will incentivize the private sector to co-invest in activities and ensure the long-term viability of any USDA investment. Funds will be dispersed with precision, deferring to data-driven spending decisions. POA anticipates that funds spent on new linkages will exponentially increase agriculture sector output and two-way trade, creating an excellent return on investment for all stakeholders.

All costs within the budget are deemed reasonable, allocable, and necessary to project implementation for FFPr Tunisia as they directly related to the activities outlined in the Plan of Operations and contribute to achieving the project's components efficiently and effectively. Each cost is justified in terms of its necessity for project success. Prices are based on quotes, research, and POA experience to determine its fair market value. This ensures that resources are utilized responsibly, promoting transparency and accountability in project expenditures.

Anticipated Interest Earned

FFPr Tunisia expects that interest accrued on monetization proceeds will be $342,286 over the life of the project (LOP) based on an investment of the fund in an interest-bearing account with Bank of America. Based on current quotes, the compounding interest rate for a separate interest-bearing savings account with Bank of America is 1.00%.

Management of Monetization Proceeds

Payment will be secured and received from the buyer(s) through an irrevocable Letter of Credit from a bank(s) acceptable to POA. Upon receipt of payment, the funds will be deposited into a separate U.S.-based interest-bearing U.S. dollar account under the supervision of POA’s CFO, who will be responsible for the disbursement of funds once approval has been received from the Senior Program Director for FFPr Tunisia through a request for funding form. Funds from the monetization proceeds will only be disbursed when an immediate cash need for project activities and prior approval from the Senior Program Director for FFPr Tunisia is obtained and review is conducted by POA’s CFO. POA’s CFO and Controller oversee core functions related to award administration, accounting, internal controls, and financial reporting, with additional compliance support from the Grants and Contract Compliance Unit. The Grants and Compliance Unit will conduct periodic compliance spot checks and annual internal audits with POA and contractors. Annually POA undergoes a formal external audit, in which all bank accounts and release of funds are tested.

II. Administration

Total Administration Costs: $5,203,902 ($3,703,902 in monetization, $1,500,000 in CCC funds, $0 in cost share)

- Total Direct Costs: $4,056,674 ($2,887,357 in monetization, $1,169,317 in CCC funds)

- Total Indirect Costs: $1,147,227 ($816,545 in monetization, $330,683 in CCC funds)

2.1 Salaries/Personnel - Total $1,097,668 ($520,668 monetization, and $577,000 CCC funds)

USN/TCN Staff. None.

CCN Staff. Budgeted at 100% LOE for all five years of the project, the Chief of Party (COP) will be a Tunisian national with more than 20 years of experience in international development, strategic consulting, and entrepreneurship. The COP will oversee a team of experts and support staff, prepare reports and work plans, align project initiatives with in-country priorities, and ensure project compliance with federal regulations. Other CCN staff include Technical Director, 3 Component Technical Leads, 3 Component Technical Specialists, 2 Capacity Building Specialists, Sociocultural & Gender Specialist, 3 Sociocultural & Gender Officers, Communications Specialist, M&E Director, M&E Specialist, Finance Director, Contracts & Compliance Specialist, 2 Grants & Procurement Officers, Accountant, Administrative Office Human Resources Manager, and 3 Drivers. The CCN staff salary is distributed between Administrative and Activities as appropriate for each role. POA proposes the Chief of Party, Technical Director, and Finance Director as key personnel positions. The proposed salary rates align with market research, benchmarking analysis, and local in-country consultations that were conducted by POA. To account for annual salary increases, POA has increased the salary by 5% after Y1 through LOP.

As key personnel, POA is proposing Ms. Rym Ayari with a monthly salary of $13,000. POA aimed to recruit a Tunisian national because local candidates have the connections that are critical to be successful in Tunisia and for the USDA project. While for a local national the salary is high, POA did its due diligence to verify experience and prior salary and compensation history to determine a reasonable salary. Ms. Ayari had previously worked with other USG projects, including serving as Deputy Chief of Party and Senior Advisors. Additionally, her salary falls within POA standard salary scale for COPs. Ms. Ayari’s boasts two decades of international development experience and has the local technical knowledge and connections for successful implementation of the project.

Headquarters (HQ) Staff. POA HQ salary rates are based on the current annual salaries of staff, POA’s salary matrix, and industry benchmarking surveys. The POA HQ team will be led by the Senior Program Director of Agriculture & Food Security, who oversees the HQ team in the project’s interventions, providing compliance and technical support. The HQ Associate Director will serve as the primary day-to-day support to the field team and assists with achieving programmatic, financial, and administrative compliance. They will be supported by the HQ Monitoring, Evaluation, Research, and Learning (MERL) Senior Director and HQ Compliance Team. The HQ MERL Senior Director and the HQ Compliance Team are not listed in the budget, as these positions are funded by POA’s indirect costs, therefore, no direct costs for these positions are included. To account for annual salary increases, POA has increased the salary by 5% after Y1 through LOP.

2.2 Fringe Benefits – Total $357,015 ($112,887 in monetization, and $244,128 in CCC funds)

### Fringe Benefits CCN Tunisia

Fringe benefits for CCN staff are budgeted at 45.50% of their total salary and are based on local labor law, in-country required benefits, and POA’s fringe benefit policy. This includes:

- 16.57% - Social Security (National Social Security Fund (CNSS))

- 0.5% - Work Insurance

- 1.0% - Housing Levy

- 2.0% - Development Levy

- 8.33% - 13th Month

- 8.33% - Severance (1 month per year of service)

- 1% - Life Insurance

- 5.77% - Annual leave 15 days (1.25 days per month of service)

- 2% - Private Medical Insurance

POA has consulted with a local Tunisian payroll advisor, and the following benefits are the minimum benefits required by law in Tunisia to be withheld from payroll: Social Security (CNSS), Work Insurance, Housing Levy, and the Development Levy. These benefits are withheld by POA, then remitted to the appropriate tax authorities.

Total CCN Fringe Administrative Benefits = $205,282.

Fringe Benefits – HQ

POA charges fringe benefit costs in accordance with POA’s personnel policy and its NICRA letter. POA has charged a 23.47% fringe rate on HQ salaries. Fringe benefits include insurance, mandatory taxes, pension, and other employee benefits. Total Headquarters Administrative Fringe Benefits is $151,733.

2.3 Travel – Total $318,660 ($297,871 in monetization and $20,789 in CCC funds)

International Travel ($72,459)

POA HQ staff will make 25 international trips from Washington, DC to Tunisia during the period of performance. The purpose of the trips will be to provide monitoring, oversight, and technical guidance. The total HQ staff international travel cost (airfare) estimate is $40,255. Flight costs are based on current quotes for economy airfare and compliant with the Fly America Act.

Tunisia staff will make 20 international trips during the period of performance. The purpose of the trips will be to hold meetings, attend technical training, and attend conferences. The Chief of Party and the Technical Director will each make at least 5 international trips to HQ in Washington, DC. The total Tunisia staff international travel cost (airfare) estimate is $32,204. Flight costs are based on current quotes for economy airfare and compliant with the Fly America Act.

Local Travel ($28,466)

POA estimates $7,763 in ground transportation for 45 trips based on a rate of $150/trip for HQ and Tunisia staff international travel. The purpose of the trips will be for program oversight, to attend trainings and meetings/events, as well as perform M&E and data collection. The rate is based on prior program experience and represents a reasonable local rate in Tunisia and Washington, DC.

POA estimates $20,703 in local transportation for Tunisia staff to make 3 domestic trips per month at $100/per trip. Local transportation includes car rental and taxis. There is a total of 180 trips over LOP. The purpose of the trips will be for program oversight, to attend trainings and meetings/events, as well as perform M&E and data collection. Rates are based on POA’s travel policy, historical program experience, and represent a reasonable local rate in Tunisia.

Vehicle Fuel ($25,234)

POA estimates the administrative cost for vehicle fuel expense for 3 vehicles to be $450/month. The total vehicle fuel cost estimate for 48 months is $25,234. This is based on POA’s historical experience implementing similar projects in the region.

Per Diem & Lodging ($192,500)

International Travel – HQ Staff: POA estimates $42,670 in lodging, and meals & incidental expenses (M&IE). POA estimates lodging and M&IE at $212/day ($92 for M&IE and $120 for lodging) for 25 trips of 7 days each. Per diem is based on a reduced percentage of Department of State Office of Allowances rates for Tunisia and POA’s travel policy. Lodging is based on market prices for hotels in Tunisia, and will not exceed the maximum cap listed by Department of State Office of Allowances in Tunisia for lodging. POA also estimates $1,438 in other travel related costs (baggage, visa, insurance, etc.), estimated at $50/trip for 25 trips. The purpose of trips will be for monitoring, oversight, and technical guidance.

International Travel – Tunisia Staff: POA estimates $40,416 in lodging and M&IE. POA estimates lodging and M&IE at $251/day ($71 for M&IE and $180 for lodging) for 20 trips of 7 days each. Per diem is based on current a reduced percentage of GSA rates for Washington, DC and POA’s travel policy. Lodging is based on market prices for hotels in Washington, DC, and will not exceed the maximum cap listed by GSA in Washington, DC for lodging. POA also estimates $1,150 in other travel-related costs (baggage, visa, insurance etc.), estimated at $50/trip for 20 trips. The purpose of the trips will be for program oversight, to attend trainings and meetings/events.

Local Travel – Tunisia Staff: POA estimates $106,826 in lodging and M&IE, estimated at $129/day ($44 for M&IE and $85 for lodging) for 4 day long trips. Tunisia staff will make 3 domestic trips per month for a total of 180 days over LOP. Per diem is based on current a reduced percentage of State Department rates for Tunisia and POA’s travel policy. Lodging is based on market prices for hotels in Tunisia, and will not exceed the maximum cap listed by Department of State Office of Allowances in Tunisia for lodging. The purpose of the trips will be for program oversight and to perform M&E and data collection.

2.4 Professional Services/Contractual – Total $1,509,134 ($1,215,334 in monetization, and $293,800 in CCC funds)

Professional Services

Monetization Agent Fee ($253,134)

The Monetization Agent fee is estimated at 1.67% of monetization proceeds received for $253,134.

Monetization Impact Assessment ($60,000)

POA estimates $60,000 for a monetization impact assessment to evaluate the market impact of the monetization.

Support Services ($247,500)

POA has included expenses related to support services over the life of the program. These costs are directly attributable to the project and include local program audit costs ($7,500); legal services & registration fees ($22,500); security services, risk assessments, and security assessments ($2,500); short-term technical advisors (STTA) to support on tasks such as reviews of technical packages, training of staff, and development of training modules ($189,000), and a start-up consultant ($26,000). The rate for the STTA is based on a daily rate of $350 and an average of 10 days a month. Given their technical expertise, these will be highly qualified consultants with 5+ years of specialized experience on the technical topics. The rate is in line with market rates for these types of consultants based either in the U.S. or other international locations and is consistent with prior rates paid for similar consultant, with the specialized experience required by the deliverable.

Evaluations

Evaluations ($500,000)

POA estimates external evaluation fees for the Baseline, Midterm, and Final Evaluations to be $150,000, $170,000, and $180,000, respectively. POA will host an open procurement to select an external evaluator for the evaluations. POA will consider factors such as the soundness of the proposal, unique capabilities, cost, schedule, technical competency, and experience in Tunisia.

Special Studies ($280,000)

POA proposes two special studies: 1) Carbon and Biodiversity Study and 2) Living Income Study, which will occur in Y2 and Y3. In the first study, POA will measure ecosystem services produced by the three-floor oasis agroforestry system. POA will select farms to measure changes in soil organic carbon and key biodiversity indicators like bird and insect populations. For the second study, POA will aim to assess households’ ability to increase income in absolute terms, generate greater resilience to economic and environmental shocks, and position the household for economic ascension. Both studies will cost $140,000, totaling $280,000. POA will conduct a competitive bidding process to select the contractors. POA will consider factors such as the soundness of the proposal, unique capabilities, cost, schedule, technical competency, and experience in Tunisia.

### Conduct Rapid Complementary Cost-Benefit Analysis ($45,000)

### In Y1, POA will conduct a Rapid Complementary Crop Cost-Benefit Analysis to validate the preliminary cost-benefit analysis conducted during the proposal process, a Gender and Equity Assessment will also be included in this contract. Contractors will be selected based on a competitive bidding process. The cost includes translation into multiple languages. POA estimates the cost to be $45,000 based on provider quotes.

Monitoring Guidelines Development ($46,000)

### POA will develop M&E guidelines, including the cost of creating, translating, and printing at a one-time rate of $8,000. As part of its adapting and learning process, POA also estimates $8,000 for any revisions to the guidelines, including translation and additional printing needed over LOP. Once the Monitoring Guidelines have been developed, POA will provide training to all staff on indicators and data collection/analysis, including ongoing training for existing and updated guidelines, for a total of $30,000.

M&E Database ($77,500)

### POA is budgeting for a cloud based M&E database/platform subscription fee, including training, to accurately track project data and M&E across regions and activities. The total M&E database and training cost is $77,500.

2.5 Equipment – Total $180,000 ($180,000 in monetization and $0 in CCC funds)
POA plans to purchase three 4x4 specialized vehicles ready for the deserts and rural areas. Based on local quotes, POA estimates the cost at $60,000/vehicle, including customs, taxes, and import fees, for a total of $180,000 for 3 vehicles. POA will follow USDA procurement guidelines and sourcing requirements. POA conducted a buy vs. lease analysis and found it more cost-effective to purchase vehicles given the frequent travel for data collection, trainings, and site visits to locations 6+ hours from the capital city.

2.6 Office – Total $450,776 ($438,776 in monetization and $12,000 in CCC funds)

POA estimates the cost of its main in-country office in Tunis and a satellite office in Tozeur to be $450,776; the costs include communications costs (internet, phone, data); office rent, utilities, and cleaning; banking and cash handling fees; courier fees/services and postage; recruitment/procurement advertising; meeting expenses; payroll processing and local accounting books preparation; and licenses and subscriptions for program management. In Tunis POA is estimating the cost for rent (includes furniture), utilities, and cleaning all in one as the space that will be rented will be a private office space in a coworking building. As such, all these costs are bundled into the rental price. In Tozeur, POA will rent a space in an office building and will need to furnish it. Meeting expenses include room rental space, and A/V equipment rental for small meeting rooms, that would be rented by the hour. Average hourly estimate for these rental spaces is $10/hour, and POA estimates using these spaces on average 25 hours a month. Estimated rates are based on POA’s historical program experience and current market rates locally in Tunisia.

2.7 Supplies – Total $82,692 ($64,092 in monetization and $18,600 in CCC funds)

Appliances ($67,173)

POA plans to purchase 26 desktop/laptop computers for HQ and CCN staff; 26 phones for CCN staff; 2 all-in-one printers, a photocopier, and a scanner; 4 tablets; 2 projectors and video conferencing equipment; and office furniture for the Tozuer office (costs not included for Tunis office as POA is planning to rent a private coworking space), including desks, chairs, tables, shelves, filing cabinets, safes, and A/C units. Estimated costs are $67,173. Estimated costs are based on market prices in Tunisia.

Office Supplies ($15,519)

The budgeted monthly office supply costs are estimated at $250. The costs cover all necessary office supplies such as notebooks, pens, calculators, office bags, clip files, registers, photocopy paper, flip chart paper, markers, transparency paper, flip chart boards, etc. POA estimates are based on past experience with projects of similar size and market research.

2.8 Other – Total $60,729 ($57,729 in monetization and $3,000 in CCC funds)

Training ($45,000)

POA plans for $9,000 yearly in training, workshop, conference, and registration fees per year for LOP. The price is based on a registration or training fee of $1,500/event or training and 6 trainings/events per year. The costs will cover trainings, workshops, and/or courses on USG Rules and Regulations, program management, and technical conference and registration fees as necessary for the successful implementation of the project. The total for training is $45,000.

Maintenance ($10,697)

POA estimates equipment and office repairs and maintenance ($2,875), and vehicle maintenance ($7,822) to be a total of $10,697 over LOP.

Insurance ($5,032)

POA estimates property and liability insurance ($2,875), and vehicle insurance ($2,157) to be a total of $5,032.

2.9 Indirect Costs – Administration – Total $1,147,228 ($816,545 for monetization and

$330,683 for CCC)

In accordance with POA’s most recently approved NICRA, indirect costs are estimated at $1,114,986.

III. Activities

- Total $12,101,324 ($11,796,098 in monetization funds and $305,226 in cost share)

- Total Direct Costs: $9,500,812 ($9,195,586 in monetization funds and $305,226 in cost share)

- Total Indirect Costs: $2,600,512 ($2,600,512 in monetization funds)

Activity 1: Increase Use of Climate Smart Agriculture and Water Management

– Total $3,957,401 ($3,860,925 in monetization funds and $96,476 in cost share)

### 3.1.1 Salaries/Personnel – $1,034,484

USN/TCN Staff. None.

CCN Staff. Budgeted at 100% LOE for all five years of the project, the Chief of Party (COP) will be a Tunisian national with more than 20 years of experience in international development, strategic consulting, and entrepreneurship. The COP will oversee a team of experts and support staff, prepare reports and work plans, align project initiatives with in-country priorities, and ensure project compliance with federal regulations. Other CCN staff include Technical Director, 3 Component Technical Leads, 3 Component Technical Specialists, 2 Capacity Building Specialists, Sociocultural & Gender Specialist, 3 Sociocultural & Gender Officers, Communications Specialist, M&E Director, M&E Specialist, Finance Director, Contracts & Compliance Specialist, 2 Grants & Procurement Officers, Accountant, Administrative Office Human Resources Manager, and 3 Drivers. The CCN staff salary is distributed between Administrative and Activities as appropriate for each role. POA proposes the Chief of Party, Technical Director, and Finance Director as key personnel positions. The proposed salary rates align with market research, benchmarking analysis, and local in-country consultations that were conducted by POA. To account for annual salary increases, POA has increased the salary by 5% after Y1 through LOP.

### 3.1.2 Fringe Benefits – Total $470,690

CCN Tunisia staff benefits are per POA’s fringe benefit policy and local labor laws and are calculated at 45.50% of the employee’s base salary ($470,690). See Section 2.2 for details regarding benefit rates.

### 3.1.3 Travel – Total $61,846

Local Travel ($32,678)

POA is estimating $50/month for local transportation related to activity 1 for a total of $2,804. This includes taxis or car rental for a day. This fund will be utilized if all project vehicles are already in use, and additional vehicle for the day’s activities are required. POA is budgeting for transportation for staff to assist in the development of communications materials and is estimated at a cost of $300/trip with 3 trips in each Y1 and Y2 with a total cost of $1,836 for 6 trips. POA has allotted $5,701 for transportation of staff to attend local agricultural events at an estimated cost of $200/trip with 6 trips per year (3 staff for 2 events) in Y2-Y5. POA has allocated $886 for the local transportation for the leaders of Northern Tunisian Cooperatives to attend training sessions at an estimated cost of $200/trip with 2 trips per year in Y2 and Y3. Additionally, to make trainings more accessible, POA will provide transportation stipends of $10/participant to attend Farmer Field School for a total of $21,425. Partners estimates a total of 2,000 participants attending from Y1-Y3. All costs are based on market research and experience on similar programs. Stipend rates are based on the expected distance participants will travel.

Vehicle Fuel ($14,019)

POA estimates fuel for project vehicles at $250/month for a total of $14,019 for 48 months over LOP. The transport will be for implementation of Activity 1. The rate is based on POA’s historical experience implementing similar projects in the region.

Per Diem & Lodging ($15,149)

POA estimates $2,403 in lodging and M&IE for development of communications materials, estimated at $129/day for 18 days in Y1 and Y2, with 9 days per each year. POA estimates a cost of $11,031 in lodging and M&IE for staff attending local agricultural events at an estimated cost of $129/day and 3 days per trip, for 6 trips each year in Y2-Y5, for a total of 72 days over LOP. POA estimates $1,714 in lodging and M&IE for 4 staff leaders of Northern Tunisian Cooperatives to attend training sessions, estimated at $129/day and 3 days per trip, for 2 trips each year in Y2 and Y3, for a total of 12 days over LOP.

### 3.1.4 Professional Services/Contractual – Total $286,900

### Contract for Development of Materials for Communications Campaign (includes budget for videos, social media reels, etc.) ($100,000)

### POA will hire a communications consultant to support a campaign to showcase cost-effective practices and technologies and drive the adoption of climate-smart agricultural innovations and technologies that enhance water management, reduce soil salinity, and improve soil health. POA will partner with producers and producer organizations to craft the communications campaign and ensure the content aligns with their interests and needs. The contractor will produce high quality videos, social media content and reels, and other key tools for dissemination. The cost is estimated at $50,000/per 6 months with a full year’s final cost of $100,000 split evenly between Y1-Y2. Contractors will be selected based on a competitive bidding process.

### Contract for Communications Campaign Dissemination ($100,000)

### POA will establish a contract to facilitate the distribution of paid ads and short videos on media outlets commonly used by farmers, such as Facebook, Radio, and YouTube in Y2-Y5. The cost is estimated at $25,000/year with four years covered between Y2-Y5 for a final cost of $100,000. Contractors will be selected based on a competitive bidding process.

### Contract for Private Agriculture Service Providers (PASPs) to Manage Model Farms and Training for Farmer Field Days ($22,400)

### Approximately 2,000 participants will attend farmer-field schools between Y1-Y3. For these trainings, POA will intentionally target young, female, and minority farmers to attend farmer field schools. Private Agriculture Service Providers (PASPs) will be contracted to manage model farms and conduct farmer field days alongside FFPr technical staff. The cost of training has been estimated at $700/day with 8 days of training in Y1, 16 days of training in Y2, and 8 days of training in Y3 for a final cost is estimate of $22,400 over LOP. The cost is based on PASPs provider quotes. Contractors will be selected based on a competitive bidding process.

### Consultant for Producer Organization Capacity Building ($27,000)

### POA will hire a consultant to assist FFPr Tunisia to increase select producer groups  organizational capacity and their member’s use of climate-smart agriculture. The consultant will develop training modules for training producer organizations on using Information and Communications tools. Consultant will be selected based on a competitive bidding process. The estimated cost of this is $4,500/month with 3 months of consultation services in both Y2 and Y3 for a final cost of $27,000.

### Consultant (Financial & Legal) to Advise on Grant Mechanism and Blended Finance Structure ($12,500)

### In Y1, POA will design the FFPr Tunisia grants mechanism. POA will hire a consultant to help with the grant mechanism's financial and legal aspects. The cost of this has been estimated based on provider quotes at $625/day with 20 days of consultation services allotted for Y1. The final cost is $12,500.

### Security Services, Risk Assessments, & Security Assessment ($25,000)

### POA will contract a firm to provide security services and conduct risk and security assessments under activity 1 to ensure the well-being of staff and program participants at $5,000/year for the LOP for a total cost of $25,000.

### 3.1.5 Equipment – Total $0

### None.

### 3.1.6 Office – Total $0

### None.

### 3.1.7 Supplies – Total $34,000

Inputs for Model Farms (Demonstration Plots) Set-up and Maintenance ($32,000)

POA is budgeting for model farms to demonstrate climate-smart agriculture to increase producer adoption of techniques, innovations, and technologies in each of the four project governorates in Y1-Y2. Based on prior experience setting us demonstration plots, POA estimates $8,000/plot for each of the 4 plots, totaling $32,000 over LOP. Please see plot breakdown below.

Table 1 Demonstration Plot Cost Breakdown*

| Demonstration Plot Item | Cost |
| --- | --- |
| Bubbler Irrigation Equipment | $4,000 |
| Solar Panels | $1,500 |
| Improved Date Varieties | $300 |
| Small tools | $300 |
| Two-wheel Tractor | $1,000 |
| Labor | $900 |
| Total | $8,000 |

*Items reflect a percentage of the overall cost and account for co-investment as well as some demonstration plot owners already possessing some of the necessary inputs.

Communication Costs for Publication of RFPs/RFAs ($2,000)

POA is estimating $500/publication in Y1-Y4 to cover communications costs related to the release of the Request for Proposals (RFP)/Request for Applications (RFA) for the grants mechanism supplies procurement and other procurements for activity 1, for a total of $2,000.

### 3.1.8 Other – Total $1,973,005

Climate Smart Agriculture Adaptations Grants ($1,899,525)

In Y2-Y4, POA will utilize its grants mechanism to distribute approximately 1,333 grants at an average of $1,425 per farmer. This will allow farmers to purchase water-saving bubbler irrigation systems and other needed climate smart supplies. The cost has been estimated based on the market value to set up the systems. The total cost is $1,899,525 over LOP for the 1,333 grants.

Table 2 Cost Breakdown of Climate-Smart Agriculture Adaptations Grants*

| Item | Cost |
| --- | --- |
| Bubbler irrigation | $800 |
| Pumps | $625 |
| Total | $1,425 |

*The costs of items reflect a portion of the cost. The grantee will be required to cover the additional 5% of costs.

POA will implement the following training activities:

Farmer Field School Trainings (Materials, Food, & Refreshment) ($28,800)

The climate-smart agriculture grant mechanism will support the producer groups selected to host model farms to hold Farmer Field Schools. POA will provide all necessary materials, food, and refreshments for the attendees of these trainings at a cost of $900/day for an estimated 63 participants and 2 staff ($10/person for food plus $250 for materials). POA will train traditional farmers and find opportunities to target young, female, and minority farmers to attend the trainings. There will be 8 days of training in Y1 and Y3, and 16 days of training in Y2. The total cost for 32 days of training is $28,800.

Trainings for Producer Organizations to Boost Climate Smart Agriculture Adoption - 3 Days ($7,560)

POA will hold three-day long training sessions for 15 high functioning Tunisian producer organizations to increase their ability to leverage SMS messaging and WhatsApp groups to conduct digital extension. Trainings are budgeted at $1,890/training for 30 participants and 3 staff ($10/person for food plus $300 for materials times 3 days). There will be two trainings each year in Y2 and Y3. The total for 4 trainings is $7,560.

Workshop with Stakeholders on Grants Mechanism ($2,120)

In Y1, POA will design the project’s grants mechanism. To ensure best practices are followed, POA will hold two workshops with key partners, including public and private banks, the World Bank, and the National Union of Farmers (UTAP). The workshops are budgeted at $1,060/workshop for a total cost of $2,120.

POA will implement the following event activities:

### Registration for Agricultural Events and Booths ($20,000)

### POA will capitalize on existing agriculture events in Tunisia to improve awareness and adoption of general climate-smart agriculture practices, such as the International Agricultural Investment and Technology Fair, the Mediterranean Fair for Agriculture and Food Industries, and other agricultural events. POA will use the events to promote critical date and oasis agriculture adaptations, project grants, and sustainable business models. POA estimates a cost of $2,500/event with 2 events yearly from Y2-Y5. The final cost is estimated at $20,000.

### Printing Materials to Distribute at Local Agriculture Events ($15,000)

### POA is estimating a one-time cost of $15,000 in Y2 to print materials to be distributed at the International Agricultural Investment and Technology Fair, the Mediterranean Fair for Agriculture and Food Industries, and other agricultural events. Cost is based on estimates from similar size programs.

### 3.1.9 Cost-Share – Total $96,476

### Cost Share for Climate Smart Agriculture Adaptations Grants ($94,976)

### POA expects co-investment under for the grants to acquire the necessary supplies, tools, and technology for Climate Smart Adaption which is estimated at $71/farmer (approximately 5% of total grant cost) for the 1,333 grants. The co-investment will be a condition written into the formal grant agreement as cost share. The total estimated cost share is $94,976.

### Donated Materials and Time from APIA for Events ($1,250)

### As cost share, POA estimates material and time donations from the Agency for the Promotion of Agricultural Investments (APIA) to assist in FFPr events. POA estimates $250/event with 1 event each year from Y1-Y5 for a total cost share of $1,250. Based on an average salary daily of $100 (assuming monthly salary of $2,000 and 20 working days a month), POA estimates that APIA staff will contribute 2 days a staff time to the events, in addition to $50 worth of materials (flyers, banner, and informational tools).

### Venue Space for Grant Mechanism Design Meeting ($250)

### As cost share, POA will acquire a venue space to hold meetings to discuss Grant Mechanism Design. Estimated cost is $125/day with 2 meetings in Y1 held for a total cost share of $250.

Activity 2: Increase Productivity of the Oasis Agricultural System – Total $2,560,689 ($2,395,689 in monetization and $165,000 in cost share)

### 3.2.1 Salaries/Personnel – Total $1,040,637

USN/TCN Staff. None.

CCN Staff. Budgeted at 100% LOE for all five years of the project, the Chief of Party (COP) will be a Tunisian national with more than 20 years of experience in international development, strategic consulting, and entrepreneurship. The COP will oversee a team of experts and support staff, prepare reports and work plans, align project initiatives with in-country priorities, and ensure project compliance with federal regulations. Other CCN staff include Technical Director, Component Technical Lead, Component Technical Specialists, 2 Capacity Building Specialists, Sociocultural & Gender Specialist, 3 Sociocultural & Gender Officers, Communications Specialist, M&E Director, M&E Specialist, Finance Director, Contracts & Compliance Specialist, 2 Grants & Procurement Officers, Accountant, Administrative Officer, Human Resources Manager, and 3 Drivers. The CCN staff salary is distributed between Administrative and Activities as appropriate for each role. POA proposes the Chief of Party, Technical Director, and Finance Director as key personnel positions. The proposed salary rates align with market research, benchmarking analysis, and local in-country consultations that were conducted by POA. To account for annual salary increases, POA has increased the salary by 5% after Y1 through LOP.

### 3.2.2 Fringe Benefits – Total $473,490

CCN Tunisia staff benefits are per POA’s fringe benefit policy and local labor laws and are calculated at 45.50% of the employee’s base salary ($473,490). See Section 2.2 for details regarding benefit rates.

### 3.2.3 Travel – Total $13,232

Local Travel ($4,787)

POA is estimating $50/month for local transportation related to activity 2 for a total of $2,804. This includes taxis or car rental for a day. This fund will be utilized if all project vehicles are already in use, and additional vehicle for the day’s activities are required. POA estimates $100/trip for local transport for 3 staff in Y1 to attend the stakeholder workshops for a total of $300. For the technical package design POA estimates an additional 2 trips for each of the 4 regions of implementation in Y1 at a rate of $100/trip. The total for these 8 trips is $800. In addition, to make trainings accessible, POA will provide $7/participant for transportation stipends for producer organization leaders to attend PASPs trainings. Stipends are budgeted for 110 participants to attend trainings from Y2-Y4, and LOP total of $883. Stipend rates are based on the expected distance participants will travel.

Vehicle Fuel ($5,608)

POA estimates fuel for project vehicles at $100/month for a total of $5,608 for 48 months over LOP. The transport will be for implementation of Activity 2. The rate is based on POA’s historical experience implementing similar projects in the region.

Per Diem ($2,838)

POA estimates $774 in lodging and M&IE for stakeholder workshops, estimated at $129/day for 6 days over LOP. POA estimates a cost of $2,064 in lodging and M&IE for staff travel to each of the 4 regions for development of the technical package design at an estimated cost of $129/day and 2 days per trip, for 8 trips in Y1, for a total of 16 days over LOP.

### 3.2.4 Professional Services/Contractual – Total $404,200

### Contract for Private Agriculture Service Providers (PASPs) to Train on Technical Assistance Business Models ($250,000)

### In Y1, POA will contract Private Agriculture Service Providers (PASPs) for each of the 4 regions at $25,000/region to train on technical assistance business models in Y1. POA will continue the trainings and provide refreshers on the topics in Y2-Y4. For these refresher trainings, POA estimates $12,500/region, since half the number of trainings will be provided compared to Y1. Consultants and contractors will be selected based on a competitive bidding process. POA estimates the cost to be $250,000 over LOP based on provider quotes.

### Contract for Private Agriculture Service Providers (PASPs) to Support Capacity-Building Efforts for Producer Organizations ($4,200)

### POA will contract PASPs to conduct to support capacity-building efforts for producer organizations. The PASPs will aim to train 55 producer organization leaders by holding 1 day trainings in each of the 4 regions in Y2-Y4. Consultants and contractors will be selected based on a competitive bidding process. POA estimates $350/day for the trainings, and a total cost of $4,200 over LOP, based on provider quotes.

### Contract for Women-Led Enterprise Development Technical Assistance ($125,000)

### POA will identify 25 women-led processing enterprises (targeting youth and minority women as possible) to accelerate product competitiveness through one-on-one technical assistance with small businesses in Y2 and Y3. Capacity building will focus on packaging and labeling, market linkages, and access to finance. Based on experience, POA estimates technical assistance at $5,000/enterprise, for a LOP total of $125,000.

### Security Services, Risk Assessments, & Security Assessment ($25,000)

### POA will contract a firm to provide security services and conduct risk and security assessments under activity 2 to ensure the well-being of staff and program participants at $5,000/year for the LOP for a total cost of $25,000.

### 3.2.5 Equipment – Total $0

### None.

### 3.2.6 Office – Total $0

### None.

### 3.2.7 Supplies – Total $2,500

### Communication Costs for Publication of RFPs/RFAs ($2,500)

POA estimates $500/publication in Y1-Y3 to cover communications costs related to the release of the RFPs/RFAs for the grants and other procurements for activity 2, for a total of $2,500.

### 3.2.8 Other – Total $461,630

POA will implement the following training activities:

### Workshop with Stakeholders on Complementary Crop Feedback (Venue, Materials, Food, & Refreshments) ($850)

POA is planning a workshop with stakeholders on complementary crop feedback. POA estimates $850 for 35 participants ($10/participants plus $500 for venue & materials).

### Development of Technical Package (Technical Review, Printing, & Translation) ($20,000)

POA is costing in Y1 for technical review, printing, and translation of technical package. Based on prior experience, POA estimates $5,000/package for 4 regions for a total of $20,000.

### Train PASPs in Cost-Efficient Date and Complementary Oasis Production (Venue, Materials, Food, & Refreshments) ($1,460)

In Y1, POA will hold two events to train approximately 90 total service providers in the project’s technical packages to promote cost-efficient date and non-date complementary crop production. POA estimates $730/training for 25 participants and 3 staff ($10/participants plus $450 for venue & materials) for food & refreshments, materials, and venue space, with an LOP total of $1,460.

PASPs Trainings to Support Capacity-Building Efforts for Producer Organizations (Materials, Food, & Refreshments) ($3,960)

POA will hold day long training sessions for each of the 4 regions in Y2-Y4 to build capacity of providers organizations through PASPs trainers. The trainings are budgeted at $330/training for 15 participants and 3 staff ($10/person for food plus $150 for materials). There will be 4 trainings each year in Y2-Y4. The total for 12 trainings is $3,960.

Training on Best Practices with US Grains Council for Alfalfa Processers (Materials, Food, & Refreshments) ($760)

In Y2, POA will hold two trainings in collaboration with the US Grains Council on best practices for alfalfa processers. The trainings are budgeted at $330/training for 11 participants and 2 staff ($10/person for food plus $250 for materials). The total for 2 trainings is $760.

Meeting Expenses with Producer Organizations and Stakeholders ($2,100)

POA is budgeting for meeting expenses with producer organizations to cover refreshments, venue space, and materials, as necessary. Based on prior experience, POA estimates $75/meeting for 28 meetings over LOP and a total of $2,100.

POA will implement the following grant activities:

### Cold Storage Grants ($225,000)

FFPr Tunisia will invest in cold storage with producer organizations and private enterprises that can match at least 42.3% of the overall costs. POA will award 60 grants of $3,750 for cold and dry storage grants in Y2 for a total of $225,000. POA may increase or decrease funding levels of each grant or the number of grants based on proposals submitted. These estimates are the approximate value for each award.

### Grants for Alfalfa Processers ($20,000)

POA will support existing alfalfa silage and pellet processors in the South to scale production. In Y2, POA will award 4 grants of $5,000 for existing and new alfalfa processors to be supported with key equipment to unlock their productivity. The total of the 4 grants is $20,000. POA may increase or decrease funding levels of each grant or the number of grants based on proposals submitted. These estimates are the approximate value for each award.

### Women-Led Enterprise Development Grants ($187,500)

POA will collaborate with gender-focused local organizations that work in the south in Y2-Y3 to award 25 grants of $7,500 for women-led processing enterprises. The grants will support women-led companies that produce date syrup, sugar, and handicrafts and work in tourism with the goal of increasing their productivity. The total of the 25 grants is $187,500. POA may increase or decrease funding levels of each grant or the number of grants based on proposals submitted. These estimates are the approximate value for each award.

3.2.9 Cost Share – Total $165,000

Cost Share for Co-Investment of Cold Storage Grants ($165,000)

POA proposes a cost share obligation of $165,000 in the co-investment of cold storage grants. POA estimates that each grantee will co-invest and provide a minimum of $2,750/grant for the 60 grants. The co-investment will be a condition written into the formal grant agreement as cost share.

Activity 3: Increase Use of Sustainable Oasis Agricultural System Business Models – Total $2,982,722 ($2,938,972 in monetization and $43,750 in cost share.)

### 3.3.1 Salaries/Personnel – Total $1,189,910

USN/TCN Staff. None.

CCN Staff. Budgeted at 100% LOE for all five years of the project, the Chief of Party (COP) will be a Tunisian national with more than 20 years of experience in international development, strategic consulting, and entrepreneurship. The COP will oversee a team of experts and support staff, prepare reports and work plans, align project initiatives with in-country priorities, and ensure project compliance with federal regulations. Other CCN staff include Technical Director, Component Technical Lead, Component Technical Specialists, 2 Capacity Building Specialists, Sociocultural & Gender Specialist, 3 Sociocultural & Gender Officers, Communications Specialist, M&E Director, M&E Specialist, Finance Director, Contracts & Compliance Specialist, 2 Grants & Procurement Officers, Accountant, Administrative Officer, Human Resources Manager, and 3 Drivers. The CCN staff salary is distributed between Administrative and Activities as appropriate for each role. POA proposes the Chief of Party, Technical Director, and Finance Director as key personnel positions. The proposed salary rates align with market research, benchmarking analysis, and local in-country consultations that were conducted by POA. To account for annual salary increases, POA has increased the salary by 5% after Y1 through LOP.

### 3.3.2 Fringe Benefits – Total $541,409

CCN Tunisia staff benefits are per POA’s fringe benefit policy and local labor laws and are calculated at 45.50% of the employee’s base salary ($541,409). See Section 2.2 for details regarding benefit rates.

### 3.3.3 Travel – Total $166,119

International Travel ($53,292)

Two-Way Buyer Trade Tours: POA will invite 10 US date buyers to southern Tunisia to tour packing facilities. The purpose of these trips is to sign contracts and create relationships between US buyers and Tunisian companies. The estimated cost is $775/trip per attendee, which is reflective of only 50% of the expected cost, as US buyers will need to contribute to the trip. The total cost is $8,873. POA will also invite 10 Tunisian date sector stakeholders to visit the Coachella Valley in California. POA will target 10 students, young date farmers, women, and technical service providers will travel to observe production best practices and establish connections with US counterparts. The estimated cost is $1,550/trip per attendee for a total cost of $17,746.

International Food Shows: POA will send producer organization stakeholders, exporters, and processing company staff to international food shows, such as the Gulf Food Show in Dubai and the Fancy Food Show in New York. POA expects to create over 65 business-to-business connections at these food shows. The Dubai trip is estimated at $750/trip with 10 attendees between Y2-Y3 for a total cost of $8,306. The New York trip is estimated at $1,550/trip with 10 attendees between Y3-Y4 for a total cost of $18,367.

Local Travel ($12,350)

POA is estimating $75/month for local transportation related to activity 3 for a total of $4,009. This includes taxis or car rental for a day. This fund will be utilized if all project vehicles are already in use, and additional vehicle for the day’s activities are required. To make trainings accessible, POA will provide $7/participant for transportation stipends for producer organization leaders to attend PASPs trainings. Stipends are budgeted for 110 participants to attend trainings from Y2-Y4, and LOP total of $833. In Y2, POA will provide transportation stipends of $10/participant for producer organizations to attend market access training sessions for 200 participants, the total cost will be $2,140. Stipend rates are based on the expected distance participants will travel. In Y3, POA will pay for the transportation of a US-based consultant to help provide technical assistance for the project's processors and exporters with the express goal of assisting farmers achieve certifications, for a total cost of $1,775. To make trainings accessible, POA will provide $10/participant for transportation stipends to attend financial literacy trainings to increase knowledge of the benefits of record keeping, using bank accounts, and credit requirements. Stipends are budgeted for 320 participants to attend trainings from Y2-Y3, and LOP total of $3,544.

Vehicle Fuel ($17,373)

POA estimates fuel for project vehicles at $325/month for a total of $17,373 for 46 months over LOP. The transport will be for implementation of activity 3. The rate is based on POA’s historical experience implementing similar projects in the region.

Per Diem & Lodging ($83,104)

POA will provide the lodging and M&IE of a US-based consultant to help provide technical assistance for the project's processors and exporters with the goal of assisting farmers achieve certifications. The cost is estimated at $212/per day with funds for 15 days for a total of $3,641. POA is budgeting lodging and M&IE for our Tunisian attendees of our Two-Way Trade Travel tour to the US has been estimated at a cost of $219/day and each trip 7 days for a total of 70 days at a final cost of $17,551. POA is budgeting lodging and M&IE for our US attendees of our Two-Way Trade Travel tour to Tunisia has been estimated at a cost of $212/day and each trip 7 days for a total of 70 days at a final cost of $16,990. For the international foods shows POA is budgeting lodging and M&IE at $236/day based on the rate for Dubai and each trip 7 days for an LOP total of 70 days for a total cost of $18,295. Similarly, lodging and M&IE for the event based in New York has been estimated at a cost of $321/day and each trip 7 days for an LOP total of 70 days for a total cost of $26,626.

### 3.3.4 Professional Services/Contractual – Total $655,483

Subrecipient: 6th Grain ($501,733) – (UEI: TC9GW9E5T1A9)

### POA is proposing 6th Grain, a US-based GIS and remote sensing company, as a subrecipient. 6th Grain will leverage its unique technology to build a database and measure date and oasis agriculture producer risk. The company will also provide key stakeholders with GIS and remote sensing capacity building. The estimated cost for 6th Grain is $189,532 in Y1, $176,569 in Y2, and $135,633 in Y3 for a total cost of $501,733. Reference page 25 for the full 6th Grain budget narrative.

### Contract for Private Agriculture Service Providers (PASPs) to Train Producer Organizations to Leverage Economies of Scale ($4,200)

### In Y2-Y4, POA will train 55 cooperatives and associations to purchase bulk inputs and supplies to reduce costs. POA will work with ten producer organizations to develop business models illustrating membership benefits. These will then be used to market the advantages of joining their organization to grow membership and achieve economies of scale. The estimated cost for the trainer is $350/per day with 4 days allocated each year between Y2-Y4 for a total cost of $4,200.

### Contract for Organization to Provide Farmers Organic Certifications ($100,000)

### In Y3, POA will open competition for contract to a provider to support 1,000 farmers to acquire organic certifications. This has been estimated at $100/certification with a total cost of $100,000.

### US Consultant to Provide Technical Assistance for Processers and Exporters ($10,800)

### POA will contract a US-based consultant to help provide technical assistance for the project's processors and exporters with the express goal of assisting farmers achieve certifications. Due to the skillset needed, the cost has been estimated at $720/day for 15 days of consultation services in Y3 for $10,800.

### Legal Advisors for Review of Farming Contracts ($3,250)

### In Y2, POA will leverage local lawyers to build farmers’ ability to negotiate contracts to secure higher prices and ensure they receive fair deals. This cost has been estimated at $325/per day for 10 days of advisory services for $3,250.

### Contract for Expert on Agriculture Finance ($10,500)

### A contract between POA and an expert on agriculture finance will be established at $5,250/month for 2 months of services in Y2 for a total of $10,500

### Security Services, Risk Assessments, & Security Assessment ($25,000)

### POA will contract a firm to provide security services and conduct risk and security assessments under activity 3 to ensure the well-being of staff and program participants at $5,000/year for the LOP for a total cost of $25,000.

### 3.3.5 Equipment – Total $0

### None.

### 3.3.6 Office – Total $0

### None.

### 3.3.7 Supplies – Total $29,500

Supplies for Remote Irrigation Pilot ($16,000)

In Y3, POA will demonstrate remote irrigation with four large and high-functioning water associations in each region. The cost has been estimated at $4,000 per irrigation unit with 4 units and a total cost of $16,000. Costs sourced from 3S, a remote irrigation company based in Gafsa, Tunisia.

Table 3 Supplies for Remote Irrigation Pilot Cost Breakdown

| Item per unit (Four total units) | Cost |
| --- | --- |
| Hardware and application | $400 |
| Pipes | $1,000 |
| Pumps | $1,000 |
| Bubbler irrigation | $1,000 |
| Labor | $600 |
| Total | $4,000 |

Supplies for Low-Cost Water Meters ($10,000)

Water meters are a simple, cost-effective solution for farmers and producer groups to reduce water use costs. POA will work with producer groups to purchase low-cost water meters marketed by local and US companies. The cost of the water meters is estimated at $1,000/unit with 10 units to be bought in Y3 for a total cost of $10,000.

Communication Costs for Publication of RFPs/RFAs ($3,500)

POA is estimating $500/publication in Y2-Y4 to cover communications costs related to the release of the RFPs/RFAs for the grants and other procurements for activity 3, for a total of $3,500.

### 3.3.8 Other – Total $356,550

POA will implement the following grant activities:

Grant to Scale Solar Energy Technologies ($50,000)

In Y2-Y3, POA will work with farmers and producer organizations to scale solar energy technologies. POA will issue 50 grants to producer organizations to purchase solar equipment. POA has met with Sunrise Solar – a cost-efficient solar company based in Gafsa to offer interest free credit. Based on this, POA will fund a portion of the total cost, and provide $1,000/grant to producer organizations, for a total cost of $50,000. POA may increase or decrease funding levels of each grant or the number of grants based on proposals submitted. These estimates are the approximate value for each award.

Grants for Producer Organization Mechanization ($25,000)

POA will support producer organizations in seizing economies of scale to purchase equipment. In Y2-Y3, POA will issue 5 grants to strong cooperative to procure mechanization equipment resources. The cost is estimated $5,000/grant for a total cost of $25,000. POA may increase or decrease funding levels of each grant or the number of grants based on proposals submitted. These estimates are the approximate value for each award.

Grants for Youth-Led Mechanization Service Providers ($25,000)

In Y3-Y4, POA will provide 5 grants to youth-led mechanization enterprises. POA will identify opportunities that excite youth, such as drones that pollinate date palms and harvesting equipment. POA will issue $5,000/grant for a total cost of $25,000. POA may increase or decrease funding levels of each grant or the number of grants based on proposals submitted. These estimates are the approximate value for each award.

Grants for Women-Led Date Product Processing ($187,500)

In Y2, POA will provide grants to boost women-led processing enterprises’ output and marketability. Date processing is key to delivering a viable end market for varieties such as kenta, alig, and other common dates. POA will issue $7,500/grant with 25 grants being awarded, for a total cost of $187,500. POA may increase or decrease funding levels of each grant or the number of grants based on proposals submitted. These estimates are the approximate value for each award.

POA will implement the following training activities and development of materials:

PASPs Trainings to Support Capacity-Building Efforts for Producer Organizations (Materials, Food, & Refreshments) ($3,960)

POA will hold day long training sessions for each of the 4 regions in Y2-Y4 to build capacity of providers organizations through PASPs trainers. The trainings are budgeted at $330/training for 15 participants and 3 staff ($10/person for food plus $150 for materials). There will be 4 trainings each year in Y2-Y4. The total for 12 trainings is $3,960.

Market Access Trainings for Independent Producers (Materials, Food, & Refreshments) ($7,200)

POA will support independent producers in creating producer organizations to aggregate their production through Market Access Trainings. This will allow them to access markets that require high volumes of production. POA will provide all necessary materials, food, and refreshments for 2-day long trainings for Market Access at a cost of $1,800/training 50 participants and 5 staff ($10/person for food plus $350 for materials times 2 days). POA will hold 4 trainings in Y2 for a total cost of $7,200.

Meeting Expenses for Meetings with Producer Organizations and Exporters ($7,650)

POA will work with ten responsible exporters and packers, to determine their export goals. POA will then identify producer organizations with the exporters to collaborate on the Outgrower Business Model. POA is budgeting for meeting expenses estimated at $150/per meeting with 51 meetings over LOP and a total cost of $7,650.

Trainings on Financial Literacy (Materials, Food, & Refreshments) ($5,440)

POA will conduct financial literacy trainings in Y2-Y3 to increase these stakeholders’ knowledge of the benefits of record keeping, using bank accounts, and credit requirements. POA will target minority youth and women to attend. POA will provide all necessary materials, food, and refreshments for the attendees of the trainings, with an estimated cost of $680/training 40 participants and 3 staff ($10/person for food plus $250 for materials). There will be a total of 8 trainings for final cost of $5,440.

Meeting Expenses for Capacity Building Session with Financial Institutions ($1,800)

POA will hold meetings with Tunisian financial institutions to build on methods needed to increase capacity. The expenses of these meetings are estimated at $150/meeting with 6 meetings held each year in Y2-Y3 for a total cost of $1,800 for 12 meetings.

Develop Marketing Materials for Producer Organizations to Develop Business Models for Membership Benefits ($20,000)

POA will work with producer organizations to recruit new members through websites, social media, and agriculture events. In Y2, POA will work with 10 producer organizations to develop business models illustrating membership benefits. These will then be used to market the advantages of joining their organization to grow membership and achieve economies of scale. Expenses for these marketing materials are estimated at $2,000/organization. The total cost for 10 organizations is $20,000.

Materials Development on Date Grading (Printing & Translation) ($3,000)

Printing and translation assets needed to perform material development on date grading has been estimated at a cost of a one-time payment of $3,000 in Y2 of the project.

POA will implement the following event activity:

Registration and Booths for International Food Shows ($20,000)

POA will send producer organization stakeholders, exporters, and processing company staff to two international food shows, such as the Fancy Food Show in New York and the Gulf Food Show in Dubai. Registration for the shows has been estimated at $5,000/event which includes registration for participants and a booth. POA will have individuals attend 4 events between Y2-Y4 for a total cost of $20,000.

### 3.3.9 Cost-Share – Total $43,750

### Cost Share from Subrecipient: 6th Grain ($9,000)

### POA is proposing 6th Grain, a US-based GIS and remote sensing company, as a subrecipient. 6th Grain will leverage its unique technology to build a database and measure date and oasis agriculture producer risk. 6th Grain will provide $3,000/year between Y1-Y3 for a total of $9,000 in cost share through existing licenses for GIS and remote sensing technologies over the LOP. The $3,000 a year estimate is based on a percentage of license costs and is required for the performance of work.

### Venue Space Market Access Trainings ($1,000)

### POA will acquire a venue space to hold its market access trainings. The cost of the venue has been estimated at $250/per training with 4 sessions planned for a total cost share of $1,000.

### Technical Assistance from PAMPAT to Support Date Product Processors ($5,000)

### POA will be partnering with the PAMPAT II project, a Swiss-funded project building the technical capacity of processors in the South. Technical assistance from the PAMPAT project in staff time and materials has been estimated at $5,000 in cost share. Based on an average salary daily of $150 (assuming monthly salary of $3,000 and 20 working days a month), POA estimates that PAMPAT II staff will contribute 30 days of staff time to support capacity building of processors totaling $4,500. Additionally, POA estimates they will donate $500 worth of materials (tools, flyers, and informational tools).

### Venue Space for Financial Literacy Trainings ($2,000)

### POA will acquire a venue space to hold its financial literacy training sessions in. The estimated cost of said venue is $250/training with 4 trainings scheduled each year for Y2-Y3. The total cost share is at $2,000

### Packers and Exporters Support for Organic Certifications ($15,000)

### As cost share POA will receive subsidies from government (Organic Agriculture Agency) and private sector (Boudjebel) for the acquisition of Organic Product certifications for packers and exporters. The cost share is estimated at $15/certification in cash contribution for $1,000 certifications in Y3, the total cost share is $15,000. This is roughly 10% of the cost to cover the certifications.

### Airfare and Local Transport for Two-Way Trade (US to Tunisia) to - 50% of Cost ($7,750)

### Airfare and local transport for the Two-Way Trade trip from the US to Tunisia has been estimated at $775/per unit with 10 trips in Y3 for a final cost of $7,750. This cost reflects only 50% of the overall cost, as buyers will contribute to their trips as cost share.

### Contributions to Registrations and Booths for International Food Shows ($4,000)

### Additional contributions from date exporters such as Boudjebel and Horchani, to assist in registration for trips to international food shows such as the Fancy Foods Show in New York and Gulf Foods Show in Dubai has been estimated at $1,000/event with 1 event in Y2, 2 events in Y3, and 1 event in Y4. The total cost share is $4,000.

### 3.5 Indirect Costs – Activities – Total $2,600,512

In accordance with POA’s most recently approved NICRA, indirect costs are 28.28% of direct activity costs. Total Indirect Costs on Activities: $2,600,512.

Total Estimated Costs: $17,305,226 ($15,500,000 in monetization (includes interest), $1,500,000 in CCC funds, $305,226 in cost share)

6Th Grain (UEI: TC9GW9E5T1A9) – Subrecipient Budget – ($510,733) – under Activity 3

4.1.1 Salaries/Personnel ($120,817)

6th Grain will assign six staff members to work on the FFPr Tunisia project starting Y1-Y3. The project staff includes a project lead/Chief Science Officer at 10% LOE; Chief Executive Officer at 5% LOE; a Data Scientist at 15% LOE; and three Field Data Officers, one at 25% and two at 10% LOE.

4.1.2 Fringe Benefits ($15,199)

Field personnel fringe is calculated to be 28.40% of base salaries at a total value of ($4,812), and HQ fringe is 10% of base salaries at a total of ($10,387), for a total of $15,199 over the LOP.

4.1.3 Travel ($28,984)

6th Grain has budgeted for 6 international trips for US-based staff to travel to Tunisia, with $1,400/per round-trip flights for a total of $8,740. International staff and field personnel will travel from Tunis to Gafsa/other target regions 8 times over the LOP at a cost of $300/trip for a total of $2,522. M&IE for these trips budgeted $9,265 for trips in Tunis and $8,456 for other locations.

4.1.4 Professional Services/Contractual ($151,121)

6th Grain has budgeted $151,121 over the LOP to create a GIS and remote sensing dashboard application for FPPr Tunisia farmers and producer organizations in Kibili, Gafsa, Tozeur, and Gabes. The dashboard will be an interactive tool to give POA and FFPr Tunisia stakeholders information on measuring crop productivity, water use management, and disease spread to scale climate-smart agriculture adoption. The funds will be used to purchase necessary software GIS/remote sensing licenses and inputs to build the FFPr Tunisia dashboard.

4.1.5 Other Direct Costs ($140,000)

6th Grain will work with financial institutions and producer organizations to conduct Agricultural Risk Calculation at a total of $85,000 over the LOP. Under this activity, 6th Grain will use GIS and remote sensing tools to identify the risk of 100 farmers belonging to producer organizations. 6th Grain will partner with local financial institutions to use GIS and remote sensing to measure these 100 farmers’ risk and increase their ability to assess the loans. Additionally, 6th Grain will hold in-person and remote capacity-building training with key FFPr Tunisia stakeholders to increase their GIS/remote sensing tool capacity, total is $55,000 over LOP.

4.1.6 Indirect Costs ($45,612)

An Indirect Cost Recovery rate of 10% will be applied to all of 6th Grain’s total modified direct costs for a total of $45,612 over the LOP.

4.1.7 Cost Share ($9,000)

6th Grain will provide $9,000 in cost share through existing licenses for GIS and remote sensing technologies over the LOP.

Total Estimated Costs: $510,733 ($501,733 in monetization, $0 in CCC funds, $9,000 in cost share)