ATTACHMENT D

PERFORMANCE INDICATOR TABLE

The LOP Target includes the original goals from FY2021 to FY2024. However, no activities contributing to the goals were carried out during the first two years. The comments include the actual expected LOP target, calculated based on the progress made during FY2023 and FY2024 and the targets established from FY2025 onward.

| Activity | Indicator | Baseline | LOP Target | Target FY21 | Target FY22 | Target FY23 | Target FY24 | Target FY25 | Target FY26 | Target FY27 | Target FY28 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Agriculture Extension and Production Support | Custom1: Number of farms with productivity gains | 173 | 927 | 78 | 368 | 927 | 927 | ,545 | 891 | 644 | 0 | Project activities began in September 2022. POA will annually report farmers included in FFPr1 that demonstrated annual productivity increases exceeding 0.47 kg/tree, a benchmark identified in the baseline (0.46 kg/tree). Annual targets reflect the full scope of work that year. The Actual Expected LOP target reflects the number of unique people reached across the life of project. |
|  | Custom2: Number of organizations establishing improved seedstock as a result of USDA assistance | 0 | 35 | 0 | 20 | 12 | 0 | 12 | 0 | 0 | 0 | The project supports producer organizations in distributing seedlings to their members to improve crops and productivity. Each year’s target reflects the full scope of work that year. Actual Expected LOP target reflects the number of unique organizations reached across the 8 years of the project. Actual Expected LOP Target: 25 organizations |
|  | Custom3: Number of farms demonstrating improved landscape management | 0 | 5,121 | 68 | 368 | 927 | 927 | 4,411 | 4,457 | 2,275 | 0 | C4D is deployed in a wide variety of ecosystems and dispersed locations. Farmers applying pruning, replanting, crop renewal, irrigation or plantain planting will be reported under this indicator. Annual targets reflect the full scope of work that year. The LOP Target reflects the number of unique farms reached across the life of project. |
|  | Custom4: Estimated tonnage of carbon sequestered | 0 | 2,334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | During FY23-24, the project was able to introduce 18 producers into the carbon market. However, considering the complexity of accessing carbon sequestration certification, the project decided to not continue with this intervention and targets are zero for following years. |
|  | Custom5: Number of households with improved real Living Income Outcomes as a result of USDA assistance | 0 | 1,045 | 0 | 0 | 0 | 0 | 0 | 1,045 | 0 | 0 | It is expected that 20% of C4D farmers will improve their real income by the end of the project through complementary crops and an increase in productivity. Though they may not reach a Living Income, the project expects to help farmers reduce the gap between current real income and the estimated living income. This measurement will occur in FY26. |
|  | FFPr1: Yield of targeted agricultural commodities among project participants with USDA assistance (kg/tree, cacao) | 0.46 | 1 | 1 | 1 | 1 | 1 | 0.6 | 0.8 | 1 | 0 | This indicator only includes farmers with five or more visits during the reporting year, in order to adequately measure the entire harvest year. At the end of the project, the estimated yield will be 1 kg/Tree. Reporting will be per tree because plant densities are highly variable between farms. |
|  | FFPr1: Yield of targeted agricultural commodities among project participants with USDA assistance (kg/tree, complementary crop) | 0.80 | 5 | 1 | 2 | 4 | 4 | 0 | 0 | 0 | 0 | This indicator is being replaced by 2 new indicators for the complementary crops selected by the project (plantain and Tabasco peppers). |
|  | FFPr1: Yield of targeted agricultural commodities among project participants with USDA assistance (kg/tree, complementary crop Plantain) | 9.84 | 12 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | Estimated yield of 12 Kg/Tree. |
|  | FFPr1: Yield of targeted agricultural commodities among project participants with USDA assistance (kg/1/4 of hectare, complementary crop Tabasco) | 2,200 | 2,500 | 0 | 0 | 0 | 0 | 2,500 | 2,500 | 0 | 0 | The unit used in tabasco crops is Kg/ ¼ hectare. The estimated yield is 2.5 tons (2,500 Kg) for every 2,500m2 of cultivated land under complex sanitary conditions. |
|  | FFPr18: Value of annual sales of farms and firms receiving USDA assistance (cacao) | $ 1,445,858 | $ 43,068,643 | $ 1,530,128 | $ 4,054,581 | $ 6,831,423 | $ 7,849,411 | $ 7,200,200 | $ 9,601,500 | $ 6,001,400 | 0 | Project activities began in September 2022. This figure only includes farm gate sales. These targets are based on the volume targets of FFPr19. Assuming an average cacao price of USD $3,7 per kilogram (Exchange rate: COP $4,100). Actual Expected LOP Target: USD $32,007,464 |
|  | FFPr18: Value of annual sales of farms and firms receiving USDA assistance (complementary crop) | $ 150,776 | $ 7,481,295 | $ 150,776 | $ 716,129 | $ 1,790,279 | $ 2,167,104 | 0 | 0 | 0 | 0 | This indicator is being replaced by 2 new indicators for the complementary crops selected by the project (plantain and Tabasco peppers). |
|  | FFPr18: Value of annual sales of farms and firms receiving USDA assistance (complementary crop Plantain) | $ 15,135 | $ 2,744,070 | 0 | 0 | 0 | 0 | $644,590 | $ 2,099,480 | $ 0 | 0 | The first harvest starts in FY2025. These targets are based on the volume targets of FFPr19. Assuming a plantain price of USD $0,73 per kilogram (exchange rate: COP 4,100) |
|  | FFPr18: Value of annual sales of farms and firms receiving USDA assistance (complementary crop Tabasco) | 6,681 | $24,644 | 0 | 0 | 0 | 0 | $ 14,645 | $ 9,999 | - | 0 | The first harvest started in FY2024, and the first annual sales will be reported in FY25 to report the full harvest. These targets are based on the volume targets of FFPr19. The market rates for Tabasco peppers are USD $1,01 per kilogram (exchange rate: COP 4,100). |
|  | FFPr19: Volume of commodities sold by farms and firms receiving USDA assistance (cacao - Ton) | 786 | 17,000 | 818 | 2,168 | 3,653 | 4,198 | 1,946 | 2,595 | 1,622 | 0 | Project activities began in September 2022. Includes only farm gate sales (incorporates sales of wet cacao converted to dry cacao weight equivalent). Targets are based on the harvest of farmers with 2 or more technical visits each year, with an average of 1.6 ha per producer. Actual Expected LOP Target: 8,394 Ton |
|  | FFPr19: Volume of commodities sold by farms and firms receiving USDA assistance (complementary crop) | 603.07 | 29,925 | 603 | 2,865 | 7,161 | 8,668 | 0 | 0 | 0 | 0 | This indicator is being replaced by 2 new indicators for the complementary crops selected by the project (plantain and Tabasco peppers). |
|  | FFPr19: Volume of commodities sold by farms and firms receiving USDA assistance (complementary crop Plantain - Ton) | 52,4 | 3,759 | 0 | 0 | 0 | 0 | 883 | 2,876 | - | 0 | The first harvest starts in FY2025. The project’s plantain strategy includes the planting of more than 166,000 plantain plants. The expected yield after 12 months is 12 kilograms per plant, and three harvests are expected during LOP. |
|  | FFPr19: Volume of commodities sold by farms and firms receiving USDA assistance (complementary crop Tabasco - Ton) | 6,6 | 24.4 | 0 | 0 | 0 | 0 | 14.5 | 9.9 | 0 | 0 | The first harvest starts in FY2024. The project’s complementary crop strategy includes 10 Tabasco pepper pilots (7 of 0,25 Has and 3 of 0,33 Has). The expected yield after 12 months is 5,000 Kl per ¼ Ha. |
|  | FFPr2: Number of hectares under improved management practices or technologies that promote improved climate risk reduction and/or natural resources management with USDA assistance | 955 | 5,434 | 68 | 436 | 1,364 | 2,291 | 4,086 | 4,457 | 2,414 | 0 | Producers apply practices that improve climate risk reduction (Organic fertilization, drip irrigation, organic certification, and soil amendments). The assumption is that the percentage of hectares implementing those improved management practices will increase to 65% in FY27. Data collected to date shows an average of 1.6 cacao Has per farm. Actual Expected LOP Target: 5,434 hectares Annual targets reflect the full scope of work that year. The Actual Expected LOP Target reflects the number of unique hectares reached across the life of project. |
|  | FFPr21: Number of individuals who have received short-term agricultural sector productivity or food security training as a result of USDA assistance | 0 | 5,455 | 1,091 | 2,727 | 3,273 | 2,727 | 4,227 | 4,227 | 2,114 | 0 | One person is trained per farm during each extension visit. Targets are based on farmers with more than 3 visits and a gradual increase towards the universe of C4D farmers, considering that around 85% of farmers receive 3 or more visits during the year. Actual Expected LOP Target: 4,675 individuals Annual targets reflect the full scope of work that year. The Actual Expected LOP Target reflects the number of unique people reached across the life of project. |
|  | FFPr22: Number of individuals participating in USDA food security programs | 0 | 5,225 | 1,253 | 3,133 | 3,759 | 3,133 | 4,643 | 4,643 | 2,321 | 0 | Every extension visit has a food security component. Targets are based on a gradual increase towards the universe of C4D farmers with a 5% dropout rate. Annual targets reflect the full scope of work that year. The Actual Expected LOP Target reflects the number of unique people reached across the life of project. |
|  | FFPr23: Number of individuals benefiting indirectly as a result of USDA assistance | 0 | 18,170 | 3,624 | 9,085 | 10,902 | 9,085 | 11,143 | 11,143 | 5,570 | 0 | The number of individuals that received at least two technical assistance visits were multiplied by 2.4 (ratio resulting from: the average household size of 3.4, minus the head of the family - 1 person/main producer ). Actual expected LOP: 12,540 individuals Annual targets reflect the full scope of work that year. The Actual Expected LOP Target reflects the number of unique people reached across the life of project. |
|  | FFPr3: Number of hectares under improved management practices or technologies with USDA assistance | 24 | 8,360 | 136 | 873 | 2,727 | 4,582 | 7,429 | 7,429 | 3,714 | 0 | Farmers are trained during each extension visit and it is expected that all beneficiaries implement good agroforestry practices based on the success factors promoted by the project and the tools transferred to them. Data collected to date shows an average of 1.6-1.9 hectares of cacao per farm. Annual targets reflect the full scope of work that year. The Actual Expected LOP Target reflects the number of unique hectares improved across the life of project. |
|  | FFPr4: Number of individuals in the agriculture system who have applied improved management practices or technologies with USDA assistance | 10 | 5,225 | 78 | 501 | 1,566 | 2,632 | 4,643 | 4,643 | 2,321 | 0 | Farmers are trained during each extension visit and it is expected that all beneficiaries implement good agroforestry practices based on the success factors promoted by the project and the tools transferred to them. Targets are based on a gradual increase towards the universe of C4D farmers with a 5% dropout rate. Annual targets reflect the full scope of work that year. The Actual Expected LOP Target reflects the number of unique hectares improved across the life of project. |
| Ensure Financial Service/ Capital Access for Actors in the Value Chains | Custom9: Number of grants disbursed to beneficiaries as a result of USDA assistance | 0 | 122 | 1 | 30 | 45 | 1 | 41 | 3 | 1 | 0 | This is calculated by adding all the grants presented in the merit proposal budget. This was estimated by the number of grants in the budget. Actual Expected LOP Target: 45 grants |
|  | Custom10: Value of grants disbursed to beneficiaries as a result of USDA assistance | 0 | $ 1,623,413 | $ 15,000 | $ 355,000 | $ 505,000 | $ 40,000 | $638,413 | $ 60,000 | $ 10,000 | $ 0 | This is calculated by adding all the grants presented in the merit proposal budget. Actual Expected LOP Target: USD 708,413 |
|  | FFPr5: Number of individuals accessing agriculture-related financing as a result of USDA assistance | 0 | 5,368 | 78 | 423 | 1,065 | 1,065 | 4,773 | 5,368 | 4,773 | 0 | Targets are based on beneficiaries of crop insurance and loans to organizations and producers. It is estimated that 89.6% of farmers meet the requirements to access the insurance. Annual targets reflect the full scope of work that year. The Actual Expected LOP Target reflects the number of unique hectares improved across the life of project. |
|  | FFPr7: Number of loans disbursed as a result of USDA assistance | 0 | 2,570 | 68 | 368 | 927 | 927 | 30 | 250 | 0 | 0 | The baseline showed that most farmers do not have debt capacity or were not interested in getting into debt. During the baseline cacao prices were at US$2,000/Ton and this price remained for the first 3 years of the project. However, the current cacao prices are USD$6,000/ton, which are expected to remain for 4 years, and which will prompt farmers to invest in their crops. Actual Expected LOP Target: 280 loans |
|  | FFPr8: Value of agriculture-related financing accessed as a result of USDA assistance | 0 | $ 4,157,254 | $ 92,525 | $ 599,634 | $ 1,358,337 | $ 1,258,337 | $ 418,000 | $ 215,211 | $ 215,211 | $ 0 | This is calculated considering indemnities paid by the insurer over a period of 5 months and an estimate of loans to organizations and producers. These goals may change substantially, as indemnities depend on climate behavior. In addition, the baseline showed that most producers did not have debt capacity or were not interested in getting into debt. Actual Expected LOP Target: USD 1,372,208 |
| Establishment of Regional Community of Practice | Custom11: Number of logins to online Regional Community of Practice knowledge sharing platform | 0 | 4,700 | 0 | 1,000 | 1,500 | 2,000 | 200 | 200 | 0 | 0 | The community of practice website was launched in March 2024 and is currently being promoted among the different stakeholders. Actual Expected LOP Target: 538 logins |
|  | Custom12: Number of participating Regional Community of Practice members | 0 | 120 | 0 | 40 | 80 | 100 | 100 | 120 | 120 | 0 | People registered in Community of Practice (CoP) Platform/website, and who participate in at least one additional CoP event during the life of project. Annual targets are accumulative. |
| Financial Services: Endowment Establishment, Fundraising and Management | FFPr14: Value of new USG commitments and new public and private sector investment leveraged by USDA to support food security and nutrition | 0 | $6.200.000 | $ 0 | $ 100,000 | $ 100,000 | $ 2.000.000 | $ 1,000,000 | $ 1,500,000 | $ 1,500,000 | $ 0 | This indicator includes the value of agreements signed with public and private organizations, and the value leveraged with organizations to implement activities to benefit the target population. |
| Innovation and Job Creation Through Youth Engagement | Custom8: Number of Youth with increased capacity in agribusiness | 0 | 1,150 | 230 | 575 | 690 | 575 | 148 | 149 | 110 | 0 | Number of youth (16 to 29 year old) benefited by: the extension strategy, Open Innovation processes, exchange trips, grants, among other strategies. Actual Expected LOP Target: 381 youth Annual targets reflect the full scope of work that year. The Actual Expected LOP Target reflects the number of unique youths reached across the life of project. |
| Post-Harvest Aggregation & Processing | Custom6: Number of processors and aggregators displaying improved quality of post-production products as a result of USDA assistance. | 0 | 20 | 0 | 2 | 8 | 14 | 14 | 20 | 0 | 0 | POA proposes changing this indicator from focusing solely on post-production processes to encompassing processes related to the entire value chain, thereby better reflecting the project's strategy. In the disaggregation, POA will report specifically those related to post-harvest. Annual targets are accumulative. |
|  | Custom7: Number of new agreements signed between buyers and sellers, as a result of USDA assistance | 0 | 30 | 0 | 0 | 12 | 20 | 25 | 30 | 0 | 0 | This indicator measures how many new agreements producers, aggregators, processors, transporters, and input suppliers sign with buyers along the value chain with C4D assistance Annual targets are accumulative. |
|  | FFPr16: Total increase in installed storage capacity (dry or cold storage) as a result of USDA assistance | 0 | 1,700 | 0 | 200 | 600 | 700 | 200 | 0 | 0 | 0 | While the C4D strategy is not currently focused on expanding storage infrastructure capacity, some grants under the merit extension may implement related activities. Actual Expected LOP Target: 400 M3 |
| Producer Organization Development & Commercialization | FFPr12: Number of organizations with increased performance improvement with USDA assistance | 0 | 57 | 1 | 8 | 29 | 48 | 57 | 57 | 0 | 0 | The measurement of organizational development for target producer organizations will be conducted upon completion of the strengthening process during FY2025-FY2026. Annual targets are accumulative. |
|  | FFPr13: Number of public-private partnerships formed as a result of USDA assistance | 0 | 66 | 0 | 20 | 20 | 15 | 4 | 4 | 3 | 0 | Includes partnerships with producer organizations, private sector, buyers, local and national government. |
| Value Chain Development | FFPr9: Number of technologies, practices, and approaches under various phases of research, development, and uptake as a result of USDA assistance (Phase 4) | 0 | 17 | 0 | 0 | 3 | 1 | 3 | 5 | 5 | 0 | Includes technologies, practices, and approaches disseminated or in use by one or more value chain actors across all project activities. It is estimated that 60% of the technologies designed or tested are transferred to value chain actors Actual Expected LOP Target: 42 |
|  | FFPr9: Number of technologies, practices, and approaches under various phases of research, development, and uptake as a result of USDA assistance (Phases 1-3) | 0 | 60 | 5 | 13 | 11 | 5 | 15 | 8 | 3 | 0 | Includes technologies, practices, and approaches designed and tested across all project activities. Actual Expected LOP Target: 70 |