## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | Palma Futuro |  |  |  | Total Award Amount: | 7360289 | Program Manager(s) (including dates):
Internal Grant Number: | DOL420 |  |  |  | Total Obligation Amount: | 7360289 | Macarena Jimenez
Award Number: | IL-32820-18-75-K |  |  |  | Cost Share Amount: | N/A
Donor: | USDOL |  |  |  | Leverage Amount: | N/A
CFDA: | 18-1605-2019-2501651819AD20190165000318MILAB0M0000MILB00MILIFH-M9K111- 410043--- |  |  |  | USAID Only: Geographic Code: | N/A
Award Start Date: | 2019-01-01 |  |  |  | Key Personnel: | Angelica Nieto, Oscar Sanchez
Award End Date: | 2024-07-31 |  |  |  | Approved Indirect Rate(s) %: | 28.28%
Program Director: | Angelica Nieto |  |  |  | Prior Approvals Required: | Per 2 CFR 200 and MPG
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Leyla Strotkamp |  |  |  | Treatment of Program Income: | Addition
Agreement Officer (AO)/Grants Officer (GO): | Evan Hughes
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Agreement | 2018 | 2019-2022 | 2018-08-23 | 2018-11-28 | Notice of Award | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FAward%2FIL32820award%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FAward | Original Award
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2019 | 2019-2022 | 2019-07-16 | 2019-08-30 | Award Modification 1 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FProject%20Revision%2F1%2E%20Submitted%20to%20USDOL%20%2D%20July%2016%202019%20%2D%20Mod%20001%20Approved%2FApproved%20Modification%20001%20%2D%20September%202019%2FIL%2D32820%20Modification%201%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FProject%20Revision%2F1%2E%20Submitted%20to%20USDOL%20%2D%20July%2016%202019%20%2D%20Mod%20001%20Approved%2FApproved%20Modification%20001%20%2D%20September%202019 | Project Revision to reduce Project Director's LOE, replace RML Officer, realign personnel structure & budget
Modification 02 | 2021 | 2019-2022 | 2021-04-23 | 2021-06-02 | Award Modification 2 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FProject%20Revision%2FIL%2D32820%20Modification%202%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&q=modification%202&parent=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor&parentview=7 | Project Revision to replace Project Director and RML Officer, and realign budget
Modification 03 | 2022 | 2019-2023 | 2022-08-23 | 2022-10-20 | Award Modification 3 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FProject%20Revision%2F5%2E%20Approved%20PR%2010%2D22%2FIL%2D32820%20Modification%203%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FProject%20Revision%2F5%2E%20Approved%20PR%2010%2D22 | Project Revision to realign the Ecuador strategy, request a no-cost extension, replace RML Officer, and realign budget
Modification 04 | 2023 | 2019-2024 | 2023-03-31 | 2023-05-05 | Award Modification 4 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FProject%20Revision%2F7%2E%20Approved%20PR%205%2D23%20%28submitted%203%2D23%29%2FIL%2D32820%20Modification%204%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FProject%20Revision%2F7%2E%20Approved%20PR%205%2D23%20%28submitted%203%2D23%29 | Project Revision for 13 month cost extension, budget realignment and adjusted NICRA rate
Modification 05 | 2023 | 2019-2024 | 2023-07-12 | 2023-08-04 | Award Modification 5 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FProject%20Revision%2F8%2E%20June%202023%20%2D%20Project%20Director%2FApproved%20by%20USDOL%2FNotice%20of%20Award%5FCost%20Increase%20Aug%202023%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FDonor%2FProject%20Revision%2F8%2E%20June%202023%20%2D%20Project%20Director%2FApproved%20by%20USDOL | Project Revision to replace Project Director
Modification 06 | 2023 | 2019-2024 | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
CMEP | 2019 | 2019-2022 | 2019-08-23 | 2020-01-23 | Annex 3 Palma Futuro Data Reporting Form_FINAL 012320 | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7B7E141FBC-BA85-41E3-B5FD-C9242B6B9932%7D&file=Annex%203%20Palma%20Futuro%20Data%20Reporting%20Form_FINAL%20012320.xlsx&action=default&mobileredirect=true | Original CMEP document sent to donor in first year of award
CMEP Modification (Cost Extension) | 2023 | 2019-2024 | 2023-09-29 | 2023-10-13 | Annex 3 Palma Futuro Data Reporting Form (Oct 2023) | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7B90838279-1EDE-4AF0-AF7D-20D096585C45%7D&file=Annex%203%20Palma%20Futuro%20Data%20Reporting%20Form%20(Oct%202023).xlsx&action=default&mobileredirect=true | Revised CMEP document sent to and approved by USDOL upon formal cost extension
| FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
| FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
| FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Original Work Plan | 2019 | 2019-2022 | 2019-06-27 | 2019-06-27 | Palma Futuro - Work Plan 2019-06-27 V1 | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7BA671686C-5B9F-4CFE-A079-E8FCDA598744%7D&file=Palma%20Futuro%20-%20Work%20Plan%202019-06-27%20V1.xlsx&action=default&mobileredirect=true | First version of project workplan
Work Plan Revision 1 - No Cost Extension | 2022 | 2019-2022 | 2022-08-23 | 2022-10-20 | Annex II - DOL420- Updated Work Plan Palma Futuro - 081822 | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7BE9EDD451-14F4-46E6-BA42-B027D40ACC3B%7D&file=Annex%20II%20-%20DOL420-%20Updated%20Work%20Plan%20Palma%20Futuro%20-%20081822.xlsx&action=default&mobileredirect=true | Revised workplan to June 2023 with no-cost extension and revised activities according to new Ecuador strategy
Work Plan Revision 2 | 2023 | 2019-2023 | 2023-03-31 | 2023-05-05 | Annex II - DOL420 - Updated Work Plan Palma Futuro Julio 2024 | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7BD66B4B9E-818A-4890-B7F5-2335055D10A5%7D&file=Annex%20II%20-%20DOL420%20-%20Updated%20Work%20Plan%20Palma%20Futuro%20Julio%202024.xlsx&action=default&mobileredirect=true | Revised workplan to July 2024 with cost-extension and revised activities according to updated Ecuador and Peru strategies
Most Recently Updated Work Plan (October 2023, submitted with TPR) | 2023 | 2019-2024 | 2023-10-27 | N/A | Annex B - Updated Work Plan - Palma Futuro October 2023 | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7B006B2D53-1D7D-4930-9BAE-CA837A22D8F0%7D&file=Annex%20B%20-%20Updated%20Work%20Plan%20-%20Palma%20Futuro%20October%202023.xlsx&action=default&mobileredirect=true | Updated workplan submitted with most recent TPR (October 2023)
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
Award funds must not duplicate existing foreign government activities or substitute for activities that are the responsibility of the foreign government. Any award funds budgeted to support host country governments during the life of the award require USDOL prior approval in accordance with the MPG.
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Montly Meeting with USDOL GOR | 2023 | 2019-2024 | 2023-10-13 | N/A | N/A | Link to Meeting Notes
Montly Meeting with USDOL GOR | 2023 | 2019-2024 | 2023-11-03 | N/A | N/A | Link to Meeting Notes
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Compliance Matrix Details
Breakdown of Award Requirements
| Award Terms & Conditions | Compliant Y/N | Comments | Program Description | Compliant Y/N | Comments | Work Plan FY2023 | Compliant Y/N | Comments | Workplan FY2024 | Compliant Y/N | Comments | Work Plan FYXX | Compliant Y/N | Comments | Workplan FYXX | Compliant Y/N | Comments | MEL Plan FY2023 | Compliant Y/N | Comments | Indicators | Compliant Y/N | Comments | Environmental Mitigation and Monitoring Plan - EMMP | Compliant Y/N | Comments | Activities in Budget Narrative | Compliant Y/N | Comments
1 | Financial Reporting: Quarterly FFRS | Y |  | Description: XXX |  |  | Submit Technical Progress Report 2 (TPR) - October 2023 | Y |  | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | Revised CMEP according to cost-extension activities | Y | Revised CMEP approved by USDOL 10/23 | PO1: Number of organizations in Latin America that promote social compliance system practices in the palm oil sector | Y |  |  |  |  | 1.1.1 Form Multi-Stakeholder Advisory Councils for providing project updates and convening stakeholders | Y
2 | Financial Reporting: XXX |  |  | Geographic Scope: XXX |  |  | Gender Considerations: XXX |  |  | Gender Considerations: XXX |  |  | Gender Considerations: XXX |  |  | Gender Considerations: XXX
3 | Financial Reporting: XXX |  |  | Recommend organizing by component/activity |  |  | Sustainability: XXX |  |  | Sustainability: XXX |  |  | Sustainability: XXX |  |  | Sustainability: XXX
4 | Financial Reporting: XXX
5 | Accrual Reporting | Y |  |  |  |  | Field trips to Cesar and Magdalena (Colombia) | Y | [13 empty] | PO 2: Number of palm oil entities with improved Social Fingerprint® performance scores | Y |  |  |  |  | 1.1.2 Conduct targeted research on gaps identified by the palm oil sector including the prevalence, nature, and risks of child labor and forced labor | Y
6 | Substantial Involvement | Y | The project complies by meeting regularly with the USDOL GOR to provide updates on project implementation and receiving and responding to USDOL's input, in addition to sharing project deliverables for USDOL approval |  |  |  | Field trips to Orellana (Ecuador) | Y | [13 empty] | OTC 1.1.: Number of palm oil entities with improved Social Fingerprint® management systems scores | Y |  |  |  |  | 1.1.3 Coordinate market analysis plans with stakeholders | Y
7 | Accrual Reporting: XXX
8 | Accrual Reporting: XXX
9 | Projections to Donor: 2023 projections
10 | Projections to Donor: XXX | [27 empty] | Y
11 | Projections to Donor: XXX
12 | Projections to Donor: XXX
13 | Annual Implementation Plans:
14 | Annual Implementation Plans: XXX
15 | Annual Implementation Plans: XXX
16 | Annual Implementation Plans: XXX
17 | Activity Monitoring and Evaluation (AMEP Plan): XXX
18 | Activity Monitoring and Evaluation (AMEP Plan): XXX
19 | Semi-Annual reports: April - October 2023 Technical Progress Report (due October 31) | Y | Most recently submitted TPR was sent on time (October 27 2023) |  |  |  | Field trips from Colombia team to Ecuador | Y | [13 empty] | SOTC 1.1.1: Percentage of key stakeholders who attend annual sectoral workshops who demonstrate a change in their understanding of labor practices and risks in supply chain | N | Target is 80%, actual is 76.4%; two sectoral workshops will be held during this reporting period and progress will be reported for these |  |  |  | 1.1.4 Carry out annual sectoral action-oriented workshop addressing child labor, forced labor, acceptable conditions of work | Y
20 | Quarterly Performance Reports: XXX
21 | Quarterly Performance Reports: XXX
22 | Quarterly Performance Reports: XXX
23 | Quarterly Performance Reports: XXX | [27 empty] | Y
24 | Branding (Social Media, use of USDOL seal, press releases/major events) | Y | The project complies with all branding requirements set forth in the MPG |  |  |  | Field trips to Peru | Y | [13 empty] | OTP 1.1.1.1 Final research report on CL and FL and labor conditions completed | N | Qualitative studies are delayed but will be finalized in early 2024 when the target will be met. |  |  |  | 1.1.5 Develop and disseminate materials to promote acceptable conditions of work and address child labor and forced labor | Y
25 | Annual Reports: XXX
26 | Final Program Report: XXX
27 | Short-Term Consultant Reports, Technical Briefs/Reports, Special and External Reports: XXX
28 | Short-Term Consultant Reports, Technical Briefs/Reports, Special and External Reports: XXX | [27 empty] | Y
29 | Closeout Plan: XXX | [27 empty] | Y
30 | Development Experience Clearinghouse Requirements: XXX
31 | Foreign Tax Reports: XXX
32 | DEVRESULTS: XXX
33 | DEVRESULTS: XXX | [27 empty] | Y
34 | Program Income: XXX
35 | [6 empty] | Qualitatiave Studies - Review and submission of Final Reports for USDOL approval | Y | The revision process for the reports has been delayed, but the workplan has been updated according to this delay and we are currently on track to comply with the most recently updated timeline | [12 empty] | OTP 1.1.2.1 Number of reports on promising practices and benefits of social compliance and benefits completed | Y |  |  |  |  | 1.1.6 Sub-award to JE Austin for market analysis | Y
36 | [6 empty] | Third and Fourth Annual Sectoral Workshop of Labor Practices and Risks in Supply Chain - Ecuador and Colombia | Y | [13 empty] | OTP 1.1.3.1 Number of stakeholders reached with the findings of the project’s research | N | Currently under target, but the project ancipates meeting this target in 2024 after diesseminating the results of the qualitative studies |  |  |  | 2.1 Collaborate with FEDEPALMA to highlight issues of child labor, forced labor, and the promotion of workers rights at the annual International Palm Oil Conference | Y
37 | [6 empty] | Fifth Annual Sectoral Workshop of Gender Approach in Palm Oil Sector - Ecuador | Y | [13 empty] | SOTC 1.2.1 Number of suppliers trained by private sector partners | N | A larget part of the delay on meeting this target is due to bud rot which has decreased the universe of palm oil suppliers that can participate in project trainings |  |  |  | 2.2 Provide opportunities for stakeholders from target project countries to attend global events outside the South American region | Y
38 | [6 empty] | A-1.2.2.1 Deliver training on Social Compliance System to private partner companies and their suppliers | Y | [13 empty] | SOTC 1.2.2 Number of private sector partners’ suppliers that complete assessment process | N | A larget part of the delay on meeting this target is due to bud rot which has decreased the universe of palm oil suppliers that can complete the assessment process |  |  |  | 2.3. Organize regional forums in the South American region to share best practices and disseminate knowledge | Y
39 | [6 empty] | A-1.2.2.1.1 Deliver training on Social Compliance System to private partner companies and their suppliers in Peru | Y | [13 empty] | SOTC 1.2.3 Number of private sector partners’ suppliers that develop an improvement plan | Y | On track to meet target by end of project |  |  |  | 2.4 Conduct study tours and workshops for the target project countries | Y
40
41 | GENDER: XXX
42 | [6 empty] | A-1.2.2.2 Provide mentoring on Social Compliance System to private partner companies and their suppliers | Y | [13 empty] | OTP 1.2.1.1 Social compliance toolkits completed | Y |  |  |  |  | 2.5 Provide a virtual platform to share research, lessons, and tools from the project | Y
43 | [6 empty] | A-1.2.2.3 Deliver the Training of Trainers program to private partner companies | Y | [13 empty] | OTP 1.2.2.1 Number of private sector partners and suppliers provided technical assistance | Y | On track to meet target by end of project |  |  |  | 2.6 Identify and promote leading private sector entities that have strong/exemplary human rights programs/standards | Y
44 | [6 empty] | A - 1.2.2.3.1 Deliver the Training of Trainers program to private partner companies in Peru | Y | [13 empty] | OTP 1.2.2.2 Number of people from private sector partners provided technical assistance | Y |  |  |  |  | 3.1 Database Development | Y
45 | [6 empty] | A - 1.2.2.3.2 Deliver the Training of Trainers program to social leaders from community circles | Y | [13 empty] | OTP 1.2.2.3 Percentage of surveyed supply chain workshop participants who demonstrate a change in understanding of labor practices and risks of child labor and forced labor | Y | Target is 80%; will be measured at end of project. Palma Futuro conducted endline surveys during this reporting period; however, the level of participation was lower than anticipated. Only 58 individuals completed the endline survey compared to the 96 who completed the baseline survey. Additionally, the results indicate that only 68.97% of workshop participants demonstrated an improved understanding of labor practices and the risks associated with CL and FL. Several factors may have contributed to these outcomes. Firstly, the personnel responsible for conducting the endline surveys were not always the same individuals who conducted the baseline surveys. While this was expected due to the anticipated turnover over the four-year project duration, it may have influenced the comparability of the results. Secondly, feedback from survey participants has highlighted that the survey language was somewhat confusing. This feedback is valuable and suggests that improvements in survey clarity are necessary to enhance the quality of data collected. Thirdly, many of the survey questions are based on training content delivered at the outset of the project. Given the substantial time gap between these initial training sessions and the endline surveys, it is reasonable to expect challenges in participant recall. Additionally, new project participants may not have had the opportunity to attend these earlier training sessions, further affecting their understanding. |  |  |  | 3.2 Monitoring Guidelines Development | Y
46 | [6 empty] | A -1.2.2.5.2 Deliver training on Social Compliance System to new members of social performance teams in Colombia | Y | [13 empty] | OTP 1.2.3.1 Number of stakeholder organizations provided training directly by the project | Y | Target is 46, will be measured at end of project. In the next reporting period, Palma Futuro will continue advancing towards this target by conducting trainings for additional stakeholder organizations, including the Juntas de Acción Comunal and Juntas Directivas in Colombia and Ecuador. |  |  |  | 3.3. On-going M&E Training | Y
47 | [6 empty] | A -1.2.2.5.2 Deliver training on Social Compliance System to OHS Committees in Colombia | Y | [13 empty] | OTP 1.2.3.2 Number of people from external stakeholder groups provided training directly by the project | Y |  |  |  |  | 3.4 Collection of Reliable Data | Y
48 | [6 empty] | A -1.2.2.5.3 Develop worker circles in Colombia and Ecuador | Y | [13 empty] | OTP 1.2.3.3 Number of communities reached through outreach events | Y |  |  |  |  | 3.5 Pre-Situational Analysis | Y
49 | [6 empty] | A -1.2.2.5.4 Deliver training on Social Compliance System to worker circles in Colombia and Ecuador | Y | [13 empty] | OTP 1.2.3.4 Number of community circles formed to cascade learnings from trainings | N | Current target is 60, actual number is 59. In next reporting period, the project will form Worker Circles in both countries to continue advancing towards this target. |  |  |  | 3.6 Pre-CMEP Workshop | Y
[7 empty] | A - 1.2.2.9.1 Engage Community Assemblies in Colombia and Ecuador and deliver training on social compliance system | Y | [13 empty] | OTP 1.2.3.5 Number of actions taken by community circles to cascade learning | N | Current target is 60, actual number is 53. The project will continue working with community circles in the next reporting period to meet the end-of-project target |  |  |  | 3.7 CMEP Workshops | Y
[7 empty] | A - 1.2.2.9.2 Engage producers' organizations in Colombia and Ecuador and deliver training on social compliance system | Y | [13 empty] | OTC 2.1 Number of organizations that participate in forums where the project presents promising practices and lessons learned | N | Although the actual numbers for this indicator are under target, the project plans to make significant progress towards this indicator's target over the next two reporting periods, after consolidating the project's Handbook and Toolkits, promising practices and lessons learned. |  |  |  | 3.8 Annual CMEP Review Workshop | Y
[7 empty] | A-1.2.2.16.1 Develop a communications strategy for PSPs to disseminate information to internal stakeholders through communication channels with workers | Y | [13 empty] | OTC 2.2 Percentage of surveyed regional study tour participants who demonstrate an increased understanding of SCS promising practices. | Y |  |  |  |  | 3.9 External Evaluations | Y
[7 empty] | Ongoing strategy meetings with Partners and project partners in Colombia/Ecuador | Y | [13 empty] | OTP 2.1.1 Number of regional discussion forums organized in Region | Y |  |  |  |  | 3.10 End-of-Project Final Analysis on CMEP Indicator Data and Overall Results Analysis | Y
[7 empty] | Ongoing budget and workplan updates | Y | [13 empty] | OTP 2.1.2 Number of instances in which project generated material is shared at international or regional forums, or published in reports | N | The project plans to hold/participate in a variety of dissemination events the next reporting period as it finalizes the qualitiative studies and consolidates best practices of the project, in order to meet the end-of-project target.
[7 empty] | Internal meetings and project management | Y | [13 empty] | OTP 2.2.1 Number of webinars hosted by the project | Y |  |  |  |  | `
[7 empty] | Prepare and submit monthly financial reports | Y | [13 empty] | OTP 2.2.2 Number of organizations that participate in webinars hosted or supported by the project | Y
[7 empty] | Prepare and submit quarterly progress reports | Y | [13 empty] | OTP 2.2.3 Number of organizations with formal agreements to participate in the network | Y
[7 empty] | Ongoing training/calibration/workplanning between SAI HQ and Lead Trainers | Y
[7 empty] | Deliver training on gender equity and inclusion to PSPs in Colombia and Ecuador | Y
[7 empty] | Support PSPs on formulation of policies or actions related to gender and inclusion approach | Y
[7 empty] | Webinar 7 to provide a flexible opportunity to target all stakeholders around relevant topics of interest | Y
[7 empty] | Upload information and materials to the Knowledge Management Platform | Y
[7 empty] | Collect data at six-month intervals for performance information | Y
[7 empty] | Monitoring activities to verify consistency with targets reported | Y
[7 empty] | Develop the communications strategy with a special emphasis on the Social Compliance System Handbook and Toolkits and the findings of the project’s research and studies | Y
50
Y

## Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | Social Accountability International |  |  |  | Total Award Amount: | 2332439 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOL420 - Palma Futuro |  |  |  | Total Obligation Amount: | 1903979 | Macarena Jimenez
Subaward Number: | ​SAI SC 2019-01-25 to 2022-09-25 |  |  |  | Cost Share Amount: | N/A
Donor: | USDOL |  |  |  | Leverage Amount: | N/A
CFDA: | 18-1605-2019-2501651819AD20190165000318MILAB0M0000MILB00MILIFH-M9K111- 410043--- |  |  |  | USAID Only: Geographic Code: | N/A
Subaward Start Date: | 2019-01-25 |  |  |  | Key Personnel: | N/A
Subaward End Date: | 2024-05-31 |  |  |  | Approved Indirect Rate(s) %: | 10%
Subaward Point of Contact: | Jane Hwang |  |  |  | Prior Approvals Required: | - The Sub-Awardee shall not use Sub-Agreement funds to (1) procure goods or services over US $10,000 in transaction value without PARTNERS prior approval, or (2) create or transfer ownership of intangible property (including, without limitation, copyrights, patents, trademarks, and other intellectual property) without PARTNERS prior approval in writing. - - Participant support costs are allowable with the prior approval of PARTNERS and USDOL.
POA Point of Contact: | Macarena Jimenez |  |  |  | Treatment of Program Income: | Addition
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2019 | 2019-2022 | 2019-01-25 | 2019-01-25 | ​SAI SC 2019-01-25 to 2022-09-25 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FAgreements%2FSub%2Dawards%2FSAI%2FSub%2DAgreement%2FSubmitted%20to%20Contracts&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32 | Formalize sub-agreement with SAI for implementation of DOL420 Palma Futuro project
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2021 | 2019-2022 | 2021-01-20 | 2021-01-20 | DOL420 Sub-Agreement Modification No.1 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FAgreements%2FSub%2Dawards%2FSAI%2FSub%2DAgreement%2FMod01%2FSAI%20POA%20Palma%20Contract%20Modification%20signature%20page%2016Feb2021%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FAgreements%2FSub%2Dawards%2FSAI%2FSub%2DAgreement%2FMod01 | Increase obligation amount to 916,852 USD
Modification 02 | 2022 | 2019-2023 | 2022-09-29 | 2022-09-29 | ICMOD 210 Mod 002 DOL 420 Econometria S.A. | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FAgreements%2FSub%2Dawards%2FSAI%2FSub%2DAgreement%2FMod%20002%2FICMOD%20210%20Mod%20002%20DOL%20420%20Econometria%20S%2EA%2E%20%281%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FAgreements%2FSub%2Dawards%2FSAI%2FSub%2DAgreement%2FMod%20002 | Extend period of performance to March 31 2023 and increase obligation amount to $1,571,000 USD.
Modification 03 | 2023 | 2019-2023 | 2023-03-30 | 2023-03-30 | SAMOD 96 DOL420 SAI Sub-Award Mod 003 01_25_2019 - 06_30_2023 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FAgreements%2FSub%2Dawards%2FSAI%2FSub%2DAgreement%2FMod03%2FSAMOD%2096%20DOL420%20SAI%20Sub%2DAward%20Mod%20003%2001%5F25%5F2019%20%2D%2006%5F30%5F2023%20%281%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FAgreements%2FSub%2Dawards%2FSAI%2FSub%2DAgreement%2FMod03 | Extend period of performance to June 30, 2023; increase obligation amount to $1,903,979 USD; modify budget category table in Article 5 and total direct cost line on Annex B
Modification 04 | 2023 | 2019-2024 | 2023-06-30 | 2023-06-30 | SAMOD 106 DOL420 SAI Sub-Award Mod 004 01_25_2019 - 05_31_2024 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FAgreements%2FSub%2Dawards%2FSAI%2FSub%2DAgreement%2FMod%2004%2FSAMOD%20106%20DOL420%20SAI%20Sub%2DAward%20Mod%20004%2001%5F25%5F2019%20%2D%2005%5F31%5F2024%20%281%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL420%2FAgreements%2FSub%2Dawards%2FSAI%2FSub%2DAgreement%2FMod%2004 | Extend period of performance to May 31, 2024; update total award amount to $2332,439 USD; update Annex B, detailed budget and update submission dates in Article 13 and Annex D.
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
N/A (Subaward M&E plan incorporated into project CMEP)
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
N/A (Subaward Work plan incorporated into project work plan)
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
N/A
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Compliance Letter Meeting | 2023 | 2019-2024 | 2023-02-15 | N/A |  | https://partnersnet107.sharepoint.com/:w:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7B849F1F2D-0440-4937-A90A-19FBD4AF1E88%7D&file=Notice%20of%20Noncompliance%20Letter_SAI_%20Final.docx&action=default&mobileredirect=true | Meeting to discuss concerns regarding noncompliance, in accordance with the letter sent to SAI (see below)
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Noncompliance Letter sent on 2/28/2023 | 2023 | 2019-2024 | 2022 |  | Late submission of monthly technical reports; failure to reply to outstanding issues and provide Fringe reconciliation; lack of supporting documentation after multiple requests to include in future reports; not sending proof of staff salaries in a timely manner | https://partnersnet107.sharepoint.com/:w:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7B849F1F2D-0440-4937-A90A-19FBD4AF1E88%7D&file=Notice%20of%20Noncompliance%20Letter_SAI_%20Final.docx&action=default&mobileredirect=true | Document outlying compliance concerns and notifying SAI of noncompliance. Notice of 30 days to resolve outstanding issues listed in letter.
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY