## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | Colombia Ports |  |  |  | Total Award Amount: | 5000000 | Program Manager(s) (including dates):
Internal Grant Number: | DOL422 |  |  |  | Total Obligation Amount: | 5000000 | Macarena Jimenez
Award Number: | IL-35742-20-75-K |  |  |  | Cost Share Amount: | N/A
Donor: | USDOL |  |  |  | Leverage Amount: | N/A
CFDA: | 21-1605-2021-2501652021AD20210165000320MILAB0M0000MILB00MILOTLM9K106-410043--- |  |  |  | USAID Only: Geographic Code: | N/A
Award Start Date: | 2020-12-09 |  |  |  | Key Personnel: | Eduardo Bejarano, Maria Catalina Useche
Award End Date: | 2024-12-08 |  |  |  | Approved Indirect Rate(s) %: | 28.28%
Program Director: | Eduardo Bejarano |  |  |  | Prior Approvals Required: | Per 2 CFR 200 and MPG
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Tara Barancik |  |  |  | Treatment of Program Income: | Addition
Agreement Officer (AO)/Grants Officer (GO): | Evan Hughes
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Agreement | 2020 | 2020-2024 | 2020-10-08 | 2020-12-09 | Notice of Award | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL422%2FDonor%2FAward%2FIL%2D35742%20Award%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL422%2FDonor%2FAward | Original award
Cost Extension
Modification 01 | 2022 | 2020-2024 | 2022-01-21 | 2022-02-11 | Award Modification 1 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL422%2FDonor%2FAward%2FMod01%2FIL%2D35742%20Modification%201%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL422%2FDonor%2FAward%2FMod01 | Modification 1 to replace M&E Officer
Modification 02
Modification 03
Modification 04
Modification 05
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
PMP | 2023 | 2020-2024 | 2023-01-31 |  | Colombia Ports Project- Performance Monitoring Plan- Interventions 1, 2 and 3 | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7BC76F40F7-6549-461D-BF1A-C7B84D120755%7D&file=Colombia%20Ports%20Project-%20Performance%20Monitoring%20Plan-%20Interventions%201%2C%202%20and%203.xlsx&action=default&mobileredirect=true | Most recent version of PMP sent to USDOL on Jan 31 2023
| FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
| FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
| FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Work Plan January 2023 | 2023 | 2020-2024 | 2023-01-31 |  | Colombia Ports Project - Work Plan Interventions 1, 2 and 3 | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7BA5D7E71C-C0E0-443C-AAD2-6F4602AF62A6%7D&file=Colombia%20Ports%20Project%20-%20Work%20Plan%20Interventions%201%2C%202%20and%203.xlsx&action=default&mobileredirect=true | Workplan sent to USDOL in response to letter of noncompliance on Jan 31 2023
Most Recently Updated Work Plan (October 2023, submitted with TPR) | 2023 | 2020-2024 | 2023-10-30 | N/A | Annex A - Work Plan CPP Apr 2023 - Sept 2023 | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7BA04F36AC-0369-4D6A-8ADF-9AB6CFB03413%7D&file=Annex%20A%20-%20Work%20Plan%20CPP%20Apr%202023%20-%20Sept%202023.xlsx&action=default&mobileredirect=true | Most recently revised Work Plan sent with October 2023 TPR
Updated workplan submitted with most recent TPR (October 2023)
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
Award funds must not duplicate existing foreign government activities or substitute for activities for which such governments have already assumed responsibility. Any award funds budgeted to support activities by host country governments during the life of the award require USDOL prior approval in accordance with the MPG.
POA is required to meet with USDOL soon after the award is signed to discuss the plans for the overall needs assessment before beginning work on it including the rationale and research and/or data consulted to recommend pilots in Cartagena and Santa Marta as well as a rationale for its recommendations on the commodities to be tracked. As part of the needs assessment at the beginning of the project, the implementer is also required to do a Do No Harm analysis as required by the Funding Opportunity Announcement. The implementer must receive USDOL approval on its plans before beginning the needs assessment.
POA must meet with USDOL soon after the award is signed to further explain its interaction with the various levels of and many relevant offices with the Ministry of Labor, the primary government entity responsible for enforcing Colombian labor laws. Also, as the MOL has limited resources in Buenaventura, the implementer must further explain to USDOL how it plans to engage with the MOL in Buenaventura and how POA plans to work with other government actors in Buenaventura responsible for administering operations in the port related to labor law enforcement, for example the Pension and Parafiscal Management Unit (UGPP) and Superintendent of Ports and Transport
POA must meet with USDOL soon after the award to explain its plans to engage key local stakeholders such as local governments and mayors, and in the port of Buenaventura specifically, how POA will engage with members from the 2017 Civic Strike Committee. This is especially important given that the current mayor of Buenaventura comes from the Civic Strike Committee. As the barriers to achieving the reforms that came out of the 2017 Buenaventura Civic Strike are critical to consider, POA should prepare to detail its plan to overcome these barriers. POA should also prepare to detail how the project will engage with leaders of various port authorities, the Afro-Colombian Labor Council, port workers' unions in Buenaventura, and worker and community organizations to ensure their critical buy-in and support of the project.
Many of the key stakeholders in the port sector, especially in Buenaventura, have strong mistrust, different interests, and often disagree with one another on needed reforms, making tripartite negotiations difficult. Soon after the award is signed, POA must meet with USDOL to detail the strategy to help manage these challenges and the activities POA plans on to overcome these obstacles.
Once the needs assessment is complete, POA will be required to meet with USDOL to present the needs assessment findings. POA is required to receive USDOL’s approval on the ports to do pilot interventions in, commodities to track, and other intervention activities recommended as a result of the needs assessment before it proceeds with interventions and activities.
POA must submit to USDOL security protocols, which include but are not limited to COVID19 protocols as well as general safety protocols, for POA, sub-awardee, and any consultant staff members working on project activities. An initial set of protocols must be submitted to USDOL by February 15, 2021 that would take address any physical security concerns but largely focus on COVID-19 protocols for staff in Colombia. Considering that the COVID-19 situation may be different in different parts of Colombia, protocols relevant to different parts of Colombia should be considered at the onset of the project and reevaluated during project implementation with updated protocols submitted to USDOL as necessary. USDOL expects that POA would consult any local security entities and any relevant local health authorities to assist with these protocols. After the security entity or entities conduct(s) the Security/Risk Analysis, POA must also submit the findings to USDOL and submit updated security protocols at that time based on the Security/Risk Analysis findings. As the project implementation is ongoing, POA must keep abreast of any known security risks with continued coordination with local security entities as appropriate. POA must advise USDOL of any known security risks that would affect project staff and/or stakeholders. USDOL will have a meeting with POA soon after the award is signed to discuss this
Soon after the award is signed, POA will be required to meet with USDOL to provide more information on its plans for its suggested Sustainable Union Management/Sustainable Unionism activities before work begins on those activities
POA will be required to liaise and work with, when appropriate, other current and/or future project teams implementing U.S. Government-funded projects in Colombia.
POA will be required to manage all aspects of project work related to its sub-awardees and any contractors, including, but not limited to, the scheduling, planning, and facilitation of meetings and/or activities with USDOL and/or U.S. Embassy involvement.
POA will be required to manage all aspects of project work related to its sub-awardees and any contractors, including, but not limited to, the scheduling, planning, and facilitation of meetings and/or activities with USDOL and/or U.S. Embassy involvement.
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Biweekly meeting with USDOL GOR | 2023 | 2020-2024 | 2023-10-03 | N/A | N/A | Link to Meeting Notes | Biweekly meeting to provide updates on project implementation
Biweekly meeting with USDOL GOR | 2023 | 2020-2024 | 2023-10-17 | N/A | N/A |  | Biweekly meeting to provide updates on project implementation
Biweekly meeting with USDOL GOR | 2023 | 2020-2024 | 2023-10-31 | N/A | N/A | Link to Meeting Notes | Biweekly meeting to provide updates on project implementation
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Compliance Matrix Details
Breakdown of Award Requirements
| Award Terms & Conditions | Compliant Y/N | Comments | Program Description | Compliant Y/N | Comments | Work Plan FY2023 | Compliant Y/N | Comments | Workplan FY2024 | Compliant Y/N | Comments | Work Plan FYXX | Compliant Y/N | Comments | Workplan FYXX | Compliant Y/N | Comments | MEL Plan FY2023 | Compliant Y/N | Comments | Indicators | Compliant Y/N | Comments | Environmental Mitigation and Monitoring Plan - EMMP | Compliant Y/N | Comments | Activities in Budget Narrative | Compliant Y/N | Comments
1 | Financial Reporting: Quarterly FFRS | Y |  | Description: XXX |  |  | Develop contracts' procurement plan for the implementation of Interventions 1-3 | Y |  | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | Updated PMP sent in response compliance letter on January 31 2023 | Y | Updated PMP approved by USDOL | # of collective structures or institutions related to the port sector that have institutionalized more effective processes to improve labor compliance in the port sector. | Y | This indicator will be measured by the end of the project. |  |  |  | Activity 1.1 -Develop a Compilation on the main pronouncements of Colombia´s Supreme Court of Justice and Constitutional Court in relation to labor intermediation and outsourcing (Compilation) to shed light onto the nature and limits of labor intermediation and outsourcing | Y
2 | Financial Reporting: XXX |  |  | Geographic Scope: XXX |  |  | Gender Considerations: XXX |  |  | Gender Considerations: XXX |  |  | Gender Considerations: XXX |  |  | Gender Considerations: XXX
3 | Financial Reporting: XXX |  |  | Recommend organizing by component/activity |  |  | Sustainability: XXX |  |  | Sustainability: XXX |  |  | Sustainability: XXX |  |  | Sustainability: XXX
4 | Financial Reporting: XXX
5 | Accrual Reporting | Y |  |  |  |  | Develop procurement plan for sub-awards for Outcome 2 | Y | [13 empty] | # of collective structures or institutions within the port sector with improved delivery of services associated with improved compliance with labor law. | Y | This indicator will be measured by the end of the project. |  |  |  | Activity 1.2 Analyze the Compilation with a selected group of experts from each sector (workers, business sector and the Ministry of Labor-MOL) to identify key information for the development of a Guideline that will serve as an information/education tool | Y
6 | Substantial Involvement | Y | The project complies by meeting regularly with the USDOL GOR to provide updates on project implementation and receiving and responding to USDOL's input, in addition to sharing project deliverables for USDOL approval |  |  |  | Develop project communication plan | Y | Completed but with delay, communications officer was hired later than expected | [12 empty] | # port workers demonstrating increased demand for services associated with improved labor law compliance. | Y | This indicator will be measured by the end of the project. |  |  |  | Activity 1.3 Organize a Tripartite Workshop with workers, business sector and government representatives to analyze the concepts from the Guideline, identify their relevance for the port sector, develop key messages and build stakeholder-specific Action Plans for the business sector and workers to design communication materials, a dissemination strategy, and a monitoring plan to measure its effectiveness and review as necessary. | Y | The original workplan had a shorter implementation period, but this activity is taking longer than expected.
7 | Accrual Reporting: XXX
8 | Accrual Reporting: XXX
9 | Projections to Donor: 2023 projections
10 | Projections to Donor: XXX
11 | Projections to Donor: XXX
12 | Projections to Donor: XXX
13 | Annual Implementation Plans:
14 | Annual Implementation Plans: XXX
15 | Annual Implementation Plans: XXX
16 | Annual Implementation Plans: XXX
17 | Activity Monitoring and Evaluation (AMEP Plan): XXX
18 | Activity Monitoring and Evaluation (AMEP Plan): XXX
19 | Semi-Annual reports: April - October 2023 Technical Progress Report (due October 31) | Y | Most recently submitted TPR was sent on time (October 30 2023) |  |  |  | Submit Sustainability Strategy | Y | [13 empty] | # port key stakeholders with increased linkages that enables them to better address labor law compliance issues, claim their rights or fulfill their duties. | N | Due to challenges faced in implementation, the project identified the need to revise its original strategy for this indicator. Consequently, activities linked to this indicator, such as monthly meetings with the Champions, have been temporarily suspended while the project formulates a new work plan and strategy. The new work plan with revised activities for the Champions strategy will be implemented from October 2023 onwards. |  |  |  | Activity 1.4 Implement and monitor the stakeholder-specific Action Plans with periodic group and plenary meetings to share progress and adjust scope and strategies as necessary. | Y | Activity 1.4 was affected by Activity 1.3 delays. Overall implementation for Intervention 1 remains on time.
20 | Quarterly Performance Reports: XXX
21 | Quarterly Performance Reports: XXX
22 | Quarterly Performance Reports: XXX
23 | Quarterly Performance Reports: XXX
24 | Branding (Social Media, use of USDOL seal, funding acknolwedgement, disclaimer, press releases/major events) | Y | The project complies with all branding requirements set forth in the MPG |  |  |  | Submit Federal Financial Report (FFR) Standard Form (SF) 425 | Y | [13 empty] | # port key stakeholders with increased capacity that enables them to better address labor law compliance issues, claim their rights or fulfill their duties. | Y |  |  |  |  | Activity 2.1 Identify key stakeholders to constitute formal social dialogue spaces for the port sector at the district and state levels. These instances will be extensions of social dialogue mechanisms where the ports sector is not currently represented: the Comité Asesor del Sector Portuario (CASP) in Buenaventura and the Subcomisiones Departamentales de Concertación de Políticas Salariales y Laborales (SDCPSLs) in Atlántico (Barranquilla), Bolívar (Cartagena) and Magdalena (Santa Marta). | Y | Completed but took longer than expected
25 | Annual Reports: XXX
26 | Final Program Report: XXX
27 | Short-Term Consultant Reports, Technical Briefs/Reports, Special and External Reports: XXX
28 | Short-Term Consultant Reports, Technical Briefs/Reports, Special and External Reports: XXX
29 | Closeout Plan: XXX
30 | Development Experience Clearinghouse Requirements: XXX
31 | Foreign Tax Reports: XXX
32 | DEVRESULTS: XXX
33 | DEVRESULTS: XXX
34 | Program Income: XXX
35 | [6 empty] | Submit full Technical Progress Report (TPR) | Y | [13 empty] | # of collective structures or institutions within the port sector with increased capacity that enables them to better address labor law compliance issues. | Y |  |  |  |  | Activity 2.2 Engage with the MOL for the inclusion of port related issues identified by the stakeholders into their existing Social Dialogue Plans (SDPs) under each formal instance of social dialogue. | Y | In progress with delays due to pending MOL approval
36 | [6 empty] | 1.3.1 Present Assessment Findings to Relevant Stakeholders – Second Phase | Y | [13 empty] | # of collective structures or institutions within the port sector with tools and resources that enable them to better address labor law compliance issues. | Y |  |  |  |  | Activity 2.3 Support the implementation of the SDPs in relation to activities relevant to the port sector. | Y | In progress, extended implementation time for sustainability
37 | [6 empty] | Submit Assessment to USDOL for review and approval | Y | [13 empty] | # of collective structures or institutions within the port sector with increased motivation to address labor compliance issues. | N | The Tripartite Pedagogical Workshop was delayed by one month, delaying other related activities. The workshop took place in August 2023 and communication materials are currently being developed. By December 2023, this indicator will be up to date. |  |  |  | Activity 2.4 Conduct a mapping exercise in Buenaventura to identify key individuals (Champions) among the various stakeholders that can become agents of change and dialogue promoters. | Y
38 | [6 empty] | Socialization of the Guideline and communications material with stakeholders in Buenaventura, Barranquilla, Cartagena and Santa Marta | Y | [19 empty] | Activity 2.5 Organize a workshop with the Champions to identify areas of mutual interest that can propel an action oriented and specific social dialogue to work on solutions regarding working conditions at the port. | Y
39 | [6 empty] | Development of communication materials with each stakeholder group | Y | Communications materials' development was affected by tripartite workshop delays. More time is required for material's development and distribution. | [18 empty] | Activity 2.6 Develop a strategy to facilitate those action-oriented dialogues and implement the strategy in the most effective way for each case (formal and informal conversations, workshops, group meetings, etc.). | Y | In progress as planned
40 | [6 empty] | Ongoing communication, periodic group and plenary meetings to share progress
41 | GENDER: XXX | [5 empty] | Dissemination by CPP of communication materials through social media, digital channels, radios, project activities, etc.
42 | [6 empty] | Ongoing communication, periodic group and plenary meetings to share progress | Y | Meetings will start in October 2023-January 2024 once the communications material are available. | [18 empty] | Activity 3.1 Conduct a participatory workshop to gather information on capacity gaps, needs and interests of the existing Worker Organizations (WOs) in the Buenaventura port. | Y
43 | [6 empty] | Dissemination by CPP of communication materials through social media, digital channels, radios, project activities, etc. | Y | Delays in material development affected dissemination plans. | [18 empty] | Activity 3.2 Use workshop’s input to develop a training plan, selecting useful topics according to each WO level of development. | Y | In progress with delays due to selection of implementing partner taking longer than planned
44 | [6 empty] | Presentation of the results of the Comprehensive Assessment in the Mesa de Diálogo and in the Subcommissions | Y | The socialization process began once the Assessment was approved by USDOL ( June 27, 2023), and the material was prepared in July-August. | [18 empty] | Activity 3.3 Implement the training plan using participatory and creative methodologies and focusing on WOs ability to communicate and apply the new learning and self-assess results. | Y | Activities slightly delayed due to selection of implementing partner
45 | [6 empty] | Support the Mesa de Diálogo in the elaboration of its SDP, including the port sector related issues | Y | First draft of the SDP pending MOL approval | [18 empty] | Activity 3.4 Introduce and implement USAID’s Organizational Capacity Assessment Tool (OCA) for each union at the Buenaventura port, to self-assess and systematically work on strengthening their internal capacities in the areas covered by the methodology. | Y | In progress with delays, selection of OCA consultant took longer than expected
46 | [6 empty] | Logistics support to guarantee the regularity of the meetings | Y
47 | [6 empty] | Workshops on fundamental labor rights, social dialogue, collective bargaining, resolution of labor disputes, mediation, labor law, social security, labor intermediation, outsourcing, labor formalization, presentation of good practices on social dialogue and resolution of labor collective conflicts, among others | Y
48 | [6 empty] | Exchange of international practices in relevant supply chains | Y | Postponed to first focus on strengthening the Subcommission
49 | [6 empty] | Hold meetings with stakeholders identified by Champions to work on solutions | Y | Meetings have been held but targets have not been met due to challenges in motiviating champions; new strategy is being developed
[7 empty] | Hiring of implementing partner to develop and implement a training plan for port workers | Y | Completed with delay
[7 empty] | Development of training plan | Y | The implementing partner selection process will delay the training plan
[7 empty] | Implementation of the training plan in Buenaventura | Y | The implementing partner selection process has delayed the activity
[7 empty] | Application of new learnings by the WOs in Buenaventura | Y | The implementing partner selection process has delayed the activity
[7 empty] | Implementation of the OCA Tool with each of the four WOs in Buenaventura: Union Portuaria (UP), the Sindicato Nacional de Trabajadores de Rama, Servicios de la Industria del Trabajo y Logística de Colombia (SNTT), the Sindicato de la Industria de la Actividad de los Trabajadores de la Rama Portuaria, Transporte y su Logística Colombiana (SINAPORTLC) and the Sindicato de Trabajadores Portuarios (STP) | Y | CPP determined more time will be required for the implementation of this activity which has extended to the end of 2024.
[7 empty] | Support the implementation of the Action Plans resulting from the OCA elaborated by each WO in Buenaventura | Y | The development of Action Plans is taking longer than expected and their implementation will initiate in October, 2023. The implementation has been extended until the end of 2024. | [18 empty] | `
[7 empty] | Conduct meetings with USDOL to review project implementation | Y
[7 empty] | Plan and conduct baseline evaluation | Y
[7 empty] | Collect and analyze Learning Agenda information | Y
[7 empty] | Ongoing monitoring of data collection and submission to M&E Officer | Y
[7 empty] | Ongoing data quality review by M&E Officer | Y
[7 empty] | Regular monitoring visits to project offices at prioritized ports | Y
[7 empty] | Collect qualitative data to review progress and adapt PMP | Y
Y