## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | Mexico Awareness-Raising Project |  |  |  | Total Award Amount: | 10000000 | Program Manager(s) (including dates):
Internal Grant Number: | DOL423 |  |  |  | Total Obligation Amount: | n/a | Carmen Pena (2021)
Award Number: | IL-35868-21-75-K |  |  |  | Cost Share Amount: | n/a | Macarena Jimenez, (2022-present)
Donor: | U.S. Department of Labor |  |  |  | Leverage Amount: | n/a
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Award Start Date: | 2021-01-01 |  |  |  | Key Personnel: | Ingrid Ceballos, Luis Madrid
Award End Date: | 2025-06-15 |  |  |  | Approved Indirect Rate(s) %: | 28.28% (NICRA)
Program Director: | Ingrid Ceballos |  |  |  | Prior Approvals Required:
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Carolina Chavez, chavez.carolina@dol.gov |  |  |  | Treatment of Program Income: | Addition
Agreement Officer (AO)/Grants Officer (GO): | Bradley Sickles, sickles.bradley.a@dol.gov
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Agreement | 2021 | 2021-2025 | 2023-10-09 | 2021-01-01 | IL-35868 Base Award | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FDonor%2FAward%2FIL%2D35868%20Base%20Award%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FDonor%2FAward | DOL423 Base Award
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2022 | 2021-2025 | 2022-05-20 |  | IL-35868 Modification1 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FDonor%2FProject%20Revisions%2F2%2E%20Project%20Revision%2D%20May%202022&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32 | Mod1 to replace Project Director and M&E Officer
Modification 02 | 2022 | 2021-2025 | 2022-09-13 | 2022-09-20 | IL-35868 Modification2 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FDonor%2FProject%20Revisions%2F3%2E%20Project%20Revision%20%2D%20September%202022%2FApproved%20by%20USDOL%2FIL%2D35868%2D21%2D75%2DK%20Modification%202%5B26%5D%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FDonor%2FProject%20Revisions%2F3%2E%20Project%20Revision%20%2D%20September%202022%2FApproved%20by%20USDOL | Mod2 to replace Project Director
Modification 03 | 2023 | 2021-2025 | 2023-06-15 | 2023-08-03 | IL-35868 Modification3 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FDonor%2FProject%20Revisions%2F4%2E%20Project%20Revision%20%2D%20June%202023%2FDonor%20Approval%2FIL358682175K%5FMod%5F3%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FDonor%2FProject%20Revisions%2F4%2E%20Project%20Revision%20%2D%20June%202023%2FDonor%20Approval | Replace M&E Officer
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | 2021 | 2021-2025 | 2021-04-16 | 2021-10-05 | Mexico Awareness Raising Performance Monitoring Plan | https://partnersnet107.sharepoint.com/:w:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7B8B321A46-51A9-4E1A-B5F7-0004E439A6E2%7D&file=Mexico%20Awareness%20Raising%20Performance%20Monitoring%20Plan.docx&action=default&mobileredirect=true | Original M&E Plan
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP | FY2021 | 2021-2025 | 2021-04-16 | 2021-10-05 | COULD NOT FIND WORK PLAN | COULD NOT FIND WORKPLAN
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Compliance Matrix Details
Breakdown of Award Requirements
| Award Terms & Conditions | Compliant Y/N | Comments | Program Description | Compliant Y/N | Comments | Work Plan FY2021-2025 | Compliant Y/N | Comments | Workplan FY2022 | Compliant Y/N | Comments | Work Plan FYXX | Compliant Y/N | Comments | Workplan FYXX | Compliant Y/N | Comments | MEL Plan FY2021-2025 | Compliant Y/N | Comments | Indicators | Compliant Y/N | Comments | Environmental Mitigation and Monitoring Plan - EMMP | Compliant Y/N | Comments | Activities in Budget Narrative | Compliant Y/N | Comments
1 | Financial Reporting:Quarterly Federal Financial Report | Y |  | MAP integrates and expands upon existing efforts in Mexico to promote information about the 2019 Mexican Labor Reform. Partners is collaborating with implementing partner SAI, a highly experienced international organization in advancing human rights in the workplace. On the local level, the project’s sub-awardees include CDM and the Comité Fronterizo de Obreras y Obreros (CFO). In line with USDOL programming, the project’s key objectives are the following: Increasing the understanding of workers, employers, and union leaders on how to utilize Mexico’s new labor systems to protect labor rights and effectively address labor disputes. Build the capacity of the federal and state level Secretariat of Labor and Social Welfare (STPS) staff and constituents from key institutions to conduct outreach regarding labor rights and implementation of the labor reforms among target audiences. | Y |  | 1.1 Baseline Survey of Key Stakeholder Groups 1.2 Expand and enhance STPS website 1.3 Mass and social media campaigns for workers and the general populace 1.4 Public Forums for the public, workers, and union leaders 1.5 Educational Workshops for Workers and Union Leaders 1.6 Trainings for union leadership 1.7 Industry sharing and communications platforms 1.8 On-Line Webinars for the Business Sector 1.9 Summits w/ STPS for Sectoral Business Associations 1.10 Exchanges on Best Practices for Labor Reform Related Best Practices 1.11 Strategy and campaign to disseminate USDOL’s Hotline 2.1 Communications capacity assessment of STPS and key institutions 2.2 Capacity-Building Action Plans for STPS units and key institutions 2.2.1 Development of website for Local Conciliation centers 2.3 Delivery of Capacity-Building Activities for STPS units and key institutions 2.4 Strengthened Coordination across STPS and Key Institutions on communication planning | y | This is the most recent work plan submitted in MAP's October 2023, and is up to date | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | NEED MOST RECENT M&E PLAN SUBMITTED 2022 | Y | Overall on track with M&E plab | 4b. Ind. 1: Number (#) of key institutions that promote the labor reform. | Y | Target: 40 Actual: 52 |  |  |  | 1.2: Baseline Survey of Key Stakeholder Groups (Pre-Program) | Y
24 | Semi-Annual reports: Bi-Annual Technical Progress Report | Y | [19 empty] | 4b. Number (#) of collective structures or institutions within a system with increased motivation to address labor rights issues, claim their rights or fulfill their duties | [5 empty] | 1.3 Development of comprehensive STPS website for multiple audiences | Y
26 | Final Program Report: Final Techncial Progress Report | Y | [19 empty] | 2a. Ind. 2: Number (#) of stakeholders with increased understanding of Mexico’s labor reform and how to protect labor rights and effectively address labor disputes. | N | Target: 2,520 Actual: 825 |  |  |  | 1.4 Mass and social media campaigns for workers and the general populace | Y
45 | [21 empty] | 2a. Number (#) of individual actors within a system with increased capacity that enables them to better address labor rights issues, claim their rights or fulfill their duties | [5 empty] | 1.5 Public Forums for the public, workers, and union leaders | Y
46 | [21 empty] | 4a. Ind. 3: Number (#) of maquiladora worker trainers (promoters) completing the GEMA program. | N | Target: 100 Actual: 25 |  |  |  | 1.6 Educational Workshops for Workers and Union Leaders | Y
47 | [21 empty] | 4a. Number (#) of individual actors within a system with increased motivation to address labor rights issues, claim their rights or fulfill their duties | [5 empty] | 1.7 Trainings for union leadership | Y
48 | [21 empty] | 1a. Ind. 4: Number (#) of participants in public forums with increased access to information on the labor reform. | Y | Target: 3,500 Actual: 4,494 |  |  |  | 1.8 Two-way messaging for employers | N
49 | [21 empty] | 1a. Number (#) of individual actors within a system with improved linkages that enable them to better address labor rights issues, claim their rights or fulfill their duties | [5 empty] | 1.9 On-Line Webinars for the Business Sector | Y
50 | [21 empty] | 9a. Ind. 5: Percentage (%) of union leaders who completed project-led trainings that take action as a result of the training. | N | Target: 104 Actual: 7 |  |  |  | 1.10 Two-Day In-Person Summits w/ STPS for Sectoral Business Associations | N
[22 empty] | 9a. Number (#) of individual actors within a system that have adopted behaviors associated with improved workers’ rights | [5 empty] | 1.11 Exchanges on Best Practices for FOA and Gender | Y
[22 empty] | 2a. Ind. 6: Number (#) of union leaders completing trainings on the labor reform. | Y | Target: 690 Actual: 585 |  |  |  | 1.12 Monitoring and Development of USMCA Cases | N
[22 empty] | 2a. Number (#) of individual actors within a system with increased capacity that enables them to better address labor rights issues, claim their rights or fulfill their duties | [5 empty] | 2.2 Initial communications capacity assessment of STPS & peer institutions | Y
[22 empty] | 1a. Ind. 7: Number (#) of workers that access resources available through the project’s social media awareness raising campaign. | Y | Target: 4M Actual: 36M |  |  |  | 2.3 Construction of Capacity-Building Action Plans for STPS | Y
[22 empty] | 1a. Number (#) of individual actors within a system with improved linkages that enable them to better address labor rights issues, claim their rights or fulfill their duties | N | Target: 100 Actual: 15 |  |  |  | 2.4 Delivery of Capacity-Building Activities | Y
[22 empty] | 1a. Ind. 8: Number (#) of employer exchanges of labor reform related best practices. | [5 empty] | 2.5 Communication and Media Outreach Technical Training Program | Y
[22 empty] | 1a. Number (#) of individual actors within a system with improved linkages that enable them to better address labor rights issues, claim their rights or fulfill their duties | [5 empty] | 2.6 Strengthened Coordination across STPS and peers on communication planning | Y
[22 empty] | 1b. Ind. 9: Number (#) of collective structures or institutions within a system with improved linkages that enable them to better address labor rights issues, claim their rights or fulfill their duties. | Y | Target:10 Actual: 15
1b. Number (#) of collective structures or institutions within a system with improved linkages that enable them to better address labor rights issues, claim their rights or fulfill their duties
[22 empty] | 2a. Ind. 10: Number (#) of officials from federal and state STPS and other labor institutions with strengthened technical capacities to conduct outreach on labor reform. | Y | Target: 20 Actual: 94
2a. Number (#) of individual actors within a system with increased capacity that enables them to better address labor rights issues, claim their rights or fulfill their duties
[22 empty] | 10. Ind. 11: Number (#) of actions to promote communication coordination between STPS and labor institutions. | Y | Target: 36 Actual: 32
10. Ind. 11: Number (#) of actions to promote communication coordination between STPS and labor institutions.
[22 empty] | 11. Ind. 12: Number (#) of individuals from the general public reached by content published on STPS and other labor institutions’ websites and social media networks, aimed at informing employers, unions, and workers about the labor reform. | Y | Target: 100k Actual: 3M
11. Ind. 12: Number (#) of individuals from the general public reached by content published on STPS and other labor institutions’ websites and social media networks, aimed at informing employers, unions, and workers about the labor reform.
[22 empty] | 12. Ind. 13: Number (#) of communications capacity building activities developed with STPS and key institutions. | Y | Target: 10 Actual: 12
12. Ind. 13: Number (#) of communications capacity building activities developed with STPS and key institutions.

## CDM Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | Mexico Awareness Raisin between POA and CDM |  |  |  | Total Award Amount: | $794,162.00 USD | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOL423 |  |  |  | Total Obligation Amount: | $378,696 USD | Carmen Pena (2021)
Subaward Number: | DOL423-2021-02 |  |  |  | Cost Share Amount: | 0 | Macarena Jimenez (2022-present)
Donor: | U.S. Department of Labor |  |  |  | Leverage Amount: | 0
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2021-10-01 |  |  |  | Key Personnel: | Macarena Jimenez, Ingrid Ceballos
Subaward End Date: | 2024-12-31 |  |  |  | Approved Indirect Rate(s) %: | 10% de minimus
Subaward Point of Contact: | Rachel Micah Jones, rachel@cdmigrante.org |  |  |  | Prior Approvals Required:
POA Point of Contact: | Ingrid Ceballos, iceballos@partners.net |  |  |  | Treatment of Program Income: | Addition
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2021 | 2021-2024 | 2021-08-12 | 2021-12-16 | Mexico Awareness Raisin between POA and CDM | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FFully%20Executed%2FSubaward%2023%20DOL423%20Subaward%20CDM%202021%2D10%2D01%20to%202024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FFully%20Executed | Original Award
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2022 | 2021-2024 | 2022-07-15 | 2022-10-25 | Sub-Grant Agreement Modification No. 001 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FMods%2FMod01%2FSAMOD%2048%20DOL423%20CDM%20Sub%2DAward%20Mod001%202021%2D10%2D01%20%2D%202024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FMods%2FMod01 | Increase obligated amount, change POA POC, eliminate bi-annual technical report requirement, change submission date of monthly financial report
Modification 02 | 2022 | 2021-2024 | 2022-11-08 | 2022-12-01 | Sub-Grant Agreement Modification No. 002 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FMods%2FMod02%2FSAMOD%2064%20DOL423%20CDM%20Sub%2DAward%20Mod002%202021%2D10%2D01%20%2D%202024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FMods%2FMod02 | Increase obligated amount, change POA POC
Modification 03 | 2022 | 2021-2024 | 2022-12-22 | 2023-02-08 | Sub-Grant Agreement Modification No. 003 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FMods%2FMod03%2FSAMOD%2075%20DOL423%20CDM%20Sub%2DAward%20Mod003%202021%2D10%2D01%20%2D%202024%2D12%2D31%20%282%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FMods%2FMod03 | Increase obligated amount
Modification 04 | 2023 | 2021-2024 | 2023-05-03 | 2023-05-05 | Sub-Grant Agreement Modification No. 004 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FMods%2FMod04&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32 | Increase Obligated amount
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | 2021 | 2021-2024 | 2021-08-12 | 2021-12-16 | Mexico Awareness Raisin between POA and CDM | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FFully%20Executed%2FSubaward%2023%20DOL423%20Subaward%20CDM%202021%2D10%2D01%20to%202024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FFully%20Executed | Original Award
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | 2021 | 2021-2024 | 2021-08-12 | 2021-12-16 | Mexico Awareness Raisin between POA and CDM | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FFully%20Executed%2FSubaward%2023%20DOL423%20Subaward%20CDM%202021%2D10%2D01%20to%202024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCDM%2FSub%2DAward%2FFully%20Executed | Original Award
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## CFO Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | Mexico Awareness Raising Project between POA and CFO |  |  |  | Total Award Amount: | $329,498.00 USD | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOL423 |  |  |  | Total Obligation Amount: | $178,508.50 USD | Carmen Pena (2021)
Subaward Number: | DOL423-2021-03 |  |  |  | Cost Share Amount: | 0 | Macarena Jimenez (2022-present)
Donor: | U.S. Department of Labor |  |  |  | Leverage Amount: | 0
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2021-10-01 |  |  |  | Key Personnel: | Macarena Jimenez, Ingrid Ceballos
Subaward End Date: | 2024-12-31 |  |  |  | Approved Indirect Rate(s) %: | 10% de minimus
Subaward Point of Contact: | Julia Quinonez, cfomaquiladoras@prodigy.net.mx |  |  |  | Prior Approvals Required:
POA Point of Contact: | Ingrid Ceballos, iceballos@partners.net |  |  |  | Treatment of Program Income: | Addition
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2021 | 2021-2024 | 2021-08-19 | 2021-11-11 | Mexico Awareness Raising Project between POA and CFO | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2FFully%20Executed%2FSubaward%2027%20DOL423%20Subaward%20CFO%202021%2D10%2D1%20to%202024%2D12%2D31%20Bilingual%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2FFully%20Executed | original Award
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2021 | 2021-2024 | 2022-02-01 | 2022-02-04 | Sub-Agreement Modification Modification No. 02 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod01%2FSAMOD%2023%20DOL423%20CFO%20Mod01%202021%2D10%2D01%20to%202024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod01 | Increase Obligation Amount
Modification 02 | 2022 | 2021-2024 | 2022-04-15 | 2022-10-20 | Sub-Agreement Modification Modification No. 02 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod02%2FSAMOD%2046%20DOL423%20CFO%20Sub%2DAward%20Mod002%202021%2D10%2D01%20%2D2024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod02 | Increase obligation amount, change POA POC, eliminate requirement of a bi-annual tech report, change monthy financial report submission date
Modification 03 | 2022 | 2021-2024 | 2022-11-08 | 2022-12-01 | Sub-Agreement Modification Modification No. 03 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod03%2FSAMOD%2066%20DOL423%20CFO%20Sub%2DAward%20Mod003%202021%2D10%2D01%20%2D2024%2D12%2D31%20%282%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod03 | Increase obligation amount, change POA POC
Modification 04 | 2023 | 2021-2024 | 2023-01-13 | 2023-02-08 | Sub-Agreement Modification Modification No. 04 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod04%2FSAMOD%2079%20DOL423%20CFO%20Sub%2DAward%20Mod%20004%20%202021%2D10%2D01%20%2D2024%2D12%2D31%20%282%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod04 | Increase obligation amount
Modification 05 | 2023 | 2021-2024 | 2023-05-03 | 2023-05-15 | Sub-Agreement Modification Modification No. 05 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod05%2FSAMOD%20100%20DOL423%20CFO%20Sub%2DAward%20Mod%20005%20%202021%2D10%2D01%20%2D2024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod05 | Increase obligation amount
Modification 06 | 2023 | 2021-2024 | 2023-10-03 | 2023-10-06 | Sub-Agreement Modification Modification No. 06 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod06%2FDOL423%20CFO%20mod%20006%20text%20for%20mod%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2F%5FMods%2FMod06 | Increase obligation amount
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | 2021 | 2021-2024 | 2021-08-19 | 2021-11-11 | Mexico Awareness Raising Project between POA and CFO | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2FFully%20Executed%2FSubaward%2027%20DOL423%20Subaward%20CFO%202021%2D10%2D1%20to%202024%2D12%2D31%20Bilingual%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2FFully%20Executed | original Award
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | 2021 | 2021-2024 | 2021-08-19 | 2021-11-11 | Mexico Awareness Raising Project between POA and CFO | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2FFully%20Executed%2FSubaward%2027%20DOL423%20Subaward%20CFO%202021%2D10%2D1%20to%202024%2D12%2D31%20Bilingual%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FCFO%2FSub%2DAward%2FFully%20Executed | original Award
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## SAI Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | Mexico Awareness Raising Project between POA and SAI |  |  |  | Total Award Amount: | $703,801 USD | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOL423 |  |  |  | Total Obligation Amount: | $320,844.00 USD | Carmen Pena (2021)
Subaward Number: | DOL423-2021-01 |  |  |  | Cost Share Amount: | 0 | Macarena Jimenez (2022-present)
Donor: | U.S. Department of Labor |  |  |  | Leverage Amount: | 0
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: |  |  | 2021-10-01 |  | Key Personnel: | Macarena Jimenez, Ingrid Ceballos
Subaward End Date: | 2024-12-31 |  |  |  | Approved Indirect Rate(s) %: | 10% de minimus
Subaward Point of Contact: | Louis Vanegas, lvanegas@sa-intl.org |  |  |  | Prior Approvals Required:
POA Point of Contact: | Ingrid Ceballos, iceballos@partners.net |  |  |  | Treatment of Program Income: | Addition
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2021 | 2021-2024 | 2021-08-12 | 2022-02-04 | Mexico Awareness Raising Project between POA and SAI | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FFully%20Executed%2FSubaward%2024%20DOL423%20Subaward%20SAI%202021%2D10%2D01%20to%202024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FFully%20Executed | Original Award
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2022 | 2021-2024 | 2022-03-01 | 2022-11-11 | Sub-Grant Agreement Modification No. 01 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FMods%2FMod01%2FSAMOD%2047%20DOL423%20Sub%20Award%20Modification%20SAI%2010%2D01%2D2021%20%2D%2012%2D31%2D2024%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FMods%2FMod01 | Modification to Article 5: Amount of Award, Estimated Cost, and Budget; Increase total obligated amount
Modification 02 | 2023 | 2021-2024 | 2023-02-27 | 2023-06-26 | Sub-Grant Agreement Modification No. 02 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FMods%2FMod02%2FSAMOD%2088%20DOL423%20SAI%20Sub%20Award%20Mod%20002%2010%2D01%2D2021%20%2D%2012%2D31%2D2024%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FMods%2FMod02 | Increase total obligated amount, change POA POC, Change due date of monthyl financial reports from 5th to 7th
Modification 03 | 2023 | 2021-2024 | 2023-08-25 | 2023-11-06 | Sub-Grant Agreement Modification No. 03 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FMods%2FMod03%2FFully%20Executed%2FSAMOD%20113%20DOL423%20SAI%20Subaward%20Mod%20003%2010%2D01%2D2021%20%2D%2012%2D31%2D2024%20%282%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FMods%2FMod03%2FFully%20Executed | Adjust SAI's SOW and reduce total award amount to reflect delays in implementation and shift in project strategy
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | 2021 | 2021-2024 | 2021-08-12 | 2022-02-04 | Mexico Awareness Raising Project between POA and SAI | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FFully%20Executed%2FSubaward%2024%20DOL423%20Subaward%20SAI%202021%2D10%2D01%20to%202024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FFully%20Executed | Original Award
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | 2021 | 2021-2024 | 2021-08-12 | 2022-02-04 | Mexico Awareness Raising Project between POA and SAI | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FFully%20Executed%2FSubaward%2024%20DOL423%20Subaward%20SAI%202021%2D10%2D01%20to%202024%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL423%2FAgreements%2FSub%2DAwards%2FSAI%2FSub%2DAward%2FFully%20Executed | Original Award
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Missing financial reports and constant delays in monthly financial performance | 2023 |  | 2023-02-01 |  | Missing financial reports from 2022; consistently late and incorrect financial reporting |  | SAI sent letter of noncompliance to submit missing reports
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY