## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | Improving Substantive Gender Equality in the Mexican Workplace |  |  |  | Total Award Amount: | $10,000,000 USD | Program Manager(s) (including dates):
Internal Grant Number: | DOL425 |  |  |  | Total Obligation Amount: |  | Macarena Jimenez, 2021- present
Award Number: | IL-37953-21-75-K |  |  |  | Cost Share Amount: | 0
Donor: | U.S. Department of Labor |  |  |  | Leverage Amount: | 0
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Award Start Date: | 2021-12-15 |  |  |  | Key Personnel: | Alma Rico Diaz. Azucena Aguirre Crespo
Award End Date: | 2026-06-14 |  |  |  | Approved Indirect Rate(s) %: | 28.28% (NICRA)
Program Director: | Dr. Alma Rico Diaz |  |  |  | Prior Approvals Required:
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Kelsey Schrenk, schrenk.kelsey.l@dol.gov |  |  |  | Treatment of Program Income: | addition
Agreement Officer (AO)/Grants Officer (GO): | Bradley Sickles, sickles.bradley.a@dol.gov
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Agreement | 2021 | 2021-2026 | 0/24/21 | 2021-12-15 | IL-37953 Notice of Award | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FDonor%2FAward%2FIL%2D37593%20Notice%20of%20Award%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FDonor%2FAward | Original Award
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2022 | 2021-2026 | MM/DD/YYYY | MM/DD/YYYY | IL-37953 Modification Number 1 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FDonor%2FProject%20Revisions%2FRevision%201%2FUSDOL%20Approval%2FIL%2D37953%20Modification%20Number%201%5B35%5D%20%281%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FDonor%2FProject%20Revisions%2FRevision%201%2FUSDOL%20Approval | Modification 1 to realign budget, replace M&E Officer, and incorporate RMS as a sub-awardee
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | 2022 | 2021-2026 | 2022-08-16 | 2022-10-11 | Improving Substantive Gender Equality In the Mexican Workplace Performance Monitoring Plan | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7BF4368FAE-7F3B-4CDF-979F-8DE176553213%7D&file=Annex%20B%20-%20PMP%20-%20Project%20Document%20August%2024%202022%20(1)%20(1).xlsx&action=default&mobileredirect=true | DOL425 approved performance monitoring plan
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | 2022 | 2021-2026 | 2022-08-16 | 2022-10-11 | Improving Substantive Gender Equality In the Mexican Workplace Workplan | https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7B9E4C95C3-CB51-4328-B015-230DF9971517%7D&file=DOL425%20Work%20Plan.xlsx&action=default&mobileredirect=true | Original approved project document workplan
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Compliance Matrix Details
Breakdown of Award Requirements
| Award Terms & Conditions | Compliant Y/N | Comments | Program Description | Compliant Y/N | Comments | Work Plan FY2021-2026 | Compliant Y/N | Comments | Workplan FYXXXX | Compliant Y/N | Comments | Work Plan FYXX | Compliant Y/N | Comments | Workplan FYXX | Compliant Y/N | Comments | MEL Plan FY2021-2026 | Compliant Y/N | Comments | Indicators | Compliant Y/N | Comments | Environmental Mitigation and Monitoring Plan - EMMP | Compliant Y/N | Comments | Activities in Budget Narrative | Compliant Y/N | Comments
1 | Financial Reporting: Quarterly Federal Financial Reports | Y | All FFRs submitted to donor on time | Description: The project seeks to increase the number of women in union leadership, strengthen protections against gender-based violence at work, address discrimination and harassment in the workplace, combat the gender wage gap and increase wages for women. To ensure a demand driven, locally led and sustainable project, the project will collaborate with CSOs to reach workers and WOs, and employers and employer associations, to incorporate a gender equity perspective into current programming. The project strategy is based on three guiding principles: 1) a women worker-centered approach dedicated to women's development and enjoyment of labor rights, including those centered in gender equity in the workplace; 2) sustainability based on collaboration with local, credible, and experienced partners; and 3) cross collaboration and best practices learned from other gender and labor programming initiatives. In line with USDOL’s programming, the project’s key objectives are the following: WOs advance issues pertaining to gender equity, including gender proportionality in leadership and participation in key activities, within their institutions. WOs undertake sustained action to promote gender equity in the workplace. | Y |  | Activity 1: Conduct a participatory diagnostic on gender equality and representation issues within WO. Activity 2: Identify and train young women workers in leadership, negotiation and conflict resolution. Activity 3: Train female leaders in WO on collective negotiation and substantive equality. Activity 4: Develop strategic plans for WO to comply with the gender provisions of the Mexican Labor Reform. Activity 5: Establish/strengthen gender committees for substantive gender equality within WO. Activity 6: Develop protocols focused on eliminating violence and harrassment within WO membership. Activity 7: Develop a toolkit for WO to support the integration of the gender perspective and the increase in women members. Activity 8: Identify, systematize, and disseminate good practices on gender, democracy, and WO administration. Activity 9: Conduct a participatory diagnosis on substantive gender equality and representation in the prioritized sectors and workplaces. Activity 10: Train WO leaders, particularly women, to advocate with authorities and leaders for policies and practices for substantive equality in the workplace. Activity 11: Provide technical assistance to companies to comply with the labor reform and USMCA's gender provisions, and how to work with WO to improve compliance. Activity 12: Establish roundtables within WO to disseminate best practices for substantive equality in the workplace. Activity 13: Develop technical roundtables on social protection systems led by WO. Activity 14: Develop and disseminate approaches based on best practices to prevent gender discrimination in the workplace and associated labor violations. Activity 15: Train workers and WO on effective methods for gathering evidence and reporting discrimination and GBVH in the workplace. Activity 16: Provide legal support to workers in cases related to gender discrimination, wage violations, failure to pay into social protection systems, harrassment or violence, and other relevant labor violations. | Y | This is the most up-to-date workplan submitted in the project's October 2023 TPR | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | Project's current donor-approved PMP: https://partnersnet107.sharepoint.com/:x:/r/sites/Programs/_layouts/15/Doc.aspx?sourcedoc=%7BF4368FAE-7F3B-4CDF-979F-8DE176553213%7D&file=Annex%20B%20-%20PMP%20-%20Project%20Document%20August%2024%202022%20(1)%20(1).xlsx&action=default&mobileredirect=true | Y | Current PMP is informing project monitoring by POA and subawardees | Indicator 1 8b. Number (#) of collective structures or institutions within a system that have institutionalized more effective services, processes or programs associated with improved workers’ rights | N | Target: 9 Actual: 0 |  |  |  | 1. Conduct a diagnostic and report on gender equality and representation issues within worker organizations | N | overspent in some elements, underspent in most
24 | Semi-Annual reports: Bi-annual Technical Progress Reports | Y | submitted to donor on time | [18 empty] | Indicator 2 2a. Number (#) of individual actors within a system with increased capacity that enables them to better address labor rights issues, claim their rights or fulfill their duties | N | Target: 340 Actual: 0 |  |  |  | 2. Identify and train young female workers in leadership, negotiation and conflict resolution. | N | underspent (approx 0% burn rate)
26 | Final Program Report: Final TPR within 90 days of project closeout | [20 empty] | Indicator 3. # of women workers and leaders trained | N | Target: 486 Actual: 0 |  |  |  | 3: Train female leaders in WO on collective negotiation and substantive equality | N | underspent (approx 0% burn rate)
45 | [21 empty] | Indicator 4 2b. Number (#) of collective structures or institutions within a system with increased capacity that enables them to better address labor rights issues, claim their rights or fulfill their duties | N | Target: 13 Actual: 0 |  |  |  | 4: Develop strategic plans for WO to comply with the gender provisions of the Mexican labor reform | N | underspent (approx 0% burn rate)
46 | [21 empty] | Indicator 5. % of cases that follow the protocol according to the established criteria | N | Target: 75% Actual: 0 |  |  |  | 5: Establish/strengthen gender committees for substantive equality within WO | N | underspent (approx 0% burn rate)
47 | [21 empty] | Indicator 6. # of WO that develop and implement strategic plans to address the gender provisions of the Labor Reform. | N | Target: 18 Actual: 0 |  |  |  | 6: Develop protocols focused on eliminating violence and harassment within WO membership | N | underspent (approx 0% burn rate)
48 | [21 empty] | Indicator 7. # of WO with functioning gender committees | N | Target: 18 Actual: 0 |  |  |  | 7: Develop a toolkit for WO to support the integration of the gender perspective and the increase of women members | N | underspent (approx 0% burn rate)
49 | [21 empty] | Indicator 8. # of WO that establish protocols for the attention of cases of violence | N | Target: 18 Actual: 0 |  |  |  | 8: Identify, systematize, and disseminate good practices on gender, democracy, and WO administration | N | underspent (approx 0% burn rate)
[22 empty] | Indicator 9 9b. Number (#) of institutions, legal entities or organizations that have collectively adopted practices associated with improved workers’ rights | N | Target: 9 Actual: 0 |  |  |  | Consultant for creating a compendium of good practices on democracy and WO administration | N | underspent (approx 0% burn rate)
[22 empty] | Indicator 10 7b. Number (#) of collective structures or institutions within a system with improved delivery of services, programs or duties associated with improved workers’ rights | N | Target: 9 Actual: 0 |  |  |  | 9: Conduct a participatory diagnosis on substantive equality and representation in the prioritized sectors and workplaces | N | underspent (approx 0% burn rate)
[22 empty] | Indicator 11. # of WO leaders who complete training to advocate with authorities and leaders for policies and practices for substantive equality in the workplace | N | Target: 270 Actual: 0 |  |  |  | 10: Train WO leaders, particularly women, to advocate with authorities and leaders for policies and practices for substantive equality in the workplace | N | underspent (approx 0% burn rate)
[22 empty] | Indicator 12. # of cases presented before the IMSS about social security problems | N | Target: 144 Actual: 0 |  |  |  | 11: Provide technical assistance to firms to comply with the Mexican labor reform and USMCA's gender provisions, and how to work with WO to improve compliance | N | underspent (approx 0% burn rate)
[22 empty] | Indicator 13 6b. Number (#) of collective structures or institutions within a system with improved access to services, benefits, protections, or programs associated with improved workers’ rights | N | Target: 18 Actual: 0 |  |  |  | 12: Establish roundtables within WO to disseminate best practices for substantive equality in the workplace | N | underspent (approx 0% burn rate)
[22 empty] | Indicator 14. # of people who complete training to present cases of discrimination and GBVH in the work place | N | Target: 144 Actual: 0 |  |  |  | 13: Develop technical roundtables on social protection systems led by WO | N | overspent in some elements, underspent in most
[22 empty] | Indicator 15 6a. Number (#) of individual actors within a system with improved access to services, benefits, protections, or programs associated with improved workers’ rights | N | Target: 540 Actual: 0 |  |  |  | 14: Develop and disseminate approaches based on best practices to prevent gender discrimination in the workplace and associated labor violations | N | underspent (approx 0% burn rate)
50 | [27 empty] | 15: Train workers and WO on effective methods for gathering evidence and reporting discrimination and GBVH in the workplace | N | underspent (approx 0% burn rate)
[28 empty] | 16: Provide legal support to workers in cases related to gender discrimination, wage violations, failure to pay social protection systems, harassment or violence, and other relevant labor violations | N | underspent (approx 0% burn rate)

## CEREAL Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | Centro de Reflexion y Accion Laboral (CEREAL) |  |  |  | Total Award Amount: | $767,624 USD | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOL425 |  |  |  | Total Obligation Amount: | $102,112 USD | Macarena Jimenez Granda (2022-present)
Subaward Number: | Subaward 42 |  |  |  | Cost Share Amount: | $0 USD
Donor: | U.S. Department of Labor |  |  |  | Leverage Amount: | $0 USD
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2022-12-01 |  |  |  | Key Personnel: | Alma Rico Diaz, Hugo Mendoza
Subaward End Date: | 2025-12-31 |  |  |  | Approved Indirect Rate(s) %: | 10% de minimus
Subaward Point of Contact: | Hugo Mendoza, director@cereal.mx |  |  |  | Prior Approvals Required:
POA Point of Contact: | Alma Rico Diaz, arico@partners.net |  |  |  | Treatment of Program Income: | addition
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2022 | 2022-2025 | 2023-01-04 | 2023-01-26 | Improving Substantive Gender Equality in the Mexican Workplace Cost Reimbursable Subaward Between POA and CEREAL | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FFully%20Executed%2FSubaward%2042%20DOL425%20Cost%20Reimbursable%20Subaward%20%2D%20CEREAL%20%2D%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FFully%20Executed | Original subaward agreement
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2023 | 2022-2025 | 2023-02-22 | 2023-05-12 | Sub-Grant Agreement Modification 001 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FMods%2FMod%2001%2FSAMOD%2086%20DOL425%20CEREAL%20Sub%20Award%20Mod%20001%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FMods%2FMod%2001 | Change key personnel, modify Section 4, Article 6: Value Added Taxes (Host Government Taxes) Reporting
Modification 02 | 2023 | 2022-2025 | 2023-05-02 | 2023-05-12 | Sub-Grant Agreement Modification 002 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FMods%2FMod%2002%2FSAMOD%2099%20DOL425%20CEREAL%20Sub%2DAward%20Mod%20002%2012%5F01%5F2022%20%2D%2012%5F31%5F2025%20%281%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FMods%2FMod%2002 | Increase obligation amount
Modification 03 | 2023 | 2022-2025 | 2023-08-18 | 2023-09-29 | Sub-Grant Agreement Modification 003 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FMods%2FMod%2003%2FSAMOD%20112%20DOL425%20CEREAL%20Subaward%20Mod%2003%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FMods%2FMod%2003 | increase obligation amount
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
Subaward Agreement | 2022 | 2022-2025 | 2023-01-04 | 2023-01-26 | Improving Substantive Gender Equality in the Mexican Workplace Cost Reimbursable Subaward Between POA and CEREAL | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FFully%20Executed%2FSubaward%2042%20DOL425%20Cost%20Reimbursable%20Subaward%20%2D%20CEREAL%20%2D%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FFully%20Executed | Original sub agreement including PMP
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Subaward Agreement | 2022 | 2022-2025 | 2023-01-04 | 2023-01-26 | Improving Substantive Gender Equality in the Mexican Workplace Cost Reimbursable Subaward Between POA and CEREAL | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FFully%20Executed%2FSubaward%2042%20DOL425%20Cost%20Reimbursable%20Subaward%20%2D%20CEREAL%20%2D%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FCEREAL%2FSub%20Award%2FFully%20Executed | Original subaward agreement including workplan
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## RMS Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | Red de Mujeres Sindicalistas (RMS) |  |  |  | Total Award Amount: | $1,730,498 USD | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOL425 |  |  |  | Total Obligation Amount: | $320,000 USD | Macarena Jimenez Granda (2022-present)
Subaward Number: | Subaward 41 |  |  |  | Cost Share Amount: | $0 USD
Donor: | U.S. Department of Labor |  |  |  | Leverage Amount: | $0 USD
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2022-12-01 |  |  |  | Key Personnel: | Alma Rico Diaz, Ines Gonzalez
Subaward End Date: | 2025-12-31 |  |  |  | Approved Indirect Rate(s) %: | 10% USG de minimus
Subaward Point of Contact: | Ines Gonzalez, inesgoni7@yahoo.com.mx |  |  |  | Prior Approvals Required:
POA Point of Contact: | Alma Rico Diaz, arico@partners.net |  |  |  | Treatment of Program Income: | addition
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2022 | 2022-2025 | 2023-01-04 | 2023-01-27 | Improving Substantive Gender Equality in the Mexican Workplace Cost Reimbursable Subaward between POA and RMS | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FFully%20Executed%2FSubaward%2041%20DOL425%20Cost%20Reimbursable%20Subaward%20Red%20de%20Mujeres%20Sindicalistas%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FFully%20Executed | Original Award
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2023 | 2022-2025 | 2023-02-17 | 2023-03-14 | Sub-Grant Agreement Modification 001 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod%20001%2FSAMOD%2085%20DOL425%20RMS%20Sub%20Award%20Mod%20001%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod%20001 | Increase obligated amount
Modification 02 | 2023 | 2022-2025 | 2023-03-30 | 2023-04-26 | Sub-Grant Agreement Modification 002 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod%20002%2FSAMOD%2094%20DOL425%20RMS%20Sub%2DAward%20Mod%20002%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod%20002 | Increase obligated amount
Modification 03 | 2023 | 2022-2025 | 2023-05-30 | 2023-06-02 | Sub-Grant Agreement Modification 003 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod%20003%2FSAMOD%20104%20DOL425%20RMS%20Sub%2DAward%20Mod%20003%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod%20003 | Increase obligated amount
Modification 04 | 2023 | 2022-2025 | 2023-07-25 | 2023-07-25 | Sub-Grant Agreement Modification 004 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod%20004%2FSAMOD%20110%20DOL425%20RMS%20Sub%2DAward%20Mod004%2012%2D01%2D2022%20%2D12%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod%20004 | Increase obligated amount
Modification 05 | 2023 | 2022-2025 | 2023-10-03 | 2023-10-09 | Sub-Grant Agreement Modification 005 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod005%2FSAMOD%20119%20DOL425%20RMS%20Subaward%20Mod%20005%2012%2D01%2D2022%20%2D12%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod005 | Increase obligated amount
Modification 06 | 2023 | 2022-2025 | 2023-11-13 | 2023-11-22 | Sub-Grant Agreement Modification 006 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod%20006%2FSAMOD%20120%20DOL425%20RMS%20Subaward%20Mod%20006%2012%2D01%2D2022%20%2D12%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FMods%2FMod%20006 | Increase obligated amount
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
Subaward Agreement | 2022 | 2022-2025 | 2023-01-04 | 2023-01-27 | Improving Substantive Gender Equality in the Mexican Workplace Cost Reimbursable Subaward between POA and RMS | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FFully%20Executed%2FSubaward%2041%20DOL425%20Cost%20Reimbursable%20Subaward%20Red%20de%20Mujeres%20Sindicalistas%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FFully%20Executed | Original Award including PMP
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | 2022 | 2022-2025 | 2023-01-04 | 2023-01-27 | Improving Substantive Gender Equality in the Mexican Workplace Cost Reimbursable Subaward between POA and RMS | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FFully%20Executed%2FSubaward%2041%20DOL425%20Cost%20Reimbursable%20Subaward%20Red%20de%20Mujeres%20Sindicalistas%2012%2D01%2D2022%20%2D%2012%2D31%2D2025%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FRMS%2FAgreement%2FFully%20Executed | Original Award including work plan
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## MasPro Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | DOL425 PURCHASE ORDER FOR IMPLEMENTING PARTNER MÁSPROYECTOS |  |  |  | Total Award Amount: | $415,299 USD | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOL425 |  |  |  | Total Obligation Amount: | n/a
Subaward Number: | FNQ3U-HR7UT-TYS59-8DGGA |  |  |  | Cost Share Amount: | n/a
Donor: | U.S. Department of Labor |  |  |  | Leverage Amount: | n/a
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2023-03-01 |  |  |  | Key Personnel: | Alma Rico Diaz, Alma Alvarez
Subaward End Date: | 2025-12-31 |  |  |  | Approved Indirect Rate(s) %: | n/a (Fixed price)
Subaward Point of Contact: | Alma Alvarez, alma.alvarez@masproyectos.org |  |  |  | Prior Approvals Required:
POA Point of Contact: | Alma Rico Diaz, arico@partners.net |  |  |  | Treatment of Program Income:
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2023 | 2023-2025 | 2023-02-27 | 2023-04-18 | DOL425 PURCHASE ORDER FOR IMPLEMENTING PARTNER MÁSPROYECTOS | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FMas%20Proyectos%2FAgreement%2FFully%20Executed%2FPO%2058%20DOL425%20Purchase%20Order%20Services%20Mas%20Proyectos%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FMas%20Proyectos%2FAgreement%2FFully%20Executed | Original purchase order agreement
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | 2023 | 2023-2025 | 2023-02-27 | 2023-04-18 | DOL425 PURCHASE ORDER FOR IMPLEMENTING PARTNER MÁSPROYECTOS | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FMas%20Proyectos%2FAgreement%2FFully%20Executed%2FPO%2058%20DOL425%20Purchase%20Order%20Services%20Mas%20Proyectos%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FMas%20Proyectos%2FAgreement%2FFully%20Executed | Original purchase order agreement including PMP
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | 2023 | 2023-2025 | 2023-02-27 | 2023-04-18 | DOL425 PURCHASE ORDER FOR IMPLEMENTING PARTNER MÁSPROYECTOS | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FMas%20Proyectos%2FAgreement%2FFully%20Executed%2FPO%2058%20DOL425%20Purchase%20Order%20Services%20Mas%20Proyectos%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FMas%20Proyectos%2FAgreement%2FFully%20Executed | Original purchase order agreement including workplan
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## TMyM Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | Improving Substantive Gender Equality in the Mexican Workplace Fixed Amount Award Between POA and Transforma MyM |  |  |  | Total Award Amount: | $167,420 USD | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOL425 |  |  |  | Total Obligation Amount: | n/a
Subaward Number: | RBYMB-GKOXU-R5GRQ-NEFMH |  |  |  | Cost Share Amount: | n/a
Donor: | U.S. Department of Labor |  |  |  | Leverage Amount: | n/a
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2023-04-01 |  |  |  | Key Personnel: | Alma Rico Diaz, Virginie Martin-Onraet, Paulina Madera
Subaward End Date: | 2026-01-31 |  |  |  | Approved Indirect Rate(s) %: | n/a (fixed price)
Subaward Point of Contact: | Paulina Madero Suárez, paulina.madero@m-m.mx Virginie Martin-Onraet, virginie.martinon@m-m.mx |  |  |  | Prior Approvals Required:
POA Point of Contact: | Alma Rico Diaz, arico@partners.net |  |  |  | Treatment of Program Income:
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2023 | 2023-2026 | 2023-04-01 | 2023-05-13 | Improving Substantive Gender Equality in the Mexican Workplace Fixed Amount Award Between POA and Transforma MyM | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FTransforma%20MyM%2FSubaward%2FFully%20Executed%2FCover%20Sheet%20459%20DOL425%20Fixed%20Price%20Subaward%20Agreement%20Transforma%20MyM%2004%2D01%2D2023%20%2D%2001%2D31%2D2026%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FTransforma%20MyM%2FSubaward%2FFully%20Executed | Original award
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | 2023 | 2023-2026 | 2023-04-01 | 2023-05-13 | Improving Substantive Gender Equality in the Mexican Workplace Fixed Amount Award Between POA and Transforma MyM | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FTransforma%20MyM%2FSubaward%2FFully%20Executed%2FCover%20Sheet%20459%20DOL425%20Fixed%20Price%20Subaward%20Agreement%20Transforma%20MyM%2004%2D01%2D2023%20%2D%2001%2D31%2D2026%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FTransforma%20MyM%2FSubaward%2FFully%20Executed | Original award Including PMP
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | 2023 | 2023-2026 | 2023-04-01 | 2023-05-13 | Improving Substantive Gender Equality in the Mexican Workplace Fixed Amount Award Between POA and Transforma MyM | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FTransforma%20MyM%2FSubaward%2FFully%20Executed%2FCover%20Sheet%20459%20DOL425%20Fixed%20Price%20Subaward%20Agreement%20Transforma%20MyM%2004%2D01%2D2023%20%2D%2001%2D31%2D2026%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOL425%2FAgreements%2F%5FSub%2DAwards%2FTransforma%20MyM%2FSubaward%2FFully%20Executed | Original award Including workplan
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY