## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | 100K Strong Colombia |  |  |  | Total Award Amount: | 367950 | Program Manager(s) (including dates):
Internal Grant Number: | DOS2002 |  |  |  | Total Obligation Amount: | 367950
Award Number: | SCO20019GR0102 |  |  |  | Cost Share Amount: | 0
Donor: | U.S. Embassy Bogotá |  |  |  | Leverage Amount: | 0
CFDA: | 19.040 |  |  |  | USAID Only: Geographic Code:
Award Start Date: | 2019-10-01 |  |  |  | Key Personnel: | Ana Rubi, Victor Moscoso, Mariana Cabrera Figueroa
Award End Date: | 2024-09-30 |  |  |  | Approved Indirect Rate(s) %: | 29.69%
Program Director: | Penelope Kim |  |  |  | Prior Approvals Required: | Yes
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Diana Patiño |  |  |  | Treatment of Program Income: | Deduction
Agreement Officer (AO)/Grants Officer (GO): | Carolyn Turpin
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Agreement | n/a | 2019-2020 | 2019-09-24 | 2019-09-24 | 100K USDS EC Grant 2019-10-01 to 2020-12-31-signed | https://partnersnet107.sharepoint.com/:b:/s/Programs/EQtnzcu9hdJEqR9Z6JDHgVEBocL-tzxkGclOfRKTPw1TgA?e=jUBwQK | Original Prime Award Agreement
Cost Extension 01 | n/a | 2019-2022 | 2021-09-10 | 2021-09-14 | 29. SCO20019GR0102-M003 (2019-10-01 TO 2022-12-31)-signed | https://partnersnet107.sharepoint.com/:b:/s/Programs/EfPhPkuTQCZGj_8tec8m7uIBKjLm1fE8N2DgWr-WxHPhew?e=oGvcrv | Addition of $50k & Approved Extension through Dec 2022
Cost Extension 02 | n/a | 2019-2022 | 2021-09-23 | 2021-09-29 | 39. AMD 4 SCO20019GR0102-M004-signed | https://partnersnet107.sharepoint.com/:b:/s/Programs/EYbkF6NtIBZNkEI_trV4d7ABNpSXvcZkdqNeuLAacHhm6Q?e=HC5HHc | Addition of $67,950
Modification 01 | n/a | 2019-2021 | 2020-08-11 | 2020-08-17 | EGC DOS-2002 Colombia No-Cost Extension Addendum (thru Dec 2021) | https://partnersnet107.sharepoint.com/:b:/s/Programs/Edoe9uLUfrxFkzZCL8FD9coBLfTCvtP9SJMfxu9LIv8Eyg?e=0lWldQ | Approved Extension through Dec 2021
Modification 02 | n/a | 2019-2024 | 2022-07-18 | 2022-09-12 | GRANTMOD 13 100K Embassy in Colombia - NCE of SCO20019GR0102 - No POA Cover Sheet | https://partnersnet107.sharepoint.com/:b:/s/Programs/Ec3BOfRHVbZPqRYK0xNTY9AB7ky7HUeTVizOkqs4A5GrUw?e=43fN0Q | Approved Extension through Sep 2024
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Scope of Work (SOW)
Implementation Plan/Scope of Work | FY20 | 2019-2024 | 2019-09-20 | 2019-09-24 | SOW 100K Colombia 2019-20 - 2019-09-20 | https://partnersnet107.sharepoint.com/:w:/s/Programs/EQ1-sVn5k3xMmB5txeqNkjkBE-d6inPqztYXTNCVZ-iDUw?e=Crwx3D | Approved Scope of Work
Special Provisions/Restrictions
Approval of Subawards
List restrictions
List special provisions or requirements
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Compliance Matrix Details
Breakdown of Award Requirements
| Award Terms & Conditions | Compliant Y/N | Comments | Program Description | Compliant Y/N | Comments | Work Plan FYXX | Compliant Y/N | Comments | Activities in Budget Narrative | Compliant Y/N | Comments
1 | Financial Reporting 01: June 30, 2020 | Y |  | Description: Leverage new commitments from the private sector, foundations, and regional partners to support the 100,000 Strong in the Americas Innovation Fund (100K Innovation Fund). These funds will be used to create new 100K-branded education exchange and training opportunities via the 100K Innovation Fund to increase Colombian and U.S. higher education institutional (HEI) partnerships. Program will be implemented in Colombian during 2020. |  |  | Develop outreach plan to seek potential donor(s) from Colombian and/or U.S. private sector and/or other regional partners to contribute to future to-be-determined (TBD) Innovation Fund grant competition which will create new 100K-branded HEI partnerships in Colombia and the United States. |  |  | Personnel: Partners has budgeted for one (1) Senior Director, one (1) Director and one (1) Program Officer at Partners’ headquarters.
2 | Interim Performance Report 01: June 30, 2020 |  |  | Geographic Scope: U.S.-Colombia |  |  | Plan outreach strategy to implement 100K-friend/fund raising cultivation efforts in coordination with WHA/PDA and PAS-Bogota. |  |  | Staff Travel: POA is budgeting for three (3) staff to travel from Atlanta, GA or Washington, DC to Bogota to participate in fundraising meetings and/or competitions announcements such as a launch event or winners announcement with donors and stakeholders.
3 | Final Program Report: December 30, 2024 | [5 empty] | Collaborate with PAS-BOG and WHA/PDA to plan, design, implement a 100K-branded workshop in 2020 that will bring together four years of program leaders and students from previous and current 100K Colombia/U.S. partnerships. This 100K-workshop will be tracked to the launch of the potential TBC new Colombia specific Innovation Fund grant competition and will create a strategic platform for 100K-program leaders to share lessons learned, best practices, tips on how to plan and implement and sustain student academic exchange and training programs between Colombia and the U.S (beyond the 100K grant period). |  |  | Innovation Fund Grants: Pending future commitments to the Innovation Fund from the government of Colombia and private sector, Partners is budgeting to provide sub-grants to Innovation Fund grant-winning teams of higher education institutions (HEIs) in the U.S. and Colombia. Innovation Fund award amounts are typically $25,000 per each 100K grant winning partnership. Partners is budgeting for 5.6 grants to be supported by the U.S. Embassy for a total of $140,000.
4 | Program Income: Deduction: Any program income earned by the Recipient as a result of this award and during the period of performance must be deducted from the total allowable costs in order to determine the net allowable costs for the award. | [5 empty] | Partners will work with WHA/PDA and PAS-Colombia related to WHA-wide 100K-branded programming, including program promotion; grant proposal evaluation/selection; and disbursement and monitoring of all 100K Innovation Fund sub-awards to future (TBC) Innovation-Fund 100K-grant winning HEI partnerships between Colombia and the United States. |  |  | Promotional Materials for Events (Banners, Folders, etc.): Partners is budgeting to print and reproduce materials to be used for potential announcements/events in Colombia. This includes branded banners, folders and one-pagers, impact reports and presentations, and copies of press releases, winners’ descriptions, booklets, and other materials.
5 | Branding & Marking: Refer to Clause 15) ADDITIONAL BUREAU/POST SPECIFIC REQUIREMENTS in the Prime Award Agreement. | Y | [7 empty] | Workshop: Partners is budgeting for catering services, the rental and use of facilities with the capacity to host approximately 150 participants for the 100K workshop in Bogota. The workshop will be a 100K-branded and collaborative effort between Partners, PAS-BOG and WHA/PDA that will bring together four years of program leaders and students from previous and current 100K Colombia/U.S. partnerships.

## FUJNC Subaward Summary
Compliance Matrix
Subaward Name/Title: | School of Literacy and Interculturality for Maternal and Perinatal Care in Native Communities |  |  |  | Total Award Amount: | 17000 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 100K-DOS2002-FUJNC FCA |  |  |  | Total Obligation Amount: | 17000
Subaward Number: | 100KSubAg. 81 100K-DOS2002-FUJNC FCA |  |  |  | Cost Share Amount: | N/A
Donor: | U.S. Embassy Bogotá |  |  |  | Leverage Amount:
CFDA: | 19.040 |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2023-02-01 |  |  |  | Key Personnel: | Ms. Daniela Herrera Grajales
Subaward End Date: | 2024-05-31 |  |  |  | Approved Indirect Rate(s) %: | 0%
Subaward Point of Contact: | Dr. Luis Gabriel Pineros Ricardo |  |  |  | Prior Approvals Required:
POA Point of Contact: | Mariana Cabrera Figueroa (Technical), Summar Lyons (Contracts) |  |  |  | Treatment of Program Income: | Deduction
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | 2023-2024 | 2023-03-21 | 2023-03-24 | 100KSubAg. 81 100K-DOS2002-FUJNC FCA | [Terminated] 100KSubAg. 82 100K-DOS2002-FUJNC FAA (2023-02-01 to 2024-05-31).pdf | FUJNC Original SubAward Agreement - terminated in Oct. 2023
Modification 01 | n/a | 2023-2024 | 2023-08-23 | 2023-08-23 | Termination of 100K-DOS2002-FUJNC | Termination of Award Agreement 100K-DOS2002-FUJNC (Aug 2023).pdf | Termination of original SubAward Agreement under DOS2002 to fund project under POAF
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Lewis Subaward Summary
Compliance Matrix
Subaward Name/Title: | SoPEF 4 Life: Soil, People, the Environment, and Food for Life |  |  |  | Total Award Amount: | 20266.11 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 100K-DOS2002-Lewis FCA |  |  |  | Total Obligation Amount: | 20266.11
Subaward Number: | 100KSubAg. 83 100K-DOS2002-Lewis FCA |  |  |  | Cost Share Amount: | N/A
Donor: | U.S. Embassy Bogotá |  |  |  | Leverage Amount:
CFDA: | 19.040 |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2023-02-01 |  |  |  | Key Personnel: | Dr. Jerry Kavouras
Subaward End Date: | 2024-05-31 |  |  |  | Approved Indirect Rate(s) %: | 20%
Subaward Point of Contact: | Dr. William Siler |  |  |  | Prior Approvals Required:
POA Point of Contact: | Mariana Cabrera Figueroa (Technical), Summar Lyons (Contracts) |  |  |  | Treatment of Program Income: | Deduction
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | 02/01/2023-05/31/2024 | 2023-03-21 | 2023-03-24 | 100KSubAg. 83 100K-DOS2002-Lewis FCA | [TERMINATED] 100KSubAg. 83 100KDOS2002-Lewis FAA (2023-02-01 to 2024-05-31).pdf | Lewis Original SubAward Agreement - terminated in August 2023
Modification 01 | n/a | 2023-2024 | 2023-08-23 | 2023-08-23 | Termination of 100K-DOS2002-Lewis | Termination of Award Agreement to Lewis_2023-08-23.pdf | Termination of original SubAward Agreement under DOS2002 to fund project under POAF
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## SDSU Subaward Summary
Compliance Matrix
Subaward Name/Title: | Collaborative Online Learning for the improvement of the Cacao Value Chain in Colombia (CATCHI) |  |  |  | Total Award Amount: | 25000 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 100K-DOS2002-SDSU-Usabana-Ucordoba |  |  |  | Total Obligation Amount: | 25000
Subaward Number: | 100KSubAg. 90 100K-DOS2002-SDSU-Usabana-Ucordoba FAA |  |  |  | Cost Share Amount: | N/A
Donor: | U.S. Embassy Bogotá |  |  |  | Leverage Amount:
CFDA: | 19.040 |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2023-06-01 |  |  |  | Key Personnel: | Dr. Carlos Paternina Arboleda
Subaward End Date: | 2024-05-31 |  |  |  | Approved Indirect Rate(s) %: | 6%
Subaward Point of Contact: | Sandra M. Nordahl, CRA |  |  |  | Prior Approvals Required:
POA Point of Contact: | Mariana Cabrera Figueroa (Technical), Summar Lyons (Contracts) |  |  |  | Treatment of Program Income: | Deduction
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | 2023-2024 | 2023-08-08 | 2023-08-10 | 100KSubAg. 90 100K-DOS2002-SDSU-Usabana-Ucordoba FAA | Fully Executed - 100KSubAg. 90 100K-DOS2002-SDSU-USabana-UCordoba FAA (2023-06-01 to 2024-05-31).pdf | SDSU SubAward Agreement
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## UniSalle-MC Subaward Summary
Compliance Matrix
Subaward Name/Title: | Circular Agriculture in Cocoa Production: A Sustainable Strategy to Promote a Healthy Environment, Food and Life |  |  |  | Total Award Amount: | 25000 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 100K-DOS2002-UniSalle-ManhattanCollege |  |  |  | Total Obligation Amount: | 25000
Subaward Number: | 100KSubAg. 91 100K-DOS2002-UniSalle-ManhattanCollege FAA |  |  |  | Cost Share Amount: | N/A
Donor: | U.S. Embassy Bogotá |  |  |  | Leverage Amount:
CFDA: | 19.040 |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2023-06-01 |  |  |  | Key Personnel: | Libardo Gutierrez Mengual
Subaward End Date: | 2024-05-31 |  |  |  | Approved Indirect Rate(s) %: | 0%
Subaward Point of Contact: | Brother Niky Alexánder Murcia Suárez |  |  |  | Prior Approvals Required:
POA Point of Contact: | Mariana Cabrera Figueroa (Technical), Summar Lyons (Contracts) |  |  |  | Treatment of Program Income: | Deduction
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | 2023-2024 | 2023-08-01 | 2023-08-01 | 100KSubAg. 91 100K-DOS2002-UniSalle-ManhattanCollege FAA | PE_100KSubAg. 91 100K-DOS2002-UniSalle-ManhattanCollege - FAA (Firmado Salle).pdf | UniSalle-Manhattan College Original SubAward Agreement
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## IUAJC Subaward Summary
Compliance Matrix
Subaward Name/Title: | From the university to the field: North and South collaboration with practical pedagogy for production, commercialization, and transformation of cocoa (DEUCAM) |  |  |  | Total Award Amount: | 2734.9 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 100K-USDA200-DOS2002-IUAJC-Wellesley |  |  |  | Total Obligation Amount: | 2734.9
Subaward Number: | 100KSubAg. 89 100K-USDA200-DOS2002-IUAJC-Wellesley FAA |  |  |  | Cost Share Amount: | N/A
Donor: | U.S. Embassy Bogotá |  |  |  | Leverage Amount:
CFDA: | 19.040 |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2023-06-01 |  |  |  | Key Personnel: | Dr. Claudia Polania
Subaward End Date: | 2024-05-31 |  |  |  | Approved Indirect Rate(s) %: | 0%
Subaward Point of Contact: | Hugo Alberto González López |  |  |  | Prior Approvals Required:
POA Point of Contact: | Mariana Cabrera Figueroa (Technical), Summar Lyons (Contracts) |  |  |  | Treatment of Program Income: | Deduction
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | 2023-2024 | 2023-11-29 | 2023-12-11 | 100KSubAg. 89 100K-USDA200-DOS2002-IUAJC-Wellesley FAA | https://partnersnet107.sharepoint.com/:b:/s/Programs/ERPQoLYOKGhElw6w3V7Jv5QBUQPpOMkPpD2EmDhA2e9lwA?e=hEoZCM | IUAJC Original SubAward Agreement
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $25,000 including funds from DOS200