## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | 100,000 Strong in the Americas |  |  |  | Total Award Amount: | 1382500 | Program Manager(s) (including dates):
Internal Grant Number: | DOS2004 |  |  |  | Total Obligation Amount:
Award Number: | SAQMIP23CA0023 |  |  |  | Cost Share Amount: | 901024
Donor: | U.S. Department of State (WHA) |  |  |  | Leverage Amount:
CFDA: | 19.777 |  |  |  | USAID Only: Geographic Code:
Award Start Date: | 2023-04-13 |  |  |  | Key Personnel: | Penelope Kim; Victor Moscoso
Award End Date: | 2025-10-31 |  |  |  | Approved Indirect Rate(s) %: | 28.28%
Program Director: | Penelope Kim |  |  |  | Prior Approvals Required: | Yes
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Maggie Hug |  |  |  | Treatment of Program Income: | N/A
Agreement Officer (AO)/Grants Officer (GO): | Soo Kang
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Agreement | n/a | 2023-2025 | 2023-04-13 | 2023-04-14 | DOS-POA 100K SAQMIP23CA0023 (2023-04-13 to 2025-10-31) | https://partnersnet107.sharepoint.com/:b:/s/Programs/EciKYOj2XrhLvT_h96oC6xYBNcph-EDrsXukAzdUwG4Dig?e=Z9v6iF | Prime Award Agreement for 100K
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan/Performance Monitoring Plan (PMP)
M&E Plan/PMP | FY23 | 2023-2025 | 2023-04-13 | 2023-04-14 | Comprehensive Performance Monitoring Plan (PMP) - REVISED 2023-03-17 - POA Version | https://partnersnet107.sharepoint.com/:w:/s/Programs/ERE_2bqLMvhClyi4W6It7lABX3qZWqdrFA8WNPAoSoZqVQ?e=fNWmmG | Approved PMP
M&E Plan/PMP - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/PMP - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Scope of Work
Implementation Plan/Work Plan | FY23 | 2023-2025 | 2023-04-13 | 2023-04-14 | 100K Strong Scope of Work 2023-25 - FINAL - 3.17.23 | https://partnersnet107.sharepoint.com/:w:/s/Programs/EbtmE6dMOjdOmhk1msEmF4cBm7jmtfWGukW-TyHlzy9kzA?e=XtIhn0 | Scope of Work
Work Plan Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
Obtain prior approval for domestic/overseas travel from WHA/PDA and GO | FY23 | 2023-2025 | 2023-04-13 | 2023-04-14
List restrictions
List special provisions or requirements
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Request for blanket approval for 2023 travel to conferences | FY2023 | 2023-2025 | 2023-07-06 | 2023-08-15 | 2023 Conference Travel | https://partnersnet107.sharepoint.com/:f:/s/Programs/EsdZyZ7S8H5Aqg1XXJy7LYABbVsbzTMx_q3imDBav-W3Eg?e=YYgb9t | Email approval from WHA on travel to 2023 conferences
Topic: Approval of final canddiate for Director of Public-Private Partnerships | FY2023 |  | 2023-11-06 | 2023-11-21 | Director of Public Private Partnerships recruitment process | https://partnersnet107.sharepoint.com/:u:/s/Programs/Ed7kVniz9stFokpTHlU6ilMB2ep0nJRKRo9uXgplzX5WrA?e=sulLTh | Email request WHA to approve candidacy of Victor Moscoso as new Director of Public-Private Partnerships for 100K.
Topic: Official Request for Change in Key Personnel: Director of Public-Private Partnerships | FY2023 | 2023-2025 | 2023-08-17 | 2023-11-30 | RE_ Award No. (SAQMIP23CA0023) - Request for key personnel approval (100K Strong grant) | https://partnersnet107.sharepoint.com/:u:/s/Programs/ERCVCBYvoHpCgU6WXP-UnXQBEc9EsKxfy3cazldG9BFIFA?e=P3Vzkw | Email approval from WHA on Key Personnel change of Victor Moscoso as new Director of Public-Private Partnerships for 100K.
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Compliance Matrix Details
Breakdown of Award Requirements
| Award Terms & Conditions | Compliant Y/N | Comments | Program Description | Compliant Y/N2 | Comments3 | Work Plan FY23-2025 | Compliant Y/N4 | Comments5 | MEL Plan FY2023-2025 | Compliant Y/N6 | Comments7 | Indicators | Compliant Y/N8 | Comments9 | Activities in Budget Narrative | Compliant Y/N10 | Comments11
1 | Financial Reporting 1: July 30, 2023 | Y |  | Description: Develop public-private sector collaboration to build HEI capacity for inclusive student exchange between the United States and the Western Hemisphere. |  |  | Starting no later than June 2023, and on an ongoing basis, implement targeted outreach campaigns to identify and cultivate new prospective donor-partners, raising their awareness of the strategic need for regional education cooperation to contribute to workforce development in the Americas and tailoring campaigns to focus on sectors and countries that align with U.S. foreign policy goals. |  |  | 30-60 days after Exchange Programs: Capture change in student participant, knowledge, skills, global perspectives & cross-cultural competencies, and HEI capacities. |  |  | Number of new donors from private sector entities, foundations, and/or non-U.S. governments to contribute to 100K |  |  | Personnel: POA has budgeted for one (1) Director of Public-Private Partnerships, one (1) Program Director, one (1) Associate Director, one (1) Program Officer, one (1) Communications Officer, one (1) MEL Officer, and one (1) Vice President of Organizational Advancement at POA’ headquarters.
2 | Financial Reporting 2: October 30, 2023 | Y |  | Geographic Scope: Western Hemisphere |  |  | Starting no later than June 2023, and on an ongoing basis, work with WHA and regional embassies to conduct an outreach campaign targeting government agencies, using Colombia/Brazil case studies as examples. |  |  | Immediately after Key Activities & Exchange Programs: Capture student and HEI participants' immediate reactions to the program, their level of engagement, and relevance of the program to their needs. |  |  | Number of competitions committed to by donor-partners |  |  | Staff Travel: All travel will be made by staff for the purpose of donor cultivation, launch of grant competitions, announcement of grant winners, program promotion, and stakeholder engagement for the program. Specific cities for travel cannot be specified in advance because it will not be known where events will occur until the locations have been confirmed by WHA, U.S. Embassies, and 100K donor-partners and where conferences will be hosted until confirmed by the organizers.
3 | Financial Reporting 3: January 30, 2024 | [5 empty] | At least five times a year, in coordination with WHA, participate in targeted conferences/events that convene donor prospects, such as the Central America Donors Forum, the Concordia Annual Summit, and the Association of American Chambers of Commerce in Latin America and the Caribbean (LAC), higher education conferences (NAFSA, FAUBAI, AIEA). Where possible, include representatives of WHA and Posts, including principals. |  |  | Within 6 months + End of Award: Application of learning will be measured twice during the lifetime of the 100K program. |  |  | Amount of funds raised from donor-partners |  |  | Tablet for In-Person Innovation Network Sign-ups: POA will allocate funds to purchase two (2) new tablets to facilitate sign up and encourage individuals and universities to register in-person at 100K events.
4 | Financial Reporting 4: April 30, 2024 | [5 empty] | By June 2023, launch a campaign with WHA and Posts for targeted opportunities to raise non-USG funds for new grants competitions under the 100K CLIMA and 100K Inclusive Education initiatives. |  |  | End of Award: Measure contribution of the 100K program to long-term change at the institutional (HEIs) and individual (students, faculty, administrators) levels. |  |  | Percent of donor-partners who report increased opportunities for workforce development as a result of engaging with 100K |  |  | Website & Digital Communications Contract: POA is proposing to hire a Website and Digital Communications Consultant who will assist in the planning, development, and execution of digital communications strategy for the 100K program, through collaboration with WHA to ensure consistency across channels and align messaging with overall communication objectives. The consultant will assist dissemination of messaging on social media, email/text marketing, website management, content development, digital online media, digital advertising, and development of mobile app. The consultant will develop communications processes, guidelines, and standards that ensure digital marketing campaigns are executed accurately and efficiently, to engage audience of potential and past program donors, HEIs, program participants and alumni. Additionally, the consultant will lead the technical re-design and development of the 100K Strong website.
5 | Financial Reporting 5: July 30, 2024 | [5 empty] | By July 2023, mobilize existing networks as force multipliers to identify prospective donors: additional Partners fundraising staff, Partners field staff, PD Section teams, and HEI administrators and faculty. |  |  | Baseline Study: Conduct a baseline study that will be used as a point of comparison throughout implementation to gauge progress toward the program’s desired results. The baseline will be established by analyzing past performance data in conjunction with previous studies commissioned for the 100K program to develop and update current online surveying tools to HEIs and students. The baseline study will capture information about the factors that have an impact on HEIs’ capacity to support student mobility access and participation. Qualitative and quantitative information will both be collected within the first six months of the startup of the HEI projects. Furthermore, demographic information will be captured in the baseline surveys. |  |  | Percent of donor-partners who report strengthening ties with HEIs as a result of engaging with 100K |  |  | POA is budgeting for bulk order of 1,000 items for outreach materials, including a set of 100K Strong branded pins and pennants for grant-winning faculty and 100K students at approximately $12.42 per set and 10 banners at $200 each, to be used and distributed during the grant competitions, along with other branded folders, notepads, and pens.
6 | Financial Reporting 6: October 30, 2024 | [5 empty] | During Program exchange projects, at least four times a year, work with Program cohorts, donor-partners, WHA, and Posts to arrange site visits and other meetings for exchange project participants, to strengthen learning, increase donor-partner engagement with beneficiaries, and expand opportunities for alumni to enter donor-partners’ workforce pipelines. |  |  | Outcome Harvesting explores the change in behavior of student and faculty beneficiaries while also documenting timing of the changed behavior, the importance of the change, and immediate impact of the change. Unlike other evaluation approaches, outcome harvesting does not necessarily measure progress towards predetermined outcomes/objectives; rather, it examines what has been achieved and determines whether and how the program contributed to the change. |  |  | Percent of U.S. participants who traveled abroad for the first time because of the 100K program |  |  | Grants Management System: POA currently uses an application and grants management system called Zengine by WizeHive to manage 100K Strong activities. This platform allows for the efficient management of the full grants lifecycle from application to review to the post-award process. POA proposes to continue using Zengine to implement the grant competitions, collect applications, track review and scores, manage the post-award process with innovation grant recipients, monitor project progress, and collect program data by administering survey tools. The system facilitates the entire grants process from start to finish, for the HEIs, WHA, and other stakeholders’ experience and that of POA staff.
7 | Financial Reporting 7: January 30, 2025 | [5 empty] | By November 2023, establish a 100,000 Strong in the Americas Advisory Council, which will engage a select group of current/past donor-partners in Program expansion efforts through communicating WHA country/theme priorities for the year, sharing opportunities for new Program investments, and soliciting input. |  |  | Social-network analysis (SNA) will be conducted to complement the findings of the outcome harvesting. SNA will explore connectedness and the nature of relationships among students, HEIs, donor-partners, Partners, and WHA. Partners will also include other local entities that are not necessarily part of the program, such as HEI associations or proposal reviewers. This will help provide a broader perspective at the system level as well as provide hints on what future programs can do to enhance and strengthen positive impact. |  |  | Percent of LAC participants who traveled abroad for the first time because of the 100K program |  |  | Data Tracking & Collection (M&E): POA is budgeting to upgrade our data collection and tracking platform to allow the team to perform more in-depth monitoring and collection of program data and results. The upgrade also includes technical support costs for 60 hours. Based on provider quotes, the hourly rate is $110 and hour to customize and build out a robust M&E database like Salesforce or another similar platform.
8 | Financial Reporting 8: April 30, 2025 | [5 empty] | At least four times a year, design grants competitions through a collaborative process with WHA, Posts, and donor-partners, ensuring competitions advance U.S. foreign policy goals while centering on academic disciplines and geographies that align with donor interests and encouraging participation by a diversity of HEIs. |  |  | Endline Study: Partners will conduct an endline study, applying a combination of quantitative surveys and qualitative techniques (e.g., focus groups discussion and key informant interviews), as well as commission a final external evaluation in the last year of the project, conducted by a third-party consulting firm that specializes in the evaluation of education programs. The endline study will integrate findings from outcome harvesting studies and be compared to baseline results. The final evaluation will assess the 100K program’s contribution to the expected results and overall impact on international education access by diverse student groups and HEIs. |  |  | Percent of participants with more favorable opinions of the U.S. Government |  |  | Platform Subscriptions: POA is budgeting to maintain platforms used to manage 100K Strong grant competitions and program activities. These platforms include Zoom at $750/year, Adobe Creative Cloud licenses for three program staff at $150/year/license, plus others project management tools.
9 | Financial Reporting 9: July 30, 2025 | [5 empty] | At least four times a year, use best practices learned from designing and managing prior Program grants competitions to craft requests for proposals (RFPs) and launch grants competitions, providing prospective applicants with clear guidance in English and Spanish/Portuguese, as well as templates and examples for critical proposal elements. |  |  | Participant Surveys (HEIs, Students, Alumni Network, PAS). Partners will administer surveys to HEIs and students through our grants management platform, Zengine, while surveys to program alumni will be sent using the network platform, Graduaway. This ensures that the records are maintained in the same system as the survey participants. |  |  | Percent of U.S. participants indicating an increase in understanding of their host country's government, culture, and values |  |  | International Conference Registration Fees: POA is budgeting for staff to register for 16 international conferences at an average rate of $450/conference. POA attends various conferences and lead panel sessions with invited 100K Strong innovation grant recipients to share information about 100K Strong grant opportunities with potential applicant universities and colleges. This level of outreach and in-person engagement is critical to ensure strong participation in all future grant competitions.
10 | Financial Reporting 10: October 30, 2025 | [5 empty] | For each Program grants competition, at least four times annually, implement an efficient, rigorous, transparent, and objective grants proposal review and evaluation process that has proven to be effective in selecting the most impactful, innovative, wellaligned, and sustainable projects for funding, by recruiting diverse and qualified volunteer proposal reviewers who are independent, academic, and professional experts in education abroad, academic exchanges, and regional higher education internationalization. |  |  | Document Reviews (Grant Applications, HEI Project Reports, Prospective Donor Records). Partners will track program progress through review and analysis of program beneficiaries’ documents. This includes the HEI grant applications and project reports submitted through Zengine, and donor records created and updated by Partners, which are maintained in Salesforce. |  |  | Percent of LAC participants indicating an increase in understanding of U.S. government, culture, and values
11 | Quarterly Performance Reports 1: July 30, 2023 | Y |  |  |  |  | At least four times annually, for each round of grants, onboard new project cohorts with orientation to administrative processes, disbursal of funds, visa requirements, clarification of responsibilities, and enable HEIs to connect with each other to promote peer mentorship and support, including through registration with the Alumni Network. |  |  | Secondary Data/Activity Analysis (Participatory Group Dialogue/Alumni Discussions, Ongoing & Direct Support to HEIs & Students). Partners will monitor student and HEI conduct throughout the program, using virtual engagement activities as opportunities for more personal observation and interaction with participants. |  |  | Percent of U.S. alumni reporting that they have used their exchange experience to make an effort to change other people’s understanding of their host country
12 | Quarterly Performance Reports 2: October 30, 2023 | Y |  |  |  |  | On at least a quarterly basis, facilitate connections and knowledge transfer between past winners and new HEI applicants through conference sessions, webinars, and the mentorship functions of the Program Alumni Network. |  |  | Pause and Reflect Sessions (Internal Activity level sessions; External Implementing level sessions): Partners will facilitate regular pause and reflect sessions with WHA and HEI grantees that will be carried out at two levels. Based on what is learned, Partners will determine its future strategies and amend the scope of work. |  |  | Percent of LAC alumni reporting that they have used their exchange experience to make an effort to change other people’s understanding of the U.S.
13 | Quarterly Performance Reports 3: January 30, 2024 | [5 empty] | For each grants competition, conduct up to three informational webinars in English and Spanish/Portuguese to prepare HEI applicants with tips and strategies for identifying institutional and inter-departmental partners and writing a competitive Program grant proposal. |  |  | Learning Dissemination: Program briefs; 2 online learning events (one at the beginning of the second year and another at the end of the award), and learning webinars |  |  | Percent of participants/alumni who identify as a DOS program participant/alumni
14 | Quarterly Performance Reports 4: April 30, 2024 | [5 empty] | Following each capacity-building activity, on at least a quarterly basis, share session presentations, recordings, a Q&A report, and a list of HEI associations, networks, and venues through which HEIs can find prospective partners widely available, including on the Program website and promoted to the Program Network. | [5 empty] | Percent of participants who learned about new resources & opportunities for engaging with DOS/100K and other participants/alumni
15 | Quarterly Performance Reports 5: July 30, 2024 | [5 empty] | On a target-of-opportunity basis, at least once a year, provide in-depth training through participant-led technical assistance workshops, in which the subject matter areas and topics are driven by HEIs and the sessions are led by past/current Program sub-grantees. Schedule training and networking workshops with WHA and Posts to take advantage of HEI convenings such as FAUBAI, CAIE, CCID, and NAFSA. | [5 empty] | Percent of participants who are connected to International Exchange Alumni networks through a U.S. Department of State-managed platform
16 | Quarterly Performance Reports 6: October 30, 2024 | [5 empty] | By the beginning of 2024, establish partnerships with at least eight new domestic and regional HEI associations, to amplify Program messaging and outreach, while maintaining existing HEI association partnerships. On at least a quarterly basis, share information with these partners about activities and opportunities. | [5 empty] | Percent of U.S. alumni who are using their program network to collaborate
17 | Quarterly Performance Reports 7: January 30, 2025 | [5 empty] | On a monthly basis, coordinate with WHA and Posts to curate, develop, and transmit the Program e-newsletter, to the Program Network and by any other relevant platforms, that highlights exchanges and participants and features information about grants competitions, relevant events, and “save-the-date” notices about upcoming opportunities, as well as impact data, case studies, effective practices, and Program participant impact stories. | [5 empty] | Percent of LAC alumni who are using their program network to collaborate
18 | Quarterly Performance Reports 8: April 30, 2025 | [5 empty] | For each grants competition, at least four times a year, create and publish press releases and social media communication kits to announce the launch of new Program grants competitions and winners. For the announcement of winners, create social media toolkits for HEIs, WHA, and Posts to amplify grant-winning teams and projects. Create promotional/social media graphics that relay competition eligibility at the start and during the round, and that display and congratulate the winners at the end of the round. Coordinate winners announcement events with WHA, Embassies, and donors. | [5 empty] | Percent of U.S. alumni who are still in contact with counterpart 100K program alumni and/or host institutions
19 | Quarterly Performance Reports 9: July 30, 2025 | [5 empty] | At least quarterly, at Program-related events, take photos and videos for use in targeted outreach and promotion. | [5 empty] | Percent of LAC alumni who are still in contact with counterpart 100K program alumni and/or host institutions
20 | Quarterly Performance Reports 10: October 30, 2025 | [5 empty] | Create new promotional tools, such as print and digital materials and graphics, for reaching different audiences, including potential HEI applicants and donors from the private sector, foundations, and non-U.S. governments, with a focus on highlighting the benefits of Program awards, showcasing sustainable exchange programs in the region, and sharing effective practices and models for international mobility programming. | [5 empty] | Percent of alumni who report using information or resources provided by the U.S. Government
21 | Final Program Report: XXX | [5 empty] | On at least a monthly basis, promote the Program and share impact and highlights through social media, using Partners.net, Twitter, Facebook, Instagram, and LinkedIn and including the #100KStrongAmericas hashtag. When appropriate, Partners will also tag WHA, donors, HEI beneficiaries, Embassies, and other Partners to maximize visibility and reach. | [5 empty] | Number of HEIs that participate in 100K Strong competitions
22 | Short-Term Consultant Reports, Technical Briefs/Reports, Special and External Reports: XXX | [5 empty] | On at least a quarterly basis, manage and update the Program website (www.100KStrongAmericas.org) with impact statistics, testimonials, news, resources, and opportunities for engagement with prospective donors and grant applicants. | [5 empty] | Total number of student participants in 100K Strong projects
23 | Short-Term Consultant Reports, Technical Briefs/Reports, Special and External Reports: XXX | [5 empty] | On at least a quarterly basis, launch and promote grants competitions through targeted outreach campaigns to diverse HEIs, such as community colleges, small- to mediumsized, rural, and minority-serving institutions. | [5 empty] | Number of students studying abroad as a result of grants
24 | Substantial Involvement: The program office (WHA/PDA) will have substantial, frequent, and on-going involvement and collaboration with the Recipient throughout the life of this award. Partners of the Americas (“PoA”), the Recipient, will work in close coordination with WHA/PDA to design, plan, implement, and evaluate 100K Strong programming, | Y |  |  |  |  | By the beginning of 2024, as noted under Goal 2 above, build partnerships with at least eight new HEI associations to reach a greater diversity of institutions. | [5 empty] | Percent of participants reporting an increase in their job as a result of 100K program participation
25 | Branding & Marking: U.S. DEPARTMENT OF STATE STANDARD TERMS AND CONDITIONS FOR FEDERAL AWARD: https://www.state.gov/wp-content/uploads/2020/10/U.S.-Department-of-State-Standard-Terms-and-Conditions-10-21-2020-508.pdf | Y |  |  |  |  | Starting in Spring 2023, once a year, hold virtual or in-person capacity-building engagements (in coordination with Posts) with HEIs in countries that are not currently able to host international students in exchange programs, to expand the geographic diversity of destination countries. | [5 empty] | Percent of participants reporting an increase in their soft skills as a result of 100K program participation
[7 empty] | In stimulating institutional partnerships, on at least a quarterly basis, lead sessions to share strategies, tools, and resources for partnership building and management with MSIs, targeted student recruitment, support services for first-time student travelers, etc., and invite presenters from HEIs that traditionally serve marginalized/underserved communities to ensure that diverse backgrounds, viewpoints, and occupational fields are represented. | [5 empty] | Percent of participants reporting an increase in their technical skills as a result of 100K program participation
[7 empty] | On a quarterly basis, implement virtual training sessions to expand HEI capacity to recruit and support diverse student populations. | [5 empty] | Percent of participants reporting an increase in their language skills as a result of 100K program participation
[7 empty] | For each grants competition, require HEI applicants to describe how they plan to expand access for students less commonly served by exchange programs, and give special consideration to projects that benefit marginalized, underserved, and non-traditional student populations (i.e., African-Descendants, Indigenous, LGBTQI+, persons with disabilities, women, etc.), using virtual or in-person modalities as appropriate. | [5 empty] | Percent of alumni reporting that they have used skills obtained from exchange program participation to provide leadership in a professional or volunteer capacity
[7 empty] | At least four times a year, tracked to regional/domestic funding sources and donor preferences, work with WHA, Posts, and donors to ensure that eligible academic themes include underrepresented academic disciplines, such as health, technology, climatefocused and clean-energy focused engineering, sustainable agriculture, and the sciences. | [5 empty] | Percent of alumni reporting that they have used skills obtained from exchange program participation to benefit their career, education, or volunteer work
[7 empty] | By August 2023, update the current M&E template for HEI-managed projects to be more comprehensive and aligned with the PMP and new M&E objectives, particularly to indicators that measure HEI and student diversity. | [5 empty] | Number of HEIs competing for innovation grants
[7 empty] | By September 2023, implement template requiring HEI applicants to develop a detailed plan for engaging with and including diverse student groups. | [5 empty] | Number of HEIs that receive 100K Strong innovation grants
[7 empty] | For proposal reviews, which will occur on at least a quarterly basis, recruit reviewers from a diverse range of HEIs in the United States and the region, including from MSIs and HEIs that traditionally serve marginalized/underserved student populations to participate and provide insight and feedback on proposals. Inform all reviewers of the diversity of HEI grant applicants, with varying financial and human capacity to carry out projects, and emphasize the importance of weighing the relative capacity of the applicants and the contexts in which they operate. | [5 empty] | Number of capacity-building and training workshops and meetings conducted to promote 100K grants and to build the 100K Network with domestic and regional HEIs
[7 empty] | By July 2023, work with WHA to evaluate the possibility of restricting some grants competition pools or establishing quotas for MSIs and HEIs with limited capacity, which would ensure diversity in funded projects. Consider grouping repeat 100K winners as well, to ensure the Program is building capacity at a range of HEIs. | [5 empty] | Number of U.S. and LAC higher education institutions attending 100K capacity building trainings
[7 empty] | By October 2023 and on an ongoing basis as needed, seek donor-partner sponsorship to provide resources to strengthen students’ English, Spanish, or Portuguese abilities (e.g., an open-access language course or in-kind support from Rosetta Stone and/or Duolingo), so that students of diverse socioeconomic standing and language skills can participate. | [5 empty] | Number of exchange participants in the program
[7 empty] | By August 2023, establish a mechanism to provide low-income and/or students from marginalized groups with stipends to cover passport fees. | [5 empty] | Percent of HEI faculty/administrators reporting strengthened partnerships within the Hemisphere
[7 empty] | By October 2023, launch the 100K Alumni Network on the Graduway platform, facilitating mentorship connections, connections with peers, access to job/internship postings and career fairs, and updates about 100K and other relevant USG programs and opportunities. | [5 empty] | Percent of HEI faculty/administrators reporting they are successfully implementing new models of exchanges within their institution
[7 empty] | No later than November 2023, enlist the support of volunteer Community Ambassadors/Influencers recruited from among each 100K student cohort as a keystone of the new alumni engagement strategy. Partners will recruit and prepare Community Influencers, host bi-monthly webinars on topics of interest, monitor network activity, seed discussions, and manage backend maintenance. | [5 empty] | Percent of HEIs that have sustained new study abroad/exchange partnerships after 100K Strong-funded project ended
[7 empty] | By the beginning of 2024, while continuing to enroll new students and faculty in the 100K Strong Alumni Network, implement an exhaustive outreach strategy to enroll pre-2020 alumni, verifying, updating, and organizing contact information for optimal utility. | [5 empty] | Percent of HEI grantees that present on their 100K Strong project and results in conferences, webinars or other venues
[7 empty] | By September 2023, validate and submit participant data using the designated data collection template provided by the DOS Bureau of Educational and Cultural Affairs (ECA)’s Office of Alumni Affairs to create alumni records in the Alumni Engagement Contact System (ACES). | [5 empty] | Percent of HEIs receiving 100K Strong grant funding that are MSIs, CCs, or HEIs that traditionally serve marginalized/underserved students
[7 empty] | On a quarterly basis after August 2023, validate and submit updated participant and alumni data to the Office of Alumni Affairs using the designated ACES template. | [5 empty] | Percent of student participants from marginalized/underserved communities
[7 empty] | Baseline study, collecting qualitative and quantitative baseline information within the first six months of the startup of the HEI projects, adapting existing pre- and post-project surveys as needed, and an endline study roughly 60 days before the end of the project, applying quantitative surveys and qualitative techniques (e.g., focus groups discussion, key informant interviews) and integrating findings from data collected during implementation (i.e., HEI proposals, project reports, etc.) to compare to baseline results. | [5 empty] | Percent of HEI grantees reporting that the 100K grant funding enabled their institution to provide critical access to exchanges for underrepresented students
[7 empty] | On at least a quarterly basis, and continuously as needed, maintain participants’ contact information through the 100K Alumni Network to facilitate long-term outcome evaluation. | [5 empty] | Number of new members of the 100K Innovation Network
[7 empty] | In the final phase of this cooperative award, in the first quarter of CY25, commission a final evaluation to be conducted by a third party, using similar quantitative/qualitative methodology from the baseline study. | [5 empty] | Number of visitors to 100K Strong website
[7 empty] | At least twice a year, conduct pause and reflect sessions both at the activity level, to internally review Program data, identify trends, analyze achievements, and collect feedback that contribute to better planning and evidence-based decision-making, and at the implementing level, where Partners will discuss information from activity-level sessions with WHA to identify key issues/practices affecting implementation. | [5 empty] | Number of social media impressions
[7 empty] | At least twice a year, disseminate lessons learned through various methods: Program briefs that share performance M&E data and summarize Program accomplishments, challenges, and recommendations; online learning events - one in early 2024 and another in late 2025, with key stakeholders; and learning webinars that provide a platform for HEIs grantees and 100K students to present and share their learning experiences with WHA, donor-partners, and Partners. | [5 empty] | Number of applications from new HEIs

## Subaward Summary Page
Compliance Matrix
Subaward Name/Title: |  |  |  |  | Total Award Amount: |  | POA Subaward Manager(s) (including dates):
Internal Grant Name: |  |  |  |  | Total Obligation Amount:
Subaward Number: |  |  |  |  | Cost Share Amount:
Donor: |  |  |  |  | Leverage Amount:
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: |  |  |  |  | Key Personnel:
Subaward End Date: |  |  |  |  | Approved Indirect Rate(s) %:
Subaward Point of Contact: |  |  |  |  | Prior Approvals Required:
POA Point of Contact: |  |  |  |  | Treatment of Program Income:
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY