## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | 100K Strong Peru |  |  |  | Total Award Amount: | 165000 | Program Manager(s) (including dates):
Internal Grant Number: | DOS262 |  |  |  | Total Obligation Amount: | 165000
Award Number: | SPE50020GR0055 |  |  |  | Cost Share Amount: | 0
Donor: | U.S. Embassy Lima |  |  |  | Leverage Amount: | 0
CFDA: | 19.040 |  |  |  | USAID Only: Geographic Code:
Award Start Date: | 2020-09-29 |  |  |  | Key Personnel: | Ana Rubi; Victor Moscoso
Award End Date: | 2024-07-31 |  |  |  | Approved Indirect Rate(s) %: | 28.69%
Program Director: | Penelope Kim |  |  |  | Prior Approvals Required: | No
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Jorge D Rivera |  |  |  | Treatment of Program Income: | Deduction
Agreement Officer (AO)/Grants Officer (GO):
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Agreement | n/a | 2020-2022 | 2020-09-28 | 2020-09-28 | 100K-Embassy Peru SPE50020GR0055 - (2020-09-29 to 2022-11-30) | https://partnersnet107.sharepoint.com/:b:/s/Programs/EfGXMDJPrO5AkAnljX1yLwMBPvyArfBPG9HdQi7LTxPgBw?e=fJb55g | Original Prime Award Agreement
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | 2020-2024 | 2022-07-18 | 2022-09-23 | GRANTMOD 12 100K Embassy in Peru - NCE of SPE50020GR0055 (2020-09-29 to 2024-07-31) | https://partnersnet107.sharepoint.com/:b:/s/Programs/EYXcfi0zkrtLkfWnIcjIu64BgFqYJWKwniy9oV-QW4VZCg?e=d9Rr1r | Approved No-Cost Extension Request through July 2024
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Scope of Work (SOW)
Implementation Plan/ Scope of Work | FY2020 | 2020-2024 | 2020-09-21 | 2020-09-28 | SOW for PAS Lima for EOY 2020 funds to support WHA regional 100K programs (v09212020) | https://partnersnet107.sharepoint.com/:w:/s/Programs/EYPbrOSz2uZCtIMjHL8l_HgBfNhT2mUNgsb8rw-1QFqNCg?e=Fpz7Xp | Approved Scope of Work
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Compliance Matrix Details
Breakdown of Award Requirements
| Award Terms & Conditions | Compliant Y/N | Comments | Program Description | Compliant Y/N | Comments | Work Plan 2022-2024 | Compliant Y/N | Comments | Activities in Budget Narrative | Compliant Y/N | Comments
1 | Annual Financial Reporting 01: October 28, 2021 |  |  | Description: Leverage public/private collaborations, create 100K-branded opportunities for higher ed. institutions from the U.S., Peru, and other WHA countries. |  |  | Secure commitments to the Innovation Fund from private/public sector and regional government partners |  |  | Personnel & Fringe: VP/Senior Director and Director of Partnerships
2 | Annual Financial Reporting 02: October 30, 2022 |  |  | Geographic Scope: U.S.-Peru |  |  | Convene a webinar for regional HEIs to promote new 100K opportunity in 2021 |  |  | Staff Travel: One (1) international trip to Peru for fundraising/donor cultivation, grant competition launch or winners announcement
3 | Annual Financial Reporting 03: October 30, 2023 | [5 empty] | Engage with prospective donors for potential resource cultivation to support 100K Innovation Fund partnerships |  |  | HEI Grants: Partners will provide sub-grants to Innovation Fund grant-winning teams of HEIs in the US, Peru, select WHA countries based on the 100K evaluation and selection process.
4 | Annual Performance Report 01: October 28, 2021 | [5 empty] | Support Partners’ mechanisms to build sustainability in Peru + select WHA/AND countries and leverage potential private/public sector and regional government partners’ commitments for 100K partnership opportunities |  |  | Consultant: If needed, POA will hire a fundraising consultant to support fundraising efforts in Peru.
5 | Annual Performance Report 02: October 30, 2022 | [5 empty] | Launch potential new 100K Innovation Fund competition for HEIs from Peru + select WHA countries in 2021. Partners will work with WHA/PDA and PAS-Peru to carry-out Innovation Fund grant activities, including outreach, promotion, 100K sub-grant evaluation/selection, and providing sub-award grants to TBC grant winning teams.
6 | Annual Performance Report 03: October 30, 2023
7 | Final Program Report: October 30, 2024
8 | Program Income: Deduction: Any program income earned by the Recipient as a result of this award and during the period of performance must be deducted from the total allowable costs in order to determine the net allowable costs for the award.
9 | Branding & Marking: N/A
10
11
12
13
14

## CSN Subaward Summary
Compliance Matrix
Subaward Name/Title: | Alimentaré – Alimentary: Bilateral International Exchange to Pinpoint Key Elements in Sustainable Food Systems |  |  |  | Total Award Amount: | 27430.9 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 100K-DOS262-CSN |  |  |  | Total Obligation Amount: | 27430.9
Subaward Number: | 100KSubAg. 81 100K-DOS262-CSN FAA |  |  |  | Cost Share Amount: | N/A
Donor: | U.S Embassy, Lima - DOS262 |  |  |  | Leverage Amount:
CFDA: | 19.04 |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2023-02-01 |  |  |  | Key Personnel: | Dr. Ruth Palileo
Subaward End Date: | 2024-05-31 |  |  |  | Approved Indirect Rate(s) %: | 10%
Subaward Point of Contact: | Mary Kaye Bailey |  |  |  | Prior Approvals Required:
POA Point of Contact: | Mariana Cabrera Figueroa (Technical), Summar Lyons (Contracts) |  |  |  | Treatment of Program Income: | Deduction
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | 02/01/2023-05/31/2024 | 2023-03-21 | 2023-03-24 | 100KSubAg. 81 100K-DOS262-CSN FAA | 100KSubAg. 81 100K-DOS262-CSN FAA (2023-02-01 to 2024-05-31).pdf | CSN SubAward Agreement
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## SDSMT Subaward Summary
Compliance Matrix
Subaward Name/Title: | Increasing the Partnership, Technical Training, and Exchange of Students between UPC-PERU, Lima, PE, and SDSMT, Rapid City, USA |  |  |  | Total Award Amount: | 36085.8 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 100K-DOS262-SDSMT |  |  |  | Total Obligation Amount: | 36085.8
Subaward Number: | 100KSubAg. 84 100K-DOS262-SDSMT FAA |  |  |  | Cost Share Amount: | N/A
Donor: | U.S Embassy, Lima - DOS262 |  |  |  | Leverage Amount:
CFDA: | 19.04 |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2023-02-01 |  |  |  | Key Personnel: | Dr. David Dixon
Subaward End Date: | 2024-05-31 |  |  |  | Approved Indirect Rate(s) %: | 20%
Subaward Point of Contact: | Laurie C. Anderson, Ph.D. |  |  |  | Prior Approvals Required:
POA Point of Contact: | Mariana Cabrera Figueroa (Technical), Summar Lyons (Contracts) |  |  |  | Treatment of Program Income: | Deduction
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | 02/01/2023-05/31/2024 | 2023-08-02 | 2023-08-08 | 100KSubAg. 84 100K-DOS262-SDSMT FAA | 100KSubAg. 84 100K-DOS262-SDSMT FAA (2023-02-01 to 2024-05-31).pdf | SDSMT SubAward Agreement
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## UOk Subaward Summary
Compliance Matrix
Subaward Name/Title: | Knowledge and Cultural Exchange Through the built Environment: Inti Wasi Sustainable and Affordable Cold Climate Housing |  |  |  | Total Award Amount: | 35988 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 100K-DOS262-Oklahoma |  |  |  | Total Obligation Amount: | 35988
Subaward Number: | 100KSubAg. 85 100K-DOS262-Oklahoma FAA |  |  |  | Cost Share Amount: | N/A
Donor: | U.S Embassy, Lima - DOS262 |  |  |  | Leverage Amount:
CFDA: | 19.04 |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2023-02-01 |  |  |  | Key Personnel: | Dr. Ben Bigelow
Subaward End Date: | 2024-05-31 |  |  |  | Approved Indirect Rate(s) %: | 20%
Subaward Point of Contact: | Michael Purcell |  |  |  | Prior Approvals Required:
POA Point of Contact: | Mariana Cabrera Figueroa (Technical), Summar Lyons (Contracts) |  |  |  | Treatment of Program Income: | Deduction
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | 02/01/2023-05/31/2024 | 2023-05-23 | 2023-05-29 | 100KSubAg. 85 100K-DOS262-Oklahoma FAA | 100KSubAg. 85 100K-DOS262-Oklahoma FAA (2023-02-01 to 2024-05-31).pdf | UOk SubAward Agreement
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY