## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | Mexico United 2026 |  |  |  | Total Award Amount: | $1,117,283.00 USD | Program Manager(s) (including dates):
Internal Grant Number: | DOS452 |  |  |  | Total Obligation Amount: | $1,117,283.00 USD | Fadrique Iglesias (2020-2021)
Award Number: | SLMAQM20GR2337 |  |  |  | Cost Share Amount: | $0 USD | Macarena Jimenez Granda (2022-present)
Donor: | U.S. Department of State |  |  |  | Leverage Amount: | $0 USD
CFDA: | 19.345 |  |  |  | USAID Only: Geographic Code:
Award Start Date: | 2020-09-16 |  |  |  | Key Personnel: | Macarena Jimenez Granda, Senior Director Labor Unit
Award End Date: | 2026-09-30 |  |  |  | Approved Indirect Rate(s) %: | 28.28% (NICRA)
Program Director: | TBD |  |  |  | Prior Approvals Required:
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Cara Vileno, VilenoCE@state.gov/ Ashley Nelson NelsonA6@state.gov |  |  |  | Treatment of Program Income: | Addition
Agreement Officer (AO)/Grants Officer (GO): | Selina Holt, Holtsm@state.gov
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Agreement | 2020 | 2020-2023 | 2020-06-08 | 2020-09-16 | SLMAQM20GR2337 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FDonor%2FAward%2FSLMAQM20GR2337%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FDonor%2FAward | Original award
No-Cost Extension | 2023 | 2020-2023 | 2023-03-22 | 2023-03-27 | DOS452 No Cost Extension JMcPhail Approval | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FDonor%2FExtensions%2FNo%20Cost%20Extension&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32 | No cost extension of period of performance from 03/30/2023 to 09/30/2023
Cost Extension | 2023 | 2020-2026 | 2023-08-28 | 2023-09-07 | USDOS Mexico United 2026 SLMAQM20GR2337-M002 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FDonor%2FExtensions%2FCost%20Extension%2F%5FDOS%20Approval%2FUSDOS%20Mexico%20United%202026%20SLMAQM20GR2337%2DM002%20%281%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FDonor%2FExtensions%2FCost%20Extension%2F%5FDOS%20Approval | Cost extension of period of performance from 09/30/2024 to 09/30/2026 and an additional $500,000
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | FYXX | 2020-2023 | 2020-06-08 | 2020-09-16
M&E Plan - Revision | FYXX | 2020-2023 | 2021-04-01 | 2021-04-01
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | 2020-2026 | 2023-08-28 | 2023-09-07
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | FYXX | 2020-2023 | 2020-06-08 | 2020-09-16
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | 2020-2026 | 2023-08-28 | 2023-09-07
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Compliance Matrix Details
Breakdown of Award Requirements
| Award Terms & Conditions | Compliant Y/N | Comments | Program Description | Compliant Y/N | Comments | Work Plan F2021 | Compliant Y/N | Comments | Workplan FY2022 | Compliant Y/N | Comments | Work Plan 2023 | Compliant Y/N | Comments | Workplan 2024 | Compliant Y/N | Comments | MEL Plan | Compliant Y/N | Comments | Indicators | Compliant Y/N | Comments | Environmental Mitigation and Monitoring Plan - EMMP | Compliant Y/N | Comments | Activities in Budget Narrative | Compliant Y/N | Comments
1 | Financial Reporting: Quarterly Federal Financial Reports | Y | Submitted each Jan, Apr, July, and Oct since inception | Description: In partnership with three well-established local labor rights organizations: Centro de Reflexión y Acción Laboral (CEREAL), Red de Mujeres Sindicalistas (RMS) and Centro de los Derechos del Migrante (CDM), Partners aims to strengthen Mexico’s capacity to identify, prevent and mitigate the impacts of the United 2026 games on the realization of labor rights and human rights guarantees by facilitating coordination among civil society organizations (CSOs), labor unions, the business sector, and the government. In line with DOS/DRL programming, proposed activities are organized around four objectives: · Increase workers’ knowledge and ability to understand the applicability of labor law and international labor standards relevant to the United 2026 games. · Increase engagement and coordination between labor rights organizations, the private sector, and democratic, independent unions on the United Human Rights Strategy (UHRS) and around pre-games planning of United 2026 events, including the implementation of the human rights strategy in each host city, and ways that the Government of Mexico, Fédération Internationale de Football Association (FIFA), and the Federación Mexicana de Fútbol Asociación (MFA) will address and mitigate labor rights risks associated with the games. · Strengthen the capacity of civil society actors, independent unions, and workers to monitor and report labor and human right abuses, to prepare to effectively document violations, and make strategic use of reporting and enforcement mechanisms related to the operation of the games. · Increase public awareness of Mexico’s commitments to labor rights regarding the United 2026 games | Y |  | Activity 1: Expand educational programs led by LROs in Mexico with experience in popular education methods, to train workers on protections under Mexican labor law, international labor standards, business and human rights frameworks relevant to the United 2026 games, and the risks of the games for Mexican workers. Activity 2: Establish and facilitate a civil society labor advisory network in Mexico. Activity 3: Develop training programs for human rights and labor rights defenders on monitoring, case development, and filing processes for existing grievance and conciliation procedures, and assist with the planning and implementation of alternative grievance procedures. Activity 4: Strengthen collaboration between civil society and journalists to monitor and report on labor rights impacts during the lifecycle of the games, including tracking violations and complaints submitted to grievance channels. Activity 5: Provide technical assistance to civil society to develop a media campaign to socialize information of labor rights risks, in preparation for the United 2026 games. | Y |  | Activity 1: Expand educational programs led by LROs in Mexico with experience in popular education methods, to train workers on protections under Mexican labor law, international labor standards, business and human rights frameworks relevant to the United 2026 games, and the risks of the games for Mexican workers. Activity 2: Establish and facilitate a civil society labor advisory network in Mexico. Activity 3: Develop training programs for human rights and labor rights defenders on monitoring, case development, and filing processes for existing grievance and conciliation procedures, and assist with the planning and implementation of alternative grievance procedures. Activity 4: Strengthen collaboration between civil society and journalists to monitor and report on labor rights impacts during the lifecycle of the games, including tracking violations and complaints submitted to grievance channels. Activity 5: Provide technical assistance to civil society to develop a media campaign to socialize information of labor rights risks, in preparation for the United 2026 games. | y |  | Activity 1: Expand educational programs led by LROs in Mexico with experience in popular education methods, to train workers on protections under Mexican labor law, international labor standards, business and human rights frameworks relevant to the United 2026 games, and the risks of the games for Mexican workers. Activity 2: Establish and facilitate a civil society labor advisory network in Mexico. Activity 4: Strengthen collaboration between civil society and journalists to monitor and report on labor rights impacts during the lifecycle of the games, including tracking violations and complaints submitted to grievance channels. Activity 5: Provide technical assistance to civil society to develop a media campaign to socialize information of labor rights risks, in preparation for the United 2026 games. | y |  | Activity 1: Expand educational programs led by LROs in Mexico with experience in popular education methods, to train workers on protections under Mexican labor law, international labor standards, business and human rights frameworks relevant to the United 2026 games, and the risks of the games for Mexican workers. Activity 2: Establish and facilitate a civil society labor advisory network in Mexico. Activity 3: Develop training programs for human rights and labor rights defenders on monitoring, case development, and filing processes for existing grievance and conciliation procedures, and assist with the planning and implementation of alternative grievance procedures. Activity 4: Strengthen collaboration between civil society and journalists to monitor and report on labor rights impacts during the lifecycle of the games, including tracking violations and complaints submitted to grievance channels. Activity 5: Provide technical assistance to civil society to develop a media campaign to socialize information of labor rights risks, in preparation for the United 2026 games. | y |  | Conduct M&E Training with project staff and CDM, CEREAL and RMS staff Hold coordination meetings with CDM, CEREAL, RMS to monitor project progress and make adjustments Conduct an open competition for external mid-term project evaluation Carry out an external mid-term evaluation | Y
20 | Quarterly Performance Reports | Y | All QR's submitted on time and accepted by donor
26 | Final Program Report: within 90 days end of award
29 | Closeout Plan: XXX
39 | Substantial Involvement: XXX
42 | Branding: XXX
43 | Marking: XXX
44 | Marking: XXX
45
46
47
48
49
50

## CDM Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | Mexico United 2026 between Partners of the Americas and Cetnro de los Derechos del Migrante |  |  |  | Total Award Amount: | 60759.41 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOS452 |  |  |  | Total Obligation Amount: | n/a: fixed price | Fadrique Iglesias, 2021
Subaward Number: | DOS452-2021-01 |  |  |  | Cost Share Amount: | 0 | Macarena Jimenez Granda, 2022-present
Donor: | U.S. Department of State |  |  |  | Leverage Amount:
CFDA: |  |  |  |  | USAID Only: Geographic Code: | 0
Subaward Start Date: | 2021-07-01 |  |  |  | Key Personnel:
Subaward End Date: | 2022-12-31 |  |  |  | Approved Indirect Rate(s) %: | 10% de minimus
Subaward Point of Contact: | Rachel Micah-Jones, Rachel@cdmigrante.org |  |  |  | Prior Approvals Required:
POA Point of Contact: | TBD |  |  |  | Treatment of Program Income: | addition
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2021 | 2021-2022 | 2021-05-31 | 2021-07-27 | Mexico United 2026 between Partners of the Americas and Cetnro de los Derechos del Migrante | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCDM%2FSub%20Award%20Agreement%2FFully%20Executed%2FSubawardFC%202%20DOS452%20CDM%20Fixed%20Price%20Sub%2DAward%202021%2D07%2D01%20to%202023%2D06%2D30%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCDM%2FSub%20Award%20Agreement%2FFully%20Executed | Fixed-price subaward agreement between POA and CDM for implementation of the Mexico United 2026 project
Modification 01 | 2021 | 2021-2022 | 2021-10-12 | 2021-10-25 | Sub-Agreement Modification No. 1 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCDM%2FSub%20Award%20Agreement%2F%5FMod%2FMod01%2FSAMOD%2016%20DOS452%20CDM%20Subaward%20Mod%202021%2D09%2D01%20to%202022%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCDM%2FSub%20Award%20Agreement%2F%5FMod%2FMod01 | Modification to adjust the completion date of CDM's first deliverable from Septmber 20 to December 31, 2021
Modification 02 | 2021 | 2021-2022 | 2021-12-15 | 2021-12-20 | Sub-Agreement Modification No. 2 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCDM%2FSub%20Award%20Agreement%2F%5FMod%2FMod02%2FSAMOD%2021%20DOS452%20CDM%20Subaward%20Mod%2002%202021%2D09%2D01%20to%202022%2D12%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCDM%2FSub%20Award%20Agreement%2F%5FMod%2FMod02 | Adjust the completion date of deliverable 2 from December 1, 2021 back to September 20, 2022 to correct an error in the previous modification
Modification 03 | 2022 | 2021-2022 | 2022-10-18 | 2022-11-22 | Sub-Agreement Modification No. 3 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCDM%2FSub%20Award%20Agreement%2F%5FMod%2FMod03%2FSAMOD%2061%20DOS452%20CDM%20Sub%20Award%20Mod%2003%202021%2D07%2D01%20%2D%202022%2D%2012%2D%2031%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCDM%2FSub%20Award%20Agreement%2F%5FMod%2FMod03 | Change subaward supervisor from Alma Rico to Saskia Cabrera; Change subaward technical monitors from Alma Rico and Fadrique Iglesias to Saskia Cabrera and Macarena Jimenez; Adjust the date of three deliverables- second educational video, second awareness raising workship, and mass media campaign
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | FY2021 | 2021-2022 | 2021-05-31 | 2021-07-27 | Mexico United 2026 between Partners of the Americas and Cetnro de los Derechos del Migrante | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCDM%2FSub%20Award%20Agreement%2FFully%20Executed%2FSubawardFC%202%20DOS452%20CDM%20Fixed%20Price%20Sub%2DAward%202021%2D07%2D01%20to%202023%2D06%2D30%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCDM%2FSub%20Award%20Agreement%2FFully%20Executed | Subawardee to follow the project's M&E plan
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## CEREAL Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | Mexico United 2026 between Partners of the Americas and Centro de Reflexion y Accion Laboral |  |  |  | Total Award Amount: | 50412 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOS452 |  |  |  | Total Obligation Amount: | n/a: fixed-price award | Fadrique Iglesias, 2021
Subaward Number: | DOS452-2021-02 |  |  |  | Cost Share Amount: | 0 | Macarena Jimenez, 2022-present
Donor: | U.S. Department of State |  |  |  | Leverage Amount: | 0
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2021-07-21 |  |  |  | Key Personnel: | TBD
Subaward End Date: | 2022-10-31 |  |  |  | Approved Indirect Rate(s) %: | 10% de minimus
Subaward Point of Contact: | Hugo Mendoza, cerealdireccion@gmail.com |  |  |  | Prior Approvals Required:
POA Point of Contact: | TBD |  |  |  | Treatment of Program Income: | Addition
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2021 | 2021-2022 | 2021-06-14 | 2021-07-27 | Mexico United 2026 between Partners of the Americas and Centro de Reflexion y Accion Laboral | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCEREAL%2FSub%20Award%20Agreement%2FFully%20Executed%2FSubawardFC%204%20DOS452%20CEREAL%20Fixed%20Price%20SubAward%202021%2D07%2D01%20to%202022%2D10%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCEREAL%2FSub%20Award%20Agreement%2FFully%20Executed | Fixed-price subaward agreement between POA and CERAL
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2021 | 2021-2022 | 2021-09-01 | 2021-10-04 | Sub-Agreement Modification No. 1 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCEREAL%2FSub%20Award%20Agreement%2F%5FMods%2FMod001%2FSAMOD%2014%20DOS452%20CEREAL%20Subaward%20Modification%2001%202021%2D07%2D01%20to%202022%2D10%2D31%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCEREAL%2FSub%20Award%20Agreement%2F%5FMods%2FMod001 | Adjust completion date of deliverable 1.6 from August 31, 2021 to October 31, 2021
Modification 02 | 2022 | 2021-2022 | 2023-08-10 | 2022-08-31 | Sub-Agreement Modification No. 2 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCEREAL%2FSub%20Award%20Agreement%2F%5FMods%2FMod002%2FSAMOD%2045%20DOS452%20SA%20Mod002%20CEREAL%202021%2D07%2D01%20%2D%202022%2D10%2D31%20%281%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FCEREAL%2FSub%20Award%20Agreement%2F%5FMods%2FMod002 | Adjust the content of workshops under deliverable 6.1
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## RMS Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | Mexico United 2026 between Partners of the Americas and Red de Mujeres Sindicalistas |  |  |  | Total Award Amount: | 58000 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | DOS452 |  |  |  | Total Obligation Amount: | n/a: fixed price award | Fadrique Iglesias, 2021
Subaward Number: | DOS452-2021-03 |  |  |  | Cost Share Amount: | 0 | Macarena Jimenez Granda, 2022-present
Donor: | U.S. Department of State |  |  |  | Leverage Amount: | 0
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: | 2021-07-01 |  |  |  | Key Personnel:
Subaward End Date: | 2022-11-30 |  |  |  | Approved Indirect Rate(s) %: | 10% de minimus
Subaward Point of Contact: | Rosario Ortiz, rosaria21@gmail.com |  |  |  | Prior Approvals Required:
POA Point of Contact: | TBD |  |  |  | Treatment of Program Income: | Addition
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2021 | 2021-2022 | 2021-06-22 | 2021-07-27 | Mexico United 2026 between Partners of the Americas and Red de Mujeres Sindicalistas | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FRMS%2FSub%20Award%20Agreement%2FFully%20Executed%2FSubawardFC%205%20DOS452%20RMS%20Fixed%20Price%20Sub%2DAward%202021%2D07%2D01%20to%202022%2D11%2D30%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FRMS%2FSub%20Award%20Agreement%2FFully%20Executed | Fixed-price subaward agreement between POA and RMS
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | 2022 | 2021-2022 | 2021-12-15 | 2022-03-25 | Sub-Agreement Modification No. 01 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FRMS%2FSub%20Award%20Agreement%2F%5FMods%2FMod01%2FSAMOD%2024%20DOS452%20RMS%20Subaward%20Mod01%202021%2D07%2D01%20to%202022%2D11%2D30%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FRMS%2FSub%20Award%20Agreement%2F%5FMods%2FMod01 | Adjust completion date of various deliverables due to delays in implementation; change comic book deliverable to a video to reach the target audience
Modification 02 | 2022 | 2021-2022 | 2022-06-08 | 2022-08-30 | Sub-Agreement Modification No. 02 | https://partnersnet107.sharepoint.com/sites/Programs/CPU/Forms/AllItems.aspx?id=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FRMS%2FSub%20Award%20Agreement%2F%5FMods%2FMod02%2FSAMOD%2036%20DOS452%20Subaward%20Modification%20002%20RMS%2007%2D01%2D2021%20%2D%2011%2D30%2D2022%20%282%29%2Epdf&viewid=41774e83%2D824b%2D449c%2Da804%2Dacd3c5941c32&parent=%2Fsites%2FPrograms%2FCPU%2FDOS452%2FAgreements%2FSub%2Dawards%2FRMS%2FSub%20Award%20Agreement%2F%5FMods%2FMod02 | Extend completion date of journalist meetings deliverable from may to august, 2022; modify deliverable 2 to clarify that videos will not be comics
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY