## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | John Ogonowski and Doug Bereuter Farmer-to-Farmer Program |  |  |  | Total Award Amount: | 8500000 | Program Manager(s) (including dates):
Internal Grant Number: | USAID650 |  |  |  | Total Obligation Amount: | 1623809.21 | Stephanie Verganza - Oct 1, 2023 to present
Award Number: | Cooperate Agreement No. 7200AA23LE00014 |  |  |  | Cost Share Amount: | N/A
Donor: | USAID |  |  |  | Leverage Amount: | 2766600
CFDA: | 98.009 |  |  |  | USAID Only: Geographic Code: | 937
Award Start Date: | 2023-10-01 |  |  |  | Key Personnel: | Gustavo Galdo, Jermaine Joseph, Rafael Marte Aracena, Marsha Johnson, Jose Cano
Award End Date: | 2028-09-29 |  |  |  | Approved Indirect Rate(s) %: | 28.28%
Program Director: | Gustavo Galdo |  |  |  | Prior Approvals Required:
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Margaret Carlson |  |  |  | Treatment of Program Income: | Shall be added to the USAID funding and applied towards program use. Program income is not anticipated
Agreement Officer (AO)/Grants Officer (GO): | Rachel Baltes
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Cooperative Agreement | FY24-FY28 | 2023-2028 |  | 2023-09-27 | F2F Leader CA POA FE | F2F Leader CA POA FE.pdf
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
MEL Plan | FY24-FY28 | 2023-2028 | 2023-11-29 | Pending
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan
LOP Work Plan | FY24-FY28 | 2023-2028 | 2023-11-22 | Pending | POA_F2F Caribbean Basin Program_LOP Work Plan
Year One Work Plan | FY24 | 2023-2024 | 2023-11-22 | Pending | POA_F2F Caribbean Basin_Year One Work Plan
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FY24 | 2023-2024 | 2023-11-22 | Pending | Annex 1_POA_F2F Caribbean Basin Program_EMMP
Special Provisions/Restrictions
Branding Strategy and MarkingPlan | FY24-FY28 | 2023-2028 | 2023-11-10 | 2023-11-30 | USAID650_Branding and Marking Plan_2023-11-10 | USAID650_Branding and Marking Plan_2023-11-10.docx
Special Environmental Requirements
We must comply with Section 117 of the Foreign Assistence Act of 1961. Codified in 22 CFR 216 and in ADS 201 and 204 |  |  | N/A
We must comply wiyth the terms outline in the IEE (Attachment E) |  |  | N/A
Year one Work Plan should include an EMMP |  |  | 2023-11-22 | Pending | Annex 1_POA_F2F Caribbean Basin Program_EMMP
We must follow all requirements in the PERSUAP |  |  | N/A
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes (that resulted in change of plans or approvals granted) | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Core $7,500,000 plus potential $1,000,000 in buy-ins. Up to $34,000,000 for Associate Awards

## Compliance Matrix Details
Breakdown of Award Requirements
1 | Award Terms & Conditions (Financial Reports) | Compliant Y/N | Comments | Program Description | Compliant Y/N | Comments | Work Plan FY24 | Compliant Y/N | Comments | Workplan FY25 | Compliant Y/N | Comments | Work Plan FY26 | Compliant Y/N | Comments | Workplan FY27 | Compliant Y/N | Comments | MEL Plan FY24-FY28 | Compliant Y/N | Comments | Indicators | Compliant Y/N | Comments | Environmental Mitigation and Monitoring Plan - EMMP | Compliant Y/N | Comments | Activities in Budget Narrative | Compliant Y/N | Comments
2 | Branding Strategy and Marking Plan, FY24 FY28: 10/30/2023 | Y | Approved on 11/30/2023 | Dominican Republic Watershed Management Farmer-to-Farmer Project aims to improve capacity through sustainable livelihoods, improved practices, and enhanced watershed governance. |  | Pending approval | Dominican Republic Watershed Management |  | Pending approval | [9 empty] | MEL Plan, FY24 FY28: 11/30/2023 |  |  | Input-1/ No. of Volunteer Assignments (Total) |  |  | Pesticide-related mitigation measures from the F2F IEE |  |  | (Report changes in the original Budget Narrative)
3 | Country Descriptions, FY24 FY28: 11/10/2024 | Y | Pending approval | Geographic Scope: along the Yaque del Norte |  |  | Watershed Planning: POA will recruit volunteers to work with NGOs, local governments, universities, and other relevant actors on designing and executing watershed management plans. Volunteers will work with host organizations to develop plans that use key climate information and participatory planning to successfully guide watershed management planning. | [11 empty] | Semi-annual Performance Report, FY24 Q1Q2 (October 1 through March 31): 04/30/24 |  |  | Input-1/ No. of Volunteer Assignments (Male) |  |  | (1) All POA F2F staff will be provided with and will familiarize themselves with the F2F environmental brochures. Monitor and report annually
4 | Life of Proyect Work Plan, FY24 FY28: 11/30/2023 | Y | Pending approval | • Increase natural resource use efficiency in agriculture and livestock production. |  |  | Agroforestry: Volunteers will work with producers to plan and implement strategies that incorporate trees into agriculture systems. Assignments will focus on identifying species that function well together and that produce ecosystem services such as reducing erosion, increasing water absorption, and controlling extreme temperatures. | [11 empty] | Annual Performance Report, FY24 Q1Q2Q3Q4 (October 1 through September 30): 10/30/24 |  |  | Input-1/ No. of Volunteer Assignments (Female) |  |  | (2) F2F volunteers will be provided with the Environmental brochure for F2F volunteers. Monitor and report semi-annually
5 | Year one Work Plan, FY24: 11/30/2023 | Y | Pending approval | • Build the capacity of watershed managers and planners. |  |  | Climate Information and Data: POA will conduct administrative assignments in Year One with Climate Data and Information Experts. These assignments will produce information on watershed management, high impact assignments that align with cutting edge adaptation tools, and opportunities to collect and share data. | [14 empty] | Input-1/ No. of First Time Volunteers
6 | Environmental Mitigation and Monitoring Plan, FY24 FY24: 11/30/2023 | Y | Pending approval | • Improve technical capacity to restore and conserve forests and other natural areas. |  |  | Weather forecasting and Early Warning Systems: Volunteers will work with government agencies and producer groups to improve their ability to use technologies to conduct weather forecasting. Assignments will focus on using available weather forecasting and early warning tools geared toward agriculture production. POA will use these assignments to coordinate resources and plan adaptation activities. | [11 empty] | Semi-annual Performance Report, FY25 Q1Q2 (October 1 through March 31): 04/30/25 |  |  | Input-2/ Number of Volunteer Days Completed |  |  | Mitigation Measures based on the Pesticide Evaluation Report
7 | MEL Plan, FY24 FY28: 11/30/2023 |  |  | • Increase adoption of sustainable climate-smart agriculture technologies. |  |  | Composting/Organic Fertilizers: Volunteers will conduct training on using locally available waste to produce compost that can be used as an alternative to chemical fertilizer. Assignments will focus on using bulk sources of organic matter that can be transformed into soil amendments at small and commercial production levels. These assignments will additionally focus on the importance of building long term soil health. | [11 empty] | Annual Performance Report, FY25 Q1Q2Q3Q4 (October 1 through September 30): 10/30/25 |  |  | Input-2/ Average Days Per Assignment |  |  | (1) F2F shall retain a copy of the F2F PERSUAP in their headquarters and at all country offices. Monitor and report annually
8 | Estimate of quarterly accruals, FY24 Q1: 12/15/23 |  | At least 2 weeks prior to the end of each financial Q | • Protect water resources through active soil, water, and natural resource management. |  |  | Climate Smart Irrigation: Volunteers will work with hosts to increase their knowledge of the benefits of climate smart irrigation solutions such as drip irrigation. Irrigation volunteers will work with hosts on sourcing materials, designing systems, and required maintenance. These assignments will be especially important for maintaining production in the dry season, establishing perennial species that require year-round water, and reducing the impacts of more frequent droughts and dry spells associated with climate change. | [14 empty] | Output-6/ Persons Trained (Total) |  |  | (2) POA F2F shall send relevant documents to F2F volunteers, based on the type of assignment as described in the SUAP. Report annually
9 | Standard Form SF-425, FY24 Q1: 01/30/24 |  | No later than 30 days after the end of each financial Q | • Increase host organizational capacity to address the effects of changing climate and weather patterns. |  |  | Restoration: POA will recruit experts in restoration design and maintenance. Volunteers will work with hosts to determine appropriate species for projects, costs, and upkeep required for restoration. Volunteers will work in forest, wetland, and riparian buffer zone restoration. | [11 empty] | Semi-annual Performance Report, FY26 Q1Q2 (October 1 through March 31): 04/30/26 |  |  | Output-6/ % of Persons Trained (Women) |  |  | (3) Individual country lists of approved/registered pesticides shall be kept on file at the F2F country office, and shall be provided to F2F volunteers who may be recommending and advising on specific pesticide active ingredients and products as part of their assignment (Type 1). Monitor and report annually
10 | Estimate of quarterly accruals, FY24 Q2: 03/15/24 | [5 empty] | Conservation: Volunteers will work with hosts to increase their capacity to conserve natural areas. Assignments will focus on funding projects, governance, using appropriate native species, and maintaining projects. | [11 empty] | Annual Performance Report, FY26 Q1Q2Q3Q4 (October 1 through September 30): 10/30/26 |  |  | Output-6/ % of Persons Trained (Youth) |  |  | (4a) IPM practices that volunteers recommend shall be retained in F2F country office files; and they should be enhanced by subsequent knowledgeable F2F volunteers. Monitor and report on annually (4b) F2F volunteers whose assignments involve direct or indirect assistance for the use or procurement of pesticides shall be given a copy of these practices for the specific country (Type 1 assignments). Monitor Type 1 Assignment end-of-trip report.
11 | Foreign Tax Reports, FY24: 04/16/24 |  | By April 16, 2024 | Guatemala Watershed Management Farmer-to-Farmer Project aims to improve the capacity of actors working on governance, land use management, and livelihood activities within target watersheds. |  | Pending approval | Waste Management: Volunteers will work with hosts to manage livestock waste to minimize environmental effects such as waste runoff polluting the watershed and compromising ecosystem and human health. | [14 empty] | Output-6/ % of Persons Trained (Indigenous)* |  |  | (5) POA F2F shall keep on file in country offices Material Safety Data Sheets (MSDS) for review and use of in-country staff and F2F volunteers. Report annually.
12 | Standard Form SF-425, FY24 Q2: 04/30/24 |  |  | Geographic Scope: Western Highlands |  |  | Clean Cooking Systems: Volunteers will work with communities to increase usage of clean cooking system alternatives to coal, such as solar cooking, gas, and other cooking alternatives. The provision of knowledge and training of clean cooking systems to decrease reliance on coal can decrease deforestation and improve air quality. | [11 empty] | Semi-annual Performance Report, FY27 Q1Q2 (October 1 through March 31): 04/30/27 |  |  | Output-7/ Number of Volunteer Recommendations Made |  |  | 6a) POA F2F shall retain in country offices all tools, forms, protocols, and plans that volunteers develop such as: scouting protocols, IPM monitoring forms, and measures to monitor the efficacy of pesticides. Monitor and report on annually (6b) These should be provided to subsequent volunteers so that they can build on and strengthen these resources (Type 1 assignments). Monitor as Type 1 Assignment end-of-trip reports
13 | Semi-annual Performance Report, FY24 Q1Q2 (October 1 through March 31): 04/30/24 |  | No later than 30 days after the end of the reporting period | • Increase natural resource use efficiency in agriculture production. | [14 empty] | Annual Performance Report, FY27 Q1Q2Q3Q4 (October 1 through September 30): 10/29/27 |  |  | Ouput-8/ No. of Hosts Assisted |  |  | (7) Given the low level of understanding of pesticide impacts on human health and the environment, the lack of knowledge on IPM and safe pesticide use, as well as other pesticide issues cited by F2F Pesticide Safety Assessments, F2F shall consider recruiting volunteers (through F2F in-country hosts) for assignments in pesticide safe use and IPM. Report annually
14 | Estimate of quarterly accruals, FY24 Q3: 06/14/24 |  |  | • Scale sustainable livelihood opportunities in key upper and middle watersheds. |  |  | Guatemala Watershed Management |  | Pending approval | [12 empty] | Ouput-8/ % of New Hosts Assisted* |  |  | (8) F2F Country Offices shall provide oversight to ensure that F2F volunteers understand and implement the mitigation measures (1 to 9 in Section 3.3 of IEE), and shall report to USAID AORs/CORs and MEOs in semi-annual reports on implementation of the measures. Monitor and report semi-annually.
15 | Standard Form SF-425, FY24 Q3: 07/30/24 |  |  | • Build the capacity of watershed managers and planners. |  |  | Watershed Planning: POA will recruit volunteers to work with NGOs, local governments, mancommunidades, and other relevant actors on designing and executing watershed management plans. Volunteers will work with host organizations to develop plans that use key climate information and participatory planning to successfully guide watershed management planning. | [11 empty] | Semi-annual Performance Report, FY28 Q1Q2 (October 1 through March 31): 04/28/28 |  |  | Outcome-12/ Number of Volunteer Recommendations Applied |  |  | (9) If any F2F program intends to provide assistance for the use or procurement of pesticide active ingredients other than those approved in Attachment A, Table 1, the F2F staff shall notify the USAID/F2F COR that an amendment to this Programmatic PERSUAP is needed. Monitor when Type 1 volunteers submit reports and report on as necessary in Semi-Annual Reports (the need to add any pesticides to the approved list; and submission of Amendment and approval).
16 | Annual Work Plan, FY25: 08/30/24 |  | No later than 30 days before the start of that year | • Improve technical capacity to restore and conserve forests and other natural areas. |  |  | Agroforestry: Volunteers will work with producers to plan and implement strategies that incorporate trees into agriculture systems. Assignments will focus on identifying species that function well together and that produce ecosystem services such as reducing erosion, increasing water absorption, and controlling extreme temperatures. | [11 empty] | Annual Performance Report, FY28 Q1Q2Q3Q4 (October 1 through September 30): 10/30/28 |  |  | Outcome-12/ Hosts Applying Improved Climate-Smart Recommendations* |  |  | 10) F2F partners shall ensure that volunteers submit reports as required in the SUAP for Types 1, 2 and 4 volunteers. Report annually.
17 | Estimate of quarterly accruals, FY24 Q4: 09/13/24 |  |  | • Increase key actors’ capacity to monitor environmental quality. |  |  | Climate Information and Data: POA will conduct administrative assignments in Year One with Climate Data and Information Experts. These assignments will produce information on watershed management, high impact assignments that align with cutting edge adaptation tools, and opportunities to collect and share data. | [14 empty] | Outcome-28/ Value of Volunteer Time |  |  | 11) In a separate section on Environmental Compliance (EC) in Partner’s semi-annual reports, F2F partners shall report on: 1) The types of assignments that have involved pesticides (i.e., the number of Types 1, 2, and 4 assignments, and a general description of activities that involved pesticides). 2) Key findings and recommendations from F2F volunteer reports. Report semi-annually.
18 | Standard Form SF-425: FY24 Q4: 10/30/24 | [5 empty] | Weather forecasting and Early Warning Systems: Volunteers will work with government agencies and producer groups to improve their ability to use technologies to conduct weather forecasting. Assignments will focus on using available weather forecasting and early warning tools geared toward agriculture production. POA will use these assignments to coordinate resources and plan adaptation activities. | [11 empty] | Final Program Report - The life of the award, FY24-FY28: 12/29/28 |  |  | Impact-14/ Increase in annual gross value of sales
19 | Annual Performance Report, FY24 Q1Q2Q3Q4 (October 1 through September 30): 10/30/24 |  | No later than 30 days after the end of the reporting period | Guyana Hinterland Agribusiness Development (HAD) Farmer-to-Farmer Project seeks to boost agriculture production and business in the Hinterland Regions of Guyana |  | Pending approval | Composting/Organic Fertilizers: Volunteers will conduct training on using locally available waste to produce compost that can be used as an alternative to chemical fertilizer. Assignments will focus on using bulk sources of organic matter that can be transformed into soil amendments at small and commercial production levels. These assignments will additionally focus on the importance of building long term soil health. | [14 empty] | Impact-15/ Increase in annual net income
|  |  |  | Geographic Scope: Hinterland Regions |  |  | Climate-Smart Irrigation: Volunteers will work with hosts to increase their knowledge of the benefits of climate-smart irrigation solutions such as drip irrigation. Irrigation volunteers will work with hosts on sourcing materials, designing systems, and required maintenance. These assignments will be especially important for maintaining production in the dry season, establishing perennial species that require year-round water, and reducing the impacts of more frequent droughts and dry spells associated with climate change. | [14 empty] | Impact-20/ Increased number of new products
20 | Estimate of quarterly accruals, FY25 Q1: 12/16/24 |  |  | •Increase agribusiness sustainability and resilience. |  |  | Restoration: POA will recruit experts in restoration design and maintenance. Volunteers will work with hosts to determine appropriate species for projects, costs, and upkeep required for restoration. Volunteers will work in forest, wetland, and riparian buffer zone restoration. | [14 empty] | Impact-21/ Increased number of new services
21 | Standard Form SF-425, FY25 Q1: 01/30/25 |  |  | •Improve youth and women participation in agribusiness in the Hinterlands. |  |  | Conservation: Volunteers will work with hosts to increase their capacity to conserve natural areas. Assignments will focus on funding projects, governance, using appropriate native species, and maintaining projects. | [14 empty] | Impact-16/ Hosts with increased organizational and management capacity
22 | Estimate of quarterly accruals, FY25 Q2: 03/17/25 |  |  | •Improve technical capacity of agribusiness educators and extension. | [17 empty] | Impact-19/ Area under Improved Production or Natural Resource Management (NRM) Practices
23 | Foreign Tax Reports, FY25: 04/16/25 |  |  | •Increase agribusiness product competitiveness. |  |  | Guyana Hinterland Agribusiness Development (HAD) |  | Pending approval
24 | Standard Form SF-425, FY25 Q2: 04/30/25 |  |  | •Increase the number of agribusiness products. |  |  | Food Processing: POA will recruit volunteers to work with food processing entrepreneurs, regulators, and educators. Food Processing Specialists will build hosts’ capacity to improve their product recipes, manufacturing processes, factory design, and other relevant food processing areas.
25 | Semi-annual Performance Report, FY25 Q1Q2 (October 1 through March 31): 04/30/25 | [5 empty] | Business Management: Expert volunteers will build hosts’ capacity in crucial business areas such as record keeping, business planning, revenue/profit forecasting, and implementing standard operating procedures. Agribusinesses will receive training and capacity building from U.S. Accounting, Business Operations, and Management Specialists.
26 | Estimate of quarterly accruals, FY25 Q3: 06/16/25 |  |  | Jamaica Climate-Smart Agriculture Farmer-to-Farmer Country Project aims to increase the resilience and productivity of agriculture production to changing climate and weather patterns. |  | Pending approval | Grant Writing/Business Development: POA will recruit volunteers to work with different types of hosts to improve their capacity to secure funding and resources. Grant writing and business development experts will work with agribusinesses, schools, and other types of hosts to prepare them to write successful proposals and applications for funding. These assignments will focus on securing funding through donors as well as financial institutions.
27 | Standard Form SF-425, FY25 Q3: 07/30/25 |  |  | Geographic Scope: Rural areas in key agriculture producing communities such as St. Elizabeth and Clarendon. |  |  | Organizational Strengthening: Volunteers will work to strengthen Indigenous and youth producer groups, cooperatives, organizations, and businesses’ organizational capacity. Assignments will focus on organizations fee structures, membership retention, bylaws, and leadership teams. POA has found that these assignments are often necessary precursors to grant writing/business development assignments.
28 | Annual Work Plan, FY26: 08/29/25 |  |  | •Increase natural resource use efficiency with best practices and technologies. |  |  | Food Safety: Food safety assignments will build hosts’ capacity to follow relevant certifications and standards in processed and fresh products. Experts will train hosts’ such as processors in international certifications such as HAACP as well as relevant local standards. These assignments will increase the value and competitiveness of agriculture products.
29 | Estimate of quarterly accruals, FY25 Q4: 09/16/25 |  |  | •Increase agriculture resilience to shocks and stressors, such as hurricanes. |  |  | Green Energy: POA will recruit volunteers with expertise in improving the resilience of agribusinesses through tapping into green energy sources. Volunteers will work with hosts on topics such as determining whether solar, wind, or micro-hydrological energy sources is the best fit for a business’s needs and how to finance and maintain new energy sources.
30 | Standard Form SF-425, FY25 Q4: 10/30/25 |  |  | •Increase profitability of agriculture production. |  |  | Apiculture/Honey Products: POA will train beekeepers and honey makers on best apiculture methods and practices. Assignments will focus on producing high quality honey, alternative products such as soaps, and meeting international quality standards.
31 | Annual Performance Report, FY25 Q1Q2Q3Q4 (October 1 through September 30): 10/30/25 |  |  | •Increase key agriculture sector organizations’ ability to address the effects of climate change. |  |  | Marketing: POA will place Marketing Specialists with hosts to increase capacity in social media campaigns, search engine optimization, and other key sales areas. Volunteers will also work in labeling and packaging with hosts to ensure that products are marketable.
Nursery Management: Experts in plant nursery management will work with hosts to increase their capacity to propagate plants and graft trees. These assignments will work with private agribusinesses and farms and collaborate with government stakeholders such as the National Agriculture Research Extension Institute as well as local and international NGO staff.
32 | Estimate of quarterly accruals, FY26 Q1: 12/17/25
33 | Standard Form SF-425, FY26 Q1: 01/30/26 | [5 empty] | Jamaica Climate-Smart Agriculture |  | Pending approval
34 | Estimate of quarterly accruals, FY26 Q2: 03/17/26 | [5 empty] | Climate Information and Data: POA will conduct assignments in Year One of the F2F program with Climate Data and Information Experts. These assignments will produce key climate information data sets to be used by stakeholders, identify cutting edge climate adaptation tools, and opportunities to collect and share data across the region.
35 | Foreign Tax Reports, FY26: 04/16/26 | [5 empty] | Weather forecasting and Early Warning Systems: Volunteers will work with government agencies and producer groups to improve their ability to use technologies that forecast and predict weather events. Assignments will focus on utilizing available weather forecasting and early warning tools geared toward agriculture production.
36 | Standard Form SF-425, FY26 Q2: 04/30/26 | [5 empty] | Shade House Production: Shade houses increase profitability of farms, resource usage efficiency, and climate adaptation. Volunteers will work with producers on shade house design, production, and maintenance. Shade houses create opportunities to harvest water to increase irrigation potential and reduce flood risk.
37 | Semi-annual Performance Report, FY26 Q1Q2 (October 1 through March 31): 04/30/26 | [5 empty] | Agroforestry: POA will recruit volunteers to work with producers to plan and implement strategies that incorporate trees into agriculture systems. Assignments will focus on identifying species that function well together and produce ecosystem services such as reducing erosion, increasing water absorption, and controlling extreme temperatures.
38 | Estimate of quarterly accruals, FY26 Q3: 06/16/26 | [5 empty] | Climate-smart Irrigation: Volunteers will work with hosts to increase their knowledge of the benefits of climate-smart irrigation solutions such as drip irrigation. Irrigation Volunteers will work with hosts on sourcing materials, designing systems, and required maintenance. These assignments will be especially important for maintaining production in the dry season, establishing perennial species that require year-round water, and reducing the impacts of more frequent droughts and dry spells associated with climate change.
39 | Standard Form SF-425, FY26 Q3: 07/30/26 | [5 empty] | Cover Cropping: Cover cropping assignments will increase producers’ capacity to use a diverse range of cover crops. Assignments will focus on sourcing seeds, proper seeding rate, relevant species and producing seeds. Volunteers will emphasize the importance of ground cover for building long term soil health, conserving water, and reducing runoff.
40 | Annual Work Plan, FY27: 08/31/26 | [5 empty] | Farm Management: Volunteers will train smallholder farmers in improved agribusiness and farm management practices including budgets, financial risk management, record keeping, and organizing collective sales and input purchases.
41 | Estimate of quarterly accruals, FY26 Q4: 09/16/26 | [5 empty] | Precision Input Usage: Volunteers will train producers and other relevant actors in precision input usage, particularly precision synthetic fertilizers. Assignments will focus on avoiding excessive usage of inputs to avoid negative environmental and economic consequences of over application. In some cases, this will involve utilizing locally available soil tests that effectively estimate soil nutrient needs at a low cost.
42 | Standard Form SF-425, FY26 Q4: 10/30/26 | [5 empty] | Composting/Organic Fertilizers: POA will deploy volunteers to conduct training on producing and using compost and other non-chemical fertilizers. Assignments will focus on using underutilized bulk sources of organic matter that can be transformed into soil amendments at small and commercial production levels. These assignments will additionally focus on the importance of building long term soil health.
43 | Annual Performance Report, FY26 Q1Q2Q3Q4 (October 1 through September 30): 10/30/26
44 | Estimate of quarterly accruals, FY27 Q1: 12/17/26
45 | Standard Form SF-425, FY27 Q1: 01/29/27
46 | Estimate of quarterly accruals, FY27 Q2: 03/17/27
47 | Foreign Tax Reports, FY27: 04/16/27
48 | Standard Form SF-425, FY27 Q2: 04/30/27
49 | Semi-annual Performance Report, FY27 Q1Q2 (October 1 through March 31): 04/30/27
50 | Estimate of quarterly accruals. FY27 Q3: 06/16/27
51 | Standard Form SF-425, FY27 Q3: 07/30/27
52 | Annual Work Plan, FY28: 08/31/27
53 | Estimate of quarterly accruals, FY27 Q4: 09/16/27
54 | Standard Form SF-425, FY27 Q4: 10/29/27
55 | Annual Performance Report, FY27 Q1Q2Q3Q4 (October 1 through September 30): 10/29/27
56 | Estimate of quarterly accruals, FY28 Q1: 12/17/27
57 | Standard Form SF-425, FY28 Q1: 01/28/28
58 | Estimate of quarterly accruals, FY28 Q2: 03/17/28
59 | Foreign Tax Reports, FY28: 04/14/28
60 | Standard Form SF-425, FY28 Q2: 04/28/28
61 | Semi-annual Performance Report, FY28 Q1Q2 (October 1 through March 31): 04/28/28
62 | Estimate of quarterly accruals, FY28 Q3: 06/16/28
63 | Standard Form SF-425, FY28 Q3: 07/28/28
64 | Estimate of quarterly accruals: FY28 Q4: 09/15/28
65 | Standard Form SF-425, FY28 Q4: 10/30/28
66 | Annual Performance Report, FY28 Q1Q2Q3Q4 (October 1 through September 30): 10/30/28
67 | Final Financial Report, FY24-FY28: 12/29/2028 |  | No later than 90 days after the estimated completion date of the award
68 | Final Program Report - The life of the award, FY24-FY28: 12/29/28 |  | No later than 90 days after the completion, extension, expiration, or termination of the award
69 | Closeout Plan, FY24-FY28: 04/27/2029 |  | No later than 180 days before the end of the award
70 | Projections to Donor: XXX
71 | Projections to Donor: XXX
72 | Projections to Donor: XXX
73 | Projections to Donor: XXX
74 | Annual Implementation Plans: XXX
75 | Annual Implementation Plans: XXX
76 | Annual Implementation Plans: XXX
77 | Annual Implementation Plans: XXX
78 | Activity Monitoring and Evaluation (AMEP Plan): XXX
79 | Activity Monitoring and Evaluation (AMEP Plan): XXX
80 | Grants Manual: XXX
81 | Annual Reports: XXX
82 | Short-Term Consultant Reports, Technical Briefs/Reports, Special and External Reports: XXX
83 | Short-Term Consultant Reports, Technical Briefs/Reports, Special and External Reports: XXX
84 | Development Experience Clearinghouse Requirements: XXX
85 | DEVRESULTS: XXX
86 | DEVRESULTS: XXX
87 | Program Income: XXX
88 | Substantial Involvement: XXX
89 | Substantial Involvement: XXX
90 | Substantial Involvement: XXX
91 | Substantial Involvement: XXX
92 | Substantial Involvement: XXX
93 | Environmental Compliance: XXX
94 | GENDER: XXX
95 | Branding: XXX
96 | Marking: XXX
97 | Marking: XXX
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Once the country descriptions/strategies are approved, we will record more specific activities related to these topics (assignments)
Note on T2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These requirements are also in column B, but we need to have all deliverables related to the MEL Plan/Indicators listed here

## Subaward Summary Page (hidden)
Compliance Matrix
Subaward Name/Title: |  |  |  |  | Total Award Amount: |  | POA Subaward Manager(s) (including dates):
Internal Grant Name: |  |  |  |  | Total Obligation Amount:
Subaward Number: |  |  |  |  | Cost Share Amount:
Donor: |  |  |  |  | Leverage Amount:
CFDA: |  |  |  |  | USAID Only: Geographic Code:
Subaward Start Date: |  |  |  |  | Key Personnel:
Subaward End Date: |  |  |  |  | Approved Indirect Rate(s) %:
Subaward Point of Contact: |  |  |  |  | Prior Approvals Required:
POA Point of Contact: |  |  |  |  | Treatment of Program Income:
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Timeline Reporting (hidden)
Reporting and Evaluation Requirements | Report | When | Send to | Comments | Date Sent | Date approved | John Ogonowski and Doug Bereuter Farmer-to-Farmer Program
Financial Reporting | Estimate of quarterly accruals | At least two weeks prior to the end of each financial quarter | AOR |  |  |  | Leader Cooperative Agreement No. 7200AA23LE00014
| Standard Form SF-425 | No later than 30 days after the end of each financial quarter | AOR |  |  |  | Period 10/01/2023 - 09/29/2028
| Final Financial Report | No later than 90 days after the estimated completion date of the award | AOR |  |  |  | Award | 8500000
Annual Work-Plans | Life of Project and Year One Work Plan | No later than 60 days after the effective date of the award | AOR | Should be reviewed with AOR | 11/22/203 |  | Core funds | 7500000
| Annual Work-Plans | No later than 30 days before the start of that year | AOR | Year one must include the environmental documentation (IEE). Approval is required before activities begin. Should be reviewed with AOR | 11/22/203 |  | Potential buy-ins | 1000000
Project Descriptions | Country F2F description | As early as possible | AOR | Expected results in terms of the standard F2F Performance and Impact Indicators and any Country Project Specific indicators for outputs. In-country activities can not begin until projects are approved | 2023-11-10 |  | Obligated | 1623809.21
MEL | Activity MEL plan | Within 60 days after the award is made - with the first year work-plan | AOR | Subject to AOR approval |  |  | Associate Awards | 34000000
Performance Reports | Semi-annual performance report - October 1 through March 31 | No later than 30 days after the end of the reporting period | AOR/DEC* | The report should provide updates on award achievements against objectives and progress against the agreed-upon indicators and targets |  |  | Leverage goal | 2766600
| Annual performance report - October 1 through September 30 | No later than 30 days after the end of the reporting period | AOR/DEC | The report should provide updates on award achievements against objectives and progress against the agreed-upon indicators and targets
| Final Report - The life of the award | No later than 90 days after the completion, extension, expiration, or termination of the award | AOR/DEC | Comprehensive presentation of the experience, activities and results achieved
Close-out Plan | Close-out Plan | No later than 180 days before the end of the award |  | A plan that details all equipment and provides a proposed disposition plan according to USAID regulations.
Branding Strategy and Marking Plan | According to 2 CFR 700.16 | Within 30 days of the effective date of the award |  |  | 2023-10-30
Special Environmental Requirements | Initial Environmental Examination. Attachment E | No later than 60 days after the effective date of the award | AOR | Must comply with the terms outline in the IEE
| Environmental Mitigation and Monitoring Plan | No later than 60 days after the effective date of the award | AOR | The year one work-plan should include an EMMP | 11/22/203
Follow all requirements in the PERSUAP
Reporting Host Government Taxes | Report detailing foreign taxes | By April 16 each year | AOR/Point of contact in the local Embassy or Mission | A report is required even if no taxes were paid. Detailed information in everything over $500
*USAID Development experience clearinghouse (DEC)