## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | Juntos Aprendemos / Together We Learn |  |  |  | Total Award Amount: | 35000000 | Program Manager(s) (including dates):
Internal Grant Number: | USAID800 |  |  |  | Total Obligation Amount: | 22200000 | Alexandra McWither-Santillan (XX - January 31, 2023) | GET AMS HIRE DATES FROM HR
Award Number: | 7200AA21CA0003 |  |  |  | Cost Share Amount: | 0 | María Ochoa (January 1st, 2023 - to date)
Donor: | USAID |  |  |  | Leverage Amount: | 1059006.0116
CFDA: |  |  |  |  | USAID Only: Geographic Code: | 937
Award Start Date: | February 5, 2021 |  |  |  | Key Personnel: | Chief of Party / COP (POA) - Gustavo Payán-Luna Deputy Chief of Party / DCOP (POA) - Alejandro Torres (former: Camilo Forero) Community Engagement and Outreach Director (Parque Explora) - Liliana Leiva (former: Carolina Giraldo) Education Director (Fundacion Carvajal) - Catalina Prada (former: Paola Trujillo) Partnerships and Alliances Director (Proantioquia) - Natalia Currea (former: Natalia Niño) Capacity Development Director (POA) - Silvana Torres
Award End Date: | February 4, 2026 // December 31, 2026 (mod 5) |  |  |  | Approved Indirect Rate(s) %: | 28.28%
Program Director: | Gustavo Payán-Luna |  |  |  | Prior Approvals Required: | Implementation plans: LOP work plan, annual work plans Key personnel and changes to key personnel Sub-awards and sub-award manual AMELP (removed in mod 5: Print or electronic publications) Quarterly performance reports Final report MONITOR reports (specific for USAID Colombia) Annual reports Safety & Security Plan (no approval requried) Closeout Plan
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Juan Reyes + Maria Lievano (alterante) |  |  |  | Treatment of Program Income: |  |  | PROGRAM INCOME NOT MENTIONED IN THE AGREEMENT; CONSULT WITH DANIELLE WHAT SHOULD WE INCLUDE HERE
Agreement Officer (AO)/Grants Officer (GO): | Heather Wirick
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Agreement | 2021 | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/ESRXJT_eJjpFuWFDH5xeNgUBBCRcTsnwVnBI8RRgmqgFYw?e=QTvz29
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | YYYY-YYYY | MM/DD/YYYY | 2021-06-02 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EeT4TqURT7hBobw29fimSOQB3xtnoyGvuFUkcRTe7sWdNA?e=SqrzdC | Update AOR and Alternate AOR designation and letter
Modification 02 | n/a | YYYY-YYYY | MM/DD/YYYY | 2021-12-22 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/Ee09zsTJxyRPskHDt6QSBqcBUrRuxCvNZCqhANaKtoI9-w?e=0kLO0y | Modify Attachment A (update sections A.8 Key Personnel and A.9 Reporting and Evaluation) Modify Attachment B program Description (geographic coverage) Modify Attachment D (update B&M strategy)
Modification 03 | n/a | YYYY-YYYY | MM/DD/YYYY | 2022-05-13 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EYM9E6QYW1VDt-so__mwyikBB4EQLBSb9IHkfqS52KHO3g?e=IKdmAd | To remove Special Provision: Procurement of Covered Materials and include Exchange visitors and participant training
Modification 04 | n/a | YYYY-YYYY | MM/DD/YYYY | 2022-08-25 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EcjuEI0TYk9KtciqDbSypKYB35f4zlm4k6Nx23LpDwJo6Q?e=9rmiZE | To add 5m to obligation for total oblg: $13,400,000m and update DUNS with UEI
Modification 05 | n/a | YYYY-YYYY | MM/DD/YYYY | 2023-05-26 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/Eaour-T1vmpOjkxeJOxJqI0BOTg-IRA5VusS0f2PgwZYLA?e=Dzo10a | Extend end date from February 6, 2026 to December 31, 2026; add $2,587,000 for total obligation of $15,987,000
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | 2023-09-21 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/ES0BZHPdvYRNkC26Qdy_ILwBi1AMe-lw3gu6j7CuIuqDpw?e=iX7wvE | Incremental funding in the amount of $6,213,000.00; total obligated to USD 22.2 million; update financial data; update indirect cost rate; update approvals required B&M; update min requirments to KP; include exchange rate languag; update provisions (mandatory and required as applicable)
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | 2021 | YYYY-YYYY | 2021-05-04 | MM/DD/YYYY | Juntos Aprendemos Activity - Activity Monitoring, Evaluation, and Learning Plan (AMELP) | https://partnersnet107.sharepoint.com/:u:/s/Programs/EQp_40ICIiJFkydsdgYIpS8BJgCgVSk_lS-TSaDaNtS4SA?e=vekBZM | Document not approved. USAID provided feedback.
M&E Plan - Revision | 2022 | YYYY-YYYY | 2022-02-16 | 2022-03-02 | Juntos Aprendemos Activity - Activity Monitoring, Evaluation, and Learning Plan (AMELP) | https://partnersnet107.sharepoint.com/:w:/s/Programs/Ec22C256dE9OgzZkz5s2zcwB6z-X9gtnYBAOe879uNA5Rg?e=5MXWlt Approval email: https://partnersnet107.sharepoint.com/:w:/s/Programs/Ec22C256dE9OgzZkz5s2zcwB6z-X9gtnYBAOe879uNA5Rg?e=5MXWlt
M&E Plan - Revision | 2023 | YYYY-YYYY | 2023-02-03 | 2023-02-13 | Juntos Aprendemos Activity - Activity Monitoring, Evaluation, and Learning Plan (AMELP) | https://partnersnet107.sharepoint.com/:w:/s/Programs/EfqQISMzkHpCsulP_QjmEz0BGgXVTvzim5DxTFdTbC4LgQ?e=K54Ubr Approval email: https://partnersnet107.sharepoint.com/:w:/s/Programs/Ec22C256dE9OgzZkz5s2zcwB6z-X9gtnYBAOe879uNA5Rg?e=5MXWlt
M&E Plan - Revision | 2023 | YYYY-YYYY | 2023-07-12 | 2023-07-18 | Juntos Aprendemos Activity - Activity Monitoring, Evaluation, and Learning Plan (AMELP) | https://partnersnet107.sharepoint.com/:b:/s/Programs/EbxmdbMD2cZJmLt5HT8V53wBaapk-p5t_x1QU4YcxLGNAA?e=Oxic8O Approval email: https://partnersnet107.sharepoint.com/:u:/s/Programs/EYCOFTNfaptIintZeQHFhnIBJwSiVdAzKAT8YjDjGN0tBg?e=dnrUUI
M&E Plan/Start-up Plan | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | n/a | 2021-2026 | 2021-05-18 | 2021-06-04 | Life of Project Workplan | https://partnersnet107.sharepoint.com/:f:/s/Programs/Etm7Xts2OztFt7EDXB8ObRoBYiywd8lROkuLRjyQBGgMEQ?e=z0epWk |  | PENDING: ORIGINAL SUBMISSION EMAIL + INCLUDE REVISIONS AND FINAL VERSIONS, SEPARATELY
Work Plan/PMP | 2021 | YYYY-YYYY | 2021-05-31 | MM/DD/YYYY | Annual Work Plan 2021 | https://partnersnet107.sharepoint.com/:f:/s/Programs/EpsaMl-EfLxMj0jJlD_9vvkB9NtGObuo-tHN4axAel9NxA?e=vp7T3D |  | PENDING: WP APPROVAL EMAIL; INCLUDE REVISIONS AND FINAL VERSION, SEPARATELY
Work Plan/PMP | 2022 | YYYY-YYYY | 2021-12-28 | 2022-01-25 | Annual Work Plan 2022 | https://partnersnet107.sharepoint.com/:f:/s/Programs/EpsaMl-EfLxMj0jJlD_9vvkB9NtGObuo-tHN4axAel9NxA?e=vp7T3D |  | PENDING: CLEAN FINAL APPROVED VERSION, INCLUDE REVISIONS AND FINAL VERSION, SEPARATELY
Work Plan/PMP | 2023 | YYYY-YYYY | 2022-12-16 | 2022-12-20 | Annual Work Plan 2023 | https://partnersnet107.sharepoint.com/:f:/s/Programs/Erm3qws9On5Pk-VrwtuNiR0BYBaPb7gSIL2QQkXYrEQcRQ?e=dsWiA3 |  | PENDING: CLEAN FINAL APPROVED VERSION, INCLUDE REVISIONS AND FINAL VERSION, SEPARATELY
Work Plan/PMP | 2024 | YYYY-YYYY | 2023-12-01 |  | Annual Work Plan 2024
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions |  |  |  |  | CoAg 7200AA21CA00003 Section C | https://partnersnet107.sharepoint.com/:f:/s/Programs/Erm3qws9On5Pk-VrwtuNiR0BYBaPb7gSIL2QQkXYrEQcRQ?e=dsWiA3 | All standard provisions (and restrictions) are included in Section C
List restrictions
List special provisions or requirements
List special provisions or requirements
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY | Juntos Aprendemos Running Agenda: USAID-Partners of the Americas weekly meetings | https://docs.google.com/document/d/1h3B6cpae20V12f1qt_tBNyuVG9wQU176Z_nc-3MfSm0/edit?usp=sharing
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY |  |  |  |  | CONFIRM WITH DANIELLE IF WE SHOULD INCLUDE HER COMMENTS ON COMPLIANCE OR PABLOS FINDINGS OR WHETHER THIS MAKES REFERENCE TO COMPLIANCE IDENTIFIED DURING POA AUDITS
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Compliance Matrix Details
Breakdown of Award Requirements
| Award Terms & Conditions | Compliant Y/N | Comments | Program Description | Compliant Y/N | Comments | Work Plan 2024 | Compliant Y/N | Comments | Workplan FYXX | Compliant Y/N | Comments | Work Plan FYXX | Compliant Y/N | Comments | Workplan FYXX | Compliant Y/N | Comments | MEL Plan FYXX (most recent and approved version) | Compliant Y/N | Comments | Indicators | Compliant Y/N | Comments | Environmental Mitigation and Monitoring Plan - EMMP | Compliant Y/N | Comments | Activities in Budget Narrative | Compliant Y/N | Comments
1 | Financial Reporting: SFR425 | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/Eqx9jJwRWdNIvgcEpVRPqhcB2SJvaNfNOgNdfrYyTzNf_g?e=5YZcxm | Description: To increase the capacity of the Colombian education system to provide sustainable and inclusive quality education in areas impacted by migration. |  | https://partnersnet107.sharepoint.com/:w:/s/Programs/EeQUXtHmyVRNsBV82lEMB2wBie4AsUHEp7ZiDL9qSczR_Q?e=pvQOPb | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX | [8 empty] | NA |  |  | Track differences in spending patters. Ex: budgeted X, Y, Z positions; hired A, B, C // keep it highlevel, what's substantial considering the total budget (1%), high level changes in the sub budgets
2 | Financial Reporting: XXX |  |  | Geographic Scope: Bogota, Medellin, Cali, Cucuta, Barranquilla, Cartagena, Santa Marta, Riohacha, and Bucaramanga, and adjacent areas |  |  | Gender Considerations: XXX |  |  | Gender Considerations: XXX |  |  | Gender Considerations: XXX |  |  | Gender Considerations: XXX |  |  | versión más reciente |  |  | todos los indicadores con meta
3 | Financial Reporting: XXX |  |  | Objective 1: Improved quality of education for children and youth in receptor communities |  |  | Sustainability: XXX |  |  | Sustainability: XXX |  |  | Sustainability: XXX |  |  | Sustainability: XXX |  |  | cumplimos |  |  | comentarios según los cambios (cambios en meta y cambios en alcance del indicador)
4 | Financial Reporting: XXX |  |  | IR 1.1: Improved learning environment to be safe, inclusive, and responsive to the needs of returnee and migrant learners. |  |  | lo más importante del plan de trabajo | [11 empty] | comentarios
5 | Accrual Reporting: Quarter Accrual Reports | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/EmKWNqaGFGdPhQU3RT7X5EgB7AgloRYPZLHk4rFrgVgWuw?e=DmMCT6 | IR 1.2: Strengthened organizational capacity (coordination, contingency planning, outreach, and policies) of national and local governments to provide quality education. |  |  | ej 2023: incidencia - logros // parte técnica - logros
6 | Accrual Reporting: XXX |  |  | IR 1.3: Strengthened knowledge and skills of teachers and directors to deliver improved instruction in foundational skills, including literacy, numeracy and social and emotional skills.
7 | Accrual Reporting: XXX |  |  | IR 1.4: Improved curricula for high quality traditional and alternative instruction, including distance learning, accelerated education, bridging and catch-up programming.
8 | Accrual Reporting: XXX |  |  | Objective 2: Increased access to quality education for children and youth in receptor communities
9 | Projections to Donor: Quarterly Projections | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/EmKWNqaGFGdPhQU3RT7X5EgB7AgloRYPZLHk4rFrgVgWuw?e=DmMCT6 | IR 2.1: Increased student access to appropriate and safe education opportunities. |  |  | PENDING SUBMISSION OF 2024 WP
10 | Projections to Donor: XXX |  |  | IR 2.2: Increased access to certified flexible education modalities for children and youth.
11 | Projections to Donor: XXX |  |  | Objective 3: Strengthened community engagement in educational opportunities.
12 | Projections to Donor: XXX |  |  | IR 3.1: Increased participation from local community members and organizations, including youth organizations, in education decision making and service delivery.
13 | Annual Implementation Plans: Annual Work Plans | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/EpDG7CUoPyhCpHJXSV0R1tUBzXSRurAJxyQacCH3qBfXGw?e=nYhklG | IR 3.2: Increased participation of families and caregivers to support student learning. IR 3.3: Strengthened social networks to support learning in receptor communities.
14 | Annual Implementation Plans: XXX
15 | Annual Implementation Plans: XXX
16 | Annual Implementation Plans: XXX
17 | Activity Monitoring and Evaluation (AMEP Plan): Juntos Aprendemos Activity - Activity Monitoring, Evaluation, and Learning Plan (AMELP) | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/Erjx8sKNPmFKunGIHu5h0HQBhKJsIpOatMqvy1sY8lgPYA?e=XyDz8h
18 | Activity Monitoring and Evaluation (AMEP Plan): XXX
19 | Grants Manual: Juntos Aprendemos Subaward Manual | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/EmBOtgWoqJ5IhYyqNexNJK0B0h42f7keLvPjOjZP3CSrzw?e=XjmPTI
20 | Quarterly Performance Reports: Juntos Aprendemos Quarterly Performance Reports | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/EoS7126WBmdJsuGr4b8xbEEBa4UCTbqFWWZZQ88SCdWOxg?e=NZxKw8
21 | Quarterly Performance Reports: XXX
22 | Quarterly Performance Reports: XXX
23 | Quarterly Performance Reports: XXX
24 | Semi-Annual reports: XXX | NA
25 | Annual Reports: Juntos Aprendemos Annual Report | Y; annual report submitted, instead of Q1 report | https://partnersnet107.sharepoint.com/:f:/s/Programs/EoS7126WBmdJsuGr4b8xbEEBa4UCTbqFWWZZQ88SCdWOxg?e=NZxKw8
26 | Final Program Report: XXX
27 | Short-Term Consultant Reports, Technical Briefs/Reports, Special and External Reports: XXX | NA | Activity is not required to submit consultant reports to donor
28 | Short-Term Consultant Reports, Technical Briefs/Reports, Special and External Reports: XXX
29 | Closeout Plan: XXX
30 | Development Experience Clearinghouse Requirements: XXX
31 | Foreign Tax Reports: VAT Reports | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/EgGZqlHChItKlikdaGvkk3wBwoLZFBuHi3QwKVMZkZwCuQ?e=NDcUGK
32 | DEVRESULTS: XXX
33 | DEVRESULTS: XXX
34 | Program Income: XXX
35 | Substantial Involvement: Approval of Recpient's Implementation Plans | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/EpDG7CUoPyhCpHJXSV0R1tUBzXSRurAJxyQacCH3qBfXGw?e=NHq637
36 | Substantial Involvement: Approval of Key Personnel and Any Changes in Key Personnel | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/EoqTQ3xWDkBEmd68C05oWjMB7hLklCbw9kATnPIRyT3YrA?e=WR1SKR
37 | Substantial Involvement: Collaboration and joint participation | Y | https://docs.google.com/document/d/1h3B6cpae20V12f1qt_tBNyuVG9wQU176Z_nc-3MfSm0/edit?usp=sharing
38 | Substantial Involvement: Approval of all sub-awards and sub-awards manual | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/EnFo2P5UAlxIieM1itvXK6cBrmtdTKu0dq0ZQoF-VGpViA?e=JNnwvN
39 | Substantial Involvement: Approval of the Activity Monitoring Evaluation and Learning Plan (AMELP) | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/Erjx8sKNPmFKunGIHu5h0HQBhKJsIpOatMqvy1sY8lgPYA?e=PLYAfC
40 | Substantial Involvement: Approval of print or electronic publications | Y | https://partnersnet107.sharepoint.com/:f:/s/Programs/Eg3Y-rvWFxNOi3KxzzDwLNMBK39l-LAl89ifTqkAzWnBsg?e=mZoHmF
41 | Substantial Involvement: Approval for direction or redirection | NA
42 | Environmental Compliance: XXX | NA
43 | GENDER: XXX
44 | Branding: XXX
45 | Marking: XXX
46
47
48
49
50
51
52

## Subaward FC
Compliance Matrix
Subaward Name/Title: | 800-Fundacion Carvajal |  |  |  | Total Award Amount: | 8686266 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 800-Fundacion Carvajal |  |  |  | Total Obligation Amount: | 4023258 | Claudia Johanna Rojas Hormiga (August 16, 2021 - Current)
Subaward Number: | 800-Fundacion Carvajal |  |  |  | Cost Share Amount: | 0
Donor: | USAID |  |  |  | Leverage Amount: | 315966
CFDA: | 7200AA21CA00003 |  |  |  | USAID Only: Geographic Code: | 937
Subaward Start Date: | August 16, 2021 |  |  |  | Key Personnel: | Catalina Prada Fernandez de Soto
Subaward End Date: | October 31, 2025 |  |  |  | Approved Indirect Rate(s) %: | 10%
Subaward Point of Contact: | David Alejandro Gironza Rodriguez |  |  |  | Prior Approvals Required: | Yes; Article 14 and Article 19
POA Point of Contact: | Gustavo Payan - Alejandro Torres - Claudia Johanna Rojas Hormiga |  |  |  | Treatment of Program Income: | Article 10: Added to funds committed by POA and the recipient to the program and used to further eligible program objective
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | 2021-2025 | May 31, 2021 | June 6, 2021 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/EVui6cJo261EiDasx1gzLRMBOKTHfmgFqG8ULM9l8v8_jQ?e=OEOcdH | USAID approval
| n/a | 2021-2025 | August 10, 2021 | August 13, 2021 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EX4-tejLkYlPknXl4za22T8B2YheETcYpMOGF8DW-13ojA?e=fjsboR | Subaward FE
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | 2021-2025 | October 19, 2022 | November 16, 2022 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EYP0khSFVTFBq9BYAbSdf00BbG4c-BBbhjFBpCfROmSnMg?e=MDxUMi | Subaward - Modification 1 - FE
Modification 02 | n/a | 2021-2025 | February 6, 2023 | February 21, 2023 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/Ef83SOVgDGJLgBpVnCsNYxYBKwymbWuFiPbspBToV2oJxA?e=LucuN3 | Subaward - Modification 2 - FE
Modification 03 | n/a | 2021-2025 | April 18, 2023 | May 5, 2023 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EaMViAswkFpIgtsp3rS8UgsBqwklrngFFk77wl3v8EmGSg?e=FEk2sV | Subaward - Modification 3 - FE
Modification 04 | n/a | 2021-2025 | May 26, 2023 | Jun 14, 2023 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EX7KZ6sr9hRBrV3pMJW4aYgBMsjsA7Qsfu0BIcFAeTXUtQ?e=foJwaM | Subaward - Modification 4 - FE
Modification 05 | n/a | 2021-2025 | September 28, 2023 | October 26, 2023 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EVK3KJUUc_FBhuYN41xuJGABvq_2HT03xqTkKp8ZPp5-MQ?e=0y4Y8o | Subaward - Modification 5 - FE
Modification 06 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions |  | 2021 |  |  |  | https://partnersnet107.sharepoint.com/:f:/s/Programs/Eq0iMAmT6UpBn4GvwqWmzjUBuFhF_TrL19Bsvn0UDF9EMg?e=yCYGbU | Verification
List restrictions |  | 2022 |  |  |  | https://partnersnet107.sharepoint.com/:f:/s/Programs/EpOLuuOg3h9GiSEzDjKKcsABHebFb13ORCQ_kV1jpQEyxA?e=caQUU2 | Verification
List restrictions |  | 2023 |  |  |  | https://partnersnet107.sharepoint.com/:f:/s/Programs/EvdpX7dY_BZPlhcoPsOSY2UBu7mgzXRhTQm6nB9cW8sUhw?e=0BZuN0 | Verification
List special provisions or requirements
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: POA´s Procurement approvals | FYXX |  | MM/DD/YYYY | MM/DD/YYYY |  | https://partnersnet107.sharepoint.com/:f:/s/Programs/EjrHqwuqrS1Bh7WGyUgalxkBC1SH_YnaIJUThk9ruTgcdA?e=eb7dgQ | Include all procurement approvals
Topic: POA´s STTA approvals | FYXX |  | MM/DD/YYYY | MM/DD/YYYY |  | https://partnersnet107.sharepoint.com/:f:/s/Programs/EpLeTlcO_HdOjb9ph87cddgB-n_Acx5zjYW_p_6O2uHAOw?e=a8QI0e | Include all STTAs approvals and resignation letters
Topic: POA´s STAFFs approvals | FYXX |  | MM/DD/YYYY | MM/DD/YYYY |  | https://partnersnet107.sharepoint.com/:f:/s/Programs/EhM9tCEbm6xPqPjcso95iCMBTp8fsa4AI9yOzKpzC1ivQg?e=D318su | Include all Staff approvals and resignation letters
Topic: POA´s 2ND TIER Subawardeess approvals | FYXX |  | MM/DD/YYYY | MM/DD/YYYY |  | https://partnersnet107.sharepoint.com/:f:/s/Programs/EuP8RIvvX1FJorigFg_ln8MBGciUhnjKQf2fp3F3XzFSDw?e=gbgnyR | Include all 2ND TIER Subawardeess approvals
Topic: 800-FC-001.FAA - TRASO | FYXX |  | April 4, 2022 | June 3, 2022 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EQSmxoBP2xVEhhEMyFqzKTEBRVF8GGp0_5Rr9Ghxt8C9sw?e=YaivVk | Second Tier Grant Reviews Cover Sheet
Topic: 800-FC-001.FAA - TRASO | FYXX |  | April 4, 2022 | June 7, 2022 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EWMthTrKqw1DrAYQ7V6eZi0BPb0FW5CLphygaVvaMf0taw?e=vK1MYX | Second Tier Grant POAs Approval Letter
Topic: 800-FC-002.FAA - FCA | FYXX |  | July 22, 2022 | August 1, 2022 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EQFgPbbD2P9DsXrm0fLYo9wB8UxtcFDscKYTgxknl8Uw4Q?e=T0BUl9 | Second Tier Grant Reviews Cover Sheet
Topic: 800-FC-002.FAA - FCA | FYXX |  | July 22, 2022 | August 1, 2022 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EX2WqwI4HgRAlrJSJV8fAHgB-FJAWe2SNZl3BMf-nHx7UA?e=KVgMfI | Second Tier Grant POAs Approval Letter
Topic: 800-FC-003.FAA - UNINORTE | FYXX |  | August 1, 2022 | September 7, 2022 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EbkV23BlsBVAs7depROlX7MB-YUPiAckGyVDlfQ9hl1jAw?e=W6aQPJ | Second Tier Grant Reviews Cover Sheet
Topic: 800-FC-003.FAA - UNINORTE | FYXX |  | August 1, 2022 | September 16, 2022 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/Eb_fAzp6FJ9PmDlT0V3cztgBNztP3DJd5UvHKu07eugBFQ?e=7nFZEO | Second Tier Grant POAs Approval Letter
Topic: 800-FC-004.FAA - ASPA | FYXX |  | January 25, 2023 | February 15, 2023 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EQUjd6bMjepGtfioV3hrKscBk2vnvhcQfEFf0NosypbaBQ?e=0nkRbE | Second Tier Grant Reviews Cover Sheet
Topic: 800-FC-004.FAA - ASPA | FYXX |  | January 25, 2023 | February 16, 2023 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EaHg50uEqPpBtWsh5nFnU74BpSVL60ZvjIhBnRS8Efj8nA?e=nep3OH | Second Tier Grant POAs Approval Letter
Topic: 800-FC-005.FAA - FUNDALECTURA | FYXX |  | January 10, 2023 | February 15, 2023 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/Ef4g6wGVg5lLpU-CfDZ4wKABnBy8NzS-5z4kkfDajAZ6tw?e=A2wIZv | Second Tier Grant Reviews Cover Sheet
Topic: 800-FC-005.FAA - FUNDALECTURA | FYXX |  | January 10, 2023 | February 15, 2023 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EWw0WeLrc9lHnNP5VjuuucsBUo1adB3oSae3CW2k_wr_Iw?e=NXK3sy | Second Tier Grant POAs Approval Letter
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
2023 - Audit FY2022 | FYXX |  | September 1, 2023 |  |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EYMnAyY3xXNOvMKcPUmKYyEB4BItOPZBUZZRQObX7eGa6A?e=3Y9ho1 | External Audit Management Letter
2023 - Audit FY2022 | FYXX |  | September 1, 2023 |  |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EZElEvvixTRFrl9sAGLrBW4BV87y5P8zHtx1GjYYKr9fUw?e=GspByv | Final Audit Report
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Note on D11: Claudia J Rojas H: Fecha de la carta de solicitud de FC
Note on E11: Claudia J Rojas H: Fecha de la firma total (aparece en la modificación)
Note on F11: Claudia J Rojas H: = que en la categoría

## Subaward PE
Compliance Matrix
Subaward Name/Title: | Juntos Aprendemos |  |  |  | Total Award Amount: | 6818381 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 800-Parque Explora |  |  |  | Total Obligation Amount: | 3532222 | Vanessa Ardila (August 16, 2021 - to date)
Subaward Number: | 800-Parque Explora |  |  |  | Cost Share Amount: | 0
Donor: | USAID |  |  |  | Leverage Amount: | 442234
CFDA: | 7200AA21CA00003 |  |  |  | USAID Only: Geographic Code: | 937
Subaward Start Date: | August 16, 2021 |  |  |  | Key Personnel: | Community Engagement and Outreach Director - Olga Liliana Leiva (former: Carolina Giraldo)
Subaward End Date: | October 31, 2025 |  |  |  | Approved Indirect Rate(s) %: | 10%
Subaward Point of Contact: | Andrés Felipe Roldán Giraldo |  |  |  | Prior Approvals Required: | All activities’ planning Annual work plans Approval and changes of key personnel Report outlines and report drafts All consultancies, contracts, and purchase orders over 10,000 USD Equipment purchases over 5,000 USD (unitary cost per equipment) All Second-Tier Sub-Awards Activity Monitoring Evaluation and Learning Plan (AMELP) Programmatic redirection. Print or electronic publications Leverage Plan
POA Point of Contact: | Gustavo Payan - Alejandro Torres - Vanessa Ardila |  |  |  | Treatment of Program Income: | Article 10: Added to funds committed by POA and the recipient to the program and used to further eligible program objective
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2021 | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800-Parque Explora FE.pdf | Subaward
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800 - Parque Explora - Mod 1_FE.pdf | Increase sub-obligated funding in USD $479,465, to carry out Juntos Aprendemos activities as per the approved work plan.
Modification 02 | n/a | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800 - Parque Explora - Mod 2_FE.pdf | To increase the obligation of the subaward amount by USD $944,717 from USD $1,420,438 to USD $2,365,155. To delete the DUNS number in its entirety and replace it with the Unique Entity ID (UEI) Number.
Modification 03 | n/a | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800 - Parque Explora - Mod 3_FE.pdf | To increase the obligation of the subaward amount by USD $231,000 from USD $2,365,155 to USD $2,596,155
Modification 04 | n/a | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800 - Parque Explora - Mod 4_FE.pdf | To increase the obligation of the subaward amount by USD $30,000 from USD $2,596,155 to USD $2,626,155.
Modification 05 | n/a | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800 - Parque Explora - Mod 5_FE.pdf | To increase the obligation of the subaward amount by USD $466,068 from USD $2,626,155 to USD $3,092,223. This obligation increase will provide sufficient funding for the subawardee to continue implementing activities outlined in the program description thru September 2023
Modification 06 | n/a | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  |  | To increase the obligation of the subaward amount by USD $440,000 from USD $3,092,223 to USD $3,532,223. Modify ARTICLE 8. Payments and Financial Reports: Paragraph 4, with the purpose to clarify the proper date to present advance payment request each month; Paragraph 14, with the purpose to include the text that each expense report shall contain, according with the form provided by POA. Modify ARTICLE 13. Title to and Care of Project Property: Paragraph 4, with the purpose to modify threshold cost conditions about project’s final inventory list, to include all property and equipment with a current fair market value threshold of US$100. Modify ARTICLE 14. Substantial Involvement: Include numerals e) and f) on the approval activities in charge of POA, according with the program needs and main Cooperative Agreement signed between POA and USAID. Modify ARTICLE 19. Assignment: Clarify the article to guarantee that the Subawardee understand that without prior written approval from POA may not make some decisions. Modify ARTICLE 31. Value Added Tax (VAT) Reporting: Paragraph 3, with the purpose to clarify that the sub-awardee is not the one who submits the reimbursement request to the DIAN. Update Project Coordination and supervision points of contact. Include Key Personnel. Update report submission dates.
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions | [5 empty] | VC Board of Directors | Verification
List restrictions | [5 empty] | VC Board of Directors 2022 | Verification
List restrictions | [5 empty] | VC Board of Directors 2023 | Verification
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
2023 - Audit FY2022 | FYXX |  | September 1, 2023 |  |  | 2023 - Audit FY2022 | Audit file
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Subaward PA
Compliance Matrix
Subaward Name/Title: | Juntos Aprendemos |  |  |  | Total Award Amount: | 2133979 | POA Subaward Manager(s) (including dates):
Internal Grant Name: | 800-Proantioquia |  |  |  | Total Obligation Amount: | 1220032 | Vanessa Ardila (August 16, 2021 - to date)
Subaward Number: | 800-Proantioquia |  |  |  | Cost Share Amount: | 0
Donor: | USAID |  |  |  | Leverage Amount: | 300806
CFDA: | 7200AA21CA00003 |  |  |  | USAID Only: Geographic Code: | 937
Subaward Start Date: | August 16, 2021 |  |  |  | Key Personnel: | Partnerships and Alliances Director (Proantioquia) - Natalia Currea (former: Natalia Niño)
Subaward End Date: | October 31, 2025 // August 31, 2026 (mod 5) |  |  |  | Approved Indirect Rate(s) %: | 9%
Subaward Point of Contact: | Maria Bibiana Botero |  |  |  | Prior Approvals Required: | All activities’ planning Annual work plans Approval and changes of key personnel Report outlines and report drafts All consultancies, contracts, and purchase orders over 10,000 USD Equipment purchases over 5,000 USD (unitary cost per equipment) Activity Monitoring Evaluation and Learning Plan (AMELP) Programmatic redirection. Print or electronic publications Leverage Plan
POA Point of Contact: | Gustavo Payan - Alejandro Torres - Vanessa Ardila |  |  |  | Treatment of Program Income: | Article 10: Added to funds committed by POA and the recipient to the program and used to further eligible program objective
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | 2021 | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800-ProAntioquia FE.pdf | Subaward
Cost Extension | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 01 | n/a | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800 - Proantioquia - Mod No.1 FE.pdf | To increase the obligation of the subaward amount by USD $237,367 from USD $447,655 to USD $685,022. To delete the DUNS number in its entirety and replace it with the Unique Entity ID (UEI) Number.
Modification 02 | n/a | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800 - Proantioquia - Mod No.2_FE.pdf | To increase the obligation of the subaward amount by USD $76,500 from USD $685,022 to USD $761,522.
Modification 03 | n/a | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800 - Proantioquia - Mod No.3 FE.pdf | To increase the obligation of the subaward amount by USD $50,000 from USD $761,522 to USD $811,522.
Modification 04 | n/a | 2021-2025 | MM/DD/YYYY | MM/DD/YYYY |  | 800 - Proantioquia - Mod No.4 FE.pdf | To increase the obligation of the subaward amount by USD $200,510 from USD $811,522 to USD $1,012,032.
Modification 05 | n/a | 2021-2026 | MM/DD/YYYY | MM/DD/YYYY |  | 7. 800-Proantioquia Mod No.5 FE.pdf | Extend the period of performance and change the completion date of the sub agreement (no cost extension). Modify Detailed Budget, realign the original awarded budget and include indirect costs. Update Project Coordination and supervision points of contact. Update the period of performance in the Program Description. Include Key Personnel. Update report submission dates.
Modification 06 | n/a | 2021-2026 | MM/DD/YYYY | MM/DD/YYYY |  | 800 - Proantioquia - Mod No.6 FE.pdf | To increase the obligation of the subaward amount by USD $208,000 from USD $1,012,032, to USD $1,220,032. To clarify the proper date to present advance payment request each month ans include the text that each expense report shall contain, according with the form provided by POA. To modify threshold cost conditions about project’s final inventory list, to include all property and equipment with a current fair market value threshold of US$100. Include numerals e) and f) on the approval activities in charge of POA, according with the program needs and main Cooperative Agreement signed between POA and USAID. Modify ARTICLE 19. Assignment: Clarify the article to guarantee that the Subawardee understand that without prior written approval from POA may not make some decisions. Clarify that the sub-awardee is not the one who submits the VAT reimbursement request to the DIAN, but POA. Delete in its entirety the current “ANNEX A: PROGRAM DESCRIPTION AND OBJECTIVES” and replace for the new ANNEX A with the purpose to reflect programmatic changes, indicators according with the actual AMELP, and to include double column language.
Modification 07 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 08 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 09 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Modification 10 | n/a | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Monitoring, Evaluation & Learning Plan
M&E Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan/Start-up Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
M&E Plan - Cost Extension- Updated | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP Revision | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/ Start-up/PMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Work Plan/PMP - Cost Extension | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Environmental Monitoring and Mitigation Plan (EMMP)
EMMP Plan | FYXX | YYYY-YYYY | MM/DD/YYYY | MM/DD/YYYY
Special Provisions/Restrictions
List restrictions | 2021 |  |  |  |  | VC Board of Directors | Verification
List restrictions | 2022 |  |  |  |  | Visual Compliance 2022 | Verification
List restrictions | 2023 |  |  |  |  | Visual Compliance | Verification
List special provisions or requirements
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Topic: Add description of notes | FYXX |  | MM/DD/YYYY | MM/DD/YYYY
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY