## Instructions
Instructions for completing award compliance Matrix:
· Purpose: ensure that POA is compliant with our awards
· Review award documents (award, annual work plan, PMP, M&E, indicators, etc.)
· Write down everything POA committed to completing
· Note whether POA has completed it, or not.
· If not, make a note as to why or indicate the current status.
Responsible
Home office backstops will be responsible for updating and maintain the matrix
Approvals
Compliance matrix will be review twice annually, once at the end April and October.
Senior Directors for each unit, the Senior Vice President of Programs, and the Compliance team will review and approve twice annually

## Award Summary Page
Compliance Matrix
Award Name/Title: | Cacao and Complementary Crops for Development (C4D) Food for Progress Colombia |  |  |  | Total Award Amount: | $24,776,928 (C4D $22,799,000) | Program Manager(s) (including dates):
Internal Grant Number: | USDA700 |  |  |  | Total Obligation Amount: | N/A | Sheila Posas (11/01/2022)
Award Number: | FCC-514-2020/002-00 |  |  |  | Cost Share Amount: | 1977928.07 | Javiera Salinas (01/01/2022)
Donor: | USDA, Foreign Agricultural Service, Global Programs, International Food Assistance Division |  |  |  | Leverage Amount: | N/A | Lesly Rubio (09/01/2023)
CFDA: | Food for Progress (10.606) |  |  |  | USAID Only: Geographic Code:
Award Start Date: | 2020-10-01 |  |  |  | Key Personnel: | COP (Pablo Ramirez), Technical Director (Felipe Rojas)
Award End Date: | 2025-09-30 |  |  |  | Approved Indirect Rate(s) %: | 28.69
Program Director: | Sheila Posas |  |  |  | Prior Approvals Required:
Agreement Officer Rep. (AOR)/Grants Officer Rep. (GOR): | Kyle Potaniec (Analyst) |  |  |  | Treatment of Program Income:
Agreement Officer (AO)/Grants Officer (GO): | Ingrid Ardjosoediro (Director of Program)
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Agreement | n/a | 2020-2025 | MM/DD/YYYY | 2020-09-22 | USDA700_Award_Fully Executed_2020-10 | https://partnersnet107.sharepoint.com/:b:/s/Programs/EbXFsSn3nNxLgWw23zIoSNIBUxHNjvSDzbt8B7rtTUfM2A?e=WMRi6V
Modification 01 | n/a | 2020-2025 | 2021-02-25 | 2021-04-01 | USDA700_Amendment 1_Fully Executed_2020-04 | https://partnersnet107.sharepoint.com/:b:/s/Programs/Ea3gIT7m7UpItHtHJwJDOaoB7gehxmbwMoGSKs_HiqzuGQ?e=Wjqjxi | Mod to budget summary and narrative, performance indicators and results framework.
Modification 02 - Budget realignment | n/a | 2021-2025 | Pending | Pending | Amendment 2 - In Progress | https://partnersnet107.sharepoint.com/:f:/s/Programs/EvoBp9VCByZAq4N2hFcUg5UBY723_SHW0Ug2kHqMZZSy7A?e=bk7yUV
Modification 03 - Cost Extension/Supplemental Funding | n/a | 2021-2025 | Pending | Pending | Amendment 3 (Supplemental Funding) | https://partnersnet107.sharepoint.com/:f:/s/Programs/EgNmkDe4wWpMmo8Jg1-snAYBKYTdmQKSZADDhboPQTmDGQ?e=A3ws9l
Monitoring, Evaluation & Learning Plan
M&E Plan | FY21 | 2020-2025 | 2021-04-13 | 2021-07-16 | Partners of the Americas_Evaluation Plan_USDA Approved_2021-07-16 | https://partnersnet107.sharepoint.com/:w:/s/Programs/ERirWaF8ZZ9Lrm0Dh_qO-tcBmxRAF_ffspf8aZPbD3NWIg?e=FgGxNb
Work Plan/Performance Monitoring Plan (PMP)
Implementation Plan/ Implementation PMP | FY21 | 2021-2025 | 2021-04-13 | 2021-08-27 | POA_PMP_CLEAN | https://partnersnet107.sharepoint.com/:w:/s/Programs/EZddsN6zRchLphFoRP1oqJUBLrR9XaSQGLPPD4OXFoLZEQ?e=1EBi7X
Work Plan | FY21 | 2021-2025 | 2021-05-28 | 2021-10-29 | POA_C4D Work Plan Update_2021-10 | https://partnersnet107.sharepoint.com/:f:/s/Programs/Eoh8_Z7rwp9AlHYGePUbtScBVHImocsxAqvzgUT6ELy1vA?e=M1B5Tk | Link to final version of Work Plan gantt and narrative
Work Plan Updated #1 | FY22 | 2021-2025 | 2021-08-31 | No response from USDA | POA_C4D Work Plan Update_2022-08 | https://partnersnet107.sharepoint.com/:f:/s/Programs/EkuXaawwo91Bko2sPTK1EUcB70MPHzHONIkNTty0UINI_Q?e=rtRSes | Updated LOP Work Plan FY21-FY25 (includes Theory of Change, Critical Assumptions, Activity Section, Change Management, Project Map, Organizational Chart, Travel Plan and Communication Plan) Updated Excel Work Plan (includes WBS, Dictionary, and Gantt Chart)
Work Plan Updated #2 | FY23 | 2021-2025 | Pending | Pending | POA_C4D Work Plan Update_2023-08 | https://partnersnet107.sharepoint.com/:f:/s/Programs/EnhgFTbhEYZFsWerRzKQA1gBbbQ61mfBK39pSSOObQX7wA?e=NjWgDI
Special Provisions/Restrictions
Monetization abides by 7CFR section 1499.1 (e.) | [5 empty] | https://www.ecfr.gov/current/title-7/subtitle-B/chapter-XIV/subchapter-C/part-1499
FAS’s Award General Terms & Conditions for Grants and Coop. Agreements | [5 empty] | https://fas.usda.gov/grants-and-cooperative-agreements-administrative-general-terms-and-conditions
FAS’s Award General Terms & Conditions for Grants and Coop. Agreements | [5 empty] | https://fas.usda.gov/grants-and-cooperative-agreements-national-policy-general-terms-and-conditions
Subawardee approval by USDA | [5 empty] | https://partnersnet107.sharepoint.com/:b:/s/Programs/EbXFsSn3nNxLgWw23zIoSNIBUxHNjvSDzbt8B7rtTUfM2A?e=5vDt9x
Meeting Notes with Donor (AOR/GOR Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Approval of COP (Pablo Ramírez) | FY20 |  | 2020-11-02 | 2020-11-06 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/ETUa1zAAU89JsGoqd-bbdMoBKIKcoQLAFlY2L-LsyK8JBg?e=kZehpD
Topic: Change in cadence for LOP Updated Work Plan | FY21 |  | 2021-10-15 | 2021-10-29 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/EYArFHTznE9Kl7wTkYzmnsoBAytfxt1snTo1MvrOWvUmsA?e=QcmmXB | Approval to send updated LOP Work Plan from twice per year to once a year.
Topic: Approval of Technical Director (Felipe Rojas) | FY21 |  | 2021-02-22 | 2021-03-05 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/EUegTYr18g1DljihPahhlMYB_DkpJusAgW0jUR_cw0rVwg?e=vkE7kI
Topic: Organizational chart | FY21 |  | 2021-04-29
Topic: Budget narrative approval | FY21 |  | 2021-02-16 | 2021-02-18 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/EU5u-P4rZlBJkn3C9BEQB9QBYxrZ74wyhoaIUDgMjq-3Zg?e=uzc1n5
Topic: Approval for activities 7-8 | FY21 |  | 2021-12-23 | 2022-01-04 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/ETq45i-z9oxClI3h7wtJdMQBt_IOhZ-ZyWKm7oV8WZ6zlQ?e=wCiref
Topic: Cataruben selected for the Carbon Special Study | FY22 |  | 2022-12-21 | 2022-04-28 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/ER0UbMvmSNlIlIiNfNqHl2IBdJ5u2nLB4fRkiEEkDdnTHg?e=9RcifM
Topic: Solidaridad Network Action Memo (Sub) | FY22 |  | 2022-03-28 | 2022-04-11 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/EZ3-k2rX8AlMgZg-lBy8AYMBAj1qiOWAkQ01_7VZvnHGrQ?e=grgk6Q
Topic: Philanthropy Fund consultant approval | FY22 |  | 2022-04-15 | 2022-04-18 |  | https://partnersnet107.sharepoint.com/:b:/s/Programs/ETOF6CpJn4BDj7pJoy4oRcMBbAcaXCSFYx8GFe6GpGYYjA?e=ghv059
Topic: Contract Fedecacao (non-competitive bid) | FY22 |  | 2022-12-21 | 2022-12-21 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/ETWF-zxwTntLlI0_VqAjVUIBwZr_489LZcuTWc3jKSQHSQ?e=PMtmt7
Topic: Activity 8 Transer of Funds to Stone Castel | FY22 |  | 2022-08-30 | 2022-09-14 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/EZcK5TgL4lNMiFWOojdxmWkBihukPZ554enJHo9YrRS2qg?e=7WHgSv
Topic: 16 participants to Cataruben Forum | FY23 |  | 2023-04-13 | 2023-04-20 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/EXk_oL5dXwpAgTksC2roxWcBuUsxrcVvWxM_hScx0ChJCg?e=ZYGmcZ
Topic: Approval of landing design RCOP website | FY23 |  | 2023-11-16 | Pending |  | Pending
Topic: Reallocation of funds for insurance program | FY23 |  | 2023-04-24 | 2023-05-03 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/EbkSZdvL-kNKqAOmL6CDSr8BnOhvdYcs3ckyXHme0Tue6w?e=rdJvkj
Topic: Living Income Report | FY23 |  | 2023-07-25 | 2023-08-10 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/EQXVrvfc77ROvMpCjvdeDIkB5sb0w_YurMwL8WEgYR8WOg?e=bmVR54
Topic: Approval for pre-baseline study for activities 2-6 | FY22 |  | 2022-07-29 | 2022-09-12 |  | https://partnersnet107.sharepoint.com/:u:/s/Programs/EYo9tYcIYg9Gp-YLsLH9adgBobEPeO_oGmfZhx6dY8sDeA?e=fgWbaV
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Report of compliance and finding issues in the finance unit | FY22 |  | 2023-09-14 |  | Breach of signature delegation of authority and other compliance issues by Finance Director | https://partnersnet107.sharepoint.com/:f:/s/Programs/ErsJ_iEihbxJqRNTj24UH24BoBzAfV2-Ofx3CAzD1AhgDQ?e=LVsjTc | Disciplinary report to Finance Director with details of compliance issues
Procurement and contract issues: "We Push" Case | FY23 |  | 2023-03-06 |  | Breach of compliance in contracts & procurement | https://partnersnet107.sharepoint.com/:p:/s/Programs/EQavRs64uAxJmBSOwWftN1YBN0ZkiAdEgus8oCSxZ9F3kg?e=ik7zYg | Presentation highlighting findings and training to remind compliance to FO staff
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY

## Compliance Matrix Details
Breakdown of Award Requirements
| Award Terms & Conditions | Compliant Y/N | Comments | Program Description | Compliant Y/N | Comments | Work Plan FY21 (LOP) | Compliant Y/N | Comments | Workplan FY23 (LOP) | Compliant Y/N | Comments | Work Plan FYXX | Compliant Y/N | Comments | Workplan FYXX | Compliant Y/N | Comments | Evaluation Plan FY21-FY25 | Compliant Y/N | Comments | Indicators | Compliant Y/N | Comments | Activities in Budget Narrative | Compliant Y/N | Comments
1 | Financial Reporting: April 30, 2021 | Y |  | Description: Partners of the Americas will monetize 91,350 MT of Hard Red Winter Wheat and, over a period of approximately five years, use the proceeds from such sale to implement a project in Colombia focused on achieving the following objectives: - To increase agricultural productivity and improve the living incomes of cacao farmers by supporting economically viable diversified farming systems, sustainable agricultural landscapes and equitable commercialization models, and increase production, aggregation, processing and commercialization of complementary crops of cacao farming systems - To expand trade of agricultural products by improving post-production processing and handling, facilitating lending and increasing the use of financial services and creating marketing linkages between farmers, producer groups and national and international value chain actors to develop robust and equitable access for cacao farmer farmers in Colombia. | Y |  | Youth Considerations: Creating opportunities to participate in cacao & CCs value chains through international exchanges, study trips, research grants, and agribusiness start-up grants. |  |  | Youth Considerations: Creating opportunities to participate in cacao & CCs value chains through international exchanges, study trips, research grants, and agribusiness start-up grants. | Y |  | Environmental Compliance: XXX |  |  | Environmental Compliance: XXX |  |  | Baseline Study 9/30/2021 | Y |  | FFPr1: Yield of targeted agricultural commodities among project participation (kg/tree, cacao) | Y |  | Agricultural Insurance Program. a) Using the funds from Activity #5, item 3.5.6 in the budget narrative for over 3 years. b) Program unlocks $761,299 from government to count as cost share. | Y | https://partnersnet107.sharepoint.com/:u:/s/Programs/EbkSZdvL-kNKqAOmL6CDSr8BnOhvdYcs3ckyXHme0Tue6w?e=1eZGcg
2 | Financial Reporting: October 30, 2021 | Y |  | Geographic Scope: Colombia (14 departments) | Y |  | Sustainability: POA will disseminate project learnings with Colombian stakeholders to foster sustainability. Main mechanism will be the Regional Community of Practice which will work beyond C4D compiling project's lessons learned, and disseminating promising approaches to cacao & CCs value chains. |  |  | Sustainability: POA will disseminate project learnings with Colombian stakeholders to foster sustainability. Main mechanism will be the Regional Community of Practice which will work beyond C4D compiling project's lessons learned, and disseminating promising approaches to cacao & CCs value chains. | Y |  | Gender Considerations: XXX |  |  | Gender Considerations: XXX |  |  | C4D Monitoring Guidelines 09/30/2021 | Y |  | FFPr1: Yield of targeted agricultural commodities among project participation (kg/tree, CC) | N | CCs are still in their early growth stages out in the field. | Working on a budget realignment | N | In progress
3 | Financial Reporting: April 30, 2022 | Y |  | 1. Complimentary value chain development in the cacao sector | Y |  | 1. Complimentary value chain development in the cacao sector |  |  | 1. Complimentary value chain development in the cacao sector |  |  | Sustainability: XXX |  |  | Sustainability: XXX |  |  | MEL Work Plan 11/16/2021 | Y |  | FFPr18: Value of annual sales of farms & firms receiving USDA assistance (Cacao) | Y
4 | Financial Reporting: October 30, 2022 | Y |  | 1.1. Lead value chain development in complimentary crops | Y |  | Y1 Special studies prep | Y |  | Y1 Special studies prep | Y | [7 empty] | Survey and User Manual 11/25/2021 | Y |  | FFPr18: Value of annual sales of farms & firms receiving USDA assistance (Complementary corps) | N | CCs are still in their early growth stages out in the field.
5 | Financial Reporting: April 30, 2023 | Y |  | 1.2. Review work of value chain actors in the cacao sector, as well as past programming and approaches | Y |  | Y2 Discuss results of sondeo data - finalize region selection | Y |  | Y2 Discuss results of sondeo data - finalize region selection | Y | [7 empty] | Database 02/22/2022 | Y |  | Custom1: Number of Farms with productivity gains | Y
6 | Financial Reporting: October 30, 2023 | Y |  | 1.3. Align current initiatives with national goals and strategies | Y |  | Y2 Value chain study - Value chain selection | Y |  | Y2 Value chain study | Y | [7 empty] | Final baseline study 04/30/2023 (part of special studies) | Y |  | FFPr21: Number of individuals who have received short-term agricultural sector productivity or food security training | Y
7 | Financial Reporting: April 30, 2024 | N |  | 1.4. Complete value chain feasibility studies (Value Chain Analysis & Living Income Study) | Y |  | Y2 Living Income study | Y |  | Y2 Living Income study | Y | [7 empty] | M&E Information System Buildout 05/12/2022 | Y |  | FFPr22: Number of individuals participating in USDA Food security programs | Y
8 | Financial Reporting: October 30, 2024 | N |  | 1.5. Select a set of complimentary crops value chains to evaluate market & production opportunities with a landscape approach | Y |  | Y2 Carbon Assessment | N |  | Y2 Carbon Assessment | Y | [7 empty] | C4D Monitoring Guidelines (adjustments & trainings) 04/19/2022 | Y |  | FFPr23: Number of individuals benefiting indirectly as a result of USDA Assistance | Y
9 | Financial Reporting: April 30, 2025 | N |  | 1.6. Support other diversification crops when appropriate | Y |  | Y2 Ex-ante Analysis (Carbon Assessment) | Y |  | Y3 Value chain study (continuation) | N | [7 empty] | Living Income Study: 08/20/2023 (part of special studies) | Y |  | FFPr19: Volume of Commodities sold by farm and firms (Cacao) | Y
10 | Financial Reporting: October 30, 2025 | N |  | 1.7.Select value chains to improve producers living income, create business models based on farmers' input through focus groups (Solidaridad) | Y |  | Y2 Carbon Sampling | N |  | Y3 Living Income Study (continuation) | N | [7 empty] | Value Chains Reports: 09/01/2023 (part of special studies) | N | Submitted in Nov 15,'23 | FFPr19: Volume of Commodities sold by farm and firms (CC) | N | CCs are still in their early growth stages out in the field.
11 | Results Framework: August 27, 2021 | Y |  | 1.8. Support various actors along the value chain with the suite of services outlined | Y |  | Y2 Agreement POA-CSU |  |  | Y3 Carbon assessment (continuation) | N | [7 empty] | Business Models Report: 09/01/2023 (part of special studies) | N | Not ready yet | FFPr2: Number of hectares under improved management practices or technologies that promote improved climate risk reduction and/or natural resources management | Y
12 | Performance Development Plan (PMP): August 27, 2021 | Y |  | 1.9. Carbon Assessment by Cataruben | Y |  | Y2 Support to CBP Tool | N |  | Y3 Living Income Study - Midterm | N | [7 empty] | Carbon Assessment (13 deliverables): 07/28/2023 (part of special studies) | N | 2 deliverables are due and require USDA approval | FFPr4: Number of individuals in the agriculture system who have applied improved management practices or technologies with USDA assistance | Y
13 | Evaluation Plan: July 16, 2021 | Y |  | 2. Producer organization development and commercialization | N |  | Y3-Y4 Living Income study, midterm | Pending |  | Y5 Carbon assessment (final) | N | [7 empty] | Semiannual Performace Report Apr - Sep 21 / FY21: Oct 15/21 | Y |  | Custom 2: Number of orgs establishing improved seedstock as a result of USDA assistance | N | Nursery program has not started.
14 | Semi-Annual reports: April 30, 2021 | Y |  | 2.1. Build capacity of cacao and CC organizations through supporting activities along with subrecipient (TBD). Subgrant $750,000 for training local orgs. | N |  | Y3-Y4 Carbon assessment, mid term | Pending |  | Y5 Living Income Study (final) | N | [7 empty] | Semiannual performance report Oct'21-Mar'22: FY22 Apr 15/22 | Y |  | FFPr5: Number of individuals accessing agriculture-related financing as a result of USDA assistance (make sure they count the bank accounts created for the carbon activity) | Y
15 | Semi-Annual reports: October 30, 2021 | Y |  | 2.2. Ensure farmers improved access to finance & market information | N |  | Y3 Publish Value chain study & business model per value chain | Pending |  | 2. Producer organization development and commercialization | [8 empty] | Semiannual performance report Apr-Sep'22:FY22 Oct 14/22 | Y |  | FFPRr7: Number of loans disbursed as a result of USDA assistance | N | Activity #5 is still in its early stages in the field.
16 | Semi-Annual reports: April 30, 2022 | Y |  | 2.3. Target groups will be cacao groups and fermentation/aggregation centers, and local support orgs. Cost share of $56,534 from expert advisors, SENA, org development advisor. | N |  | Y5 Carbon assesment final | Pending |  | Y2 Phase 1. Diagnosis & characterization. Commercial evaluation of producer organizations. | N | Done in FY3 | [6 empty] | Semiannual performance report Oct'23-Mar'23: FY23 Apr 14/23 | Y |  | FFPr8: Value of agriculture-related financing accessed as a result of USDA assistance | N | Activity #5 is still in its early stages in the field.
17 | Semi-Annual reports: October 30, 2022 | Y |  | 2.4. Procure subrecipient to train target producer organizations to improve admin, financial & commercial capacity. Cost share of $102,923 from expert advisors, SENA, org development advisor. | N |  | Y5 Living Income study final - post intervention | Pending |  | Y2. Phase II. Prepare work plan & gap analysis for each organization. | N | [7 empty] | Midterm Evaluation: Oct 30/23 | N | About to solicit proposals to conduct ME | FFPr9: Number of technologies, practices, and approaches under various phases of research, development, and uptake as a result of USDA assistance (Phase 4) | Y
18 | Semi-Annual reports: April 30, 2023 | Y |  | 2.5. Conduct participatory organizational capacity assessments with farmers' groups to co-design work plans to address weaknesses | N |  | 2. Producer organization development and commercialization |  |  | Y2 Phase III. Execution of PO training nationwide based on diagnosis & characterization | N | [7 empty] | Semiannual performance report Apr-Sep FY23: Oct 13/23 | Y | About to send indicators table w/comments (in addition to FAIS upload) | FFPr9: Number of technologies, practices, and approaches under various phases of research, development, and uptake as a result of USDA assistance (Phase 1-3) | N | Pending to be monitored.
19 | Semi-Annual reports: October 30, 2023 | Y |  | 2.6. POA will tailor support to ensure producer orgs have clear commercialization plan to access services needed to meet their goals | N |  | Y2 Socialize Red Cacaotera final list of orgs with EAFIT Social & determine workplan by region (Red Cacaotera) | N |  | Y3 Preparation activities (IC Fundación & POA). Hiring, work plan, M&E, introduction sessions. | Y | [7 empty] | Semiannual performance report Oct-Mar FY24: Apr 15/24 | N |  | FFPr3: Number of hectares under improved management practices or technologies with USDA Assistance | Y
20 | Semi-Annual reports: April 30, 2024 | N |  | 2.7. Evaluate and adapt work plans based on producer groups' feedback annually | N |  | Y2 Phase 1: Diagnosis & Characterization (RFP - Org. Strengthening) - Deliverable 9 - Commercial evaluation of producer orgs | N |  | Y3 M&E Plan from IC Fundacion to POA. Submission, revision and approval. Start delivery of commericalization trainings. | Y | [7 empty] | Semiannual performance report Apr-Sep FY24: Oct 15/24 | N |  | Custom 3: Number of farms demonstrating improved landcape management | Y
21 | Semi-Annual reports: October 30, 2024 | N |  | 3. Agriculture extension and production support | Y |  | Y2 Phase 2: Prepare work plan & gap analysis for each org | N |  | Y3 Review Organization Data by C4D | Y | [7 empty] | Semiannual performance report Sep-Mar FY25: Apr 15/25 | N |  | Custom 4: Estimated tonnage of carbon sequestered | N | Baseline not submitted, in 0 for now.
22 | Semi-Annual reports: April 30, 2025 | N |  | 3.1. Develop farmer-focused technical packages to provide extension services for cacao & CCs (collab w/public & private sector extension partners for region-specific packages & operations). | Y |  | Y2 Phase 3: Execution of PO training nationwide based on diagnosis & characterization | N |  | Y3 Socialization of Activity 2 - Org Strenghtening | Y | [7 empty] | Final Evaluation: Sept 23/25 | N |  | Custom 5: Number of households with improved living income outcomes | N | Not reporting yet since it's linked to mid & final evals.
23 | Semi-Annual reports: October 30, 2025 | N |  | 3.2. Work with existing extension providers to coordinate services effectively & identify early adopters to implement a training model | Y |  | Y3-Y5 In-situ training at EAFIT University | N |  | Y3 Socialization of Activity 2 - Org Strenghtening with C4D Partners | Y | [10 empty] | FFPr12: Number of organizations with increased performance improvement with USDA assistance | N | Activity #2 is still in its early stages in the field.
24 | Final Program Report: December 29, 2025 (90 days after end of performance period) | N |  | 3.3. Increase producers access to market information, leading to diversified income sources | Y |  | Y3-Y5 Deliver Commercial model training | N |  | Y3 Reports submission and approval by C4D | N | [10 empty] | FFPr13: Number of public-private partnerships formed as a result of USDA assistance | Y
25 | Work Plan Update FY22: August 31, 2022 | Y |  | 3.4. Improve & support existing seedbanks to improve producer access to seed stock | N |  | Y3-Y5 Deliver continuous improvement plan/training | N |  | Y3 Organizations Diagnosis | N | Done in FY4 | [9 empty] | FFPr14: Value of new USG commitments and new public and private sector investment leveraged by USDA to support food security and nutrition. | Y
26 | Work Plan Update FY23: August 31, 2023 | Y | Currently working on modifications | 3.5. Hire 39 extension agents. Extension partners will hire additional 6 EAs. | Y |  | Y3-Y5 Deliver competencies - strengthening & empowering training | N |  | Y3 Sistematization of diagnosis information in database | N | [10 empty] | Custom 6: Number of processors and aggregators displaying improved quality of post-production products as a result of USDA assistance (cacao, CCs) | Y
27 | Work Plan Update FY24: August 31, 2024 | N |  | 3.6. EAs will visit producers 4-6 times per year and report progress via tracking software. Living income and landscape management data will inform efficacy of technical extension and allow strategic adjustments. | Y |  | Y3-Y5 End of year evaluation of acchomplishments | N |  | Y3 Phase II. Follow-up by NDE | N | [10 empty] | FFPr16: Total increase in installed storage capacity (dry or cold storage) as a result of USDA assistance | N | Activity #2 is still in its early stages in the field.
28 | Tax Certification Report: During closeout process | N |  | 3.7. Track beneficiaries living income against their adoption of cacao & CCs business models. | N | Tracking only after living income follow-up | Y5 Close Up | Pending |  | Y3 Phase III. Analysis of challenges and opportunities | N | [10 empty] | Custom 7: Number of new agreements signed between buyers and sellers, as a result of USDA assistance (Review indicator definition) | N | IC Fundación is just starting to work, not ready to report.
29 | Program Income: (For guidelines, see USDA Grants and Agreements Links & Award) | N/A |  | 3.8. C4D will hold two meetings annually with each extension partner to report progress & adapt technical strategy based on preliminary results | Y |  | 3. Agriculture extension and production support |  |  | Y3 Evaluation of Results & Diagnosis by NDE | N | [10 empty] | Custom 8: Number of youth with increased capacity in agribusiness | Y
30 | Substantial Involvement: Selection of any subrecipient and changes to provisions. | Y |  | 3.9. C4D will increase productivity by allocating fertilizer to its best-performing farmers (through a farmer segmentation process) | N |  | Y1 Digital feedback from Agrademy. Socialize & request feedback from Agrademy platform w/private sector. Cacaograma. | Y |  | Y4 Define Proposal for Strengthening Plan | N | [10 empty] | Custom 9: Number of grants disbursed to beneficiaries as a result of USDA assistance | N | Grants program had not commenced during this timeframe.
31 | Substantial Involvement: Key personnel selection, departure or new appointments. | Y |  | 3.10. C4D will strengthen existing private sector nurseries so they can produce complementary and cacao grafing materials | N |  | Y2 Extension Agent Hiring & Training (15 by C4D & 30 by extension partners through LOP). | Y |  | Y4 Report of challenges & opportunities. Socialize with orgs. | N | [10 empty] | Custom 10: Value of grants disbursed to beneficiaries as a result of USDA Assistance | N | Grants program had not commenced during this timeframe.
32 | Substantial Involvement: Budget summary, budget narrative, performance indicators & results framework. | Y |  | 3.11. C4D will work with producer groups to establish their own seed stock supplies through nursery startup grants and training | N |  | Y2 Cacaograma for each region | Y |  | Y4 Define Reach of Strengthening Plan (Final version of C4D-approved stregthening plans for orgs) | N | [10 empty] | Custom 12: Number of logins to online Regional Community of Practice knowledge sharing platform | Y
33 | Substantial Involvement: Disengagement from project or 25% reduction of devotion to project | N |  | 4. Improve post-harvest aggregation and processing |  |  | Y2 Farm management plan | Y |  | Y4 Phase IV. Socialize results of diagnostics & implementation of strengthening plans | N | [10 empty] | Custom 13: Number of participating Regional Community of Practice members | N | Website is currently under construction.
34 | Substantial Involvement: Work plan, and update to work plan each FY of LOP | Y |  | 4.1. Use & build upon existing GIS mapping to assess farm production, biophysical conditions, & producer access to processing & aggregation infrastructure for cacao & CCs | N | Activities just in initial stage | Y2 Efficiency indicators | Y |  | Y4 Phase VI. Define business models for cacao | N
35 | Substantial Involvement: Evaluation plan and performance monitoring plan | Y |  | 4.2. Guide existing processors & aggregators to adapt their infrastructure for scaleability | N | Activities just in initial stage | Y2 Productivity enablers per region | Y |  | Y4 Phase V. Strengthening plan for management & commercial skills. Activities in entrepreneurial development, leadership, finance for associations, & planning for next year of implementation. | N
36 | Branding: Compliant to 7 CFR 1499.8 https://www.ecfr.gov/current/title-7/subtitle-B/chapter-XIV/subchapter-C/part-1499/section-1499.8 | Y |  | 4.3. POA will work with producer orgs to upgrade services & become full agribusiness hubs | N | Activities just in initial stage | Y2 Cost of production | Y |  | Y5 Phase V. Strengthening plan for management & commercial skills. Activities in entrepreneurial development, leadership, finance for associations, & evaluation. | N
37 | Marking: Compliant to 7 CFR 1499.8 https://www.ecfr.gov/current/title-7/subtitle-B/chapter-XIV/subchapter-C/part-1499/section-1499.8 | Y |  | 4.4. Provide ongoing support to processors and aggregation actors to create market connections, plan & reach commercialization goals | N | Activities just in initial stage | Y2 Field validation (cacaograma & farm management plan) | Y |  | Y4-Y5 Phase VII. Feasibility assessment to implement business models with complementary crops | N
38 |  |  |  | 4.5. Ensure access to financing services that meet the needs of processing & aggregator actors (links to activity 5) | N | Activities just in initial stage | Y3 Agreement with Agromovil & execution | Y |  | Y5 Phase VIII. Final Measure by NDE | N
39 |  |  |  | 4.6. Pilot technologies & innovations to help advance improvements of aggregation & processing infrastructure | N | Activities just in initial stage | Y2-Y3 Small grants producer organizations (nurseries), Seedstock Private sector | N |  | Y3-Y5 Phase IX. Lessons Learned | N
40 |  |  |  | 4.7. Link actors with local & regional commercial opportunities to direct trade opportunities between Colombia producers and US buyers | N | Activities just in initial stage | Y3-Y5 Extension agreements w/private sector - digital extension GIS (work plans, digital component, contract extension agents) | Y |  | Y3-5 4 Quarterly Reports, 2 Annual Reports & 1 Final Report by IC Fundación | N
41 |  |  |  | 4.8. Improve infrastructure & training to meet sanitary & phytosanitary standards - will take time and be key to long-term success of US-COL trade | N | Activities just in initial stage | Y3-Y4 Cadmium Awareness Platform & Chocosafe Platform |  |  | Y3-5 3 Quarterly Reports by NDE | N
42 |  |  |  | 4.9. POA will prioritize equitable value chain models & buyer commitments to improve living incomes for producers & the development of their communities | N | Activities just in initial stage | Y3 New Partnerships on carbon for marketing carbon offsets | Y |  | 3. Agriculture extension and production support
43 |  |  |  | 5. Ensure financial services/capital access for actors in the value chains |  |  | Y3 New partnerships on food safety, traceability and risk management (cacao) |  |  | Y1 Prepare digital version of cacaogramas | N | Done in FY2
44 |  |  |  | 5.1. Serve as liaison between cacao farmers & multiple Colombian and Int'l financial institutions throughout life of project, including local banks, cooperatives, NGOs, microfinance, impact investors & training institutuions to make existing & new financial services more accessible to producers | Y | This refers to Cacao Seguro program | Y3 Preparar plan para cultivos complementarios con NUTRESA / Seedstock for private nurseries (vegetal material production) |  |  | Y2 Extension agents hiring | Y
45 |  |  |  | 5.2. Ensure access to financial services with both direct project funding & leveraging funds from other financial actors, with business expert volunteers to advise and help entrepreneurs build networks | N |  | Y3 Fine Flavor Study (FCIA) -Design & execute study |  |  | Y2 RPF for Technical Tools (organization list final concept, cacaograma for each region, farm management plan, efficiency indicators, productivity enablers per region, cost of production, field validation, workshop for team) | Y
46 |  |  |  | 5.3. Launch business plan competitions which help identify entrepreneurs & link them to financial & technical support activities | N |  | 4. Improve post-harvest aggregation and processing |  |  | Y2 Extension agreements with private sector partners | Y
47 |  |  |  | 5.4. Work with key actors in the financial sector to improve access to capital adapted to the specific needs of beneficiaires, including link & adapt financial products to beneficiary needs & risks | N |  | Y2 Infrastructure Upgrades: Selection of potential targets; Economic evaluation & final decision | N |  | Y2 Small grants to producer organizations (nursery grants selection & delivery of grants) | N
|  |  |  | 5.5. Improve awareness among stakeholders in the value chain about services available & how to access them | Y |  | Y2 Larger fermentation station uprade: Implementation with Campo Vivo Plan | N |  | Y2 Seedstock private sector (CNCh & Nutresa). Agreements & define delivery dates. | N
|  |  |  | 6. Innovation and job creation through youth engagement |  |  | Y2 Fine Flavor Study Selection of potential region/targets; Design & execute study (Agrosavia) | N |  | Y3 Second round hiring extension agents | Y
|  |  |  | 6.1. Promote youth engagement in the growth of diversified Cacao farming systems | N |  | Y2 Logistics Study Selection of potential region/targets; Design & execute study | N |  | Y3 Fedecacao contract & start field work, management and technical committtees | Y
|  |  |  | 6.2. Range of activities will suport youth engagement at different levels including: Research Opportunities; Academic grants & Exchange visits | Y | In initial stages | Y3 Small grants - Strengthening small processors & aggregators - grantee selection | N |  | Y3 CNCH Agreement & field technical committees | Y
|  |  |  | 6.3. Internships with Cooperative groups and value chain actors | N |  | Y2-Y5 Infrastructure Upgrades: Economic evaluation & final decision | N |  | Y3 Vegetal material (survey to producers) | Y | 75% of progress and still working on it during Y4
|  |  |  | 6.4. Ensure youth led enterprises have access to the full range of services offered by the program | N |  | Y2-Y4 Larger fermentation station uprade | N |  | Y3 Complementary crop pilot project (chili pepper farms selection & alliance with Hugo Restrepo) | Y | Still ongoing in FY4
|  |  |  | 6.5. Work with established networks to lead youth exchanges to study Cacao & Comp crop sectors in Colombia & neighboring countries - to spurn innovation & knowledge sharing across Americas (also links to Act. 7) | N |  | Y3 Fine Flavor Study - Design & execute study | N |  | Y3 Complilation of construction information for platanograma, ajigrama and yucograma | Y | Still ongoing in FY4
|  |  |  | 6.6. Involve youth voices in the Regional Community of Practice (links to Act. 7) | N |  | Y3 Logistics Study - Design & execute study | N |  | Y3-Y4 Execution of extension training nationwide, digital extension and digital market tools | Y
|  |  |  | 6.7. Youth will present research findings & exchange experiences at annual summit to promote professional development & intergenerational transfer of leadership (act. 7) | N |  | 5. Ensure financial services/capital access for actors in the value chains |  |  | Y3 New partnerships on carbon for marketing carbon offsets | N
|  |  |  | 6.8. Youth engagement & training will facilitate the entry of new market participants & consequently, the achievement of a living income at a young age | N |  | Y2 Incubator Partnerships - selection of potential target | N |  | Y3 New partnerships on food security, traceability and risk management (Cacao) | N | This task is under activity #5 (cacao seguro)
|  |  |  | 7. Establishment of Regional Community of Practice |  |  | Y2 Small Grants - Niche Cacao & Complementary Crop Entreprenuership grants - grantee selection | N |  | Y3 New partnerships on food security traceability and risk management (Complementary crops) | N
|  |  |  | 7.1. POA will be active in, & lead where necessary, a robust Regional Community of Practice to coordinate efforts & investments along cacao & complementary crop value chains in Colombia | Y |  | Y3-Y5 Incubator Partnerships - contract distribution & mgmt | N |  | Y3 Digital extension user friendly tool (microlingotes de éxito) | Y | Done every year based on production season
|  |  |  | 7.2. Establish a steering Committee of Colombian entities, advised by USDA & focues on implementation | N |  | Y3-Y5 Small Grants - Niche Cacao & Complementary Crop Entreprenuership grants - grantee selection, grant distribution & mgmt | N |  | Y3 Digital extension user friendly tool (microlingotes de éxito # 2) | Y | Done every year based on production season
|  |  |  | 7.3. Establish thematic steering committee that triangulate expertise around niche topics in Colombia Ag sector | N |  | 6. Innovation and job creation through youth engagement |  |  | Y3 Small Grants Producer organizations & Seedstock Private sector (NUTRESA partnership on nurseries) | N
|  |  |  | 7.4. Lead national coordination & contribute to & exchange lessons internationally | Y |  | Y3-Y5 Student trips (study, international, business plan, Regional community of practice) Selection of potential targets, grant distribution & management | N |  | Y3 Fine Flavor Study (FCIA) | N
|  |  |  | 7.5. Organize summits throughout the Life of Project to enable exchange among actors & with the goal that the RCP continues operating & providing servies beyond project implementation | Y |  | Y3-Y5 Youth Incubation Partnership Selection of potential targets, Contract distribution & mgmt | N |  | Y3 Donation for fertilizers (carmenta) through RFP. | Y | Fertilizer was replaced by ag inputs based on farmers' needs. Bio-factories to replicate biological inputs sustainably (RFP is pending).
|  |  |  | Activities of the RCP will contribute to the positive living outcomes for producers | N |  | Y3-Y4 Niche Cacao & Under-utilized crops market research grants Selection of potential targets. Grant distribution & mgmt | N |  | Y4-Y5 Meetings of progress against targets with private sector | N
|  |  |  | 7.6. POA will allocate funds to grow select initatives that arise from the RCP, including those that help achieve sustainable landscape management & environmental goals | N |  | Y3-Y4 Youth Agribusiness Impact Investing Grants Selection of potential targets, grant distribution & mgmt | N |  | 4. Improve post-harvest aggregation and processing
|  |  |  | 8. Financial services: endowment establishment, fundraising & management |  |  | 7. Establishment of Regional Community of Practice |  |  | Y3 Small Grants. Strengthening small processors and aggregators (selection) | N
|  |  |  | 8.1. Enable continuation of programs core activities after initial 5-year implementation through a philanthropy fund | N |  | Y2-Y5 Digital Platform Execution of Content Dissemination | N |  | Y3 New partnerships in postharvest and processing | N
|  |  |  | 8.2. Form in-country partnerships to administer the endowment and contract legal advisor to create governance plan and bylaws for the fund | N |  | Y3 Regional Community of Practice Event Execution of In-person Event | N |  | Y3 FEDECACAO - Renovación de plantaciones - Infrastructure upgrades (selection & contract execution) | Y
|  |  |  | 8.3. POA - USD3 Million - Fundraise USD$4 million | N |  | Y5 Regional Community of Practice Event Execution of In-person Event | N |  | Y3-Y4 Food Safety: Cadmium & Lead - Componente 3 Agrosavia (selection of potential targets/regions, work plan & M&E plan) | N
|  |  |  | 8.4.Work with implementation steering reps from Cacao & CCs, local and public institutions, USDA, to decide best uses of fund | N |  | 8. Financial services: endowment establishment, fundraising & management |  |  | Y3-Y5 Fine Flavor Study - Componente 2 Agrosavia. Work plan, cartographic analysis, definition of agro-climatic zones & evidence on samples from first-stage harvest | Y
|  |  |  | 8.5. Accrued interest will be used to fund activities that most positively impact living incomes of producers. | N |  | Y2 Start -up Structure: Investment thesis, governance | N |  | Y3-Y5 Logistics Study: Fermentation Centers - Componente 1 Agrosavia | Y
[7 empty] | Y2-Y3 Seeding the Fund | N |  | Y4-Y5 Infrastructure upgrades (evaluation & final decision) | N
[7 empty] | Y3-Y5 Deployment of Funds & Fundraising | N |  | Y4 Large fermentation station upgrade | N
[7 empty] | Y3-Y5 Deployment of Funds & Fundraising | N |  | 5. Ensure financial services/capital access for actors in the value chains
[10 empty] | Y2-Y3 Connect farmers and associations w/existing financing sources | N
[10 empty] | Y2 Instruments to facilitate access to finance and capital | N
[10 empty] | Y3-Y5 Business plan competition | Y
[10 empty] | Y3-Y5 Pilot on parametric agricultural insurance | Y | Through Cacao Seguro
6. Innovation and job creation through youth engagement
[10 empty] | Y3 Young cocoa farmers innovation camp | N
[10 empty] | Y3-Y4 Cocoa youth international exchanges | N
[10 empty] | Y3-Y4 Student intl research exchanges in cocoa & CCs | N
[10 empty] | Y3-Y4 Open innovation grants for cocoa & CCs | N
[10 empty] | Y3-Y4 Incubation/acceleration of entrepreneur initiatives | N
[10 empty] | Y4 Value chain research market grants | N
[10 empty] | Y5 Student trips | N
[10 empty] | Y5 Youth incubation partnership | N
7. Establishment of Regional Community of Practice
[10 empty] | Y2 Digital platform & content planning | N
[10 empty] | Y3 RFP for website | N | Done in Y4
[10 empty] | Y3 RCOP 1st Cacao & CCs Knowledge Circle | Y
[10 empty] | Y2 2nd. Event (virtual) | N
[10 empty] | Y3 Participation in National Cacao Council | Y
[10 empty] | Y3-Y4 Participation in Chocoshow | Y
[10 empty] | Y4 Website execution of contract & deliverables | Y
[10 empty] | Y4 1st Virtual event (webinar) | N
[10 empty] | Y4 International Seminar: C4D-Fedecacao | N
[10 empty] | Y4 Initiatives of C4D COP to be financed | N
[10 empty] | Y5 Website desseimating material & success stories | N
[10 empty] | Y5 RCOP 3rd Cacao & CCs Knowledge Circle | N
[10 empty] | Y5 2nd Virtual event | N
8. Financial services: endowment establishment, fundraising & management
[10 empty] | Y2 Start -up, Structure, Investment thesis, governance, approval from steering committee | N | Did not get approval
[10 empty] | Y2 Incorporation (application, legal docs, registration) | N
[10 empty] | Y2 Investment Committee | N
[10 empty] | Y2-Y3 Seeding the Fund | N
[10 empty] | Y3-Y5 Deployment of Funds | N
[10 empty] | Y3-Y5 Fundraising | N
Note on M65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Requires USDA approval.

## Subaward Summary Page
Compliance Matrix
Subaward Name/Title: | "Strengthening of C4D producer organization development and commercialization" by Fundación Julio y Astrida Carrizosa ONG-IC Fundación. |  |  |  | Total Award Amount: | $$1,181,180 (C4D $799,389) | POA Subaward Manager(s) (including dates):
Internal Grant Name: |  |  |  |  | Total Obligation Amount: | 349763 | Sergio Correa Asmar / Partnerships and Investments Director (06/27/2023)
Subaward Number: | POA-C4D-SUBA-001 |  |  |  | Cost Share Amount: | 381791
Donor: | USDA |  |  |  | Leverage Amount: | N/A
CFDA: | N/A |  |  |  | USAID Only: Geographic Code: | N/A
Subaward Start Date: | 2023-06-27 |  |  |  | Key Personnel: | N/A
Subaward End Date: | 2025-09-30 |  |  |  | Approved Indirect Rate(s) %: | 5% de minimis rate
Subaward Point of Contact: | José Andrés Díaz Merchán / Legal Representative |  |  |  | Prior Approvals Required:
POA Point of Contact: | Sergio Correa Asmar / Partnerships and Investments Director |  |  |  | Treatment of Program Income: | Deduction: Program income will be deducted from award amount and Sub-Awardee may use program income to reimburse itself for allowable costs.
Category | FY | Period of Performance | Date Submitted | Date Approved | Report Title | Link to Final Approved Document | Description of Document/Modification and Source
Award
Subaward Agreement | n/a | 2023-2025 | MM/DD/YYYY | 2023-06-27 | Cover Sheet 467 USDA700 SubA-001 ICFundacion 2023-06-27 to 2025-09-30 | https://partnersnet107.sharepoint.com/:b:/s/Programs/EQZdOksZtINKhzmOZdR0nrEBicT6gPkgOv_5IKC7i0Nubw?e=Wfhv3F
Monitoring, Evaluation & Learning Plan
M&E Plan | FY23 | 2023-2025 | 2023-09-08 | 2023-09-01 | 01-08-23 Producto 1 C4D - Plan de Monitoreo y Evaluación | https://partnersnet107.sharepoint.com/:x:/s/EDHC4D/EeA3AORpHRlFuTEcipcCR6gBRH4ZZjTh_3zqw6M_Kjohfg?e=hJAVc7
Work Plan/Performance Monitoring Plan (PMP)
Work Plan | FY23 | 2023-2025 | 2023-09-08 | MM/DD/YYYY | 23-08-11 Producto 1 C4D Plan de trabajo | https://partnersnet107.sharepoint.com/:w:/s/EDHC4D/EQHa9A5gZRJImSAF7qTBAOMBJGkfSQoI78u9QbuJcjvr1A?e=njmdpn
Special Provisions/Restrictions
Notify POA about modifications to approved policies | FY23 | 2023-2025 |  |  |  | C4D Reunión de inicio_SUB 001 IC Fundación.pdf
Modifications in subaward to be notified 30 days in advance | FY23 | 2023-2025 |  |  |  | C4D Reunión de inicio_SUB 001 IC Fundación.pdf
Branding & Communications approvals | FY23 | 2023-2025 |  |  |  | C4D Reunión de inicio_SUB 001 IC Fundación.pdf
Meeting Notes with POA (Key Decisions) |  |  | Date of Meeting | Date Approved by Email
Topic: Panel Review for IC Fundación | FY23 |  | 2023-04-24 | MM/DD/YYYY
Topic: Subaward Presentation | FY23 |  | 2023-05-25 | MM/DD/YYYY | Sesión 1_ Presentación del Subaward y su clausulado-IC Fundación-20230525_140855-Grabación de la reunión | https://partnersnet107.sharepoint.com/:v:/s/Programs/EQ-CKKKtxdRGk_j1a7u2TxkBKntvtj6quZWzZgKavO__ng?e=1QGWop
Topic: Training on financial reporting & budget-based results | FY23 |  | 2023-05-26 | MM/DD/YYYY | Sesión 2_ Informes financieros - IC Fundación | https://partnersnet107.sharepoint.com/:v:/s/Programs/EaMgV-C-JJlEpQo1iX4Q8HYB8SCdTUhbC2gDTB-S6yrOzQ?e=Au9IUE
Topic: Training on 2CFR200 Regulations (inventories, proc., etc) | FY23 |  | 2023-05-30 | MM/DD/YYYY | Sesión 3_ Regulación 2CFR200-20230530_140644-Grabación de la reunión | https://partnersnet107.sharepoint.com/:v:/s/Programs/EWuYaeFYT71EoVavDBwWZGgBfcAEJ2ht01T6sBUK6rqJpg?e=rCb3ms
Topic: Training on 2CFR200 Regulations (allowable costs) | FY23 |  | 2023-05-31 | MM/DD/YYYY | Sesión 4_ Regulación 2CFR200- IC Fundación | https://partnersnet107.sharepoint.com/:v:/s/Programs/EfHMrCo8EidKh9SLBqSxyJ8BEqvUSOtSF_UDXzgF4Sftbw?e=mJpkeq
Topic: Socialization of templates for advances, expense reporting, budget & invoicing | FY23 |  | 2023-06-28 | MM/DD/YYYY | TRAINING IC-AVANCES-20230628_120458-Grabación de la reunión | https://partnersnet107.sharepoint.com/:v:/s/Programs/EenXATs9FiJLs64Judaj_KsB57BeIwYOTdkzFawCFlfPQg?e=tyYow0
Topic: Follow-Up Committees | FY23 | At least once a month | 2023-07-06 | MM/DD/YYYY | 10. Actas (folder) | https://partnersnet107.sharepoint.com/:f:/s/Programs/ErMv-xGtJr9FtynApIn1VNkB3XbbmlOmMSlQZKRiIzjzgA?e=KYXtY9
Compliance Issues or Other Finding/Concerns |  |  | Date Found |  | Issue/Concern | Link to Document
Four-month trial for advances: Invoice-based (2 months delay in reports) | FY23 |  | 2023-11-01 |  | 2 month delay in reporting while in an advances trial | Pending recording of Follow-Up Committee
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY
Indicate compliance issue/concern/finding | FYXX |  | MM/DD/YYYY