Partners of the Americas

XXX Project Budget 2023

In this section, Partners of the Americas (POA) provides a detailed explanation of the budget line items and the methods used to determine costs associated with implementing the proposed project strategy. POA has established sound financial management and internal control systems ensuring expenditures are allowable and classified in accordance with internationally accepted accounting principles. POA employs a fully automated accounting system and have annual A-133 audits. Our Finance and Administration (F&A) department is staffed with a talented group of professionals with years of experience related to financial administration and reporting. The finance department is made up of a Controller, an Accounts Payable Finance Officer, two Field Finance Officers, a Budget Analyst, a Compliance Director, and a Chief Financial Officer (CFO) with over 30 years of experience in the fields of finance and accounting, auditing, managing the financial reporting aspects reporting aspects of US Government (USG) grants and contracts, and has significant experience overseeing cooperative agreements in particular. The F&A team works closely with project staff at POA’s headquarters (HQ) to monitor spending, ensure costs are allowable, and support project staff in country to implement the project in accordance with USG rules and regulations (particularly 2 CFR 200), local laws, as well as POA’s internal policies. Our accountants also review spending with project directors on a monthly basis and assist with oversight of contracts, end-of-project reporting, and other aspects of project monitoring.

POA uses a robust and cost-effective strategy to determine cost allocation in accordance with USG cost principles, local laws, and internal policies. Our proposed budget for this project was developed by conducting thorough price analyses to identify realistic and fair market values for all projected expenses. Our budget estimates were also calculated based on past experience in implementing effective and cost-efficient USG-funded programs. POA follows US and local labor laws to determine salary and fringe benefit for all employees identified in this proposal. Indirect Costs have been applied in accordance with POA’s cost structure in our NICRA agreement with USAID. In preparing the budget, POA has minimized administrative and support costs for managing the project to the extent possible to maximize the funds available for project activities, while still ensuring overall award compliance and capacity building for implementing partners. Additionally, POA has leveraged its other programs in Colombia to reduce costs and achieve economies of scale.

Below please find the budget narrative for the xxxxxx Program for $xxx and an additional $xxxx in cost share for a total project of $xxx.

Personnel * indicates key personnel

POA will follow U.S. and local labor laws for all employees identified in this proposal. Salaries are based on comparable organizations and projects, information gathered in-country, market analysis, and other data. Proposed salaries are also consistent with those paid to other personnel engaged in similar work within and outside of POA. Level of effort (LOE) budgeted is based on the scope of the program proposed. POA has applied a xxx% yearly increase to account for inflation and for merit increases for all for staff which is consistent with POA policies.

## Headquarters (HQ) Personnel

Program Director: The HQ Program Director with a salary of $120,000 annually or $10,000/month will dedicate 10% of their time to managing the program in Year One through Four. This equals $12,000 in Year One with a 5% increase each additional year. The total will be $46,512 for 43.5 months over the life of the project (LOP). The Program Director is responsible for the backstopping function for the project, directly supervising the Project Director, providing daily support to in-country staff, ensuring compliance with USDA rules and regulations and POA’s policies, and ensuring proper on-time reporting to USDA, among other tasks.

Senior Program Officer: A HQ based Senior Program Officer will assist with program activities for a salary of $65,004 annually or $5,417/month and will dedicate 55% of their time to the program. This equals $35,750 in Year One, with a 3% increase each additional year. The total will be $138,568 for 43.5 months over the LOP. The primary role of the Senior Program Officer will be to develop training materials, provide guidance and continued support to field offices and subrecipients. Additionally, the Senior Program Officer will lead the administrative and financial aspects of the day-to-day backstopping, working closely with the Director and Associate Director.

## Field Personnel

Deputy Director*: The Deputy Director will receive a salary of $50,000 annually or $4,167/month. The Deputy Director will dedicate 100% of their time to assist the Project Director in all operational and management aspects of the project for a total of $45,833 in Year One with a 5% increase each additional year. The Deputy Director will be hired for 11 months in Year One and 12 months Year Two through Year Three and 7.5 months in Year Four. The total will be $189,634 for 42.5 months over the LOP. The Deputy Director will be a technical expert in fertilizer and coordinate the design of any required assessments, analyses, and evaluations of staff, consultants, and potential contractors. This position will oversee the team, prepare reports and annual operating plans, and align project initiatives with in-country priorities and work with headquarters staff on budget compliance and pipeline analyses.

Finance & Administration Director: The Finance & Admin Director will receive a salary of $45,000 annually or $3,750/month and dedicate 15% of their time and implement financial management systems and controls to ensure compliance, transparency, and effective utilization of resources. S/he will manage the FRC budget and oversee disbursements, reporting, and complying with USG regulations and POA-specific policies and procedures. S/he will also conduct internal audits of field office operations and random spot checks as part POA’s fraud prevention and detection system. The total for Year One is $6,188 with a 5% increase each additional year. S/he will be hired for 11 months in Year One, 12 months Year Two and Three and 7.5 months in Year Four. The total will be $25,601 for 42.5 months over the LOP. For cost savings, this position will be split among other POA projects implemented in Colombia.

Communications Officer: The Communication Officer will receive a salary of $25,000 annually or $2,083/month. The Communications Officer will dedicate 15% of their time to implement the program’s communications strategy. The position will support outreach, communications, and partnership development, material design, and event planning for roundtables and the Community of Practice. The total in Year One is $2,813 with a 5% increase each additional year. S/he will be hired for 9 months in Year One,12 months Year Two and Three, and 6 months in Year Four. The total will be $13,055 for 39 months over the LOP. For cost savings, this position will be split among other POA projects implemented in Colombia.

Accountant: The Accountant will receive a salary of $21,000 annually or $1,750/month. The Accountant will dedicate 100% of their time to provide data entry for the financial and administrative systems. The total in Year One is $15,750 in Year One with a 5% increase each additional year. S/he will be hired for 9 months in Year One, 12 months Year Two and Three, and 6 months Year Four. The total will be $73,108 for 39 months over the LOP.

M&E Director: The M&E Director will receive a salary of $45,000 annually or $3,750/month. The M&E Director will dedicate 15% of their time to lead the design and management of MEL system, including the MEL Plan, related reporting, and additional surveys and assessments required to monitor project performance. S/he will provide overall M&E guidance and tracking project progress through indicators, outputs, and outcomes. The total in Year One is $6,188 in Year One with a 5% increase each additional year. S/he will be hired for 11 months Year One, 12 months Year Two and Year Three, and 7.5 months Year Four. The total will be $25,601 for 32.5 months over the LOP. For cost savings, this position will be split among other POA projects implemented in Colombia.

M&E Assistant: The M&E Manager will receive a salary of $20,000 annually or $1,667/month. The M&E Manager will dedicate 100% of their time to support the implementation of the monitoring and evaluation plan. This position will coordinate with POA HQ staff to ensure compliance and integrity of MEL activities and data. The position will support the design, development, and application M&E tools, and integrate good practices and expertise of POA in the field. The total in Year One is $15,000 in Year One with a 5% increase each additional year. S/he will be hired for 9 months in Year One, 12 months Year Two and Year Three, and 7 months Year Four. The total will be $71,556 for 40 months over the LOP.

Total Personnel over the LOP is $XXXX.

# Fringe Benefits

HQ Fringe Benefits

Fringe Benefits –Headquarters: In accordance with POA’s personnel policy, POA has charged a 23.47% fringe rate for POA Headquarters staff. Fringe benefits include insurance, mandatory taxes, pension, and other employee benefits. Please see attached NICRA and Fringe Benefit rate justification. HQ benefits are $65,593 for the LOP.

Field Fringe Benefits

### Fringe Benefits CCN – Colombia (above $3,100 monthly): Fringe benefits for Cooperating Country Nationals (CCN) that receive more than 10 minimum salaries in Colombia which for 2023 is the approximate USD equivalent of $3,100/month, are budgeted at 53.864% of their total salary and are based on POA’s current practice in-country. This includes the required benefits in Colombia:

- 8.33% for severance aid (cesantías) on annual income

- 1% interest on severance aid on annual income

- 5.66% for vacation (15 days of vacation/265 working days a year) on annual income

- 8.33% bonus (prima legal de servicios or 13th & 14th month bonus) on annual income

- 8.5% health insurance (aporte a salud) on annual income

- 12% pension (aporte a pensión) on annual income

- 1.044% workers compensation (Riesgos Laborales - Level II) on annual income

- 4% Family Welfare Fund (caja de compensación) on annual income

- 3% for the Instituto Colombia Bienestar Familiar (ICBF) on annual income

- 2% for the Sistema de Aprendizaje National (SENA) on annual income

Total CCN Colombia Fringe Benefits (above $3,100 monthly) in Year One is $49,027 and a total of $145,799 over LOP.

Total Fringe over the LOP is $XXX.

# Travel

Assumptions:

- Round trip rates are based on coach/economy class airfares and compliance with Fly America Act.

- Travel costs for domestic in-country travel are budgeted based on local prevailing transportation costs in Colombia.

- Per-diem rates and allowances are in accordance with POA policies and are based on an average reduced rate of USG allowable per-diems

- Lodging rates are based on hotel quotes, market research and an average reduced rate of the USG allowable rate.

- Local transportation includes domestic airfare, transport to and from airports and some local transportation.

- All travel costs after Year One include 2% increase for inflation for U.S. based goods/services and a 3% increase for inflation for locally purchased goods/services in Colombia.

HQ Travel

T.1 Project Management Travel to Field

International Airfare to Colombia: POA HQ staff will plan two trips/year for Year One through Year Four, for program implementation, compliance spot checks and audits, and M&E visits. The proposed number of trips are necessary to conduct project management (technical and financial oversight). Based on average market price flight cost of $800/trip. The LOP for international airfare for 8 trips by POA HQ staff is $6,595.

Meals and Incidentals: POA is budgeting meals and incidentals for ten (10) days/per trip for HQ staff for program implementation, compliance spot checks and audits, and M&E visits. There will be two trips/year for Year One through Year Four, for a total of 8 trips, the equivalent of 80 days through LOP. Based on POA policy it estimates an average reduced USG rate of $90/day, for a total of $7,419

Lodging: POA is budgeting lodging for ten (10) nights/per trip for HQ staff for program implementation, compliance spot checks and audits, and M&E visits. There will be two trips/year for Year One through Year Four, for a total of 8 trips, the equivalent of 80 nights through LOP. Based on secure hotel quotes and POA policy it estimates an average reduced USG rate of $120/day, for a total of $9,892

Local Transportation: POA is budgeting for local domestic flights in-country, transport to and from airports and some local transportation at an average daily rate. The estimate is $25/day for HQ staff for program implementation, compliance spot checks and audits, and M&E visits. There will be two trips/year for Year One through Year Four, for a total of 8 trips the equivalent of 80 days through LOP. The total is $2,061.

Other Travel Related Expenses: POA is budgeting for other travel costs including communication, reproduction, bank fees, visa fees, translation, and material costs. Based on POA experience implementing similar programs, it estimated at $50/per trip for program implementation, capacity building and training, compliance spot checks and audits, and M&E visits. There will be two trips/year for Year One through Year Four, for a total of 8 trips. The total is $412.

Field Travel

T.2 Colombia Staff Local Travel for M&E, Training, Mentoring, and Capacity Building

Local Transportation: POA is budgeting for local domestic flights in-country, transport to and from airports, rental car/driver as necessary and other local transportation at an average of $250/trip based upon prior programmatic experience in Colombia. This local travel is needed conduct assessments, provide training and technical assistance. POA is planning 9 trips in Year One, 12 trips in Year Two and Three and 7 trips in Year Four. There are 40 trips through LOP for a total of $10,435.

Meals and Incidentals: POA is budgeting for meals and incidentals at $80/day based on POA policy and an average reduced USG rate. POA estimates that the Field Staff will be traveling to conduct assessments, provide training and technical assistance for three days/trip. There is a total of 40 trips over the LOP. The total for 40 trips of 120 days through LOP for a total of $10,018.

Lodging: POA is budgeting for lodging at $100/night based on secure hotel quotes, POA policy, and an average reduced USG rate. POA estimates that the Field Staff will be traveling to conduct assessments, provide training and technical assistance for three nights/trip. There will be a total of 40 trips over the LOP. The total for 40 trips of 120 nights through LOP for a total of $12,522.

Other Travel Related Expenses: POA is budgeting for other travel cost including communication, reproduction, bank fees, visa fees, translation, and material costs. Based on POA experience implementing similar programs in Colombia, it estimated at $25/trip. There will be 40 through LOP for a total of $1,043.

Total travel over the LOP is $XXX.

# Supplies

HQ Office Supplies

Laptop, Bag, Accessories: POA will purchase two (2) laptops for HQ staff at $1,200/each for a total of $2,400.

Program Specific Office Supplies and Stationery for HQ: Based on prior programmatic experience, POA estimates the cost of office supplies, stationary and printing specific to workshops, events, and the project will be $150/month for 43.5 months for a total of $6,703 through LOP.

The LOP total for HQ Office Supplies is $9,103.

Field Office Supplies

Laptop, Bag, Accessories: POA will purchase 9 laptops for each field staff at $1,200/each for a total of $10,800.

Office Furniture (Includes Desk, Chairs, Table, Shelves, & Filing Cabinet): POA will purchase a set of office furniture which will include desks, chairs, shelves, and filing cabinets. Based on market research, POA estimates that this will cost $5,000. This is a reduced cost, as POA will utilize some furniture it owns for the project.

General Office Supplies, PPE, and Stationery for Field Office: Based on prior programmatic experience, POA estimates the cost of office supplies, personal protective equipment (PPE), stationary and printing specific to field office for the project will be $250/month for 39.5 months. The total is $10,322 through LOP.

The total LOP amount for supplies is $XXX.

# Contractual

Contracts

Subrecipient Agrosavia: POA is budgeting for a subaward to Agrosavia. The award will cover personnel, fringe, travel, equipment, supplies, contractual, and other direct expenses to carry out activities. Agrosavia will lead the USDA FRC fertilizer and greenhouse gas assessments for target value chains. Expert Agrosavia staff will coordinate with major agricultural federations and other research centers to complete the assessments. These assessments will require constant monitoring by highly specialized staff. POA estimates the total subaward of $800,000. Please see detailed budget breakdown on page XX.

Contract for Application (PaLaTierra) Development: POA will hire a contractor to further develop the Colombian agriculture app PaLaTierra. The contractor will build out and expand the following features: Digital Library, Peer-to-Peer Sharing. Product Catalog, and Soil Testing. Additionally the contractor will integrate the Microbiometer into the app. Based on previous app build out for prior projects, POA estimates $40,000.

Contract for Website Development: POA will hire a contractor to develop an online platform to facilitate collaboration and communication between the FRC Community of Practice, project beneficiaries, and other key stakeholders. The platform will include a database of research publications, webinars, case studies, manuals on best practices, extension training materials, other educational resources, and a forum to crowdsource answers to questions from FRC Community of Practice experts. Based on previous website development for prior projects, POA estimates $20,000.

The LOP total for Contractual is $XXXX, plus an additional $XXX in cost share for a total of $XX.

# Other Direct Costs

Assumptions:

- All other direct costs are based off prior program operating costs and experience in the field.

- All office costs after Year One include 2% increase for inflation for U.S. based goods/services and a 3% increase for inflation for locally purchased goods/services in Colombia.

HQ – Other Direct Costs

Dues, Licenses & Subscriptions: Based on prior program experience, POA is budgeting $250/month for tools such as Formstack at $1,000/year, Dropbox at $150/year, and Zoom at $500/year, $480/year for PandaDoc e-signature, plus others such as Expensify subscriptions to manage office expenses, Office 365, Microsoft Teams, and data sharing tools such as DropBox or Google Drive Pro. The estimated total for 43.5 months is $11,171 through LOP. This is a reduce monthly cost for these platforms, as the cost savings will be realized among other POA projects in Colombia.

Meetings/Events - HQ: POA is budgeting for costs associated with HQ meetings and events and transport to the meetings/events. This cost includes expenses related to attending or hosting meetings to share program information, best practices, and lessons learned, and attending other meetings in DC with USDA or other stakeholders. POA is budgeting $1,000/year from Year One through Year Four based on prior program experience. The cost over the LOP is $4,122.

Field Office (FO) – Other Direct Costs

Dues, Licenses & Subscriptions: Based on market quotes, POA is budgeting $325/month for subscriptions to Microsoft Teams, Zoom at $500/year, PandaDoc at $480/year, and Replicon for online timekeeping and expense reporting at $11/user a month. The estimated total for 36 months is $12,145 through LOP.

Courier Fees/Postage Services: Based on prior program experience, POA is budgeting $25/month. The cost covers courier fees and postage services in country for project related activities from Year One through Year Four for 33 months. The LOP total is $859.

Banking & Cash Handling Fees: Based on fees for current POA operations in Colombia, POA is budgeting $150/month for setting up a bank account, bank fees, wire, and transfer costs ($30/wire) and transaction fees in country from Year One through Year Four for 36 months. The LOP total is $5,605.

Procurement/Advertising/Recruitment Fees: Based on prior experience in Colombia, POA is budgeting $500/year for costs related to recruiting/procuring contractors and field staff in country from Year One through Year Four. The LOP total is $2,092.

Meeting and Events: Based on prior program experience, POA is budgeting $150/month for meetings and events for both internal staff meetings as well as external stakeholder events with implementing POA and beneficiaries. This cost is intended to include rental space and materials from Year One through Year Four for 33 months. The LOP total for field office is $5,155.

Office Communications (Ex. Phone, Internet, Email): Based on prior program experience in Colombia, POA is budgeting $350/month for communication expenses. These expenses are intended to cover office phones, internet, email, and cell phones with calling and data plans costs from Year One through Year Four for 33 months. The LOP total for field office is $12,029.

Office Rent & Office Maintenance & Utilities: Based on provider quotes, coworking office space costs in Bogota are estimated $750/month from Year One through Year Four for a secure space in a safe location which includes security, office maintenance, cleaning services, electricity, water, sewage, and trash service. POA is budgeting for office space for 33 months for a total LOP cost of $25,777. POA will utilize a coworking space shared with other projects in Colombia to maximize economies of scale, and result in cost savings for USDA.

Payroll and Accounting Costs: Based on market quotes from Back Startup (payroll provider in Colombia), POA is estimating $100/month from Year One through Year Four for an external firm to process payroll, remit tax payments, process benefits, and register new staff in the necessary social security platforms. The monthly cost is specific to the employees that work on the FRC program. POA is budgeting for these payroll and accounting costs for 36 months for a total LOP cost of $3,737. The payroll services are shared with other projects POA has in Colombia, therefore will maximize economies of scale, and result in cost savings for USDA.

Legal Fees: Based on prior experience, POA is estimating legal fees and services at $1,000/year for Year One through Year Four. The legal fees include costs for legal review of employment contracts, assistance with termination, and other legal guidance that may be needed which is specific for the FRC program. The LOP total cost is $4,184.

Activities

Soil Tests: Based on lab quotes, POA is estimating Microbiometer soil tests at $25/test. These Microbiometer soil tests will be integrated into PaLaTierra’s agriculture smartphone app, which will allow farmers to identify the level of microbial activity in their soil. As cost share, POA will contribute 2,500 soil tests for a total LOP cost of $62,500.

Demonstration Plots (includes land, labor, seeds, tools, & maintenance): Based on prior program experience under USDA’s Cacao for Development (C4D), POA is estimating demonstration plots at $20,000/plot. POA will charge FRC $15,000/plot and POA will contribute $5,000/plot as cost share. POA will set up one demonstration plot in Year One and 9 plots in Year Two. This includes costs for land, labor, seeds, tools, and maintenance. Demonstration plots will be used as sites to train farmers. The USDA LOP total cost is $150,000. As cost share, POA will contribute an LOP total of $65,000.

License and Use of Existing PaLaTierra App: POA has coordinated with the developers of the PaLaTierra App, and they will provide license and use of the existing application to POA, who will further expand and develop the app. The estimated cost for the license for the app and existing infrastructure is $20,000 based off vendor quotes. As cost share POA will cover the cost and acquire the use of PaLaTierra’s agriculture smartphone app for $20,000.

Printing of Educational Materials & Resources: Based on prior program experience, POA is budgeting $1,000/year for Year One and Year Two for printing of extension materials and resources, such as best fertilization practice booklets and manuals to hand out to farmers during trainings. The total LOP cost is $2,000.

Dissemination of Extension Materials: Based on prior program experience, POA will contribute $1,000/year as cost share for Year One through Year Four for target value chain crop federations to disseminate extension materials via campaigns. The total LOP cost is $4,000 which POA will contribute.

Community of Practice Roundtables: Based on similar program costs, POA is budgeting $250/meeting for Year One through Year Four. These roundtables will bring together program stakeholders to guide activities, support assessments, validate technologies, disseminate educational resources, present program results, discuss lessons learned, and make any needed adjustments to program implementation. Costs include venue and equipment rental, snacks and refreshments, and meeting materials. POA anticipates 12 meetings throughout the LOP, for a total LOP cost of $3,000.

Annual Community of Practice Summit: Based on prior program experience, POA is budgeting $40,000 in Year Four to host a week-long Community of Practice Summit. The Summit will bring together program stakeholders to highlight program results, successes, lessons learned, widely adopted innovations; and to build relationships with one another to ensure future productive collaborations and lasting capacity improvement. Costs include travel, venue and equipment rental, snacks and refreshments, and meeting materials. The total LOP cost is $40,000.

Monitoring, Evaluation, and Collection of Reliable Data

M&E Database Set-up and Subscription: The cost for set-up of and subscription to the Salesforce or other similar M&E database is $3,500/year, based upon POA’s license agreement. The cost also covers the hosting, maintenance, and add-on components of the database. POA will utilize this database for Year One through Year Four, for a total of $12,569 throughout LOP.

Data Collection Tools: POA is budgeting for data collection tools to conduct the monitoring and evaluation of activities for the project. Based on prior experience, POA is budgeting $1,500 in Year One, for a total LOP cost of $1,500.

On-going M&E Training Workshops: POA is budgeting for on-going M&E training workshops to build capacity and reinforce M&E requirements and guidelines within their staff and contractors for the accurate collection and reporting of data on project activities based on USDA requirements. POA estimates 4 workshops for Year One through Year Three, and 2 workshops in Year Four. Based on similar program experience, POA is budgeting is $250/workshop, for a LOP total of $3,591.

Monitoring Guidelines Creation, Translation & Printing: POA plans to develop M&E guidelines which covers creation, translation, and printing and publishing costs. Based on prior experience, POA is budgeting $1,000 in Year One, for a total LOP cost of $1,000.

Monitoring Guidelines Staff Training Workshop: Once the Monitoring Guidelines have been developed, POA plans provide a training to all staff to review the guidelines. POA is budgeting a workshop which covers meeting rooms, materials, and catering. Based on prior experience, POA is budgeting $1,000 in Year One, for a total LOP cost of $1,000.

The LOP total for other direct costs is $XX, with $XXX contributed by DONOR and $XXX contributed as cost share by POA.

# Indirect Costs

Indirect Costs have been applied in accordance with POA’s cost structure as indicated in our respective NICRA. These documents can be found as an attachment to the cost proposal. A summary of these charges follows:

| Firm | Year 1 | Year 2 | Year 3 | Year 4 |
| --- | --- | --- | --- | --- |
| POA NICRA (28.28%) | $165,436 | $310,833 | $279,917 | $125,636 |

Total Project Value (budget plus POA cost share): $XXX.