## Proposal Schedule
Sample Proposal Schedule
Days for Proposal Development
No. | Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Receive and Analyze the RFP
2 | Review Opportunity/Capture Plan
3 | Review Requirements
4 | Create Compliance Matrix Chart
5 | Create Proposal Outline
6 | Set Proposal Schedule
7 | Establish Collaboration Site
8 | Validate/Adjust Proposal Win Themes
9 | Hold Team Kickoff Meeting
10 | Collect and Submit Questions
11 | Storyboard/Annotated Mockup Development
12 | Pink Team Review
13 | Compile/Distribute Pink Team Comments
14 | Develop Red Team Draft
15 | Red Team Book Development
16 | Red Team Review
17 | Compile/Distribute Red Team Comments
18 | Red Team Fixes and Revisions; Edit
19 | Gold Team Review
20 | Gold Team Recovery
21 | Final Production
22 | Ship/Send
23 | Proposal Due Date