## Action Plan
POA Policies Update/Creation Timeline
Step 1: Create/Update Policies | [5 empty] | Overall Policy Timeline |  |  | Timeline for Internal Due Dates
Priority | Task (Action Item) | Action Needed | Status | Status | Assigned | Start Date | Due Date | Planned Weeks | Send for ELT Feedback By | Date Sent | Receive ELT Feedback By | Date Received | Incorporated Feedback By | Send for John's Approval By | Date Sent | Receive Final Approval By | Date Approval Received | Notes
HR Policies
High | Employee Handbook | Update Policy | Waiting on John Approval | 100% | Danielle, Natalie, & Paola | 2023-04-01 | 2023-10-31 | 30.4286 | 2023-09-01 | 2023-09-01 | 2023-09-14 | 2023-09-21 | 2023-10-12 | 2023-10-12 | 2023-10-20 | 2023-10-31 |  | Debbie, Carmen, & Juliana provided feedback, most feedback received during ELT presentation
Medium | Expat Fringe Benefit Policy | Update Policy | Waiting on John Approval | 100% | Danielle, Natalie, & Paola | 2023-04-01 | 2023-10-31 | 30.4286 | 2023-09-01 | 2023-09-01 | 2023-09-14 | 2023-09-21 | 2023-10-12 | 2023-10-12 | 2023-10-20 | 2023-10-31 |  | No feedback received
Operational Policies
High | Child Safeguarding, Sexual Abuse, etc. Update with new ADS | Create Policy | Not Started | 0% | Danielle | 2023-12-15 | 2023-10-27 | -7 | 2023-12-20 |  | 2024-01-05 |  | 2024-01-09 | 2024-01-16 |  | 2023-10-27 | 2023-10-27 | No ELT feedback received
High | Travel Policy | Update Policy | Waiting on John Approval | 100% | Danielle | 2023-08-01 | 2023-09-26 | 8 | 2023-09-01 | 2023-09-01 | 2023-09-08 | 2023-09-08 | 2023-09-18 | 2023-09-18 | 2023-09-12 | 2023-09-26 |  | Only Debbie made comments
High | Trafficking in Persons (TIP) Policy | Create Policy | Approved | 100% | Danielle | 2023-04-01 | 2023-10-27 | 29.8571 | 2023-09-11 | 2023-09-11 | 2023-09-18 | N/A | 2023-10-01 | 2023-10-01 | 2023-10-20 | 2023-10-27 | 2023-10-27 | No ELT feedback received
High | Procurement Policy | Update Policy | Waiting on John Approval | 100% | Danielle | 2023-08-28 | 2023-10-27 | 8.5714 | 2023-09-11 | 2023-09-11 | 2023-09-18 | N/A | 2023-10-01 | 2023-10-01 | 2023-10-20 | 2023-10-27 |  | No ELT feedback received
High | Delegation of Authority Policy | Update Policy | Approved | 100% | Danielle | 2023-08-28 | 2023-10-31 | 9.1429 | 2023-09-11 | 2023-09-11 | 2023-09-18 | 2023-10-16 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-31 | 2023-10-30 | No ELT feedback received, so scheduled meeting during October ASM to review
High | VAT Reporting Policy | Create Policy | In progress | 0% | Danielle | 2023-09-05 | 2023-11-21 | 11 | 2023-10-31 |  | 2023-11-07 |  | 2023-11-14 | 2023-11-14 |  | 2023-11-21
High | Vetting Policy (Visual Compliance) | Create Policy | In progress | 0% | Danielle | 2023-09-05 | 2023-11-21 | 11 | 2023-10-31 |  | 2023-11-07 |  | 2023-11-14 | 2023-11-14 |  | 2023-11-21
High | FFATA Policy | Update Policy | Approved | 100% | Danielle | 2023-04-01 | 2023-09-26 | 25.4286 | 2023-09-01 | 2023-09-01 | 2023-09-08 | 2023-09-08 | 2023-09-18 | 2023-09-18 | 2023-09-12 | 2023-09-26 | 2023-10-15 | Only Debbie made comments
High | Vehicle Policy | Update Policy | Waiting on John Approval | 100% | Danielle | 2023-04-01 | 2023-10-31 | 30.4286 | 2023-09-11 | 2023-09-11 | 2023-09-18 | 2023-09-18 | 2023-10-12 | 2023-10-12 | 2023-10-20 | 2023-10-31 |  | Only Debbie made comments
High | Global Security Policy | Create Policy | Waiting on John Approval | 100% | Danielle & Natalie | 2023-04-01 | 2023-12-19 | 37.4286 | 2023-11-17 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 2023-12-07 | 2023-12-12 | 2023-12-19 |  | No comments received from ELT
Medium | Country Specific Plans | Create Policy | In progress | 10% | Program staff, with Danielle's Review | 2023-06-01 | 2024-02-14 | 36.8571 | 2023-12-29 |  | 2024-01-12 |  | 2024-01-31 | 2024-01-31 |  | 2024-02-14
IT Policies
Medium | AI Usage Policy | Create Policy | Approved | 100% | Danielle & Abe | 2023-06-20 | 2023-10-27 | 18.4286 | 2023-07-10 | 2023-07-10 | 2023-07-17 | 2023-07-17 | 2023-07-28 | 2023-10-20 | 2023-10-20 | 2023-10-27 | 2023-10-27
Medium | Policy to address Section 889 of FAR | Create Policy | Waiting on John Approval | 100% | Danielle | 2023-10-15 | 2023-12-19 | 9.2857 | 2023-11-15 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 2023-12-07 | 2023-12-12 | 2023-12-19 |  | No feedback received
Medium | Policy to address Section 508 of FAR | Create Policy | Waiting on John Approval | 100% | Danielle | 2023-10-15 | 2023-12-19 | 9.2857 | 2023-11-15 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 2023-12-07 | 2023-12-12 | 2023-12-19 |  | No feedback received
Medium | General IT Security Policy | Create Policy | In progress | 0% | Danielle | 2023-11-01 | 2023-12-19 | 6.8571 | 2023-11-17 |  | 2023-11-30 |  | 2023-12-08 | 2023-12-08 |  | 2023-12-19
Medium | IT Access control and network security policy | Create Policy | In progress | 0% | Danielle | 2023-11-01 | 2023-12-19 | 6.8571 | 2023-11-17 |  | 2023-11-30 |  | 2023-12-08 | 2023-12-08 |  | 2023-12-19
Medium | Password Policy | Create Policy | Waiting on John Approval | 100% | Danielle | 2023-11-01 | 2023-12-19 | 6.8571 | 2023-11-17 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-08 | 2023-12-08 | 2023-12-12 | 2023-12-19 |  | Only Debbie made comments, no other ELT member
Medium | IT acceptable use policy | Create Policy | Waiting on John Approval | 100% | Danielle | 2023-11-01 | 2023-12-19 | 6.8571 | 2023-11-17 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-08 | 2023-12-08 | 2023-12-12 | 2023-12-19 |  | No comments from ELT
Finance Policies
High | Record Retention Policy | Update Policy | Not Started | 0% | Danielle | 2023-09-05 | 2023-11-15 | 10.1429 | 2023-10-25 |  | 2023-11-01 |  | 2023-11-08 | 2023-11-08 |  | 2023-11-15
High | SharePoint File Structure Policy | Update Policy | Approved | 100% | Danielle | 2023-06-01 | 2023-10-01 | 17.4286 | 2023-06-26 | 2023-06-26 | 2023-06-30 | 2023-06-30 | 2023-09-15 | 2023-09-15 | N/A | 2023-10-01 | 2023-10-01
High | Inventory Management Policy | Update Policy | Not Started | 0% | Danielle | 2023-09-05 | 2023-11-15 | 10.1429 | 2023-10-25 |  | 2023-11-01 |  | 2023-11-08 | 2023-11-08 |  | 2023-11-15
High | Credit Card Management Policy | Update Policy | In progress | 85% | Danielle, Debbie, & Sara | 2023-09-05 | 2023-11-15 | 10.1429 | 2023-10-25 |  | 2023-11-01 |  | 2023-11-08 | 2023-11-08 |  | 2023-11-15
Medium | Request for Funding Policy | Create Policy | Not Started | 0% | Danielle, Debbie, & Sara | 2023-09-11 | 2023-12-04 | 12 | 2023-11-15 |  | 2023-11-22 |  | 2023-11-27 | 2023-11-27 |  | 2023-12-04
Medium | Revenue Recognition Policy | Update Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-11-28 | 22 | 2023-11-06 |  | 2023-11-13 |  | 2023-11-17 | 2023-11-17 |  | 2023-11-28
High | Financial Reporting Policy | Create Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-04 | 22.8571 | 2023-11-15 |  | 2023-11-22 |  | 2023-11-27 | 2023-11-27 |  | 2023-12-04
Medium | Foreign Currency Policy | Create Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-31 | 26.7143 | 2023-11-30 |  | 2023-12-08 |  | 2023-12-15 | 2023-12-15 |  | 2023-12-31
High | Cost Allocation Policy | Create Policy | Waiting on John Approval | 100% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-19 | 25 | 2023-11-17 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 2023-12-07 | 2023-12-12 | 2023-12-19 |  | No comments received from ELT
Medium | Cost Accounting Standards Policy | Create Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-31 | 26.7143 | 2023-12-08 |  | 2023-12-15 |  | 2023-12-15 | 2023-12-15 |  | 2023-12-31
High | Allowable Cost Policy | Create Policy | Waiting on John Approval | 100% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-19 | 25 | 2023-11-17 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 2023-12-07 | 2023-12-12 | 2023-12-19 |  | No comments received from ELT
Medium | Financial Systems Management Policy | Create Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-31 | 26.7143 | 2023-12-08 |  | 2023-12-15 |  | 2023-12-15 | 2023-12-15 |  | 2023-12-31
Medium | Cost Monitoring and Control Policy (Includes Reclass Policy) | Create Policy | Waiting on John Approval | 100% | Debbie & Sara w/review Danielle | 2023-06-27 | 2024-01-10 | 28.1429 | 2024-12-15 | 2024-12-14 | 2024-12-20 | 2024-12-20 | 2023-12-31 | 2024-01-02 | 2024-01-02 | 2024-01-10 |  | No ELT feedback received
Low | Global Finance Manual | Create Policy | Not Started | 0% | Debbie & Sara w/review Danielle | 2023-10-01 | 2024-01-26 | 16.7143 | 2024-01-02 |  | 2024-01-12 |  | 2022-01-19 | 2022-01-19 |  | 2024-01-26
Low | Finance Manual | Update Policy | Not Started | 0% | Debbie & Sara w/review Danielle | 2023-10-01 | 2024-01-26 | 16.7143 | 2024-01-02 |  | 2024-01-12 |  | 2022-01-19 | 2022-01-19 |  | 2024-01-26
Program & Sub Management Policies
Medium | Compliance Matrix in Excel | Create Policy | Approved | 100% | Danielle | 2023-06-01 | 2023-10-01 | 17.4286 | 2023-06-23 | 2023-06-23 | 2023-06-30 | 2023-07-06 | 2023-09-15 | 2023-09-15 | N/A | 2023-10-01 | 2023-10-01
Medium | Risk Assessments & Contractor/Sub-recipient Monitoring | Update Policy | Not Started | 0% | Danielle | 2023-09-21 | 2023-12-04 | 10.5714 | 2023-11-13 |  | 2023-11-20 |  | 2023-11-27 | 2023-11-27 |  | 2023-12-04
Medium | Program Start-Up Policy/Procedure (Use Checklist) | Create Policy | In progress | 10% | Danielle, Michael & Operation Officer | 2023-11-01 | 2023-12-04 | 4.7143 | 2023-11-13 |  | 2023-11-20 |  | 2023-11-27 | 2023-11-27 |  | 2023-12-04
Medium | Program Implementation/Management (Use Compliance Matrix) | Create Policy | Not Started | 0% | Danielle, Michael & Operation Officer | 2023-10-15 | 2023-12-15 | 8.7143 | 2023-11-22 |  | 2023-12-01 |  | 2023-12-08 | 2023-12-08 |  | 2023-12-15
Medium | Program Closeout Policy/Procedure (Use Checklist) | Create Policy | Not Started | 0% | Danielle, Michael & Operation Officer | 2023-12-01 | 2023-12-29 | 4 | 2023-12-08 |  | 2023-12-15 |  | 2023-12-18 | 2023-12-18 |  | 2023-12-29
Medium | Subaward Manual | Create Policy | Not Started | 0% | Danielle, Michael & Operation Officer | 2023-12-01 | 2024-02-01 | 8.8571 | 2024-01-08 |  | 2024-01-18 |  | 2024-01-25 | 2024-01-25 |  | 2024-02-01
Low | Subcontract Manual | Create Policy | Not Started | 0% | Danielle, Michael & Operation Officer | 2024-03-01 | 2024-05-31 | 13 | 2024-05-10 |  | 2024-05-17 |  | 2024-05-24 | 2024-05-24 |  | 2024-05-31
Step 2: Create Cheat Sheets | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) |  | Phase | Status | Assigned | Start Date | Due Date | Planned Hours | Department |  |  |  | Materials Required | Cost |  | Notes |  | Notes
Step 3: Create Training Video | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) |  | Phase | Status | Assigned | Start Date | Due Date | Planned Hours | Department |  |  |  | Materials Required | Cost |  | Notes |  | Notes
Formulas:
Due Date = [Receive Final Approval By]
Planned Weeks = (DAYS([Due Date],[Overall Policy Timeline])/7)
Send for John's Approval By = [Incorporated Feedback By]
Note on O23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: sent again in October
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: which covers: a. Protecting information assets from unauthorized access, use, disclosure, disruption, modification, or destruction b. Data backup (frequency and where is it stored) c. Outlines disaster recovery plans and procedures to ensure business continuity d. Encryption e. Accessibility (Information and Communication Technology Accessibility (April 2018) (Deviation No. M-OAA-DEV-AIDAR-22-06c) (also known as Section 508 compliance), f. Protection of information (Media and Information Handling and Protection (April 2018) (Deviation No. M-OAA-DEV-AIDAR-22-06c), g. Handling of sensitive information (Privacy and Security Information Technology Systems Incident Reporting (April 2018) (Deviation No. M-OAA-DEV-AIDAR-22-06c), and h. Cloud computing (Cloud Computing (April 2018) (Deviation No. M-OAA-DEV-AIDAR-22- 06c)
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: a. Establishes measures to protect the organization's network infrastructure from unauthorized access, attacks, and intrusions. b. Outlines firewall rules, intrusion detection/prevention systems, and network segmentation practices. a. Establishes measures to protect the organization's network infrastructure from unauthorized access, attacks, and intrusions. b. Outlines firewall rules, intrusion detection/prevention systems, and network segmentation practices.
Note on B29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: a. Sets guidelines for the appropriate use of IT resources, including computers, networks, and software b. Addresses the prohibition of activities such as unauthorized access, software piracy

## DM Summary
POA Policies Update/Creation Timeline
Step 1: Create/Update Policies | [5 empty] | Overall Policy Timeline |  |  | Timeline for Internal Due Dates
Priority | Task (Action Item) | Action Needed | Status | Status | Assigned | Start Date | Due Date | Planned Weeks | Send for ELT Feedback By | Date Sent | Receive ELT Feedback By | Date Received | Incorporated Feedback By | Send for John's Approval By | Date Sent | Receive Final Approval By | Date Approval Received | Notes
HR Policies
High | Employee Handbook | Update Policy | Waiting on John Approval | 100% | Danielle, Natalie, & Paola | 2023-04-01 | 2023-10-31 | 30.4286 | 2023-09-01 | 2023-09-01 | 2023-09-14 | 2023-09-21 | 2023-10-12 | 2023-10-12 | 2023-10-20 | 2023-10-31 |  | Debbie, Carmen, & Juliana provided feedback, most feedback received during ELT presentation
Medium | Expat Fringe Benefit Policy | Update Policy | Waiting on John Approval | 100% | Danielle, Natalie, & Paola | 2023-04-01 | 2023-10-31 | 30.4286 | 2023-09-01 | 2023-09-01 | 2023-09-14 | 2023-09-21 | 2023-10-12 | 2023-10-12 | 2023-10-20 | 2023-10-31 |  | No feedback received
Operational Policies
High | Travel Policy | Update Policy | Waiting on John Approval | 100% | Danielle | 2023-08-01 | 2023-09-26 | 8 | 2023-09-01 | 2023-09-01 | 2023-09-08 | 2023-09-08 | 2023-09-18 | 2023-09-18 | 2023-09-12 | 2023-09-26 |  | Only Debbie made comments
High | Trafficking in Persons (TIP) Policy | Create Policy | Approved | 100% | Danielle | 2023-04-01 | 2023-10-27 | 29.8571 | 2023-09-11 | 2023-09-11 | 2023-09-18 | N/A | 2023-10-01 | 2023-10-01 | 2023-10-20 | 2023-10-27 | 2023-10-27 | No ELT feedback received
High | Procurement Policy | Update Policy | Waiting on John Approval | 100% | Danielle | 2023-08-28 | 2023-10-27 | 8.5714 | 2023-09-11 | 2023-09-11 | 2023-09-18 | N/A | 2023-10-01 | 2023-10-01 | 2023-10-20 | 2023-10-27 |  | No ELT feedback received
High | Delegation of Authority Policy | Update Policy | Approved | 100% | Danielle | 2023-08-28 | 2023-10-31 | 9.1429 | 2023-09-11 | 2023-09-11 | 2023-09-18 | 2023-10-16 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-31 | 2023-10-30 | No ELT feedback received, so scheduled meeting during October ASM to review
High | VAT Reporting Policy | Create Policy | In progress | 0% | Danielle | 2023-09-05 | 2023-11-21 | 11 | 2023-10-31 |  | 2023-11-07 |  | 2023-11-14 | 2023-11-14 |  | 2023-11-21
High | Vetting Policy (Visual Compliance) | Create Policy | In progress | 0% | Danielle | 2023-09-05 | 2023-11-21 | 11 | 2023-10-31 |  | 2023-11-07 |  | 2023-11-14 | 2023-11-14 |  | 2023-11-21
High | FFATA Policy | Update Policy | Approved | 100% | Danielle | 2023-04-01 | 2023-09-26 | 25.4286 | 2023-09-01 | 2023-09-01 | 2023-09-08 | 2023-09-08 | 2023-09-18 | 2023-09-18 | 2023-09-12 | 2023-09-26 | 2023-10-15 | Only Debbie made comments
High | Vehicle Policy | Update Policy | Waiting on John Approval | 100% | Danielle | 2023-04-01 | 2023-10-31 | 30.4286 | 2023-09-11 | 2023-09-11 | 2023-09-18 | 2023-09-18 | 2023-10-12 | 2023-10-12 | 2023-10-20 | 2023-10-31 |  | Only Debbie made comments
High | Global Security Policy | Create Policy | Waiting on John Approval | 100% | Danielle & Natalie | 2023-04-01 | 2023-12-19 | 37.4286 | 2023-11-17 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 2023-12-07 | 2023-12-12 | 2023-12-19 |  | No comments received from ELT
Medium | Country Specific Plans | Create Policy | In progress | 10% | Program staff, with Danielle's Review | 2023-06-01 | 2024-02-14 | 36.8571 | 2023-12-29 |  | 2024-01-12 |  | 2024-01-31 | 2024-01-31 |  | 2024-02-14
IT Policies
Medium | AI Usage Policy | Create Policy | Approved | 100% | Danielle & Abe | 2023-06-20 | 2023-10-27 | 18.4286 | 2023-07-10 | 2023-07-10 | 2023-07-17 | 2023-07-17 | 2023-07-28 | 2023-10-20 | 2023-10-20 | 2023-10-27 | 2023-10-27
Medium | Policy to address Section 889 of FAR | Create Policy | Waiting on John Approval | 100% | Danielle | 2023-10-15 | 2023-12-19 | 9.2857 | 2023-11-15 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 2023-12-07 | 2023-12-12 | 2023-12-19 |  | No feedback received
Medium | Policy to address Section 508 of FAR | Create Policy | Waiting on John Approval | 100% | Danielle | 2023-10-15 | 2023-12-19 | 9.2857 | 2023-11-15 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 2023-12-07 | 2023-12-12 | 2023-12-19 |  | No feedback received
Medium | General IT Security Policy | Create Policy | In progress | 0% | Danielle | 2023-11-01 | 2023-12-19 | 6.8571 | 2023-11-17 |  | 2023-11-30 |  | 2023-12-08 | 2023-12-08 |  | 2023-12-19
Medium | IT Access control and network security policy | Create Policy | In progress | 0% | Danielle | 2023-11-01 | 2023-12-19 | 6.8571 | 2023-11-17 |  | 2023-11-30 |  | 2023-12-08 | 2023-12-08 |  | 2023-12-19
Medium | Password Policy | Create Policy | Waiting on John Approval | 100% | Danielle | 2023-11-01 | 2023-12-19 | 6.8571 | 2023-11-17 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-08 | 2023-12-08 | 2023-12-12 | 2023-12-19 |  | Only Debbie made comments, no other ELT member
Medium | IT acceptable use policy | Create Policy | Waiting on John Approval | 100% | Danielle | 2023-11-01 | 2023-12-19 | 6.8571 | 2023-11-17 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-08 | 2023-12-08 | 2023-12-12 | 2023-12-19 |  | No comments from ELT
Finance Policies
High | Record Retention Policy | Update Policy | Not Started | 0% | Danielle | 2023-09-05 | 2023-11-15 | 10.1429 | 2023-10-25 |  | 2023-11-01 |  | 2023-11-08 | 2023-11-08 |  | 2023-11-15
High | SharePoint File Structure Policy | Update Policy | Approved | 100% | Danielle | 2023-06-01 | 2023-10-01 | 17.4286 | 2023-06-26 | 2023-06-26 | 2023-06-30 | 2023-06-30 | 2023-09-15 | 2023-09-15 | N/A | 2023-10-01 | 2023-10-01
High | Inventory Management Policy | Update Policy | Not Started | 0% | Danielle | 2023-09-05 | 2023-11-15 | 10.1429 | 2023-10-25 |  | 2023-11-01 |  | 2023-11-08 | 2023-11-08 |  | 2023-11-15
High | Credit Card Management Policy | Update Policy | In progress | 85% | Danielle, Debbie, & Sara | 2023-09-05 | 2023-11-15 | 10.1429 | 2023-10-25 |  | 2023-11-01 |  | 2023-11-08 | 2023-11-08 |  | 2023-11-15
Medium | Request for Funding Policy | Create Policy | Not Started | 0% | Danielle, Debbie, & Sara | 2023-09-11 | 2023-12-04 | 12 | 2023-11-15 |  | 2023-11-22 |  | 2023-11-27 | 2023-11-27 |  | 2023-12-04
Medium | Revenue Recognition Policy | Update Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-11-28 | 22 | 2023-11-06 |  | 2023-11-13 |  | 2023-11-17 | 2023-11-17 |  | 2023-11-28
High | Financial Reporting Policy | Create Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-04 | 22.8571 | 2023-11-15 |  | 2023-11-22 |  | 2023-11-27 | 2023-11-27 |  | 2023-12-04
Medium | Foreign Currency Policy | Create Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-31 | 26.7143 | 2023-11-30 |  | 2023-12-08 |  | 2023-12-15 | 2023-12-15 |  | 2023-12-31
High | Cost Allocation Policy | Create Policy | Waiting on John Approval | 100% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-19 | 25 | 2023-11-17 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 2023-12-07 | 2023-12-12 | 2023-12-19 |  | No comments received from ELT
Medium | Cost Accounting Standards Policy | Create Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-31 | 26.7143 | 2023-12-08 |  | 2023-12-15 |  | 2023-12-15 | 2023-12-15 |  | 2023-12-31
High | Allowable Cost Policy | Create Policy | Waiting on John Approval | 100% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-19 | 25 | 2023-11-17 | 2023-11-17 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 2023-12-07 | 2023-12-12 | 2023-12-19 |  | No comments received from ELT
Medium | Financial Systems Management Policy | Create Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-31 | 26.7143 | 2023-12-08 |  | 2023-12-15 |  | 2023-12-15 | 2023-12-15 |  | 2023-12-31
Medium | Cost Monitoring and Control Policy (Includes Reclass Policy) | Create Policy | In progress | 10% | Debbie & Sara w/review Danielle | 2023-06-27 | 2023-12-31 | 26.7143 | 2023-11-30 |  | 2023-12-08 |  | 2023-12-15 | 2023-12-15 |  | 2023-12-31
Low | Global Finance Manual | Create Policy | Not Started | 0% | Debbie & Sara w/review Danielle | 2023-10-01 | 2024-01-26 | 16.7143 | 2024-01-02 |  | 2024-01-12 |  | 2022-01-19 | 2022-01-19 |  | 2024-01-26
Low | Finance Manual | Update Policy | Not Started | 0% | Debbie & Sara w/review Danielle | 2023-10-01 | 2024-01-26 | 16.7143 | 2024-01-02 |  | 2024-01-12 |  | 2022-01-19 | 2022-01-19 |  | 2024-01-26
Program & Sub Management Policies
Medium | Compliance Matrix in Excel | Create Policy | Approved | 100% | Danielle | 2023-06-01 | 2023-10-01 | 17.4286 | 2023-06-23 | 2023-06-23 | 2023-06-30 | 2023-07-06 | 2023-09-15 | 2023-09-15 | N/A | 2023-10-01 | 2023-10-01
Medium | Risk Assessments & Contractor/Sub-recipient Monitoring | Update Policy | Not Started | 0% | Danielle | 2023-09-21 | 2023-12-04 | 10.5714 | 2023-11-13 |  | 2023-11-20 |  | 2023-11-27 | 2023-11-27 |  | 2023-12-04
Medium | Program Start-Up Policy/Procedure (Use Checklist) | Create Policy | In progress | 10% | Danielle, Michael & Operation Officer | 2023-11-01 | 2023-12-04 | 4.7143 | 2023-11-13 |  | 2023-11-20 |  | 2023-11-27 | 2023-11-27 |  | 2023-12-04
Medium | Program Implementation/Management (Use Compliance Matrix) | Create Policy | Not Started | 0% | Danielle, Michael & Operation Officer | 2023-10-15 | 2023-12-15 | 8.7143 | 2023-11-22 |  | 2023-12-01 |  | 2023-12-08 | 2023-12-08 |  | 2023-12-15
Medium | Program Closeout Policy/Procedure (Use Checklist) | Create Policy | Not Started | 0% | Danielle, Michael & Operation Officer | 2023-12-01 | 2023-12-29 | 4 | 2023-12-08 |  | 2023-12-15 |  | 2023-12-18 | 2023-12-18 |  | 2023-12-29
Medium | Subaward Manual | Create Policy | Not Started | 0% | Danielle, Michael & Operation Officer | 2023-12-01 | 2024-02-01 | 8.8571 | 2024-01-08 |  | 2024-01-18 |  | 2024-01-25 | 2024-01-25 |  | 2024-02-01
Low | Subcontract Manual | Create Policy | Not Started | 0% | Danielle, Michael & Operation Officer | 2024-03-01 | 2024-05-31 | 13 | 2024-05-10 |  | 2024-05-17 |  | 2024-05-24 | 2024-05-24 |  | 2024-05-31
Step 2: Create Cheat Sheets | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) |  | Phase | Status | Assigned | Start Date | Due Date | Planned Hours | Department |  |  |  | Materials Required | Cost |  | Notes |  | Notes
Step 3: Create Training Video | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) |  | Phase | Status | Assigned | Start Date | Due Date | Planned Hours | Department |  |  |  | Materials Required | Cost |  | Notes |  | Notes
Formulas:
Due Date = [Receive Final Approval By]
Planned Weeks = (DAYS([Due Date],[Overall Policy Timeline])/7)
Send for John's Approval By = [Incorporated Feedback By]
Note on O22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: sent again in October
Note on B25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: which covers: a. Protecting information assets from unauthorized access, use, disclosure, disruption, modification, or destruction b. Data backup (frequency and where is it stored) c. Outlines disaster recovery plans and procedures to ensure business continuity d. Encryption e. Accessibility (Information and Communication Technology Accessibility (April 2018) (Deviation No. M-OAA-DEV-AIDAR-22-06c) (also known as Section 508 compliance), f. Protection of information (Media and Information Handling and Protection (April 2018) (Deviation No. M-OAA-DEV-AIDAR-22-06c), g. Handling of sensitive information (Privacy and Security Information Technology Systems Incident Reporting (April 2018) (Deviation No. M-OAA-DEV-AIDAR-22-06c), and h. Cloud computing (Cloud Computing (April 2018) (Deviation No. M-OAA-DEV-AIDAR-22- 06c)
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: a. Establishes measures to protect the organization's network infrastructure from unauthorized access, attacks, and intrusions. b. Outlines firewall rules, intrusion detection/prevention systems, and network segmentation practices. a. Establishes measures to protect the organization's network infrastructure from unauthorized access, attacks, and intrusions. b. Outlines firewall rules, intrusion detection/prevention systems, and network segmentation practices.
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: a. Sets guidelines for the appropriate use of IT resources, including computers, networks, and software b. Addresses the prohibition of activities such as unauthorized access, software piracy

## List (hidden)
Status | Action Needed
Not Started | Update Policy
In progress | Create Policy
Drafted
ELT Review
Incorporating ELT Feedback
Waiting on John Approval
Approved