## APP
ANNUAL PROCUREMENT PLAN
Prepared by:
Funder/Grant or Dept.:
Contract / Agreement No. (if Applicable):
Period Covered: |  | January 1, 2025 to June 30, 2025
No. | INTERVENCIÓN | Item description (What to procure) | Deadline to submit Purchase Requisition Form | Day and month when goods/services must be received | Quantity (How many) | Expected delivery location/procurement region | Responsible Staff Member for the Purchase Requisition Form | Estimated Cost COP | Procurement method (select from drop down) | Type of Procurement (select from drop down) | Donor prior approval and/or wavier required? (select from drop down)
1 | 2 | Cartilla diálogo social 2 (Tomo 1 y 2) - diseño e impresión | 2025-01-10 | 2025-01-24 | 2400 | Bogota | Carolina Hernández | 12000000 | Small purchase | Technical - Workplan | Neither needed
2 | 1 | Cápsulas (6) diálogo social Ministerio del Trabajo | 2025-01-10 | 2025-03-07 | 5 | Bogota | Carolina Hernández | 40000000 | Small purchase | Technical - Workplan | Neither needed
3 | 2 | Cartilla interactiva Diálogo Social | 2025-01-30 | 2025-03-28 | 1 | Bogota | Carolina Hernández | 20000000 | Small purchase | Technical - Workplan | Neither needed
4 |  | Contratación encuestas actores clave para indicador 9a | 2025-02-15 | 2025-04-30 | 1 | Bogotá | Catalina Useche | 5000000 | Micro-purchase | Technical - Workplan | Neither needed
5 | 1 | Campaña ugpp cuñas | 2024-12-13 | 2025-01-03 | 6 | Bogotá | Carolina Hernández | 14400000 | Small purchase | Technical - Workplan | Neither needed
6 | 1 | Campaña ugpp folletos digitales | 2024-12-20 | 2025-01-03 | 2 | Bogotá | Carolina Hernández | 3000000 | Micro-purchase | Technical - Workplan | Neither needed
10 | 1 | Preguntas frecuentes | 2025-01-17 | 2025-02-21 | 1 | Bogotá | Carolina Hernández | 8000000 | Micro-purchase | Technical - Workplan | Neither needed
11 |  | Video conclusiones Evaluación integral | [7 empty] | Technical - Workplan | Neither needed
12 |  | Testimoniales graduandos | [7 empty] | Technical - Workplan | Neither needed
13 |  | Slide Deck proyecto | [7 empty] | Technical - Workplan | Neither needed
14 |  | Quote cards | [7 empty] | Technical - Workplan | Neither needed
15 |  | Historia de vida trabajador 1 | [7 empty] | Technical - Workplan | Neither needed
16 |  | Historia de vida trabajador 2 | [7 empty] | Technical - Workplan | Neither needed
17 |  | Historia de vida trabajador 3 | [7 empty] | Technical - Workplan | Neither needed
18 |  | Historia de vida Empresa 1 | [7 empty] | Technical - Workplan | Neither needed
19 |  | Historia de vida Empresa 2 | [7 empty] | Technical - Workplan | Neither needed
20 | [9 empty] | Technical - Workplan | Neither needed
21 | [9 empty] | Technical - Workplan | Neither needed
22 | [9 empty] | Technical - Workplan | Neither needed
23 | [9 empty] | Technical - Workplan | Neither needed
24 | [9 empty] | Technical - Workplan | Neither needed
25 | [9 empty] | Technical - Workplan | Neither needed
26 | [9 empty] | Technical - Workplan | Neither needed
27 | [9 empty] | Technical - Workplan | Neither needed
28 | [9 empty] | Technical - Workplan | Neither needed
29 | [9 empty] | Technical - Workplan | Neither needed
30 | [9 empty] | Technical - Workplan | Neither needed
11 | M&E | Video conclusiones Evaluación integral | 2025-01-17 | 2025-02-20 | 1 | Bogotá | Carolina Hernández | 4000000 | Micro-purchase | Technical - Workplan | Neither needed
12 | M&E | Testimoniales graduandos | 2025-01-17 | 2025-02-20 | 4 | Bogotá | Carolina Hernández | 2500000 | Micro-purchase | Technical - Workplan | Neither needed
13 | M&E | Historia de vida trabajador 1 | 2024-12-20 | 2025-01-03 | 1 | Bogotá | Carolina Hernández | 1500000 | Micro-purchase | Technical - Workplan | Neither needed
14 | M&E | Historia de vida trabajador 2 | 2025-01-08 | 2025-01-22 | 1 | Bogotá | Carolina Hernández | 1500000 | Micro-purchase | Technical - Workplan | Neither needed
15 | M&E | Historia de vida trabajador 3 | 2025-01-15 | 2025-01-29 | 1 | Bogotá | Carolina Hernández | 1500000 | Micro-purchase | Technical - Workplan | Neither needed
16 | M&E | Historia de vida Empresa 1 | 2025-02-06 | 2025-02-20 | 1 | Bogotá | Carolina Hernández | 1500000 | Micro-purchase | Technical - Workplan | Neither needed
17 | M&E | Historia de vida Empresa 2 | 2025-02-06 | 2025-02-20 | 1 | Bogotá | Carolina Hernández | 1500000 | Micro-purchase | Technical - Workplan | Neither needed
18 |  | Facilitadores Escuela de Diálogo Social | 2025-02-14 | 2025-03-28 | 4 | Buenaventura, Barranquilla, Cartagena, Santa Marta | Ana María Hernández | 14000000 | Small purchase | Technical - Workplan | Neither needed
19 | M&E | Video de cierre | 2025-04-02 | 2025-05-15 | 1 | Bogotá | Carolina Hernández | 5000000 | Micro-purchase | Technical - Workplan | Neither needed
20 |  | Contrato con ESTARTER | 2025-01-06 | 2025-06-15 | 1 | Bogotá | Catherine Ramos | 20000000 | Small purchase | Operational | Neither needed
22 |  | Facilitador taller virtual Liderazgo para mujeres | 2025-02-20 | 2025-02-28 | 1 | Bogotá | Libia Alba | 1500000 | Micro-purchase | Technical - Workplan | Neither needed
23 | M&E | Ampliación contrato Enrique Borda | 2025-03-13 | Monto agotable o hasta la finalización del proyecto | 1 | Bogotá | Libia Alba | 30380000 | Small purchase | Technical - Workplan | Neither needed
24 |  | Contrato asesor en derecho laboral | 2025-01-30 | 2025-04-30 | 1 | Bogotá |  | 6450000 | Micro-purchase | Technical - Workplan | Neither needed
25 | M&E | Webinar rendición de cuentas cierre proyecto | 2025-04-15 | 2025-04-30 | 1 | Bogotá | Catalina Useche | 5000000 | Micro-purchase | Technical - Workplan | Neither needed
| M&E | Webinar midterm (USDOL) |  |  |  |  | Carolina Hernández | 5000000 | Micro-purchase | Technical - Workplan | Neither needed
26 | 1 | Diseño de cartilla interactiva para empleadores sobre aportes al sistema de la seguridad social | 2025-01-30 | 2025-02-28 | 1 | Bogotá | Libia Alba y Carolina Hernandez | 20000000 | Small purchase | Technical - Workplan | Neither needed
27 | 1 | Emisión de cuñas UGPP | 2025-01-30 | 2025-02-28 | 6 | Bogotá | Carolina Hernández | 30000000 | Small purchase | Technical - Workplan | Neither needed
|  | Facilitadores OCA - gobernanza | 2025-02-14 | 2025-03-14 | 1 |  | Pastora Gonzalez | 4000000 | Micro-purchase | Technical - Workplan | Neither needed
|  | Facilitadores OCA - género | 2025-02-14 | 2025-03-14 | 1 |  | Pastora Gonzalez | 4000000 | Micro-purchase | Technical - Workplan | Neither needed
28 |  | Facilitadores OCA - comunicaciones | 2025-02-14 | 2025-03-14 | 1 |  | Pastora Gonzalez | 4000000 | Micro-purchase | Technical - Workplan | Neither needed
29 |  | Facilitadores OCA - proyectos | 2025-03-14 | 2025-04-14 | 1 |  | Pastora Gonzalez | 4000000 | Micro-purchase | Technical - Workplan | Neither needed
30 |  | Consultor cierre OCA - Raquel patron | 2025-02-14 | 2025-04-30 | 1 |  | Pastora Gonzalez | 6000000 | Micro-purchase | Technical - Workplan | Neither needed
Total: | [7 empty] | 275730000
Reviewed and Approved by: |  |  |  |  | Date:
Signature:

## Lists
Micro-purchase
Small purchase
Competitive proposal
Non-competitive (sole source)
Both prior approval & wavier needed
Neither needed
Prior approval needed
Wavier needed
Technical - Workplan
Operational